## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Tunisia: Strengthening social protection and economic relief systems for vulnerable and marginalized segments of the population as a response to COVID-19 | Overall Duration (months) | 10 May to April 31
Programme Number (if applicable) | 121683 | Start Date (dd.mm.yyyy) | 10 May.2020
MPTF Office Project Reference Number: | UNDP Tunisia | Original End Date (dd.mm.yyyy) | 30.12.2020
Country | TUN | Current End date(dd.mm.yyyy) | 31.03.2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UN Habitat, UN Women,WFP | National counterparts (government, private, NGOs & others) and other International Organizations | South Development office (Ministry of development) , the ministry of youth and sports, ,Tunisian National instiute of stastic,the national Tunisian office of handcrafts ,Local civil society
Report Cleared By
o Name: | Mohamed Nahali
o Title: | M&E Officer (RCO)
o Email address: | mohamed.nahali@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Through the COVID-19 MPTF-funded programme in Tunisia, UN agencies in Tunisia achieved the following results: 1) UNFPA and its implementing parterns were able to provide social support to vulnerable women and women victims of gender-based violence, as well as members of the LGBTG community and people with disabilities in Tunisia. Psychological support was also provided to the LGBTQ community and vulnerable youth and adolescents in remote areas. In addition, people with disabilities had better accessibility to essential information on COVID19 and youth needs in relation with the impact of COVID19 were assessed. 2) UN Women was able to insure that more than 46 public servants have been involved in Gender Responsive Budgeting training sessions. 33 of them are working in different sectoral ministries and 13 from the National Institute of Statistics (INS). Moreover, six operators working on the telephonic hotline 1899, in addition to 5 members from the National Observatory of fighting violence against women have been trained on Law n°2017-58 giving the growing number of abused women in Tunisia during the confinement. 3) UNDP team, as lead on the Outcome 3 of the MPTF project, was able to work on helping people become more resilient by providing them equal access to business opportunities that will make them resist to the Covid shock through financial instruments and technical/digital tools, allowing them to adapt their activities according to the Covid-19 context. Also UNDP team worked on supporting the Government in scaling-up its actions and strengthening women-headed micro enterprises resilience to the Covid-19 pandemic, preventing this segment of the population from further marginalization and impoverishment. In that sense, the project has identified 740 vulnerable women microentrepreneurs in the Southern regions of Tunisia, has filed them in a database, in order to target them as beneficiaries of the capacity strenghtening and support their microentreprises on the other project activities. 4) IOM Tunisia engaged in emergency interventions to help vulnerable and marginalised segments of the population cover their immediate needs, by distribution of vouchers and support in accessing social aid protection and health information services. During the reporting period, IOM Tunisia realized 12 distributions actions of vouchers. The vouchers could be used in over 100 stores over the country. 5) Under the responsibility of UN-Habitat, the project has supported in 2020 the homeless people, and persons evicted from their homes as a result of the COVID outbreak which has been done through a concrete support to the Orientation and Social Support Centres in charge of hosting the homeless people and their SAMU Social (Emergency Social Support Service) was given in 3 major cities of Tunisia (Tunis, Sousse and Sfax), to provide the homeless with shelters, access to basic hygiene facilities and socio-psychological support; this was done with the collaboration of the Ministry of social affairs who provided a list of needs. 6) UNHCR provided urgent cash assistance to hard-hit urban refugees and asylum seekers registered with UNHCR Tunisia, with some 85% of recipients having experienced loss of income during the lockdown period (March-June) applied in Tunisia. This initiative was part of UNHCR’s efforts to enhance its cash assistance interventions during the COVID-19 response, which included specific cash supplementation for particularly vulnerable refugees and asylum seekers. MPTF funding allowed some 1,000 extremely vulnerable refugees and asylum seekers countrywide to receive a one-time of 250 TND (90USD) cash grant. Cash delivery was made possible thanks to UNHCR’s pre-existing partnership with the Tunisian Post Office. 7) WFP during the project period conducted a diagnosis of the existing social protection system, and advocacy was undertaken to make it shock responsive inclusive and accessible to the most vulnerable populations. A concreate support was given to ministry of social affairs and minisitry of education to improve the targeting of vulnerable groups and the governance of programs by identifying vulnerable groups, digitizing and modernizing the social protection system; Set up the OOESCO/Ministry of Education database and connect it to the Ministry of Social affairs database to include the 73% of households with children benefiting school meals as safety nets which are currently excluded.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The number of indirect beneficiaries of the COVID-19 MPTF programme interventions, is 346 117. The number of direct beneficiaries of the COVID-19 MPTF programme interventions, is 5 274 (2514 women and 2760 men), divide as follows: Beneficiaries from UNFPA actions: - 209 women victims of violence have benefitted from legal, medical, psychological and social services from the new shelter for women victims of violence - 258 persons from the LGBT groups received mental health support (164) and social aid (94). - 1043 persons received social aid consisting mainly of treatments, cash-based aid, food, medicine, transportation, rent reimbursement, utilities bills, medical fees, medical equipment, hygiene kits and dignity kits, of whom 637 young people with disabilities and 406 vulnerable women. - 328 747 people with disabilities were reached by the accessible sensitization supports - 1676 young people (15-29) reached to participate to the study on the impact of COVID19 on young people - 62 young people (65% F; 35% M) called the green line for the psychological support In terms of trainings insured by UN Women : Training on the law 2017-58 on violence against women : 11 women 0 men Training on GRB and gender sensitive statistics : 30 women 16 men Direct beneficiaries from the outcome 3 interventions (UNDP): 482 women microentrepreneurs desagregated by region as follows: - Gabès : 105 women - Gafsa : 46 women - Kébili : 80 women - Médenine : 54 women - Tataouine : 97 women - Tozeur : 100 women Direct beneficiaries from IOM interventions: 2 298 (1 410 men, 888 women) Direct beneficiaries from UNhabitat: 178 men and 230 women Direct beneficiaries from UNHCR: 1,000 individual vulnerable asylum seekers/refugees, including 613 men and 365 women. Direct beneficiaries from WFP: 542 household
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1: Government agencies are equipped with tools to target more effectively vulnerable and marginalized populations with their COVID-19 responses. Key Result1: Beneficiaries received unconditional cash to cover daily minimum existential needs, with shelter, food, medication and health services, and hygiene products being the top expenditures. Key Result2: DataBase of benficiaries is now finalised. Key Result3: collaboration with the Ministry of social affairs is effective, who provided a list of needs. Key Result4: Capacity building (trainings) in favor of government intitution representatives and public partners have been organized. Outcome 2: Emergency interventions help vulnerable and marginalized segment of the populations to cover their immediate needs during the COVID-19 crisis Key Result 1: The socio-economic needs of vulnerable women were met Key Result 2: The access to information and social protection for people with disabilities was strengthened. Key Result 3: The access to mental health support and social protection for LGBT groups was strengthened. Key Result 4: The access to psychological support to vulnerable youth and adolescents was Increased. Key Result 5: The Impact of COVID19 on young people was assessed Key Result6: The light rehabiliatation work was done, the Van fo 15 seat the car was purchased, An assessment of the capacities of the homeless centers in Tunis, Sousse and Sfax in terms of reception conditions and psychological support for the homeless has been done and Social exclusion analysis was done Outcome 3: The marginalized women entrepreneurs reinforce their economic resilience Key Result: The economic resilience of marginalized women micro entrepreneurs is reinforced
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1: Newly targeted vulnerable and left behind people are included in the social registry as beneficiaries of shock-responsive social protection top-ups DataBase of beneficiaries is now finalized and effective this was done with the collaboration of the Ministry of social affairs. A concreate support was given to ministry of social affairs and ministry of education to improve the targeting of vulnerable groups and the governance of programs by identifying vulnerable groups, digitizing and modernizing the social protection system; Set up the OOESCO/Ministry of Education database and connect it to the Ministry of Social affairs database to include the 73% of households with children benefiting school meals as safety nets which are currently excluded. Output:1.2: Gender-responsive macro-economic policy solutions integrated into the legal normative frameworks and government socio-economic, financial and fiscal measures 6 knowledge products have been produced under MPTF project and dealing mainly with pandemic impact on women socio-economic conditions and access to health services. Among them, 2 policy briefs (PB) have been already published. 2 other PB, a national methodology on violence against women and a legal report are in the printing process and should be ready for the closure event planned to take place on March 08th. A last report on Socio-economic, taxation, spending, and SDG policies during Covid-19 pandemic in Tunisia, is in its final stage of drafting. Output 1.3: Support the collection and analysis of gender and sex-disaggregated data in order to accurately identify the differential impact of the outbreak on the population and increase the population’s awareness More than 46 public servants have been involved in Gender Responsive Budgeting training sessions. 33 of them are working in different sectoral ministries and 13 from the National Institute of Statistics (INS). The most important thing here is that through MPTF project, UN Women Tunisia succeeded to bring onboard very interesting partners such as the Ministry of Economics, finance and support to investment in addition to the INS. The Impact of COVID19 on young people was assessed. In partnership with the Arab Institute for Human Rights, an assessment on the impact of COVID19 on young people (15-29) was conducted. A team of 46 field investigators have reached out 1676 young people from different regions of Tunisia. Results will be analyzed during the first quarter of 2021 in order to develop policy briefs on the impact of COVID19 on young people, especially on their access to SRH services and information, their mental health and on gender based violence during the COVID19 outbreak. Output 2.1: Increased access of vulnerable groups to social aid, protection and health information and services Beneficiaries from the MPTF COVID-19 program received a one-time 250 TND cash grant (90 USD) thanks to pre-existing partnership with the Tunisian Post Office (WFP, UN Habitat, UNHCR). The socio-economic needs of vulnerable women were met were met through quick assistance complementarily to the Government’s Covid-19 Response Plan and in accordance with Civil Society Women victims of gender-based violence were able to benefit from social aid (cash-based aid, food, medicine, transportation, rent reimbursement, utilities bills, etc...). A shelter was also provided through the renovation and equipment of an existing but out-of-service center belonging to the NGO “UNFT” (national union of Tunisian women). Support was given to strengthen the access to information on COVID-19 and SRH and GBV to persons with disabilities by translating into sign language information and communication tools and messages on social networks and on media to allow increased access to treatments and liaison with care services. In addition, UNFPA Tunisia and the Arab Institute for Human Rights (AIHR) launched, on November 2020, a campaign to support people with disabilities in times of COVID19 crisis. In partnership with an Organization of People with Disabilities “Ibsar Association”, UNFPA and AIHR implemented a program of action that consisted on the Provision of social aid consisting on mainly treatments, medical fees, medical equipment, hygiene kits and dignity kits to 637 young people with disabilities across the country in coordination with national structures and organizations of persons with disabilities. The first hotline for psychological support to adolescents and youth was launched in Tunisia on November 2020. This activity initiated by UNFPA Tunisia in partner with Nebras Institute - The Tunisian Institute for the Rehabilitation of Survivors of Torture, aimed at addressing the impacts of COVID19 on the mental health of young people. The green line is managed by psychologists and with the contribution of a network of psychiatrists and child psychiatrists across the country that are available to provide psychological support confidentially and for free. The MPTF COVID-19 project allowed UN agencies to work of a light rehabilitation of the women's living unit in the Homeless Center of Tunis, in particular interior and exterior painting, maintenance of the sanitary blocks, and maintenance of the garden. This intervention allowed to improve the conditions of reception of women in the center and generated other interventions financed by other donors such as the purchase of beds by the center of Tunis, equipped the two living units with air conditioning by the Samu Social International. Output 3.1: The digital transition and capacity development for vulnerable women, especially in southern areas, are supported The project has identified 740 vulnerable women microentrepreneurs in the Southern regions of Tunisia, has filed them in a database, in order to target them as beneficiaries of the capacity strengthening and support their microenterprises of the other project activities. In terms of support to the creation/scale up of women led microenterprises, the project work in collaboration with UNDP's "Access to rights" project to fund local NGOs to support 50 entrepreneurship project for victims of trafficking. A consultancy firm has also been recruited to assess the digital divide in Southern Tunisia. The objective of the ongoing study is to inform on the digital divide and digital exclusion of vulnerable women entrepreneurs in the targeted governorates of the South (Gabes, Tozeur, Médenine, Gafsa, Kebili, Tataouine). This study targets exclusively vulnerable women micro-entrepreneurs (including women artisans) in both the formal and informal sectors in the governorates mentioned above. It’s assessing and analyzing the opportunities and actual challenges in terms of digital inclusion in Southern areas, to identify the roots of this deficiency. Output 3.2: The financial inclusion of vulnerable women micro-entrepreneur is supported Trough the funding of 2 associations/NGO that directly support women led entrepreneurship projects in the South of Tunisia, 45 vulnerable women micro-entrepreneur has been supported with the interventions proposed by the associations. In order to better target beneficiaries and assess their needs in terms of financial services, a mapping of the most vulnerable women micro-entrepreneurs was conducted in the governorates of Gabès, Gafsa, Kébili, Médenine, Tataouine and a database created. Following the definition of vulnerability criteria specific to the target regions, 482 women micro-entrepreneurs were identified and integrated in the database. Specific training on financial services was developed based on the assessment of the needs of women entrepreneurs that has been conducted in the Southern governorates. The results have been achieved through collaborative work with the Ministry of Youth, Sports and Professional integration, the South Development Office and local civil society organizations. In addition, as part of the celebration of the National Women's Day on August 13, the project supported the Ministry of Women's Affairs for the organization of a forum under the theme: "Sustainable Development Goals from a Gender Perspective: Tunisia's Priorities after the COVID-19 pandemic ". This forum, bringing together various stakeholders was an opportunity to present Tunisia's achievements in the field of women's protection and the strengthening of their rights in the fight against COVID-19 pandemic.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The main difficulty encountered during the implementation of the MPTF COVID-19 project activities were: 1)The prioritization of the distribution of aids: Due to the high demand registered, the funds available were unable to cover the needs of the beneficiaries. Therefore, a tool was developed (UNFPA) and used by the implementing partners to objectively assess the level of vulnerability of the beneficiaries and ensure a fair distribution of aid. 2)During the previous months, working with Tunisian government within a very incertain pandemic climate was not easy in the sense that on one side political instability and socio-economic continuous problems were handicapping the work of UN agencies, and on the other side, the pandemic spread during the second vague (since July 2020) has largely contributed to the uncertainty of number of events that have been scheduled during the fourth quarter of 2020. 3)A major challenge faced during the reporting period was the constantly aggravating epidemiological situation in Tunisia in terms of the spread of COVID-19 which led to the adoption of a series of preventive measures, mainly the restriction of gatherings, by national and local authorities. Moreover, in several cases suitable municipal and public spaces allowing for physical distancing were not available. As a result, UN agencies active in Tunisia changed their course of action and organized either door to door distributions or distributions by appointment, ensuring that all necessary sanitary protocols are respected. 4)In terms of data collection, it was expected to organize qualitative and quantitative surveys focusing on marginalized population. This was not allowed because of the pandemic spread and restrictions imposed by the government (confinement, curfew, travel restrictions between governorates), and in some other cases, due to social tensions that happened from time to time in some regions within the country. 5)COVID-19 cash assistance for refugees and asylum seekers was distributed at the same time as the distribution of cash by the government to vulnerable Tunisians, which was also done through the Tunisian Post Office. As a result, access to the Post Office was challenging in certain locations due to the number of people collecting their assistance at the same time. However, the support provided by the government was a one-off package, so the congestion was punctual. 6)The main challenge in achieving the results is the persistence of the pandemic for almost one year, which was not expected when launching the project's activities. The sanitary measures imposed by the government, which some of them are still currently ongoing in 2021, caused important delays in the implementation of the planned activities (consultants unable to conduct their missions and meet with stakeholder, impossibility to organize workshops). 7)Mission for data collection for the vulnerable women's database has been seriously impacted by the travel restrictions from a region to another. After a period of adaptation to the new working conditions and tools, the project was able to continue the implementation of some of the initially planned actions, mainly by shifting to digital activities (especially training and capacity strengthening).
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The project has contributed significantly to gender equality and the empowerment of women and girls through the alleviation of the socio-economic burden of the COVID-19 pandemic. The project has also supported homeless people, and persons evicted from their homes as a result of the COVID outbreak. Based on our multiple meetings and training sessions where representatives from sectoral ministries have been involved, it seems that an important set of statistics exists at ministry levels, sometimes they are gender sensitive but sometimes they are not. These statistics are not very well communicated among all ministries which would leads, controversially, to a lack of data at the national level. This was notified by sectoral ministry representatives themselves who pointed out the necessity of capitalizing on existing data to be able to work on GRB for the coming years. Organic budget law already exists, in addition to an important set of statistics which prepares the field for a concrete GRB. The distributions of grants allowed UN agencies to gain access and support vulnerable groups in regions where they used do not have offices or activities. These activities extended UN agencies assistance outreach as it gave the opportunity to them to share their communication channels but also inform vulnerable groups about the services available. Moreover, these activities gave the chance to collaborate for the first time with the new local municipalities and CSOs, which can be included in future programming. As a short-term response, the scale-up in cash came into its own in this crisis as a modality of assistance which is rapid, hygienic, and innovative. Cash proved to be an efficient means of getting assistance to affected refugees and asylum seekers providing protection, empowering families to meet their basic needs, and mitigating some of the negative protection and socioeconomic impacts of COVID-19 such as risk of poverty and psychosocial hardship. UN agencies operation in Tunisia adapted existing cash assistance, introducing, designing new cash grants, and targeting criteria to assist new vulnerable populations, adjusting systems and complaints and feedback mechanisms and, where appropriate, aligning cash assistance with the government social assistance.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | For the implementation activities under Outcome 1: UN agencies partnered up with “Associamed” in Sfax region in order to provide sensitization to Covid-19 prevention measures to beneficiaries during the distributions. Furthermore, they strengthened their relationships with the municipalities of Nabeul, Gabes, Djerba, Sfax, Sousse, and Ariana. Also UN agencies relies on their partnership with Tunisian institutions, such as the Ministry of Social Affairs, the Ministry of Agriculture and the Ministry of Education to make flexible responses and social monetary transfers by adapting the response system to changing risks. For the implementation activities under Outcome 2: The UN agencies relied heavily on trheir strategic partners' networks and experience on the field to properly implement the project's activities. In fact, the socio-economic aid to vulnerable women was distributed through the partner organizations' shelters for women victims of violence, mainly UNFT and the Samu Social International. The youth needs assessment required strong local partnerships to access young people out of connectivity. Thus, coordination with local NGOs covering many regions allowed to reach the target. For the implementation activities under Outcome 3: The project collaborated with the South Development office (Ministry of development) , the ministry of youth, sports and professional integration, the Tunisian National institute of statistics, the national Tunisian office of handcrafts, Local civil society and the private sector (Attijari Bank).
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | UNHABITAT: An assessment of the capacities of the homeless centers in Tunis, Sousse and Sfax in terms of reception conditions and psychological support for the homeless has been done. WFP: Market analysis and feasibility studies have been conducted.a Post Distrubution Monitoring survey is ongoing.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | UNWomen: Even if it was very helpful having three more months in the duration of the program giving the Covid-19 pandemic spread, it was a bit difficult to adjust the budget to pay human ressources for the additional period under MPTF project without any additional fund. At this level, UN Women manages to reallocate the initial budget in order to ensure the payment of all stakeholders until the new end date.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UNFPA: Recruitement of a consultant in charge of the follow-up of the project (PwD, LGBT and Youth components). UNDP: The project benefitted from the human ressources of UNDP's Entrepreneurship for Development project for the implementation of its activities (output 3.2). The project is collaborating with Attijari Bank for the implemtation of its activities on vulnerable women financial inclusion. An MOU was signed as part of the ongoing UNDP project "Entrepreneurship for Development" and MPTF is benefitting from this developped synergie. IOM: All operational ressources have been spent for the activities as of Dec 31st, 2020.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
| Planned Target : 1 800 Target as of Dec 31st, 2020 : 2 298 |  | Kobo
Outcome1: Government agencies are equipped with tools to target more effectively vulnerable and marginalized populations with their COVID-19 responses.
Baseline:
Planned Target:
Output 1.1 : Enhanced capacity of sectoral ministries and local authorities to implement gender sensitive strategies and make strategic budget allocations | Achieved with 10/7 |  | Institutions participating in the training sessions on GRB, photos, videos and minutes of our meeting with the Central unit of GBO in the Ministry of economics, finance and support to investment
Indicator 1.1.1: Nbr of national/local institutions integrating GRB principles/initiatives in Tunisia
Baseline: Baseline: Year: 2017 Value: 0
Planned Target: Target: Year: 2020 Value: 7
Indicator 1.1.2: Women gender analysis reports produced on legal framework and socio-economic measures | Achieved with 6/5 knowledge products |  | Published products (2 already published, 4 being printed and 1 in its final drafting) | 1st PB | https://www2.unwomen.org/-/media/field%20office%20arab%20states/attachments/publications/2020/07/tunisia%20brief/unw%20tunisia%20policy%20brief%20_%20en%20_%20tunisian%20women%20in%20the%20face%20of%20covid19%20during%20and%20after%20confinement.pdf?la=en&vs=2554
Baseline: Baseline: Year: 2020 Value: 0 |  |  |  | 2nd PB | https://www2.unwomen.org/-/media/field%20office%20arab%20states/attachments/publications/2020/05/tunis%20covid-19brief/un%20women_policy%20brief_gender%20and%20covid%20in%20tunisia.pdf?la=en&vs=2252
Planned Target: Target: Year: 2021 Value: 5
Output 1.2 : Enhanced capacity, tools and knowledge enabling monitoring of gender-related SDGs | Achieved in two ways : i) One of the knowldge product (still in its final drafting) entitled "Gender equality and Covid-19 in Tunisia : Socio-economic, taxation, spending, and SDG policies that leave no one behind" is monitoring gender-related SDGs ii) To enhance capacity building of our partners, a training sessions have been organized on SDG 5c1 (participants were from government institutions)
Indicator 1.2.1: Number of quality based tools produced to monitor the SDGs
Baseline: Baseline: Year: 2018 Value: 2
Planned Target: Target: Year: 2020 Value: 3
Indicator 1.2.2: Research methodology for report on the socio-economic situation of women including economic violence developed | YES (Achieved) |  | National methodology will be published end of March 2021
Baseline: Baseline: Year: March 2020 Value: No
Planned Target: Year: December 2020 Value: Yes
Outcome 2: Emergency interventions help vulnerable and marginalized segment of the populations to cover their immediate needs during the COVID-19 crisis
Indicator 2a: Number of beneficiaries receiving support
Baseline: 0
Planned Target: 13,148
Output 2.1: Increased access of vulnerable groups to social aid, protection and health information and services
Indicator 2.2.b: Number of women* who receive social aid * Women who do not receive aid through the government’s Covid-19 response plan | 406 | Higher demand than planned | Periodic reports from the CSOs involved
Baseline: 0
Planned Target: 300
Indicator 2.1c: Number of women who receive GBV services through the newly- established shelter | 209 | Higher demand than planned | Periodic report form the UNFT
Baseline: 0
Planned Target: 128
Indicator 2.1d: Number of young people who receive psychological support by sex | 62 | Low number that might be explained by the sensitivity of the topic considered as a taboo by young people | Statistics’ Reports of the green line / Nebras report
Baseline: 0
Planned Target: 5000
Indicator 2.1e: Number of persons with disabilities who receive adapted information related to COVID19 by sex | 328747 | A large communication campaign to reach this large number | Monthly and quartely reports of the Arab Institute for Human Rights / Social media interactions reports
Baseline: 0
Planned Target: 2000
Indicator 2.1e: Number of persons with disabilities who receive social aid by sex and age group | 637 | Higher demand than planned | Monthly and quartely reports of the Arab Institute for Human Rights / Field visits and follow-up meetings
Baseline: 0
Planned Target: 500
Indicator 2.1f: Number of LGBTQ who receive psychological consultations, access totheir treatment and social aid | 258 | Higher demand than planned | Monthly and quartely reports of the Tunisian Association Against STIs & AIDS / Field visits and follow-up meetings
Baseline: 0
Planned Target: 200
Indicator: Number of young people that participated to the Youth needs assessment (Impact of COVID19 on young people) | 1676 | Coordination with local NGOs allowed better outreach | Reports from the Arab Institute for Human Rights / Online google form report with responses of all participants
Baseline: 0
Planned Target: 1200
Outcome 3: The marginalized women entrepreneurs reinforce their economic resilience |  |  | Activity report
Indicator 3.a: Number of digital infrastructure enabling vulnerable women micro-entrepreneur to access to economic solutions
Baseline:0
Planned Target:1
Indicator 3.b Proportion of women supported by the project with increased resilience capacity to shocks, and its ability to support productive activities, decent job creation, entrepreneurship, creativity and innovation |  |  | Outputs 3.2.1 and 3.2.2 Reports and surveys
Baseline: 0
Planned Target: 50%
Indicator 3.c Proportion of micro, small and medium-sized supported enterprises, encouraged to be formalized, and in a scaling up process, including through access to financial services (inspired from SDG 8, target 8.3) |  |  | Outputs 3.2.1 and 3.2.2 Reports and surveys
Baseline: 0
Plannet Target: 50%
Output 3.1: The digital transition and capacity development for vulnerable women, especially in southern areas, are supported |  |  | Activity report
Indicator 3.1.a Number of women (supported by the project) in the South demonstrating integration in the ecosystem or being (re)employed or launching their own project through digitalization
Baseline: 0
Planned Target:300
Output 3.2: The financial inclusion of vulnerable women micro-entrepreneur is supported
Indicator 3.2.a Number of women-headed micro enterprises in a scaling up proces |  |  | List of Beneficiaries
Baseline: 0 |  | progress to date 45
Planned Target: 90
Indicator 3.2.b Number and type of new services (financial, technical) available for women entrepreneurs |  |  | Activity Report
Baseline: 0
Planned Target:2
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
UN Women is in the process of preparing a complete set of photos, videos and stories showing the extent to which operators working on 1899 hotline have benefited from the training UN Women organized to enhance their capacities in terms of Law 2017-58 and how did they use it to sufficiently listening, guiding and following up with abused women who are calling.
Also, each one of the organized events under MPTF program has been widely disseminated through social media, especially through twitter. Links : https://twitter.com/onufemmestn/status/1338451590857052160?s=09 https://twitter.com/onufemmestn/status/1338748195539705856?s=03
UNHCR: Facebook post on UNHCR Tunisia's page: https://www.facebook.com/UNHCRTunisie/photos/a.118870356514805/204276054640901/
UNFPA: link to a video report: https://drive.google.com/file/d/1vltRKPSV_NhVp6axsuRiPeIsZWaHW8Gw/view?ts=602d538c Filmed testimonies of people with disabilities on the impact of the COVID-19 pandemic has had on their daily lives, and the ways in which this project has contributed to meeting their specific needs. (Video credit: UNFPA and IADH)
IOM: see the leaflet inserted in this excel document
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board