## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Ensuring the access of most vulnerable families to food and working conditions facilities during COVID-19 Pandemic | Overall Duration (months) | 9 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 26.05.2020
MPTF Office Project Reference Number: | (00)121774 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | SAO TOME AND PRINCIPE | Current End date(dd.mm.yyyy) | 28.02.2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | 1. Food and Agriculture Organization (FAO) 2. International Labor Office (ILO) 3. World Food Programme (WFP) 4. United Nations Program for Human Settlements (UN-Habitat) | National counterparts (government, private, NGOs & others) and other International Organizations | 1. Ministry of Agriculture, Fisheries and Rural Development 2. CADR 3. Ministry of Labor, Solidarity, Family and Professional Training 4. Ministry of Public Works, Infrastructure, Natural Resources and Environment 5. Directorate of Geographical and Cadastral Services 6. Public Works and Urban Planning Department 7. Ministry of Finance and Blue Economy 8. District Chambers 9. Government of the Autonomous Region of Príncipe 10. HELPO (International NGO) 11. ADAPPA (National NGO)
Report Cleared By
o Name: | MR. CESALTINO VAS FERNANDES
o Title: | RCO STP Partnership Focal Point
o Email address: | cesaltino.fernandes@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project "Ensuring the access of most vulnerable families to food and working conditions facilities during COVID-19 Pandemic" was tailored in the context of an unprecedent humanitarian and health crisis that negatively impacted the food security of thousands of Santomeans in 2020. A total of 600 poor households, including children, women, and small-scale producers, considered at the highest risk of food insecurity were identified during this health emergency. During the seven months of its implementation, this joint project was able to achieve positive results by reinforcing sustainable agricultural production techniques (including food storage and processing techniques) and conditions, ensuring the operationalization of government warehouses and school gardens. The COVID-19 MPTF-funded project implemented in Sao Tome and Principe is the result of the combined efforts of four United Nations agencies: (a) Food and Agriculture Organization (FAO), (b) the International Labour Organization (ILO), (c) the United Nations Programme for Human Settlements (UN-HABITAT) and (d) the World Food Programme. The project reflects the commitment to SDG1, SDG2 and SDG17, along with ensuring careful involvement of communities and local actors and was initially planned to last for no longer than 7 months, from June to December 2020. However, due to human, logistic and operational impediments aggravated during the pandemic, the project has been extended further until end of February 2021. In June 2020, the UN agencies collaborated on drafting a macro-plan for the definition, design and implementation of the activities, ensuring that the interventions would have been operationalized in a participatory manner and would have reflected the co-joint purpose of the project. Additionally, a macro stakeholder mapping exercise was finalized to ensure involvement of all main national actors. Due to the confinement, the agencies had to rely on a virtual collaboration for the first months of the project implementation. The use of main communication platforms (such as zoom platform) and alternative communication tools (i.e. WhatsApp groups) reinforced the internal coordination mechanism among the agencies, and enabled discussions and information sharing throughout the project implementation phase over time. The activities undertaken in July 2020 focused on consolidating the first steps finalized in June 2020 - the high-level meetings with the different Ministries involved to present the initiative with a view to promoting their engagement and commitment - and strengthening the engagement of the task force designated by each ministry, of the stakeholders and the UN agencies, as well as planning next steps to initiate involvement of the communities and the field activities. From September to December 2020, the agencies finalized the training sessions designed as part of the project with a societal return on investment on 600 household families, re-activated 32 school gardens (out of the 35 initially) planned and supported the value chain of plants, seeds and cans to benefit the targeted beneficiaries. The main assumption underlying the project was to support women empowerment and mainstream into the programmatic activities a gender lens to differentiate the specific needs of women and girls highly exposed to the impacts of COVID-19. Therefore, a pre-gender analysis was conducted in close collaboration with the National Institute for Gender Equality and Parity and relevant national stakeholders.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The MPTF project - Ensuring the access of most vulnerable families to food and working conditions facilities during COVID-19 Pandemic – has been designed and delivered in STP to address the increase in food insecurity among the most vulnerable rural and peri-urban population, due to the disruptions on food systems aggravated by the COVID-19 pandemic and the restrictive measures declared by the Government to control its spread in Sao Tome and Principe. The initial design of the project targeted 540 vulnerable households from the 6 national districts of Sao Tome island. However, following the unexpected increasing food insecurity and nutrition challenges occurred during the pandemic, the MPTF team revised the project proposal to support additional 60 vulnerable households from the Autonomous Region of Principe (RAP), reaching overall 600 family groups and around 3,000 beneficiaries. During the targeting process of the beneficiaries, finalized by the MPTF team in close collaboration with governmental counterparts and national stakeholders (i.e. NGOs, community leaders), it was agreed to address the special needs of women and girls most affected by the pandemic and to focus on female-headed households (7.23% male-headed households; 92.77% female-headed households). As part of the programmatic activities implemented from May to December 2020, the MPTF team supported the re-activation and organization of school gardens from 32 national entities to the benefit of around 3,500 school children attending kindergarten and primary schools, along with a plethora of education (i.e. teachers and school directors) and school feeding (i.e. kitchen helpers and gardeners) actors working in these environments.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The results achieved based on the outcome included as part of the project design are the following: 2.1a Number of vulnerable households touched by the project who register a stability in their food security and nutrition situation 600 vulnerable households and indirect beneficiaries from 32 schools benefited from the project through support for local food production and increased knowledge about its use, which has contributed to the pursuit of food and nutrition security for these beneficiaries. It should be noted that this project addressed food and nutrition insecurity as a holistic and integrated phenomenon, devoting efforts to all its dimensions - availability, access, use and stability - thus contributing to the achievement of sustainable solutions. 2.2a Number of gender analysis undertaken pre and post interventions (at district, community and household levels) A pre-intervention gender analysis has been finalized in close collaboration with the National Institute for Gender Equality and Equity (INPG) and government counterparts. Data shows that there is the feminization of food insecurity and malnutrition at the community level, along with a "feminization of poverty". Similarly, neither men nor women have the knowledge and/or recognition that the domestic and non-domestic work done by women is crucial for the socio-economic development of the country. The post-gender analysis envisioned as part of the project and to be carried out on each household is still in the process to be finalized and was delayed as a result of the in-country challenges that triggered the extension of the activities until February 2021. This post-intervention analysis will allow conclusions to be drawn at district, community and household levels.
3.2 | Results: Output Level | Please include output level results achieved | Output 1. Capacity of trainers and beneficiaries built on agricultural techniques and better conditions of work to improve their resilience 1. A pre-intervention gender analysis was carried out, allowing for the development of training modules that addressed key gender issues through dialogue and awareness raising at household level; 2. Training of beneficiaries in innovative agricultural techniques adapted to the climatic conditions and adjusted to land availability of production sites and to their food and nutritional needs. In addition to the beneficiaries, 32 school gardeners were trained to disseminate knowledge to their households and schools. The training included modules on production in small growing spaces, introducing recyclable materials such as (PET bottles and tyres) and using practical biological methods to control and prevent pests and plant diseases; 3. Training of trainers of 25 facilitators regarding gender, safety, hygiene and labour conditions were conducted to support the delivery of training activities for the 600 beneficiaries; 4. Training of 540 vulnerable families (7.23% male-headed households; 92.77% female-headed households) in MSM and Gender and Development in the 6 Districts of Sao Tome; 4.1 Training of 50 vulnerable families in Gender and Development and, MSM and agricultural techniques in the Autonomous Region of Príncipe (RAP). This activity is still in progress and the agencies are in the process to finalize the training sessions to reach 10 more families as per the end of the project. 5. 2 gender-sensitive awareness sessions targeting rural women on topics related to women's empowerment, security measures to be taken in the current scenario of COVID-19, the importance of self-help groups and participation in decision making processes, harmful gender and social norms regarding foods, the allocation of resources within the household, specific nutrition needs of girls and boys, etc. These sessions were held with the support of the National Institute of Gender Equality and Parity (INPG); 6. Distribution of production kits to all vulnerable households and school gardeners. All targeted beneficiaries were supported by the project with the distribution of production kits consisting of agricultural materials and local plants used in Santomean meals. The composition of the list of plants took into account a balanced diet rich in various nutrients. The inclusion of plants with iron and vitamin component (such as gimboâ, maquequê and mússua) to meet the general trend of iron-deficiency and anemia among the most vulnerable population. 7. Distribution of seeds and plants. The MPFT team in collaboration with the Ministry of Agriculture distributed: (a) 1,080 plants of make-up, aubergine, okra, mosque, gimboa and compass; (b) 2,160 plants of turtle leaf ropes and banana; (c) 5,400 ropes of cassava cuttings and sweet potato and 54 kg of corn. Output 2. Conditions of storage and conservation of food and basic sanitary infrastructures on school gardens are improved 1. Rehabilitation of BECAF 10-tons cold stores. The rehabilitation of the cold stores is still undergoing and will be finalized by the end of the project that was extended until 28th of February 2021. 2. Construction of storage silos. Due to some socio-cultural and logistics impediments, the MPTF team in STP opted to re-design the activity by replacing the initially planned silos with drums that will be used by the beneficiaries to conserve food commodities and store water. The activity is still undergoing and will be finalized by the end of the project (February 2021). 3. Rehabilitation of necessary school gardens (including 12 water reservoirs). Through the MPTF project, 32 schools have benefitted from the re-habilitation of the school gardens. Initially, 35 school gardens were supposed to be re-activated. However, due to the challenging conditions in most of the national schools, the MPTF team in STP decided to reduce the number from 35 to 32 schools that met the selected criteria and to support schools and households truly interested in benefitting from this project. School gardens are currently managed by households that confirmed their interest to work under these conditions with the purpose to guaranteeing food for both families and schools in a sustainable manner, from the re-openings of the national schools. Output 3. Project implementation's is properly monitored and evaluated Project monitoring and implementation practices have been discussed among the different agencies and in close collaboration with national stakeholders. In October 2020, the MPTF team in STP submitted a detailed mid-term report regarding the progress of the activities, also used to update the respective counterparts from the civil society organizations and the national government ensuring careful involvement regarding the challenges and the growing results achieved throughout the project. All the agencies and national stakeholders were supported throughout the monitoring, evaluation and reporting activities and managed to meet the project expectation by submitting relevant reports and analysis for each output. The team closely collaborated with the government counterparts on the pre-covid gender analysis which was submitted and finalized. However, due to the extension of the project activities until February 2021, the post-intervention gender analysis is still in the process to be finalized, cleared and submitted. Finally, to ensure proper collection of key data regarding the impact of the activities, the MPTF team discussed with relevant implementing partners and government counterparts a monitoring and evaluation plan to be operationalized in early 2021.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | 1. (Challenge) The MPTF team faced some challenges with the in-country unavailability of agricultural equipment and the sharp price fluctuation of the necessary materials. During the pandemic, the sea and air connections to São Tomé were suspended, leading to a further delay in receiving the materials to the country and distributing them to beneficiaries. (Mitigation Measure) Faced with this situation, the FAO, the agency responsible for the procurement process, reinforced its human resource capacity through the hiring of a national consultant to draw up lists of technical specifications for each material in record time, so as to enable this procurement process to be revised, cleared and finalized. 2. (Challenge) A second challenge relates to the Implementation of activities on the field due to mobility constraints imposed by Covid-19 containment measures. (Mitigation Measure) To address this challenge, partnerships, roles and monitoring plans were re-discussed with all the main local entities working in the field (i.e. the Ministry of Agriculture and Rural Development, National Institute for Gender Parity (INPG), National Support Center for Rural Development (CADR), International NGO HELPO, NGO ADAPPA). 3. (Challenge) Another challenge encountered was related to socio-cultural habits that resulted in the lack of acceptance to share community silos for the storage of dry and granulated food produced by the beneficiaries of the MPTF project. (Mitigation Measure) The operational solution was agreed with institutional authors and NGOs and the UN agencies opted for purchasing reservoirs to be distributed to targeted family groups benefitting from the project for storage of water and/or food. However, a further challenge was to import the 300 reservoirs to STP and from STP to the remote island of Principe (RAP). 4. (Challenge) Beneficiaries involved in the training sessions presented different profiles (i.e. different level of literacy, different knowledge regarding gender-related topics, some physical illnesses). (Mitigation Measure) Training were designed and tailored to the different target audiences and to ensure smooth learning based on their deficiencies, level of knowledge regarding the topic and level of literacy.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | As the second smallest economy in Africa, São Tomé and Príncipe covers two islands and several – mostly uninhabited – islets in the Gulf of Guinea. During the pandemic, São Tomé and Príncipe faced significant challenges due to its insularity, remoteness and irregular landscape. Some practical lessons learned from the MPTF project may be generalized to similar operations (i.e. small island developing states, islands, costal countries) as follows: 1. In small island developing states, supply chain and logistics may become an impediment during emergency contexts in which - as for the COVID-19 - the government in STP made the decision to close the national borders, cancelling, as a result number of available flights and maritime transportation. 2. Due to the remote geographical location and weak structure of the national economy, in small island developing states, it is important to consider that the portfolio of materials designed as part of the project might be affected by the price fluctuation typical in SIDS and similar operations, along with limiting in-country availability. 3. The involvement of the community leaders in project design and implementation and the previous knowledge of the socio-cultural heritage and/or background of the communities can be an added value for project implementation. In particular, it is important to ensure that programmatic activities and/or operational solutions designed for groups of beneficiaries reflect the individualistic and/or collectivistic cultural genoma of a country. 4. HR and administrative constraints, especially in small countries with limited UN representation compared to bigger costal and/or in-land operations, might be an impediment particularly during a pandemic and need to be considered in the project design. 5. Considering the agricultural component of the project, it was essential to consider the time for crop growth to accurately assess the impact on the beneficiaries' livelihood and the expected return on investment. For instance, the timeline for activities involving plantation varies based on the type of plant identified. Follow up monitoring and evaluation and reporting activities need to be clearly stated in the design of the project as may need extra time to be accomplished and provide an overall overview regarding the impact of the co-joined interventions.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The involvement of multiple national actors allowed the UN system agencies to reinforce their understanding of the role and technical expertise of several stakeholders involved along the implementation of the activities and with a stronger historical collaboration over others. Some of the civil society actors such as the International NGO HELPO and the national NGO ADAPPA showed great commitment to the project and technical expertise in the roll out of the activities. This was highly considered by other agencies that were not used to collaborate on similar projects with the civil society counterparts before the MPTF. For instance, following this successful collaboration, FAO and HELPO are going to partner on nutrition-related activities in 2021. Similarly, trust and acknowledgment of technical expertise among agencies was reinforced as a result of the collaboration during the co-joined activities. For instance, the agencies are discussing the possibility to fundraise in a collaborative manner in 2021, along with collaborating on MPTF-related projects to continue addressing food security and nutrition national issues, reinforce incorporation of the gender-transformative component in activities with a direct return on investment on vulnerable communities, along with planning co-joined capacity strengthening interventions to further advance achievement of SDG5 through the collaboration with the institutional counterparts. To ensure the long-term sustainable results of the project, FAO, ILO, UN-HABITAT and WFP agreed to adopt a “whole of society approach” in which all the main stakeholders, along with the government and the communities, were expected to be involved in a participatory process to enable their feeling of ownership regarding the growing results achieved throughout the collaboration and as a clear result of the co-join efforts to support the response to the covid-19 pandemic. Engagement and cross-collaboration improved over the months and thematic expertise of each agency was increasingly recognized and valued. The technical expertise from WFP in responding to crises and counteracting emergencies was highly valued during the implementation of the activities and in the design of the project extension to the autonomous region of Principe. FAO expertise in the production of plants and in the respective types of plants present in Sao Tome and the ones present in Principe was considered as a valuable asset in the implementation of the project. ILO and UN-HABITAT respective technical knowledge in gender-related and engineering matters was particularly useful to support the finalization of the activities.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | As part of the main activities to implement, the MPTF team planned to conduct in close collaboration with the National Institute of Gender Equality and Equity and national stakeholders a pre-Covid-19 gender analysis. The main empirical evidence are as follows: 1. there is a need for continued action to support the advancement of gender equality and equity in all communities present in the 6 national districts of Sao Tome. 2. there is the feminisation of vulnerability in all the communities of the country, i.e. in the universe of the 540 families selected to benefit from the MPTF project under COVID 19. 3. Data shows a clear feminization of poverty (71%) across all the national districts in Sao Tome and access to land and control of resources is predominantly in the hands of men, mainly due to socio-cultural factors. Indeed, there is an implicit belief that men are the main domestic actors responsible for managing financial resources, even if when these are mobilized by women. 4. Neither men nor women have the knowledge and/or recognition that the work managed by women at home contributes extensively to the socio-economic development of the family and the community in which they operate.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | 1. Due to socio-cultural and communities' beliefs, the agencies had to revise the programmatic activities of UN-HABITAT to meet the requests and needs of the communities switching from the initially planned silos to store food to the delivery of 300 water reservoir. 2. To support the alarming food insecurity and nutrition status of the vulnerable communities in the Autonomous region of the Principe, the agencies revised the project proposal including 60 household families (300 beneficiaries) from the RAP. The design and implementation of the activities were both customized to meet the supply chain, logistics and natural (i.e. types of plants) constraints of the added geographical environment. However, considering the incorporation of the Autonomous Region of Principe at a later stage of the project, and after the finalization of the data collection of the pre-intervention gender analysis, the final product is only going to target the initially planned 540 (household) beneficiaries to ensure data reliability.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
Ensure food security and nutrition to the most vulnerable rural families during the Covid-19 epidemic | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 600 household families (3000 beneficiaries) | The MPTF team added 60 household families (300 beneficiaries) to incorporate the autonomous region of principe (RAP). Additionally, due to operational challenges aggravated by the covid-19, project extension was approved until February 28th 2021. | Reports
2.1a Number of vulnerable households touched by the project who register a stability in their food security and nutrition situation
Baseline: 0
Planned Target: 540 household families (2700 beneficiaries)
Outcome 1[1] | 1 (pre-intervention) gender analysis (activity still ongoing to collect post-intervention data to integrate into the final product) | Due to operational challenges aggravated by the covid-19, project extension was approved until February 28th 2021. This activity is still ongoing and will be finalised upon completion of all the programmatic interventions. | Reports
2.2a Number of gender analysis undertaken pre and post interventions (at district, community and household levels)
Baseline: 0
Planned Target: 1 gender analysis for each level (district level, community level and household level)
Output 1. Capacity of trainers and beneficiaries built on agricultural techniques and better conditions of work to improve their resilience | 1 pre-intervention gender analysis + development of training modules for all beneficiaries |  | Project report, training modules sensible to gender issues
Indicator 1.1a Pre-intervention gender analysis and development of training modules including key gender issues through dialogue at household level.
Baseline: 0
Planned Target: 1 gender analysis
Indicator 1.2a Training beneficiaries on innovative production techniques adapted to the edaphoclimatic conditions of production sites, and food utilization | 600 families (3000 beneficiaries) + 25 trainers and 32 school gardeners |  | Training reports, project reports
Baseline: 0
Planned Target: 20 trainers, 2700 people, 540 families
Indicator 1.3a Trainings beneficiaries on safety, health and hygiene at workplace particularly small producers, workers/employers, other relevant labour market institutions and actors. | Training of trainers of 25 facilitators to support the delivery of training activities for 590 household families (Training of 540 vulnerable families in the 6 Districts of Sao Tome + training of 50 vulnerable families from the Autonomous Region of Príncipe) | This activity is still in progress (95%) and the agencies are in the process to finalize the training sessions to reach 10 more families from the autonomous region of principe as per the end of the project (28th of February 2021) reaching in total 600 household families (3000 beneficiaries). | Training reports, project reports
Baseline: 0
Planned Target: 540 families (2700 beneficiaries)
Indicator 1.4a Gender-sensitive awareness sessions aimed at rural women on topics related to women's empowerment, security measures to be taken in the current scenario of covid-19 etc | 2 gender-sensitive awareness sessions targeting all rural women on topics related to women's empowerment, security measures to be taken in the current scenario of COVID-19, the importance of self-help groups and participation in decision making processes, harmful gender and social norms regarding foods, the allocation of resources within the household, specific nutrition needs of girls and boys, etc. These sessions were held with the support of the National Institute of Gender Equality and Parity (INPG); |  | Training reports, project reports
Baseline: 0
Planned Target: 540 household families - 1400 women
Indicator 1.5a Distribution of production kits to families, farmers, and canteen/school gardeners. | Finalised for 600 household families and 32 gardeners |  | Project reports
Baseline: 0
Planned Target: 540 households (2700 beneficiaries)
Indicator 1.6a Acquisition of seeds and plants | Achieved (including 60 household families from Autonomous Region of Principe) - Distribution of seeds and plants. The MPFT team in collaboration with the Ministry of Agriculture distributed: (a) 1,080 plants of make-up, aubergine, okra, mosque, gimboa and compass; (b) 2,160 plants of turtle leaf ropes and banana; (c) 5,400 ropes of cassava cuttings and sweet potato and 54 kg of corn. |  | Project reports
Baseline: 0
Planned Target: X seeds and y plants (cassava, sweet potatos and taro)
Output 2: Conditions of storage and conservation of food and basic sanitary infrustructures on school gardens are improved | The rehabilitation of the cold stores is still undergoing and will be finalized by the end of the project that was extended until February, 28th of February 2021. | The MPTF team added 60 household families (300 beneficiaries) to incorporate the autonomous region of principe (RAP). Additionally, due to operational challenges aggravated by the covid-19, project extension was approved until February 28th 2021. | Reports provided by the UN agencies
Indicator 2.1a Rehabilitation of BECAF 10-ton cold stores
Baseline: 0
Planned Target: 4
Indicator 2.2a Construction of storage silos | 300 drums | Due to some socio-cultural and logistics impediments, the MPTF team in STP opted to re-design the activity by replacing the initially planned silos with drums that will be used by the beneficiaries to conserve food commodities and store water. The activity is still undergoing and will be finalized by the end of the project (February 2021). | Project report
Baseline: 0
Planned Target: 6
Indicator 2.3a Rehabilitation of necessary school gardens | 32 (12 water recevoirs) | Through the MPTF project, 32 schools have benefitted from the re-habilitation of the school gardens. Initially, 35 school gardens were supposed to be re-activated. However, due to the challenging conditions in most of the national schools, the MPTF team in STP decided to reduce the number from 35 to 32 schools that met the selected criteria and to support schools and households truly interested in benefitting from this project. | Project report
Baseline: 0
Planned Target: 35
Output 3: Project implementation is properly monitored and evaluated | Mid-term report and Annual report finalised - along with all the planned project reports, pre-intervention gender analysis regarding the activities finalised by 31st of December | The MPTF team added 60 household families (300 beneficiaries) to incorporate the autonomous region of principe (RAP). Additionally, due to operational challenges aggravated by the covid-19, project extension was approved until February 28th 2021. Monitoring and Evaluation practices are ongoing for the field activities and interventions planned to be finalized by end of February 2021. | Project reports
Indicator 3.1 Monitoring and evaluation of the implementation of the beneficiaries' activities in the field
Baseline: 0
Planned Target:

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
The task force responsible for the formulation and implementation of the project "Ensuring access to food for the most vulnerable families, their conservation infrastructure and better working conditions during the Covid-19 pandemic", met with the Director of the National Institute for the Promotion of Gender Equality and Equity (INPG) of Sao Tome and Principe, Ernestina Menezes, to ensure careful incorporation of the gender-transformative component across all the programmatic activities of the project. “Gender is an implicit background identity and women are increasinly risking to be subject to discrimination during the pandemic”, say the MPTF members of the team in Sao Tome and Principe. Supporting women empowerment and addressing socio-economic gender issues arised during the pandemic were underlying operational and motivational drivers of the MPTF project in Sao Tome and Principe. Involvement of the INPG as a specialist institution in the field of gender, along with the one of multiple national actors from the communities and other representatives from the civil society, was key to ensure careful incorporation of different techncial perspectives across the definition, design, implementation and final documentation of the co-joint action managed to support vulnerable women from all the national districts in Sao Tome. As a result of this collaboration, all the main partners agreed on clear gender-sensitive guidelines to maximise the impact on the project, along with identifing the main criteria to target beneficiaries from urban, peri-urban and rural areas. During the targeting process of the initially planned 540 family groups benefitting from the intervention, it was agreed to address the special needs of women and girls most affected by the pandemic and to focus on female-headed households (2700 beneficiaries -7.23% male-headed households; 92.77% female-headed households). It is recalled that this project is the result of the combined efforts of four United Nations agencies - the World Food Programme (WFP), the United Nations Programme for Human Settlements (UN-HABITAT), the Food and Agriculture Organization (FAO) and the International Labour Organization (ILO) - closely collaborating with national governmental institutions, community leaders and civil society actors, to mitigate the socio-economic impact of Covid-19 in Sao Tome and Principe, and aims to ensure that the food and nutritional security of the most vulnerable populations is counteracted within the Covid-19 scenario".
Kindly note that the team experienced technical issues to upload the relevant pictures, and social media cards, produced to support the communication, visibility and success stories efforts of the project - these are going to be shared through email - in case of any interest the MPTF office team is invited to contact the main RCO Focal Point at cesaltino.fernandes@un.org
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Kindly note that the team experienced technical issues to upload the relevant pictures, and social media cards, produced to support the communication, visibility and success stories efforts of the team - these will be shared through - in case of any interest the MPTF office team is invited to contact the main RCO Focal Point at cesaltino.fernandes@un.org

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board