## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Strengthening a gendered and generational socioeconomic response through evidence-based policy advocacy and analyses. | Overall Duration (months) | 17
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-10-13
MPTF Office Project Reference Number: | 00124306 | Original End Date (dd.mm.yyyy) | 1 Apr 2022
Country | Uruguay | Current End date(dd.mm.yyyy) | 1 Apr 2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UNFPA, UNICEF & UNWOMEN. | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Education and Culture, Ministry of Social Development & National Institute of Statistics.
Report Cleared By
o Name: | Soledad Salvador
o Title: | Project Coordinator
o Email address: | soledad.salvador@unwomen.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The two most substantive activities that were carried out in the first two months of project implementation were the intensification of the dialogue with government actors where working groups were formed by project components, and the installation of the Project Management Committee that had its first meeting in early December. Given that, along with the start of project activities, there was a resurgence of the pandemic and a return to teleworking both in the United Nations offices and in government institutions, all communications and meetings were carried out virtually. Four working groups have been formed: 1) the one on data that includes the interoperability of the databases and the georeferencing of the entire SIAAS system, where INE-IDE-DINEM participate by the government and UNFPA and UN Women by the agencies; 2) that of Employability and care, made up of INMUJERES, MIDES, UN Women; 3) Education, made up of UNICEF and ANEP; 4) Territory where UNDP and UNICEF agreed to an alliance to develop the components with territorial landing, together with MIDES. AUCI is the agency that supports and accompanies the project coordination in dialogue with government actors. With AUCI, the integration of the Management Committee was defined, which includes the representatives of the United Nations agencies involved in the project, the Office of the Resident Coordinator, government institutions (representatives of ANEP, INE, MIDES-DINEM, INMUJERES, UCC). This committee exercises the governance of the project, for which it must monitor the activities committed to the execution of each component of the project and their execution schedules; define the evaluation and monitoring mechanisms for the project as a whole, and adopt the decisions that are necessary to guarantee the correct application of the project funds. Therefore, in the first meeting of the committee, it was defined that the frequency of the meetings will be bimonthly, and changes were proposed and approved to a result, two products and one of their indicators. In this committee, a presentation of the entire project was also made so that all the actors have a more global perspective and the articulation between the different components can be favored. One of the most important achievements has been to reach a political commitment between INMUJERES and INE to develop a new Time Use Survey at the national level. The last survey is from 2013, but at the moment, given the budgetary restrictions and some changes in the implementation of the Continuous Household Survey (within the framework of which the NTUS is raised to take advantage of the sociodemographic information collected by said survey), they put at risk the possibility of applying this survey this year. The funds committed in this project that are relevant to fulfill the proposed objective have been crucial to achieve said agreement.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The purposes of the project are: - generate integrated information systems and analytical reports on vulnerability that are meant to leverage resources and improve their allocation to all those households living in poverty and extreme poverty, as well as to those that, while not in poverty in 2019, were barely above the poverty line and/or shared other critical welfare deficits regarding housing and basic infrastructure. So, in its broadest sense, our target population comprises all the population belonging to what we define as the low-income strata (living below 1,8 poverty lines per-capita). This first estimate, based on the 2019 household survey and using the official poverty line, is that this group represents 34,2% of the population of Uruguay, that is, 330,000 households or 1.2 million people. - The implementation of a 2021 national time use survey that contribute with new data to gender equality policy making going forward. - the development of an employment program for women articulated with childcare services. - guarantee the educational continuity of secondary school students from vulnerable sectors. - Through the UNDP’s Accelerator Lab in Uruguay, an innovation platform will be activated that connects data, information systems and community experiences in order to create transformative solutions for the future delivery of social protection programs.
3.1 | Results: Outcome Level | Please include outcome level results achieved | No results yet
3.2 | Results: Output Level | Please include output level results achieved | No results yet
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Since the approval of the project and with the hiring of the coordinator, dialogues were established with the stakeholders involved to define and agree on the work plans for each component. In some cases, such as the Education component, ANEP, which is the governing body of public education at the national level, considered it pertinent to propose a change that implied a readjustment of the objectives and goals proposed in the project. Instead of developing a hybrid education modality (which combines face-to-face and virtual) it considers more pertinent to guarantee full attendance at all levels of the educational system, and to redirect project resources to support the educational continuity of young people in secondary education (levels 1 to 3 of secondary) of vulnerable sectors. This was agreed with the agency implementing the project and was approved by the Management Committee. On the other hand, the component referring to Employability and Care modified its initial focus on the development of alternatives to solve childcare for those women who have interrupted their labor insertion to guarantee their return to employment, towards the formulation of an employability program for women from vulnerable sectors, guaranteeing their job placement and coverage in care services to accompany the process of training and job placement. A dialogue was also established with the National Employment Directorate (DINAE), which is developing a digital literacy program for low-income women, with the purpose of offering them employment opportunities through the Uruguayan Chamber of Information Technologies (CUTI) so that they consider in their program the care solutions that can be developed or sustained within the framework of this project. In relation to the risks foreseen in the Risk Management Matrix, they are still latent. The risk associated with the budget constraint is real and will become apparent as budgetary resources are required to expand coverage in childcare services. It has been a relevant issue to advance in the agreement on the development of a new Time Use Survey since the limitation in human resources could be resolved if there were more funds to finance them. Administrative fragmentation has also manifested itself in the reduction of the areas of inter-institutional articulation, but it is sought that the project manages to overcome those barriers that are being imposed, without visualizing the costs that they can generate in terms of efficiency. The purpose of increasing the interoperability of information sources to define a new social protection floor that includes more information about individuals and households is representing a significant effort to understand the limitations that arise and try to overcome them. The strategy has been to strengthen the work with State agencies so that they value the importance of cross-checking data and making the allocation of resources more efficient. Regarding the social distancing measures that are still active, it is expected that they will not hinder the implementation of the employability program. MIDES policy has been to suspend the execution of these programs since March 2020, but its implementation is being resumed as of March 2021. Finally, and in relation to the risk derived from the effects of the economic crisis on employment opportunities for women, the program that is being developed seeks to solve it by offering these opportunities after training.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The results of the project are not yet available, but the products that will have an impact at a regional or global level due to their innovative nature are identified. Among them, the construction of a set of economic empowerment indicators that can be considered when defining the granting of economic benefits and inclusion in social and employment programs. Also the development of the experiments that the UNDP will carry out in the territory for an upskilling and reskilling strategy with focus on women employed in the informal sectors and care services of target territories. The development of a new National Time Use Survey that always generates challenges and learning for the academic community at the regional and international level; but it also allows the presentation of progress at the country level both in relation to the SDGs, in particular SDG 5, and in the commitments assumed in the Women's Conferences (the CSW and the regional conference of ECLAC).
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The work with the project partners has been developed through four working groups: 1) the Group referring to data issues that was formed prior to the approval of the project, but it provided the resources to advance in the integration of databases to strengthen the interoperability of the statistical system (SIIAS - Sistema de Integrated Information of the Social Area) and support the georeferencing of the entire system. Participating in the group for the government is the National Statistics Institute (INE), the IDE (Spatial Data Infrastructure area) and the MIDES Evaluation and Monitoring Directorate, which is in charge of defining the beneficiaries for social benefits. For the United Nations agencies, referents from UNFPA and UN Women participate, and those responsible for the Uruguayan Agency for International Cooperation (AUCI) are always present. The project funds complement the resources that the institutions are already allocating for these purposes. In turn, a specific group will be formed on the Time Use Survey where the following will participate: INE, INMUJERES, UNFPA and UN Women. 2) the Employability and Care group made up of INMUJERES, MIDES and UN Women. This group is formed within the framework of this project and while it seeks to advance in the definition of the program's guidelines, it has made contacts with leaders from the interior of the country, to identify the areas where it can be implemented. In turn, links have been established with other actors such as the National Director of Employment because they are developing similar programs, although they had not considered the issue of care. In meetings with the heads of INMUJERES and UCC, these issues have been raised and joint actions will be articulated to seek solutions to the care needs of women inserted in these programs. 3) The Education group made up of UNICEF and ANEP is working on a new program that has been defined to support 12 secondary and technical-professional schools in contexts of greater social vulnerability. The support will be allocated to personalized accompaniment and work with families to contribute to their integration and permanence in the centers. The results will be extremely useful for the inclusion of this component in the following editions of the program. At the same time, when the contagion curve has risen and we are one month away from starting classes, several agencies led by UNICEF, UNFPA, UNESCO, PAHO and UN Women are calling for a "back to school" campaign. So that the efforts being made by the government to guarantee full attendance are matched with good attendance. To do this, it has sought to bring a message of trust to families assuming that educational institutions are "the first to open and the last to close". Funds from this project will be earmarked for said campaign if ANEP's approval is obtained and other support from other agencies will be added. 4) Finally, the group with the greatest emphasis on the Territory, UNDP and UNICEF agreed to an alliance to develop these components together with MIDES and local governments.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | They have not yet been developed because the implementation of the project is just beginning.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The First Management Committee approved the change in Outcome 2, Outputs 2.1 and 2.2, and indicator 2.1.2. The Outcome 2: “Expanded in-school system and care services are available for most vulnerable Uruguayans by 2021, especially in critical territories, minimizing epidemiological risks while reducing women's unpaid care workload”, was redefined as: "Employability program for women in situations of economic and social vulnerability, and improvements in the educational trajectories of adolescents ". The Output 2.1: “A national plan and protocol for the expansion of in school and care services is designed in dialogue with national stakeholders, using standards and international best practices” was redefined as: "Support for the ANEP Center Development Plan to guarantee the permanence and educational continuity of adolescents from a critical socio-economic context and UCC initiatives to strengthen positive parenting practices ". The Indicator 2.1.2: “Number of teachers with self-reported increased abilities to quality digital and remote education, by sex” is replaced by two others, which are: "Number of students who receive psychotechnical support until the end of the school year , out of the total number of students who start the courses in March "and" Number of students who finish the school year out of the total students who started the courses in March ". The targets for the new indicators are: "All students who require psychotechnical support receive it throughout the school year"; and "All students who started the school year finish it". The Output 2.2: “Large scale programs of care for children in most vulnerable areas will be piloted in partnerships with subnational governments and the private sector allowing working parents (particularly mothers) to return and remain in the labor force, combined with training and employment strategies targeted for vulnerable women ”was redefined as:" Employability program for women in a situation of economic and social vulnerability together with the development of care strategies that allow women to participate in the program and sustain their labor insertion ".
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The project mobilizes resources from government partners because the activities are co-financed, both the resources for georeferencing and interoperability of databases, the development of a Time Use Survey, the program for the educational continuity of adolescents of ANEP, and the campaign that is about to start to support the “return to classes” in face-to-face mode.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] A new basic protection floor is in place for 2021 allowing to better target the most vulnerable Uruguayans, particularly women head of households and women working in the informal sector | There is no data yet because the project implementation strategy is being developed. |  | The National Continuous Household Survey 2020 that will be available between March and April, and DINEM (National Directorate of Evaluation and Monitoring) data sources.
Indicator 1.1: Percentage (%) of beneficiaries of social protection schemes for vulnerable population, by type of programme. (Indicator contributing to SERP indicator 2.5)
Baseline:By type of programme: Cash Conditional Transfers (CCT): 68,5% of poor households; Uruguay Social Card (TUS): 39,2% of poor households. Sex dissagregation not available yet. Percentage (%) of female-headed households of poor household=40% (Source: Social Sciences Faculty, based on National Continuous Household Survey 2019, INE.)
Planned Target:CCT=at least 85% TUS=at least 50% Sex dissagregation will be advocated for
Indicator 1.2: Percentage (%) of poor female headed household benefitting from cash transfer programmes.
Baseline:66% (Source: own estimations based on National Continuous Household Survey, 2019, INE)
Planned Target: Percentage (%) of women-headed households: at least 70%
Output 1.1 An Integrated data system is delivered to be used by the Uruguayan Government, to improve the capacity of social protection policies to target vulnerable population, particularly women working in the informal sector and women heads of household in charge of children. | There is still no significant progress, but the inter-institutional dialogue to improve the interoperability of the available databases has begun. |  | the reports made by DINEM based on the databases of the SIIAS (Integrated Information System of the Social Area) system.
Indicator 1.1.1: An integrated non-contributory social protection system and emergency support mechanism is adopted by national institutions.
Baseline: Boolean: Weak. Low interoperability incompleteness
Planned Target: Boolean: Strong. High Interoperability, completeness
Indicator 1.1.2: Number of indicators sensible and gender transformative integrated as part of the new proposal of non-contributory social protection system and emergency support | The design of these gender transformative indicators has just begun. |  | The document with the proposal prepared by the National Institute for Women (INMUJERES).
Baseline: 0
Planned Target: At least 3
Output 1.2 A redefinition of the non-contributory social protection systems and emergency support that responds to the new challenges brought by COVID-19 and prepares the country to face future outbreaks. | There are no results yet, but progress was made in the inter-institutional dialogue (IDE-INE-DINEM) to support the realization of the Unique System of Geographic Addresses of Uruguay. With this, it will be possible to advance in the georeferencing of personal data. |  | Information from the IDE (Spatial Data Infrastructure) on the institutions that have adopted the system.
Indicator 1.2.1: Number of institutions that own and have capacities to operate an integrated data system to activate emergency support mechanisms and inform public policies to face future outbreaks.
Baseline: Number of national institutions with capacity to operate the integrated data system: 1
Planned Target: At least 4
Output 1.3 Effective coordination institutional capacities developed in target territories, with focus in subnational governments capacities and multi-level coordination of social policies | There are no results yet, but the implementation of the strategy in the territory has already been agreed. |  | Reports on progress in the implementation of the strategy that will include photos, videos, stories, etc..
Indicator 1.3.1: Number of social development offices and development offices that engage in the regional network
Baseline: 4
Planned Target: 8
Indicator 1.3.2: National & subnational governements agree on an agenda to overcome implementations gaps in target territories | No progress yet. |  | The agendas agreed with each local government.
Baseline: Boolean: No
Planned Target: Boolean: Yes
Outcome 2. Expanded in-school system and care services are available for most vulnerable Uruguayans by 2021, especially in critical territories, minimizing epidemiological risks while reducing women’s unpaid care workload | No progress yet. | The Outcome 2 statement was redefined as: "Employability program for women in situations of economic and social vulnerability, and improvements in the educational trajectories of adolescents". | ANEP's statistical sources.
Indicator 2.1 Percentage (%) of children from the first quintile of social vulnerability that participated in public education proposals.(Indicator contributing to SERP Indicator 2.2)
Baseline: Primary school: 72%, Secondary school: 28% & Technical school: 44% (Source: "Educational situation in the context of the health emergency". Teacher Survey - ANEP, July 15, 2020) Sex dissagregation not available yet.
Planned Target: Primary school: at least 85%, Secondary school: at least 40%, Technical school: at least 55%. Sex dissagregation will be advocated for.
Output 2.1: A national plan and protocol for the expansion of in school and care services is designed in dialogue with national stakeholders, using standards and international best practices. | The Output 2.1 statement was redefined as: "Support for the ANEP Center Development Plan to guarantee the permanence and educational continuity of adolescents from a critical socio-economic context and UCC initiatives to strengthen positive parenting practices".
Indicator 2.1.1: A communication campaign, gender and age responsive, to promote the importance of educational continuity. | It is not yet available, it will be designed in February to be disseminated before and during the start of classes. |  | The communication campaign.
Baseline: Boolean: No
Planned Target: Boolean: Yes
Indicator 2.1.2: Number of teachers with self-reported increased abilities to quality digital and remote education, by sex. | This indicator is replaced by two others, which are: "Number of students who receive psychotechnical support until the end of the school year, out of the total number of students who start the courses in March" and "Number of students who finish the school year out of the total students who started the courses in March ". | The targets for the new indicators are: "All students who require psychotechnical support receive it throughout the school year"; and "All students who started the school year finish it". | The monitoring and evaluation reports carried out by ANEP.
Baseline: Male: 57, Female: 109
Planned Target: Male: 150, Female: 300
Output 2.2: Large scale programmes of care for children in most vulnerable areas will be piloted in partnerships with subnational governments and the private sector allowing working parents (particularly mothers) to return and remain in the labor force, combined with training and employment strategies targeted for vulnerable women. | The Output 2.2 statement was redefined as: "Employability program for women in a situation of economic and social vulnerability together with the development of care strategies that allow women to participate in the program and sustain their labor insertion".
Indicator 2.2.1: Number of new gender and age-responsive care initiatives developed in partnership with local stakeholders. | No progress yet.
Baseline: 0
Planned Target: 4
Indicator 2.2.2: A new socioeducational and labour programme within the institutional offer is targeted exclusively for vulnerable women developed and piloted. | The UCC program and the National Institute of Women are jointly designing this program. |  | The program itself.
Baseline: Boolean: No. (The programme Uruguay Trabaja is delivered for both women and men)
Planned Target: Boolean: Yes
Indicator 2.2.3: Percentage of time deliver in paid and unpaid work for women and men, based on National Time Use Survey. | The institutional commitment of INMUJERES and the INE to carry out a new NTUS in the second half of 2021 was politically agreed. |  | The results report of the National Time Use Survey 2021.
Baseline: According to the last TUS 2013: Women: 35.5% paid work and 64.5% in unpaid work; Men: 68.1% paid work and 31.9% in unpaid work. (Source: Module Use of time and unpaid work of the Continuous Household Survey 2013, INE-INMUJERES-FCS)
Planned Target: New National Time Use Survey: tbd
Output 2.3: Experimentation and innovation strategy for women economic empowerment and a new architecture of solutions for care
Indicator 2.3.1: Number of gender and age responsive implemented and evaluated experiments in target territories. | No progress yet. |  | The reports with the results of the experiments.
Baseline: 0
Planned Target: 3
Indicator 2.3.2: Participative roadmap for a local innovation strategy elaborated and ready for implementation. | No progress yet. |  | The agreed roadmap.
Baseline: Boolean: No
Planned Target: Boolean: Yes
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
We do not yet have stories to tell, but we are eager to begin that process of collecting evidence that shows the effects of the project in mitigating the socio-economic impacts of COVID-19.
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board