## Annual Work Plan&Budget
PROJECT WORK PLAN
Project Title:
Results | Baseline and targets | Activities | 2021 | [11 empty] | Responsible parties | Key deliverables | Budget description | Budgeted for 2021 |  | Total Budgeted for 2021 | Level of expenditure/commitments in USD |  | Total Commitments
|  |  | J | F | M | A | M | J | J | A | S | O | N | D |  |  |  | Voz di Paz | Interpeace |  | Voz di Paz | Interpeace
Outcome 1: Relationships between youth leaders and key government institutions/authorities at the national and local level are improved | [17 empty] | 71054.0303 | 34996.7612 | 106050.7915 | 0 | 0 | 0
Output 1.1: Young men and young women leaders are connected to representatives of key government institutions, including government institutions in charge of promoting gender equality/women’s empowerment and participation | [17 empty] | 39701.3818 | 19554.4119 | 59255.7937 | 0 | 0 | 0
Indicator 1.1.1: | Baseline 1.1.1: Target 1.1.1: | A 1.1.1: Mapping of key stakeholders from local, regional and national authorities as well as youth leaders (young men and women) from CSO, grass root associations, political parties and Security and Defense Forces (SDF) with ERD contribution | [12 empty] | Interpeace and Voz di Paz | 1 mapping file and its visualization | categories 1 and 6 | 20970.2093 | 10328.6106 | 31298.8199 | 0 | 0
Indicator 1.1.2: | Baseline 1.1.2: Target 1.1.2: | A 1.1.2: 11 regional dialogue spaces/circles in the regions and in Bissau to identify main institutional and societal barriers to youth participation at the regional and national level | [12 empty] | Voz di Paz with interpeace and ERD support | 1 report and 1 record for each dialogue session | categories 1 and 6 | 18731.1724 | 9225.8013 | 27956.9738 | 0 | 0
Output 1.2: Participants in the dialogue process develop a common vision on meaningful youth participation and establish regional plans for their future involvement and inclusion in local/regional and national decision making bodies/bodies | [17 empty] | 31352.6485 | 15442.3493 | 46794.9978 | 0 | 0 | 0
Indicator 1.2.1: | Baseline 1.2.1: Target 1.2.1: | A 1.2.1: Develop and design 11 common strategy and action plan (roadmaps) on how to make youth participation effective tackling the obstacles and barriers identified | [12 empty] | Voz di Paz with Interpeace and ERD support | 11 roadmaps document (1 for each session) validated by participants | categories 1 and 6 | 15975.5775 | 7868.568 | 23844.1455 | 0 | 0
Indicator 1.2.2: | Baseline 1.2.2: Target 1.2.2: | A 1.2.2: 11 Validation meetings with institutions and participants in the dialogue process to validate and “endorse” the recommendations elaborated at regional level | [12 empty] | Voz di Paz with interpeace and ERD support |  | categories 1 and 6 | 15377.0711 | 7573.7813 | 22950.8524 | 0 | 0
Outcome 2: Capacities and self-confidence of young men and women to influence public decision-making at the local, regional and national level are strengthened | [17 empty] | 63404.8491 | 31229.254 | 94634.1032 | 0 | 0 | 0
Output 2.1: 220 young leaders, 50% of whom are women, are supported and connected through mentoring platforms. | [17 empty] | 19434.177 | 9572.0573 | 29006.2343 | 0 | 0 | 0
Indicator 2.1.1: | Baseline 2.1.1: Target 2.1.1: | A 2.1.1: Creation of 11 mentoring platforms that serve as safe spaces for young men and women leaders to exchange experiences, capacities, and competencies on how to participate in and influence upon decision-making processes | [12 empty] | Voz di Paz with interpeace and ERD support | 1 report for each "constitutional" session. | categories 1 and 6 | 19434.177 | 9572.0573 | 29006.2343 | 0 | 0
Output 2.2: Young leaders’ access to technical and financial support to design and develop local initiatives promoting youth engagement in decision-making is increased | [17 empty] | 43970.6721 | 21657.1967 | 65627.8688 | 0 | 0 | 0
Indicator 2.2.1: | Baseline 2.2.1: Target 2.2.1: | A 2.2.1: Establishment of a pilot micro-grant mechanism for youth-led initiatives promoting effective youth engagement in decision-making | [12 empty] | Interpeace will lead an internal workshop to define the microgrant mechansim. Implementation will be done with VdP | 1 micro-grant mechanism (TDR and guidelines + documentation of the call and the selection process) | categories 1 and 6 | 24636.0986 | 12134.1978 | 36770.2964
Indicator 2.2.2: | Baseline 2.2.2: Target 2.2.2: | A 2.2.2: Establishment and implmentation of a monitoring system of funds granted with ERD | [12 empty] | ERD guided by VdP with IP technical support | Database of monitoring of youth granted | categories 1 and 6 | 19334.5736 | 9522.9989 | 28857.5725 | 0 | 0
Outcome 3: Local/regional and national support for new youth-owned leadership model is increased challenging the common narrative around young men and women leadership | [17 empty] | 33082.0655 | 22626.1517 | 49376.2171 | 0 | 0 | 0
Output 3.1: Successful experiences of youth leaders are shared with to key institutions and the wider public. | [17 empty] | 33082.0655 | 16294.1517 | 49376.2171 | 0 | 0 | 0
Indicator 3.1.1: | Baseline 3.1.1: Target 3.1.1: | A 3.1.1: Trainings of 24 youth leaders in Bissau on participatory video-making, storytelling and communication techniques for social change | [12 empty] | Voz di Paz AV team with Interpeace support | 24 youth trained | categories 1 and 6 | 17477.8988 | 8608.5173 | 26086.4161 | 0 | 0
|  | A 3.1.2: Production and dissemination of 24 videoclips | [12 empty] | Voz di Paz AV team | 24 videoclipes produced by youth granted | categories 1 and 6 | 0 | 0 |  | 0 | 0
Indicator 3.1.2: | Baseline 3.1.2: Target 3.1.2: | A 3.1.3: Production and dissemination of 11 radio programmes broadcasted nationwide | [12 empty] | Voz di Paz AV team | 11 radio programmes | categories 1 and 6 | 15604.1667 | 7685.6343 | 23289.801
Indicator 3.1.3: | Baseline 3.1.3: Target 3.1.3: | A 3.1.4: Realization of 20 radio debates between youth leaders and key people from the older generation | [12 empty] | Voz di Paz AV team | 20 radio debates | categories 1 and 6 | 0 | 0 |  | 0 | 0
Project management | [17 empty] | 0 | 6332 | 6332 | 0 | 0 | 0
Additional personnel costs
Additional Operational Costs | [16 empty] | category 1 | 0 | 2982 | 2982 | 0 | 0
Monitoring &Communication budget | [16 empty] | categories 4 and 5 |  | 3350 | 3350
Budget for independent final evaluation | [17 empty] | 0 | 0 |  | 0 | 0
[19 empty] | TOTAL | 256393.1118 |  | TOTAL | 0
[19 empty] | ISC 7% | 17947.5178 |  | ISC 7% | 0
[19 empty] | TOTAL | 274340.6296 |  | TOTAL | 0
Note on E5: [Comentário por tópicos] A sua versão do Excel permite-lhe ler este comentário por tópicos. No entanto, as edições feitas ao comentário serão removidas se o ficheiro for aberto numa versão mais recente do Excel. Saiba mais: https://go.microsoft.com/fwlink/?linkid=870924 Comentário: The timeline of activities will be updated on a monthly basis to demonstrate if project is on track
Note on S5: [Comentário por tópicos] A sua versão do Excel permite-lhe ler este comentário por tópicos. No entanto, as edições feitas ao comentário serão removidas se o ficheiro for aberto numa versão mais recente do Excel. Saiba mais: https://go.microsoft.com/fwlink/?linkid=870924 Comentário: As per UN budget categories: 1. Staff and other personnel 2. Supplies, Commodities, Materials 3. Equipment, Vehicles, and Furniture (including Depreciation) 4. Contractual services (including M and E) 5.Travel (including M and E) 6. Transfers and Grants to Counterparts 7. General Operating and other Direct Costs
Note on W5: [Comentário por tópicos] A sua versão do Excel permite-lhe ler este comentário por tópicos. No entanto, as edições feitas ao comentário serão removidas se o ficheiro for aberto numa versão mais recente do Excel. Saiba mais: https://go.microsoft.com/fwlink/?linkid=870924 Comentário: An estimate of financial commitments will be updates on a monthly basis to monitor budget implementation levels