## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | COVID-19 Response to Vulnerable Population and Frontline Workers In Belize | Overall Duration (months) | 8
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 21.05.2020
MPTF Office Project Reference Number: | 00121700 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | Belize | Current End date(dd.mm.yyyy) | 31.12.2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | PAHO/WHO; UNHCR; UNFPA; ILO | National counterparts (government, private, NGOs & others) and other International Organizations | Governement - Ministry of Health & Wellness
CSOs: Belize Family Life Association Humana People to People Belize Help for Progress Belize Red Cross Society Belize Chamber of Commerce and Industry National Trade Union Congress of Belize
Report Cleared By
o Name: | Birgit Gerstenberg
o Title: | UN Resident Coordinator
o Email address: | erika.gerstenberg@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
| Questions | Guidance to respondents
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The COVID-19 MPTF joint programme in Belize was successfully implemented with all related activities completed having reached an estimated 206,435 persons (49% of population) who have benefitted from the five outputs under this joint programme. For the risk communication interventions, major progress was made in the public health sector by developing, with national health authorities, an upgraded National Risk Communication Strategy along with a new repository of ready-to-use COVID-19 messages tailored to the specific target groups, with a growing stock of other communication products available. There was also progress made in the area of occupational safety and health (OSH) with the completion of the campaign on COIVD-19 in the workplace. The campaign was developed and implemented in collaboration with the National Trade Union Congress of Belize (NTUCB) and the Belize Chamber of Commerce and Industry (BCCI). It was approximated that the OSH public service announcements reached about 75% of the population. Scaling-up community-based health services and isolation facilities were completed. Major progress was made under this output as medical equipment and personal protective equipment for the isolation facilities in the Central Health Region and Western Health Region (Belize and Cayo Districts) were handed over to the Ministry of Health and Wellness, strengthening the capacity of the health sector in managing COVID-19 cases. Furthermore, an adjusted package of medical equipment and supplies as well as emergency beds and space dividers were provided to the isolation area of the Rural Health Center of Valley of Peace, Cayo District which is one of the few community-based COVID-19 isolation facilities in Belize. Despite the challenges with international procurement and transportation of selected medical items, Community-based health workers (CHW) were provided with adequate equipment and instruments to advise, first respond and/or refer vulnerable COVID-19 patients. A total of 250 kits containing diagnostic items, such as sphygmomanometers, urine dipsticks, hand sanitizers, masks, gloves, were donated to CHWs operating in the Western Health Region and Southern Health Region. An orientation session was attended by all CHWs to ensure appropriate use of the kits in the community. District Health Educators also participated in the orientation session. Lastly, interrupted services for antenatal and postnatal care, were restored and made very good progress, as service delivery strategically focuses on the reinforcement of breastfeeding, undertaking face-to-face sessions for counseling mothers on the benefits of breastfeeding, substantially outweighed the potential risks for transmission of COVID-19. The conduct of telehealth services for pre and postnatal care also provided support in the prevention of COVID-19 transmission by reducing walk-ins and allowing health professionals to remotely follow-up with clients and schedule in-person appointments as needed (e.g. for high risk pregnancies). In addition, COVID-19 tests and extraction kits were made available to the Central Medical Laboratory for the testing of pregnant women. Another interrupted service, sexual and reproductive health (SRH), also continued through the conduct of SRH/Contraceptive mobile clinics which included HIV & STI counselling, delivery and administering of contraceptives, and where applicable, safe identification and referral of GBV survivors for psychosocial support e-services.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The purpose of the joint programme was to assist government and rural communities in Belize in (i) halting the transmission of the COVID-19 in government-selected priority rural areas; and (ii) reducing the impact on human lives, by facilitating access to health services, ensuring essential medical care for pre-existing conditions and reducing the risk of frontline health workers and the labour force in tourism-related sectors. The isolation facilities provided isolation services to the most vulnerable persons - Belizeans and refugees/asylum-seekers. A total of 31,584 persons were direct beneficiaries of improved COVID-19 isolation facilities, of which 29,031 Belizeans and 2,823 asylum-seekers. When including the support provided to CHWs, the number of direct beneficiaries increases to 41,542, all Belizeans and residents. In the Central Health Region, an estimated 127,683 persons benefitted from the donated medical supplies and equipment. By 31 December 2020, BFLA conducted 27 mobile clinics under the joint programme funded support to provide the essential package of SRH family planning services to a total of 499 persons disaggregated by age group and sex below: Female = 438 (Adolescent <20yrs = 26; Adult >20 =412) Male = 61 (Adolescent <20yrs = 8; Adult >20 = 53)
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output 1 - Risk Communication | Please include output level results achieved | Risk Communication and Community Engagement (RCCE) Strategy targeted and adapted actions to enable populations in situations of vulnerability to access COVID-19 health services with 500 COVID-19 Quick Facts and Resources Booklets developed, printed and made available to 150 CHWs. Booklets were provided to all CHWs and ensuring availability for the communities they serve to have access to important COVID-19 information and resources. Translation of COVID-19 preventive messages to languages that are understood by Afro-descendants and indigenous people facilitated effective prevention actions to protect their health. 32 posters developed and printed with COVID-19 preventative messages - 12 posters in Garifuna, 10 posters in Mopan Maya and 10 posters in Q'qechi Maya. Additionally, to raise awareness and visibility of the MPTF Response and Recovery Fund, labels/decals were designed and printed and placed on the various equipment and items donated. This included the branding on the 150 CHW bags that were bought to hold the diagnostic items provided. As a result of the increased public information, driven by the dissemination of targeted and tailored risk communication products, in combination with the improved operations of CHWs in communities and neighborhoods some 206,435 persons were informed on how to prevent the transmission of COVID-19 and when and where to seek medical attention. BFLA posted 130 of the UNFPA, UNICEF, PAHO/WHO and MOH posters, or products and flyers and audio messages on main social media pages. The sharing of the messages cumulatively reached 55,689 persons. 65.5% of those viewers to the pages and posts were women and 34% men. For MOH, flyers were given to pregnant women when booked for prenatal care. These were available at health facilities and during mobile clinics. The posters were placed at 100% of the health facilities in public areas, reaching approximately 625 unique women who would have accessed services from the Maternal & Child Care Units. In 2021, dissemination will continue with placement in public areas e.g. stores and supermarkets.
| Results: Output 2 -Practical guidelines and knowledge products for workers addressing OSH |  | An OSH campaign on COVID-19 in the workplace was developed in cooperation with the National Trade Union Congress of Belize (NTUCB) and the Belize Chamber of Commerce and Industry (BCCI). The campaign consisted of: - 3 Radio public service announcements designed and aired - 3 Newspaper public service announcements designed and printed - 3 TV public service announcements designed and aired - 3 Infographics about how to prevent contagion at the workplace designed and disseminated - 3000 Pamphlets about how to prevent contagion at the workplace All assets for the campaign were produced in English and Spanish. Radio and newspaper public service announcements were broadcasted for 6 weeks, starting in December 2020. The recording and production of the television PSA announcements was delayed because of the restrictions imposed by COVID-19. It is expected that these PSAs will start to be broadcasted in February 2021. It is anticipated that the public service announcements would reach about 75% of the population. The 3000 pamphlets were distributed between the NTUCB and the BCCI, for disseminated among their member organizations/entities.
| Results: Output 3 - Facilities & Community Health Care Services |  | Medical equipment and personal protective equipment for the isolation facility in the Central Health Region were handed over to the Ministry of Health and Wellness, strengthening capacity of health sector to manage COVID-19 cases. The following PPEs were purchased in consultation with MOHW: a) PPEs: 1000 KN95 masks, 1000 surgical masks, 1000 disposable gowns, 650 googles, 650 face shields, medical waste bags and sharp containers; b) Medical equipment: 5 Patient monitors, 5 Laryngoscopes, 2 AED Defibrillators. In addition, an adjusted package of medical equipment and supplies as well as emergency beds and space dividers were provided to the isolation area of the Rural Health Center of Valley of Peace, which is one of the few community-based Covid-19 isolation facilities in Belize.
| Results: Output 4 - Community-based Health Workers |  | A total 150 kits containing diagnostic items, such as sphygmomanometers, urine dipsticks, hand sanitizers, masks, gloves, were donated to CHWs operating in the Central and Northern Health Regions. An orientation session was attended by all CHWs to ensure appropriate use of the kits in the community. District Health Educators also participated in the orientation session. UNHCR was able to provide similar basic field health care Covid-19 basic field kits (total of 100) to all 73 CHWs operating in the Western Health Region plus 27 CHWs operating in the Independence catchment area of the Southern Health Region.
| Results: Output 5 - Interrupted Services for AN/PN Care |  | A total of 14,400 COVID-19 test kits and 2,500 extraction kits were procured and handed over to the Maternal and Child Health unit of the MOHW to support the testing of pregnant women. Mobile Services: Pregnant and lactating mothers receive follow-up correspondences by phone to ensure timely and adequate care for appointment system targeting pregnant women diagnosed with COVID-19 (170) and other diseases. Preliminary data indicate that the following number of services were delivered in the last six months of 2020: Child Health Services – 27,731; Prenatal care total - 17,136; Postnatal care - 1,870 and vaccines administered – 70,252. Approximately 90% (N=3228) achievement of target for 6 months implementation which is 50% (N=3625) of originally estimated annual births (7250). However, preliminary data is already indicating a reduction in childbirths in 2020 (i.e. 6549). At 31 December 2020, BFLA conducted 27 mobile clinics funded by the joint programme to provide the essential package of SRH family planning services to a total of 499 persons disaggregated by age group and sex below: Female = 438 (Adolescent <20yrs = 26; Adult >20 =412) Male = 61 (Adolescent <20yrs = 8; Adult >20 = 53)
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Operational: In the course of the first phase of the Joint Programme, characteristics of the pandemic had evolved, creating a challenge for identifying critical needs of the health sector as well as geographic priorities. The pandemic had shifted geographic focus of the infection clusters and as a result the Southern region was deemed to be also in need of attention for building an improved defense to an anticipated increase in community spread. This resulted in an additional focus on the Independence area of the Southern Health Region, where UNHCR co-funded from its core agency resources along with MPTF funds to provide support to the MOH Polyclinic Independence. In addition, COVID-19 related restricted measures caused the cancellation of CHW technical training events during which the distribution of CHW kits were envisioned to take place; the distribution was completed by way of a formal hand-over to MOH. In November 2020, Belize held general elections while the programme was under full implementation, lowering the impact on the implementation of the activities. The Programme experienced major challenges due to the risks posed by natural disasters. Although, the first weather disturbance on 3 September 2020 did not impact operations significantly, the two consecutive storm systems (Eta and Iota) placed additional pressures on the government, including MOH, as the unprecedented levels of flooding in many geographic zones of the country resulted in population groups moving to temporary shelters, thereby increasing the risk of heightened community transmission. Procurement efforts were re-prioritized to respond to needs of affected communities. Additionally, some PAHO/WHO staff had been re-assigned to follow-up on purchases of medical equipment and supplies which was part of this project. These storm systems only slightly delayed SRH/Contraceptive mobiles given the resulting flooding in some targeted communities. Delivery: The printing of the English and Spanish COVID-19 booklets for the CHWs experienced some delay due to illness of some staff members of the printing company. Furthermore, some handbooks were printed late in December due to the high demand for printing services from the hired company. Close follow-up with the printing company was made to ensure that materials were delivered timely. 2 Maternal & Child Health (MCH) health nurses of the MOHW contracted COVID-19 but did not significantly impact on the delivery of telehealth services.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Interagency coordination and collaboration: UN collaboration with the Ministry of Health in view of the development of an overall Risk Communication and Community Engagement Strategy resulted in a comprehensive exercise that created a solid basis and concrete tailored reference communication products for current and future Risk Communication & Community Engagement beyond the joint programme. The inter-agency risk communication effort was fully integrated into the work agenda of the UN Communications Group (UNCG), allowing for a whole of UN approach in support to risk communication for COVID-19. Gender Marker: The procurement of PCR tests for pregnant women, SRH mobile services and remote ante and prenatal care services which both included other forms of SRH information and services such as STI counselling, directly targeted women and girls of reproductive age, responding to SDG target 3.7. These activities also empowered women and girls to choose freely and responsibly, if and when to have children, and the number and spacing of them. Anecdotal evidence suggested that several rural facilities discontinued or curtailed services such as SRH services to prioritize COVID-19 prevention and response. The telehealth support facilitated the prevention of COVID-19 transmission by reducing walk-ins and allowed health professionals to remotely follow-up with clients and schedule in-person appointments as needed (e.g. for high risk pregnancies).Although women were targeted, services and commodities were delivered to men as well given the demand encountered in the community. These included HIV testing and counselling as well as the dissemination of condoms to men. Inclusion: The National Garifuna Council and the Belize National Indigenous Council expressed appreciation in being included in the development of the language-specific (Garifuna, Mopan, and Q'eqchi) posters appropriate for these population groups. As target groups sometimes left behind, they were grateful that posters were made to target their populations. It is expected that these two councils will be included in future development of communication materials also to be developed to target these population groups. CHWs recognized and expressed the value of equipment/supplies for the effective day-to-day work at community level as they encounter persons with chronic diseases. The additional equipment/supplies provided contributed to increasing moral and motivating of CHWs in their work. This will now be followed by specific training on COVID-19 and chronic diseases that will enhance proper use of equipment. The expectation is that this capacity strengthening efforts will contribute the CHWs being integrated as part of the referral health network at community level.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The development of the Risk Communication and Community Engagement Strategy strengthened the existing relationship with the Ministry of Health and Wellness allowing the ministry to work closer with all the UN agencies in developing strategies and key messages that targeted various population groups responsive to agency mandates. Apart from the MOHW, the relationship was also strengthened with the Ministry of Foreign Affairs through the assistance in airing of COVID-19 PSAs and voting ads leading up to the general elections held in November 2020 in Belize. The CHWs sessions during the World Breastfeeding Week strengthened existing partnerships with Health Education and Community Participation Bureau of Belize (HECOPAB), the Institute of Nutrition of Central American and Panama (INCAP), the Ministry of Health, and other UN agencies such as UNICEF. The training of Community Health Workers and this intervention was done though the collaboration of PAHO/WHO and UNHCR and this complemented the efforts of the MOHW in strengthening local level capacity to provide basic level primary care. UNHCR Direct Implementation modality did not result in developing new programmatic partnerships but brought new levels of inter-institutional familiarity and communication between UNHCR and local health authorities and staff, providing additional avenues to strengthen UNHCR’s community-based intervention for adequate inclusion and integration of persons with international protection needs in local and regional initiatives for improved social services.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | UNFPA Caribbean conducted a Reproductive Health Commodity Security (RHCS) Assessment across the Caribbean, including Belize. The draft report is being finalized and results will become available in 2021. UNFPA Caribbean also conducted a Caribbean Youth Sexual and Reproductive Health Needs Assessment during COVID-19 which was both a qualitative and quantitative research. The draft report is being finalized and results will become available in 2021.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | No programmatic revisions were done for the joint programme. Budget revision was completed by implementing UN entities to adjust budget allocation by expense categories.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | PAHO/WHO reoriented funds from its current European Union funded Health Sector Support Programme to support COVID-19 response in Belize. Complementary actions were made between this project and that of the EU grant, particularly in enhancing communication and community health services. Additionally, a project proposal was recently approved by the India-UN Development Partnership Fund to strengthen clinical management of COVID-19 patients and reduce risk of COVID-19 transmission among healthcare workers in Belize. Initially, UNHCR had projected to engage a consultant for managing the UNHCR portion of the joint programme but revised that plan as most of the activities were related to procurement, which was done in close collaboration with PAHO/WHO. List of items and specifications for COVID-19 isolation facilities and basic field kits for MOH CHWs were agreed and consistent. It was mutually decided to procure through separate processes to comply with specific agencies’ procurement policies and regulations. Financial management was undertaken by the UNHCR Belize office in consultation and collaboration with the parent UNHCR Multi-Country Office Panama. UNHCR did not mobilize additional resources from other partners but co-financed from its own core resources the COVID-19 support provided to the MOH Independence Polyclinic. 10% Liaison Officer time ($10,863.20) and 20% Programme/Operations Clerk time ($4,764) for administrative functions (establishment of IP, HACT processes, etc.) and monitoring. In kind support was mobilized from the Ministry of Health via the Community Health Workers who supported with community mobilization for the SRH/Contraceptives mobiles. In kind support in the form of venue from other government ministries for the conduct of the SRH mobiles (e.g. Ministry of Human Development, San Pedro). UNFPA developed key messages and communication products in the context of COVID-19 were utilized by IP to conduct risk communication

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome: Rural and urban vulnerable population/communities have increased their knowledge to prevent and recover from COVID-19 through actions led by government institutions | 206,435 persons | N/A | Program Documentation Diagnostics from Social Media Platforms UNFPA/BFLA Monitoring Tables
Indicator: The number of vulnerable populations/communities that know how to prevent the transmission of COVID-19 and when and where to seek medical attention
Baseline: Total 45,075 (20%); Women 22,550 (20%); Men 22,525 (20%); Refugees 385 (20%)
Planned Target: Total 90,150 (40%); Women 45,100 (40%); Men 45,050 (40%); Refugees 963 (50%)
Output 1.1: Risk communication interventions delivered, reaching the targeted, most-vulnerable populations in the country | 206,435 persons CHWs - 250 | N/A | Program Documentation Diagnostics from Social Media Platforms UNFPA/BFLA Monitoring Tables
Indicator 1.1.1: The number of persons from vulnerable populations exposed to formal information on how to protect themselves against COVID-19 at home consistent with human rights principles.
Baseline: NA
Planned Target: Population of Belize: 419,199; CHWs: 233
Output 1.2: Practical guidelines and knowledge products for workers in high-risk health & tourism sectors developed, addressing occupational health and safety challenges related to COVID-19. | The media company in charge of the development and dissemination of the assets of the campaign (Ignite Ltd.) have informed that the public service announcement would reach about 75 per cent of the population | The Department of Labour was not reactive and therefore the content of the awareness and sensitization activities were agreed with the NTUCB and BCCI . This situation changed the scope of this Output and only focused on the OSH campaign in the workplace. | Official notification from the Labor Department and adoption by workers’ and employers’ organizations The formal document agreed by the management and workers
Indicator 1.2.1: Number of workers from high-risk employment sectors exposed to formal information on minimum occupational safety standards related to COVID-19. Disaggregation: employment sector
Baseline: Health Sector: 0 ; Tourism Sector: 0
Planned Target: Health Sector: 500 Tourism sector: 1,500
Output 1.3: Facility and community-based health care services equipped and prepared to provide preventive and curative care to COVID-19 patients, particularly form vulnerable populations in rural and remote communities in Cayo and Belize Districts | 4 MOH public health facilities benefited from basic medical equipment, medical items and PPE items to the isolation units: Belmopan Western Regional Hospital; Valley of Peace Rural Health Center; Independence Polyclinic and Central Health Regional Hospital. | The pandemic had shifted geographic focus of the infection clusters and as a result, the Southern region was deemed to be also in need of attention for building an improved defense to an anticipated increase in community infection spread. | Donation letter, Press Release; Letter of receipt, signed by persons in charge of the respective health facility.
Indicator 1.3.1: Number of COVID-19 isolation facilities equipped and meeting minimum human rights standards.
Baseline: 0
Planned Target: 2
Output 1.4: Community-based health workers (CHW) provided with adequate equipment and instruments to advice, first respond and/or refer vulnerable community residents who register health complaints related to COVID infection as well as non-communicable diseases | 250 COVID-19 basic field kits were provided to CHWs |  | Donation letter, Press Release; Letter of receipt, signed by Health Education and Community Participation Bureau (HECOPAB) of MOH.
Indicator 1.4.1: Number of CHWs equipped and trained with new skills related to adequate community response to COVID infections as well as NCDs
Baseline: 0
Planned Target: 233
Output 1.5: Interrupted services for antenatal and postnatal care are restored and reaching out to vulnerable pregnant women and new-borns | 3228 |  | MOH Administrative data BFLA Administrative data and reporting from the Open EMR system
Indicator 1.5.1: Number of pregnant women/Lactating women receive remote ANC/PNC support during the next six months
Baseline: 0
Planned Target: 1,500 (100%)
Please include all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
Handover of kits and items to the Ministry of Health & Wellness
On 29 October, the United Nations through the COVID-19 Response and Recovery Multi-Partner Trust Fund handed over 30,000 sets of Personal Protective Equipment (PPE), 150 test kits, and various essential health commodities to the Ministry of Health (MOH) to support the Government of Belize to curb the spread of COVID-19. The total value of equipment and supplies is estimated at USD $118,000.00. The United Nations Resident Coordinator Office (UNRCO), the Pan American Health Organization/World Health Organization (PAHO/WHO), and the United Nations High Commissioner for Refugees (UNHCR) handed over the items to the Director of Health Services, Dr. Marvin Manzanero; Principal Public Health Inspector, John Bodden; and HECOPAB Technical Advisor, Kathleen Azueta-Cho, on behalf of the Ministry of Health.
Story available at: https://belize.un.org/en/98640-united-nations-hands-over-test-kits-personal-protective-equipment-ppe-and-essential-health
Handover of kits to the CHWs in Central Health Region
UNHCR Aid Gives Relief to Over-Stretched Polyclinic in Belize Amid COVID-19
In the framework of the project “COVID-19 response to vulnerable populations and frontline workers in Belize” being implemented by the United Nations (UN), the International Labour Organization (ILO) is supporting a bipartite public awareness campaign for safe, healthy and resilient workplaces during the COVID-19 pandemic.
The support comes as a specific response to national partners who recognized the importance of focusing on Occupational Safety and Health (OSH) in order to realize a safe and healthy return to work and participate in efforts to help prevent a second wave of contagion while Belize shapes its new and better normal. Consequently, the Belize Chamber of Commerce and Industry (BCCI) and the National Trade Union Congress of Belize (NTUCB) are the main partners in implementing the campaign. The ILO support is a targeted and topical intervention aimed at fostering bipartite dialogue, building trust and producing results while the businesses operate and reopen in a COVID-19 climate.
Story available at: https://www.ilo.org/caribbean/newsroom/WCMS_766746/lang--en/index.htm
Infographics and pamphlet for OSH Campaign
In support of the response to COVID, which claimed the life of a colleague and friend of these medical professionals, UNHCR, the UN Refugee Agency, donated medical and personal protective equipment to the Independence Polyclinic, including 300 face shields, 5,000 masks, 1,700 disposable gowns, 200 pairs of gloves, and five patient monitors.
The support provided by UNHCR seeks to benefit both Belizeans and refugees, in line with spirit of the Global Compact on Refugees and its application in Central America, the MIRPS, the Comprehensive Regional Protection and Solutions Framework. Through the MIRPS, governments like Belize’s seek to provide a holistic response to the needs of forcibly displaced across Central America and Mexico.
These donations were made under the wider UN response by a joint effort between PAHO, ILO, UNFPA and UNHCR in Belize through the Multi-Partner Trust Fund. Through the Fund, the UN System supports national efforts to stop transmission of COVID-19 in rural areas and reduce the impact of the virus on human lives, in line with the sustainable development goals.
Story available at: https://belize.un.org/en/111981-unhcr-aid-gives-relief-over-stretched-polyclinic-belize-amid-covid-19
Communication Products for Pregnant Women and SRH Campaign
SRH Mobile in Arenal Village, Belize