## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Education Continuity in response to COVID-19 in the Kingdom of Bhutan | Overall Duration (months) | 7,5 months
Programme Number (if applicable) | Grant SM200423 | Start Date (dd.mm.yyyy) | Start Date: 15th May 2020
MPTF Office Project Reference Number: | Project ID 00121885 | Original End Date (dd.mm.yyyy) | End Date: 31st December 2020
Country | Kingdom of Bhutan | Current End date(dd.mm.yyyy) | End Date: 31st December 2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Education, School Planning and Coordination Division
Report Cleared By
o Name: | Will Parks
o Title: | UNICEF Representative
o Email address: | wparks@unicef.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The COVID-19 emergency has upended the whole education system since mid-March 2020 resulting to the closure of all the schools in the country since March 2020. COVID-19 caught the education sector in Bhutan ill prepared to respond quickly. Capitalizing upon its global regular programming and humanitarian nexus experience, UNICEF provided support for the development of a COVID-19 Education Response Plan which was approved by the government. The Plan outlined Education in Emergency in a phased manner, highlighting curriculum adjustment and delivery, safety protocols when children return to school and psycho-social support to children. Online learning was delivered to more than 170,000 children (32,000 in hard-to-reach areas; approximately 50 per cent female) through TV, Google Classrooms as well as printing and distribution of Self-Instructional Materials to more than 32,000 children living in remote parts of the country while 9,188 (4,602 F) preschool children were reached by home-based early learning and parenting programmes, ensuring continuity of education services in response to the COVID-19 induced closure of schools and early learning centers. The Education in Emergency (EiE) Guidelines were developed in March 2020 as well as an EiE Phase-II COVID-19 response plan with school re-opening protocols, highlighting curriculum adjustment and delivery, safety protocols when children return to school and psycho-social support to children. Self-Instructional Materials (SIM) and Radio lessons were developed by the Ministry of Education (MoE) and Royal Education Council (REC) to facilitate the learning of students residing in remote parts of the country who were unable to attend e-lessons due to lack of access to Bhutan Broadcasting Service (BBS) television or smartphones. The learning activities in the SIM were developed considering the class levels and learning ability of the students. At the first stage the materials were printed and distributed to support the education of 17,000 initially identified children. In July 2020, the MoE identified another 15,135 children to be included into SIM programme as children who do not have access to online education and the programme coverage has changed to 32,135 children to be reached by SIM with the theme ‘Reaching the Unreached’. Due to increase of the number of targeted children to be reached by SIM, the additional funding for stage V was requested and received from the Global Partnership of Education (GPE) COVID-19 Accelerated Funding to support the RGoB pandemic response. According to the MoE data, the highest percentage of students without access to BBS and Internet are located in hard to reach areas and socio-economically low ranking. A total of 171,938 SIM booklets were distributed to the schools of which 86,072 SIM booklets were supplied by the MOE, 34805 booklets by the Dzongkhag and Thromdey Education offices in addition to 51061 copies printed in the schools. Amongst the resources provided by the MoE, SIM was found the most resourceful and meaningful enhancing students’ learning irrespective of accessibility to technologies and teacher’s instruction. SIM along with the videos developed for learning continuity will serve in the longer-term to maintain children’s participation.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The total number of beneficiares reached is 32135 (60% girls; 40% boys). At the preprimary level 4165, Class I - 3013; Class II - 2991; Class III - 2830; Class IV - 3056; Class V - 3103; Class VI - 2880; Class VII - 2413; Class VIII - 2236; Class IX- 1983; Class X - 1549; Class XI - 948; Class XII - 968. Class XI and XII were reached with support of GPE. In total 740 students with disabilities ( 438 boys and 302 girls) received SIM adapted to their needs
3.1 | Results: Outcome Level | Please include outcome level results achieved | UNICEF supported the Government of Bhutan in addressing the problem of reaching more than 170,000 children (of whom 74,726 also missed out on regular school meals) with home based learning in the context of schools closure as a result of COVID-19. In addition to TV, google cl Classrooms, an innovative intervention, the Self-Instructional Materials (SIM), was developed to support the continuity of learning for the most vulnerable children, who had no access to either online or TV-based lessons during the pandemic benefiting than 32,000 children far to reach and pre-school children. SIM are print materials specially prepared teaching-learning materials, that carry the same learning lessons as per the adapted curriculum which have been structured in such a way that learners can do most, if not all, their learning from the materials alone, currently being broadcast through BBS TV. The printing of SIM package materials had been completed and distributed. A total of 171,938 SIM booklets were distributed to the schools.
3.2 | Results: Output Level | Please include output level results achieved | UNICEF has provided technical support and training to Sherig Counselling Online services providers. UNICEF has also developed school counsellor guidelines which have been distributed by the Ministry of Education. Ministry of Health and Ministry of Education supported to incorporate COVID-19 prevention and containment messages in the e-learning programme (hand washing, physical distancing, psychosocial support for children, signs and symptoms, dos and don’ts during CoVID-19 pandemic). WASH interventions COVID-19 pandemic included in the Safe Schools Guidelines for school reopening during the pandemic. With the installation of handwashing stations at schools in 2020, total number of handwashing tap points has increased to 17,071, (an increase of 77 percent) compared to 9,654 tap points before the onset of the pandemic in early 2020.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The implementation of Education in Emergency curriculum is unprecedented and poses diverse challenges and opportunities. Some of the challenges include equity and equality to access educational programmes for students due to geographical location, affordability and connectivity; educational background of parents; capacity of teachers in keeping track of students’ learning through remote learning mode; and the quality and accuracy of lessons. The number of children for Self-Instructional Materials (SIM) was recalculated resulting in insufficient funds to reach the new total of 32,135 children with SIM. Additional funds were requested from Global Partnership for Education through explanation to the Ministry of Education and GPE. As the result the GPE Accelerated Funding Proposal was approved and Bhutan got additional funds for SIM. The students in Wangsel and Muenselling Institutes and schools with SEN programmes follow the adapted curriculum with some modifications through the Bhutan Broadcasting Service (TV), SIM, and radio lessons. These most-at-risk children need assistive devices such as a mobile/tablet that is compatible for quality audio/visual systems, can store adequate amount of audio and visual learning materials shared, and upload their learning progress to their respective teachers. To ensure that children can meaningfully engage with the assistive devices for maximum learning and be accountable, guidelines were developed focusing on online safety, usage, updates, maintenance and on hand-over details. At the moment not yet all children have assistive devices needed. One of the eastern Dzongkhags reported that mobile teaching in the dzongkhag was found difficult due to the landscape, type of settlement and weather condition. The report stated that teachers could not reach out to all the students through mobile teaching since they lived scattered from one another without a motor road connection. Furthermore, unfavorable weather condition risked teachers’ lives.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | New innovative programmes were introduced to ensure that children who do not have access to online learning continue learning reaching 42.3% of the schools. The SIM was developed to reach the unreached children in the most remote areas and materials were also adjusted for children with special education needs. A SIM assessment is being currently undertaken and will be finalised by the end of February 2021 to capitalize on the experience and learn lessons for the future. The preliminary finding of the assessment revealed that 80.8% of the respondents found SIM user-friendly and adequate for learning, 81.6 % stated that the SIMs were effective for teaching and learning, 72.8% of schools across the nation reported that the coverage of syllabus in SIM is adequate and 80.8% found it user-friendly. However 16.1% of schools disagreed with the majority asserting that the students did not benefit academically in terms of self-learning from the material and justified that SIM for all levels and streams are clubbed together and made key stage wise which posed difficulties for lower grades included in the key stage. Other respondents reported that SIM contents lacked equal coverage of subjects that children at different levels needed to learn. Amongst other arguments not favoring SIM learning was most of the children who used SIM come from homes where parents are illiterate and were unable to guide them academically through the SIM contents. To resolve this issue, the survey analysis report recommended to plan SIM lessons based on grade rather than clubbed in key stage. The study concludes that most of the students felt online learning is not as effective as classroom teaching.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | Due to increased number of children in need of SIM after additional analysis completed by the Ministry of Education, there was a need for additional funding. A new proposal was developed through intensive discussions with multiple stakeholders including REC and Save the Children and a request to the Global Partnership for Education (GPE) was submitted by Bhutan in response to the announcement made by GPE to access COVD-19 Accelerated Funding. The proposal was developed based on the Education in Emergencies COVID-19 Response Plan Phase-II to provide support in addressing the challenges posed by COVID-19 pandemic and to strengthen the resilience of education system.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | The assessment on effective implementation of Self-Instructional Materials is ongoing. The assessment will be finalised by the end of February 2021 due to lockdown in January. UNICEF will submit the assessment after completion to document the impelmentation of the SIM.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Not applicable
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Additional funding for SIM was received from Global Partnership of Education Accelerated Funding in September 2020 to support the governement limited funding,

## RBM Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Outcome 1.1 All children continue to learn during the COVID-19 pandemic and safely return to improved schools
Indicator 1.1a 100% of school-going age children continue their learning during school closure | Out of 170,000 students, 137,865 were supported through TV and online lessons. 32,125 students were found to not have access to TV and online lessons.The MoE additionally identified 15,135 children to be included into SIM programme as children who do not have access to online education. |  | Standards Progress Report and M & E report
Baseline:153,000 (90%)
Planned Target:170,000 (100%)
Indicator 1.2b 17,000 unreached children access education and continue to learn during school closure | The target had been changed to 32,135 children as those to be reached by SIM. Due to increase of the number of targeted children to be reached by SIM, the additional funding for stage V was requested from the GPE COVID-19 Accelerated Funding. |  | Standards Progress Report and M & E report
Baseline: 0
Planned Target:17000 (100%)
Output 1.1.1 All 17,000 unreached children continue to learn during school closure through alternative modes | In terms of access to service, 758 (684 in august) children (294 girls) and 358 (133 female) adults have been referred to counsellors in their respective districts and provided with counselling services through the Sherig Counselling online platform set up to provide counselling and psychosocial support in response to COVID-19 pandemic. Additionally, since the reopening of schools for Class X and XII students from July 1st 2020, 5,336 children (2,578 girls) have been reached through counselling classes.In 4 districts 12 schools have received support for rehabilitation of WASH facilities. |  | M&E Report
Indicator 1.1.1a Needy children provided psychosocial and WASH support during school closure and upon their return
Baseline: 0
Planned Target:100% of the needy children
Output 1.2.1 100% of the unreached children (17,000) return to improved schools after school re-opening | Net Enrolment Rate in Basic (PP-X) Female - 93.25 Male - 87.95 Both - 90.56 |  | Annual Education Statistics 2020
Indicator 1.2.1:Net Enrolment Rate (NER) at basic education (PP to Class X)
Baseline:89.8% (F=92.1 and M=87.6) (2019)
Planned Target:At least 89.8% (to maintain the baseline at least)
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
1. SIM to cover students without access to television or internet April 21, 2020 https://kuenselonline.com/sim-to-cover-students-without-access-to-television-or-internet/ 2. SIM reaching students from Lunana to Dorokha May 12, 2020 https://kuenselonline.com/sim-reaching-students-from-lunana-to-dorokha/ 3. SIM keeps children in rural areas home May 19, 2020 https://kuenselonline.com/sim-keeps-children-in-rural-areas-home/ 4. Teachers distribute SIM to remote schools July 15, 2020 https://kuenselonline.com/teachers-distribute-sim-to-remote-schools/
The Self-Instructional materials lessons are available at the Ministry of Education website and on Sherig Bhutan YouTube Channel and eLibrary Bhutan:
https://drive.google.com/file/d/1s0R15LRrprZOQLwzLdokdYVzGIcCZwkO/view
https://www.youtube.com/channel/UCmlHB807dyVtiyoI_3InLow/playlists
http://www.elibrarybhutan.com/
http://www.education.gov.bt/index.php/education-in-emergency-eie-self-instructional-materials-sim-2/
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board