## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Strengthening a gendered and generational socioeconomic response through evidence-based policy advocacy and analyses. | Overall Duration (months) | 17
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-10-13
MPTF Office Project Reference Number: | 00124306 | Original End Date (dd.mm.yyyy) | 1 Apr 2022
Country | Uruguay | Current End date(dd.mm.yyyy) | 1 Apr 2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UNFPA, UNICEF & UNWOMEN. | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Education and Culture, Ministry of Social Development & National Institute of Statistics.
Report Cleared By
o Name: | Soledad Salvador
o Title: | Project Coordinator
o Email address: | soledad.salvador@unwomen.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses | Notes
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The evolution of the pandemic in Uruguay deepened in the first months of 2021, yielding towards the month of June due to the effect of vaccination. Throughout the first semester of the year, the ban on all crowds was maintained, and between March and June, educational and childcare centers were closed, and it was recommended to reduce mobility and carry out teleworking. All of this led to postponement of some activities such as the conduct of the Time Use Survey to be carried out in the second semester of 2021 because it must be surveyed in person and the implementation of the "Employability program for women in a situation of economic and social vulnerability". In the same way, the launch activity of the project that was going to be carried out in a semi-face-to-face way (with the Executive Director of the Uruguayan Agency for International Cooperation, Mr. Mariana Berro and the United Nations Resident Coordinator in Uruguay, Mireia Villar ) had to be replaced by a campaign in the press (oral and written) and on social networks. The first data from the 2020 Continuous Household Survey became available in April and was quickly processed to provide clear and timely information on the impact of the pandemic on employment, poverty and inequality. This evidenced that women from socioeconomically vulnerable sectors and from the interior of the country were the most affected by job losses and greater poverty and inequality. The data that began to be shown on the increase in poverty (100,000 new poor) did not disaggregate by sex. Given the interest that this information aroused, a brief* was released on social networks and two presentations were made (one to the legislators of the Bicameral Women's Bank on 04/20/2021 and to the edilas of the Canelones department on 06/25/2021). In turn, it was disseminated by the Uruguayan Agency for International Cooperation on its own website**, along with the social media cards that were made for dissemination on social networks. In the Project Management Committees, the communication issue was worked on in order to generate inputs that can be disseminated to the general population as progress or results of the project. A calendar began to be designed with milestones in terms of communication for the different activities that are being implemented. Starting in August, a communicator was hired to support the development of these activities and an agreement will be signed with a communication company for the production of videos with testimonies and the global tour of the project. The four working groups that were formed in the first management committee continued to work together to prepare the TOR for the calls to be carried out in order to implement the actions envisaged in the project. In this second semester and until the end of the project, activities will focus more on action and dissemination. | *UNWOMEN website
**AUCI website
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The purposes of the project are: - generate integrated information systems and analytical reports on vulnerability to improve resource mobilization and allocation to all those households living in poverty and extreme poverty, as well as for those that subsist barely above the poverty line and/or share other critical welfare deficits with regard to housing and basic infrastructure. Programmatic beneficiaries, based on the 2019 household survey and using the official poverty line, will be 34.2% of the population of Uruguay, which comprises 330,000 households and 1.2 million people. - Support to the early childhood care program to optimize the care mechanisms that were affected by the pandemic. - the implementation of a national time use survey in 2021 that provides updated information for the formulation of gender equality policies. - it will generate a pilot employment and childcare program for vulnerable women. - guarantee the educational continuity of secondary school students from vulnerable sectors. - Through the UNDP’s Accelerator Lab, an innovation platform will be activated that connects data, information systems and community experiences to create transformative solutions for the future delivery of social protection programs. Formation of a Network of Social Development Offices to strengthen capacities in subnational governments to overcome implementation gaps.
3.1 | Results: Outcome Level | Please include outcome level results achieved | No results yet
3.2 | Results: Output Level | Please include output level results achieved | No results yet
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The difficulties encountered in developing the project were concentrated in the postponement of face-to-face activities due to the pandemic. In any case, progress was made in the formulation of the calls that had their complexities since it was necessary to achieve an adequate adaptation to the needs of the counterparts and the United Nations model contracts. An important help has been the fast track system for COVID planned to streamline the contracting processes and guarantee the implementation in a timely manner. For example, the development of the Employability and Care program for women from vulnerable sectors required learning to design and formulate the proposal. In turn, there were doubts about the institutional capacities in the territory to apply, but the success was total. Very good proposals were received that were adapted to the available resources. This was possible thanks to a joint work between the State institutions and with their territorial referents. That program, in turn, will generate inputs for the employability programs developed by the Ministry of Social Development and the Ministry of Labor and which, given the budgetary restrictions, are being redesigned in order to make them more effective and efficient in the use of resources. Thus, the possible risk 2 associated with "Timing and delivery" in dealing with job loss problems will be addressed by this initiative. In turn, risk 3 referred to “Social Norms” that implies considering whether in times of crisis the position of women as beneficiaries of transfer programs could exacerbate situations of violence. In the articulations generated between programs and in particular, in the implementation of the Employability and Care program, work is carried out in a very cohesive way between the MIDES and INMUJERES programs (which provide violence care services), and the OSC that implement the employability program. Regarding risk 5 referred to social distancing measures, it has not generated inconveniences and the stage that generates greater exchange is just beginning, when the measures have already been lifted. On the other hand, the risk 6 that was related to the consequences of the economic crisis in the labor market and the destruction of jobs, the proposal that is beginning to be implemented of Employability and Care includes a final stage of accompaniment in the labor insertion for guarantee the sustainability of women in the opportunities and experiences that are generated. To guarantee these opportunities, the proposal to be implemented includes the involvement of local, government and private sector actors, so that the training is appropriate to their needs. It is also foreseen that during the training these actors will present themselves with the group of women and can socialize the demands or employment niches that they identify. On the other hand, the specific training proposal for each territory was prepared in conjunction with the referred actors (territorial referents of the institutions in dialogue with the private sector).
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Since we are still in the process of implementing the project, there are no very meaningful lessons or experiences to share. Basically highlighting the importance of constant dialogue with counterparts and between agencies to resolve possible differences or enhance the results of the activities to be developed. Among the products that will be obtained from this project and are envisioned as generators of knowledge or practices that would be worth considering or replicating in other realities are: - The interoperability of the databases that will be complemented with the georeferencing of the information based on the Single Address Register. Given that the importance of resorting to administrative records is increasingly being considered, this will be a leap in terms of the availability of information for the elaboration of public policies. - The construction of a set of indicators of economic empowerment that can be considered when defining the granting of economic benefits and the inclusion of people in social and employment programs. - The preparation of the Multidimensional Gender Poverty Index, which would be the first experience in the region. - The implementation of the Policy Acceleration Laboratories, which implies a new experience in the region and the world. These labs connect data, information systems, and community experiences to create transformative solutions for the formulation of social protection programs.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The work with the project partners has been developed through four working groups: 1) the Group referring to data issues that was formed prior to the approval of the project, but it provided the resources to advance in the integration of databases to strengthen the interoperability of the statistical system (SIIAS - Sistema de Integrated Information of the Social Area) and support the georeferencing of the entire system. The government includes the National Institute of Statistics (INE), the IDE (Spatial Data Infrastructure area) and the National Directorate for Data Transfer and Analysis (DINTAD) of MIDES, which is in charge of defining the beneficiaries. for social benefits. For the United Nations agencies, referents from UNFPA and UN Women participate, and those responsible for the Uruguayan Agency for International Cooperation (AUCI) are always present. The project funds complement the resources that the institutions are already allocating for these purposes. In turn, a specific group was formed to carry out the Time Use Survey where the following participate: INE, INMUJERES, UNFPA and UN Women. In turn, UNDP and UNICEF are supporting INE for the formulation of a Multidimensional Poverty Index. For this they will have the advice of specialists from OPHI (Oxford Poverty and Human Development Initiative). 2) the Employability and Care group made up of INMUJERES, MIDES and UN Women. This group is formed within the framework of this project. During this semester, he developed the design of the program and the TOR for the call. At this time, conversations began with the selected CSO to adjust details of the implementation of the program. For its design, conversations were held with the National Director of Employment, who is also developing training initiatives for women from low-income strata, and with references from the National Institute of Employment and Vocational Training that teaches courses for unemployed workers and has work experience with the target audience of this call. At the same time, all the capacities and expertise of those who have been implementing programs to strengthen employability at MIDES were used. 3) The Education group that makes up UNICEF and ANEP is beginning the implementation of the program that will support the María Espínola Centers that provide care for adolescents in secondary or technical-professional education in contexts of greater social vulnerability. The support will be allocated to personalized accompaniment and work with families to contribute to their integration and permanence in the centers. The results will be extremely useful for the inclusion of this component in the following editions of the program. UNICEF, UNFPA and ANEP together with UNESCO, PAHO and Plan Ceibal developed the campaign to encourage the return to classes called “Every day counts” (with financial support from the four agencies). 4) Finally, the Territory group, made up of UNDP, UNICEF, MIDES and local governments hired the Territorial Coordinator to make contacts, mobilize the agenda and develop capacities in subnational governments. An agreement was also signed with the institution that will prepare the baskets of social protection policies to identify implementation gaps. The entire strategy will be developed in the border departments (Rivera and Cerro Largo), and in Tacuarembó, Canelones and Montevideo.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | UN Women carried out a study on the impact of the pandemic on the labor market during 2020. The conclusions of the study confirmed the idea that women from vulnerable sectors and from the interior of the country had been the most affected. The impact is evident in the increase in unemployment (they had fewer possibilities of teleworking and are inserted in the sectors most affected by the pandemic: everything related to tourism, recreation, restaurants and hotels, among others). But this has repercussions in an increase in poverty and inequality. Women affected by unemployment live in single-parent households, which also contributes to the increase in child poverty.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | An important adaptation of the strategy to respond to the most urgent needs of the Ministry of Social Development was the support for the Uruguay Crece Contigo program aimed at serving families with children in early childhood. During the pandemic, care was limited and the demands exceeded the program's response capacity. For this reason, support is being implemented to generate a risk indicator, which allows differentiating the support needs and being able to assist some of the families that have been referred to the program through Telecare. UNFPA and UNICEF allocated some savings generated to make this proposal viable. Assistance is also being given to the National Directorate of Data Transfers and Analysis (DINTAD) to migrate its databases to a computer program that allows it to process the information in a more integrated way and issue standardized reports.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The project mobilizes resources from government partners because the activities are co-financed, both the resources for georeferencing and interoperability of databases, the development of a Time Use Survey, the program for the educational continuity of adolescents of ANEP, and the campaign that is about to start to support the “return to classes” in face-to-face mode. In addition, a specific human resource was hired to develop and implement the communication plan between August 2021 and March 2022, and an agreement was signed with a communication company to develop the testimonials and a video on the results of the entire project.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] A new basic protection floor is in place for 2021 allowing to better target the most vulnerable Uruguayans, particularly women head of households and women working in the informal sector | There is no data yet because the project is being implementating. Indicators are being designed to account for progress in the coverage of programs with more agile and timely information systems. |  | The National Directorate of Data Transfers and Analysis (DINTAD, exDINEM) data sources.
Indicator 1.1: Percentage (%) of beneficiaries of social protection schemes for vulnerable population, by type of programme. (Indicator contributing to SERP indicator 2.5)
Baseline:By type of programme: Cash Conditional Transfers (CCT): 68,5% of poor households; Uruguay Social Card (TUS): 39,2% of poor households. Sex dissagregation not available yet. Percentage (%) of female-headed households of poor household=40% (Source: Social Sciences Faculty, based on National Continuous Household Survey 2019, INE.)
Planned Target:CCT=at least 85% TUS=at least 50% Sex dissagregation will be advocated for
Indicator 1.2: Percentage (%) of poor female headed household benefitting from cash transfer programmes.
Baseline:66% (Source: own estimations based on National Continuous Household Survey, 2019, INE)
Planned Target: Percentage (%) of women-headed households: at least 70%
Output 1.1 An Integrated data system is delivered to be used by the Uruguayan Government, to improve the capacity of social protection policies to target vulnerable population, particularly women working in the informal sector and women heads of household in charge of children. | Progress is being made in the implementation of the interoperability of the databases through an agreement with the Unit of Methods and Access to Data (UMAD) of the Faculty of Social Sciences. |  | The reports made by DINTAD (exDINEM) based on the databases of the SIIAS (Integrated Information System of the Social Area) system.
Indicator 1.1.1: An integrated non-contributory social protection system and emergency support mechanism is adopted by national institutions.
Baseline: Boolean: Weak. Low interoperability incompleteness
Planned Target: Boolean: Strong. High Interoperability, completeness
A proposal for economic empowerment indicators was prepared to be included in the Gender Information System (GIS) of the National Institute of Women and the Observatory of Social Policies of MIDES.
Indicator 1.1.2: Number of indicators sensible and gender transformative integrated as part of the new proposal of non-contributory social protection system and emergency support |  |  | The document with the proposal prepared by the National Institute for Women (INMUJERES).
Baseline: 0
Planned Target: At least 3
Output 1.2 A redefinition of the non-contributory social protection systems and emergency support that responds to the new challenges brought by COVID-19 and prepares the country to face future outbreaks. | Work is already under way on the development of the Unique System of Geographic Addresses of Uruguay, which will allow state institutions to use the same registry for the georeferencing of personal data. This would advance the integration of the databases of different agencies and have administrative records that allow informing public policy. |  | Information from the IDE (Spatial Data Infrastructure) on the institutions that have adopted the system.
Indicator 1.2.1: Number of institutions that own and have capacities to operate an integrated data system to activate emergency support mechanisms and inform public policies to face future outbreaks.
Baseline: Number of national institutions with capacity to operate the integrated data system: 1
Planned Target: At least 4
Output 1.3 Effective coordination institutional capacities developed in target territories, with focus in subnational governments capacities and multi-level coordination of social policies | There are no results yet, but the work of the Territorial Articulator began with the offices of Rivera, Tacuarembó, Cerro Largo, Canelones and Montevideo. |  | Reports on progress in the implementation of the strategy that will include photos, videos, stories, etc..
Indicator 1.3.1: Number of social development offices and development offices that engage in the regional network
Baseline: 4
Planned Target: 8
Indicator 1.3.2: National & subnational governements agree on an agenda to overcome implementations gaps in target territories | No progress yet. |  | The agendas agreed with each local government.
Baseline: Boolean: No
Planned Target: Boolean: Yes
Outcome 2. Expanded in-school system and care services are available for most vulnerable Uruguayans by 2021, especially in critical territories, minimizing epidemiological risks while reducing women’s unpaid care workload | No progress yet. | The Outcome 2 statement was redefined as: "Employability program for women in situations of economic and social vulnerability, and improvements in the educational trajectories of adolescents". | ANEP's statistical sources.
Indicator 2.1 Percentage (%) of children from the first quintile of social vulnerability that participated in public education proposals.(Indicator contributing to SERP Indicator 2.2)
Baseline: Primary school: 72%, Secondary school: 28% & Technical school: 44% (Source: "Educational situation in the context of the health emergency". Teacher Survey - ANEP, July 15, 2020) Sex dissagregation not available yet.
Planned Target: Primary school: at least 85%, Secondary school: at least 40%, Technical school: at least 55%. Sex dissagregation will be advocated for.
Output 2.1: A national plan and protocol for the expansion of in school and care services is designed in dialogue with national stakeholders, using standards and international best practices. |  | The Output 2.1 statement was redefined as: "Support for the ANEP Center Development Plan to guarantee the permanence and educational continuity of adolescents from a critical socio-economic context and UCC initiatives to strengthen positive parenting practices".
Indicator 2.1.1: A communication campaign, gender and age responsive, to promote the importance of educational continuity. | Yes | It was replaced by a back-to-school campaign called “Every Day Counts” and developed in conjunction with other agencies such as UNESCO and PAHO. | The video and cards of the campaign.
Baseline: Boolean: No
Planned Target: Boolean: Yes
Indicator 2.1.2: Number of teachers with self-reported increased abilities to quality digital and remote education, by sex. | This indicator is replaced by two others, which are: "Number of students who receive psychotechnical support until the end of the school year, out of the total number of students who start the courses in July" and "Number of students who finish the school year out of the total students who started the courses in July ". Its implementation was delayed due to the pandemic since face-to-face classes in secondary school are starting in July. | The targets for the new indicators are: "All students who require psychotechnical support receive it throughout the school year"; and "All students who started the school year finish it". | The program evaluation report.
Baseline: Male: 57, Female: 109
Planned Target: Male: 150, Female: 300
Output 2.2: Large scale programmes of care for children in most vulnerable areas will be piloted in partnerships with subnational governments and the private sector allowing working parents (particularly mothers) to return and remain in the labor force, combined with training and employment strategies targeted for vulnerable women. |  | The Output 2.2 statement was redefined as: "Employability program for women in a situation of economic and social vulnerability together with the development of care strategies that allow women to participate in the program and sustain their labor insertion".
Indicator 2.2.1: Number of new gender and age-responsive care initiatives developed in partnership with local stakeholders.
Baseline: 0
Planned Target: 4
Indicator 2.2.2: A new socioeducational and labour programme within the institutional offer is targeted exclusively for vulnerable women developed and piloted. | The UCC program and the National Institute for Women are already beginning the implementation of the program for the employability and labor insertion of women in vulnerable sectors. |  | The program itself and its evaluation reports.
Baseline: Boolean: No. (The programme Uruguay Trabaja is delivered for both women and men)
Planned Target: Boolean: Yes
Indicator 2.2.3: Percentage of time deliver in paid and unpaid work for women and men, based on National Time Use Survey. | The call to survey the third time use survey between September and December 2021 has just been launched. |  | The results report of the National Time Use Survey 2021.
Baseline: According to the last TUS 2013: Women: 35.5% paid work and 64.5% in unpaid work; Men: 68.1% paid work and 31.9% in unpaid work. (Source: Module Use of time and unpaid work of the Continuous Household Survey 2013, INE-INMUJERES-FCS)
Planned Target: New National Time Use Survey: tbd
Output 2.3: Experimentation and innovation strategy for women economic empowerment and a new architecture of solutions for care
Indicator 2.3.1: Number of gender and age responsive implemented and evaluated experiments in target territories. | No progress yet. |  | The reports with the results of the experiments.
Baseline: 0
Planned Target: 3
Indicator 2.3.2: Participative roadmap for a local innovation strategy elaborated and ready for implementation. | No progress yet. |  | The agreed roadmap.
Baseline: Boolean: No
Planned Target: Boolean: Yes
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
An agreement was reached with an advertising agency that has already been working with UN Women on gender equality issues, to support from August 2021 until March 2022 in the production of videos that collect the testimonies of the participants of the programs and actions that are being developed within the framework of the project.
In addition, it will take care of a compilation to show the results of the project as a whole.
2. Upload here: Communications and Visibility (OPTIONAL)
- Communication activities in the press and social media by Launching the project:
1. Newspaper: Semanario Búsqueda
Interview with the United Nations Resident Coordinator in Uruguay, Mireia Villar (25/3/2021)
2. Central Television News Program: Subrayado (Canal 10)
Interview with the Project Coordinator, Soledad Salvador (25/3/2021)
3. Radio programs:
Más temprano que tarde (El Espectador, 810AM)
Interview with the Project Coordinator, Soledad Salvador (25/3/2021)
4. Social media:
Note on the Portal of the Uruguayan News Agency UY.Press (25/3/2021)
Dissemination on social networks (Twitter and Facebook)
- Communication materials to inform public policies:
Publication of a study on the impact of the pandemic on the labor market according to gender. (Abril, 2021)