## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Enabling Guinea Bissau to timely respond and stop COVID-19 transmission | Overall Duration (months)
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-05-01
MPTF Office Project Reference Number: | 00121766 | Original End Date (dd.mm.yyyy) | 2021-04-01
Country | Guinea Bissau | Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | WHO ($250K); IOM ($250K) | National counterparts (government, private, NGOs & others) and other International Organizations | VIDA, NADEL and ADPP
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | National authorities’ capacities to effectively implement the National Contingency Plan was enhanced: By organizing capacity development activities for health workers (men and women) and the staffs of the Points of Entry, developing the SoP and providing hygiene material to the health structure, the project gave to the national authorities the capacities to implement the contingency plan. The consequences of this capacity strengthen are the improvement of the laboratory which is able to collect and analyze more and more sample. In the other way the health care workers trained easily demonstrated ability, via exercises or real life event, to respond appropriately to a public health event. Urgent medical assistance for COVID-19 related needs of local population was addressed: The risk communication and community engagement team conducted several communities based discussion on the risk, the prevention and the management of the pandemic. Information were developed and diffused by local radio and social media. This campaign was focused especially on women and young girls and boys. As result the knowledge of the community was improved and the community management of the pandemic was a success
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | 1624 health care workers trained: - In 2020: 1 393 health workers - In 2021: 231 technicians (146 men and 85 women 252 Community leaders, traditional healers, religious leaders (190 men and 62 women) received key messages related to COVID-19 The 252 Community Leaders constitute a network and continue to do sensibilisation at community level. thousands of people were indirect beneficiaries.
3.1 | Results: Outcome Level | Please include outcome level results achieved | OUTCOME 1: Enhanced national authorities’ capacities to effectively implement the National Contingency Plan -Continual increasing of number of specimens. Week20 in 2020: 543; Week50 in 2020: 1303 and Week15 in 2021: 1533 -Continual reduction of new cases: Week20 in 2020: 197; Week50 in 2020: 2 and Week15 in 2021: 32 OUTCOME 2: Urgent medical and assistance COVID-19 related needs of local population addressed. -Three treatment centers were set with 20 ventilators and 45 oxygen concentrators and all health care workers were trained in the correct use and maintenance of the equipment; -Additionally Bubaque (island) health center received two oxygen concentrators and WHO provided on-the-job training in the use and maintenance of the equipment
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1: Strengthened national capacities to detect, isolate, manage and refer suspected cases of COVID-19 Infections Prevention and Control (IPC) developed 4 SoPs: - Guidelines to Prevent and Control COVID-19 in Hotels, restaurants, bars and other entertainment Places; - Tools to assess COVID-19 infection among healthcare professionals - Correct Use of Masks - Concepts and procedures for IPC during the COVID-19 vaccination Output 1.2: Improved laboratory capacities and provision of supplies needed to assure proper infection control -All results of CVID test are provided during the day (less than 24 hours) Output 1.3: Strengthened clinical gender sensitive management of severe cases of COVID-19 patients -All trainees supervised on the ground shown the abilities to respond appropriately, and continuous on-the-job training and formative supervision provided -On 29th April 2021 87% (3259 recovered / 3726 COVID+) of all COVID-19 patients recovered (60% male and 40% female) Output 2.1: National authorities, and Civil Society Organizations (CSOs) are effectively sharing key messages related to COVID-19 among vulnerable populations -From March 2020, virtual daily PHEOC meetings -From April 2021, 2 weekly meetings -Availability of the IPC materials in all health centers, confirmed by IPC evaluation in the Health centers Output 2.2: Enhanced information of all the population, especially the most vulnerable on fundamental health human rights in the COVID 19 pandemic Community visits and communication by the Risk Communication and Community Engagement Team Community radios programs in regions: -Tombali: 2 radios with 2 spots/day -Quinara: 1 radio with 2 spots/day -Bafata: 4 radios with 10 spots/day -Gabu: 6 radios with 22 spots/day Cacheu: 7 radios -Farim: 1 radio -Oio: 1 radio
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The island region is not well covered in term of surveillance. It is very difficult to work in these islands Guinea-Bissau has no ICU beds Lack of well trained staff in IPC and Case Management
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Creating a foundation for the management of hospital waste in Guinea-Bissau is a start to the implementation of a sustainable policy. With COVID-19 and the need to eliminate various hazardous waste produced, the national IPC task force created a guideline, considering the real conditions in the country for waste management. And, in a cascade, the country received several supporters for their management: purchased equipment, some already in the country, and others in the pipeline. We trained 49 trainers (35 male and 14 female) in human and animal health to teach HW management at the national level. Today, we have 441 health technicians (285 female and 156 male) from the SAB and Biombo regions trained on HW management. The aim is to reach all technicians at the national level in human and animal health by the end of 2022. Also, it is expected to validate and introduce the HW management policy in the national waste policy, elaborated by the Ministry of Environment.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | WHO works with different parteners at National and International levels. Lot of activities ont the Points of Entry were done in collaboration with IOM. Infection Prevention Control and Risk Communication / Community Engagement (CREC) activities were in collaboration with the High Commission of COVID-19 CREC worked with different national association: National Red Cross, NADEL, Battoden Golle, AMB (Associacao de Moradores de Bairos), CNI (Coseil National Islamique), Women Christian and Islamique Associations... For Case Management training and other activities were organised with AFAEM
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Enhanced national authorities’ capacities to effectively implement the National Contingency Plan
Improved good health and well being | -Continual increasing of number of specimens. Week20 in 2020: 543; Week50 in 2020: 1303 Week15 in 2021: 1533 -Continual reduction of new cases: Week20 in 2020: 197; Week50 in 2020: 2 Week15 in 2021: 32
Indicator 1.1.1: Confirmed COVID-19 cases in month
Baseline: 52
Planned Target: 30
Timely detection and response to COVID19 |  |  | Number of Specimens collected and analyzsed by the laboratory
Indicator 1.1.1: Detection Time
Baseline: 72 hours | All results are provided during the day - less than 24 hours
Planned Target: Less than 24 hours
Output 1.1: Strengthened national capacities to detect, isolate, manage and refer suspected cases of COVID-19.
Output Indicator 1.1.1a | Infections Prevention and Control (IPC) developed 4 SoPs: - Guidelines to Prevent and Control COVID19 in Hotels, restaurants, bars and other entertainment Places; - Tools to assess COVID-19 infection among healthcare professionals - Correct Use of Masks - Concepts and procedures for IPC during the COVID-19 vaccination |  | SOPs developed
# of SoPs developed for case detection, notification and surveillance
Baseline: 0
Planned Target: 3
Output Indicator 1.1.1.b |  |  | Training reports Training modules
# male and female health workers, including trained allied workers | 1624 health care workers trained:
Baseline: 0 | In 2020: 1 393 health workers
Planned Target: 1500 | In 2021: 231 technicians (146 men and 85 women)
Output Indicator 1.1.1.c |  |  | Training report
% of female and male trainees who demonstrate ability, via exercises or real-life event, to respond appropriately to a public health event | WHO: All trainees supervised on the ground shown the abilities to respond appropriately, and continuous on-the-job training and formative supervision provided. IOM: 100% (23% female and 77% male) demonstrate ability, via simulation exercise between 9 to 2 march 2021, to respond appropriately to a public health event
Baseline: 0
Planned Target: 100
Output 1.2: Improved laboratory capacities and provision of supplies needed to assure proper infection control
Output Indicator 1.2.1 a | 6197 supplies acquired to equip al PoE. |  | Number of supplies delivered for each 15 PoE
# of supplies acquired to equip all PoEs
Baseline: 0
Planned Target: 7
Output Indicator 1.2.1b | WHO: 10 Health Care Facilities (HCF): 5 Regional hospitals and 5 centers type A in 9 Regions set up and equipped one isolation room for COVID-19 suspected case. 14 HCF close to the PoE that attended the PoE directly. In total, 38% of the 159 HCF in Guinea-Bissau have an isolation room for COVID-19. IOM: 2 temporary isolation will be gender sensitive; 6 health checkpoints equipped with water tank. |  | Isolation centres set up and equipped
# of gender-sensitive temporary isolation areas available at PoEs and health centres and equipped with water and solar panel
Baseline: 0
Planned Target: 1 Isolation area for each PoE and 1 per health centre per region
Output 1.3 Strengthened gender sensitive clinical management of severe cases of COVID-19 patients
Output Indicator 1.3.1a |  |  | Laboratory confirmed negative results
% of female and male COVID19 patients recovered | On 29th April 87% (3259 recovered / 3726 COVID+) of all COVID-19 patients recovered
Baseline: 0
Planned Target: 60%
Output 1.4 Strengthened surveillance capacities and collection of real-time and reliable data in the country, including at points of entry
Indicator: Number of radio/TV spots aired in all the regions
Baseline: 0
Planned Target:
Output Indicator 1.4.1 a | (3) Case Management: -1 SOP for CM of COVID-19 suspected, and confirmed patients developed, -2 updates, accordingly WHO guidelines. (3) Infections Prevention and Control (IPC) - Hospital environmental cleaning - Rational use of Personal Protective Equipment in the context of limited resources - Hospital Waste Management Guide in Guinea-Bissau | Note contradicting responses from two responsible entities. WHO listed SOPs support the argument for completion of 6 SOPs. | Drafted SOPs
#of SOPs in place for detect, isolation, initial management and referral of an ill passenger
Baseline: 0
Planned Target: 4
Output Indicator 1.4.1b |  | Not reported by responsible entity (IOM). Possibly due to project extension | Reports of INASA/COES and PoE
# of female and male PoE personal with enhance capacities to initially manage and refer ill cases
Baseline: 0
Planned Target: 200
Output Indicator 1.4.1c |  | Not reported by responsible entity (IOM). Possibly due to project extension | Reports of INASA/COES and PoE
# of data gathering tools efficiently used at PoE and institutions involved in the epidemiologic response
Baseline: 0
Planned Target: 15
Outcome 2 | Guinea-Bissau has no ICU beds, however three treatment centers were set with 20 ventilators and 45 oxygen concentrators and all health care workers were trained in the correct use and maintenance of the equipment; Additionally Bubaque health center received two oxygen concentrators and WHO provided on-the-job training in the use and maintenance of the equipment
Urgent medical and assistance COVID-19 related needs of local population addressed.
Indicator: Number of ICU beds with ventilators in the country
Baseline: 0
Planned Target: Ventilators and other clinical services set up in all regions
Output 2.1: National authorities, and Civil Society Organizations (CSOs) are effectively sharing key messages related to COVID19 among vulnerable populations. |  |  | Minutes Number of IA activities conducted
Indicator: Coordination Meetings | From March 2020, virtual daily PHEOC meetings From April 2021, 2 weekly meetings
Baseline: 0
Planned Target: At least 1 coordination meeting health per month
Output Indicator 2.1a
Indicator: # of national authorities and CSOs disaggregated by sex with improved capacities to communicate key messages related to COVID-19 | 252 Community leaders, traditional healers, religious leaders (190 men and 62 women) were trained
Baseline:
Planned Target: 200 |  |  | Pre and postquestionnaire during awareness raising sessions
Output Indicator 2.1b
Indicator: # of community leaders and local population disaggregated by sex actively involved in COVID 19 prevention and protection
Baseline: 0
Planned Target: 200
Output 2.2: Enhanced availability of protective material to health staff and vulnerable population
Indicator: Availability of the IPC materials in all health centres
Baseline: 0
Planned Target: 2000 health personnel with adequate IPC materials
Output Indicator 2.2a |  |  | Activity report
Indicator: # of preventive supplies available for female and male migrants and population in situation of vulnerability
Baseline: 0
Planned Target: 500 COVID-19 preventive supplies to migrants and population in situation of vulnerability
Output Indicator 2.2b |  |  | Pre and postquestionnaire during awareness raising sessions
Indicator: # of households supported with hygiene supplies and other forms of direct assistance | Households were supported by local associations with the support of WHO | WHO did not provide exact figure
Baseline: 0
Planned Target: 200 households supported with hygiene items
Output 2.3: Enhanced information of all the population, especially the most vulnerable on fundamental health human rights in the COVID 19 | Community visits and communication by the Risk Communication and Community Engagement Team Community radios programs in regions: -Tombali: 2 radios with 2 spots/day -Quinara: 1 radio with 2 spots/day -Bafata: 4 radios with 10 spots/day -Gabu: 6 radios with 22 spots/day Cacheu: 7 radios -Farim: 1 radio -Oio: 1 radio |  | Number of radio/TV spots aired in all the regions
Indicator: Number of radio/TV spots aired in all the regions
Baseline: 0
Planned Target: At least 3 programmes in community radios are being aired per week with COVID-19 information
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
Note on B32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why is there such a discrepancy between the baseline and achievement
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Report should only reflect actual achievements, not planned activities

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
In order to help the community, Miguel and the team delivered a communication session on individual and collective protective measures. This was attended by 40 participants, including religious leaders, national and regional authorities, women and youth associations leaders. "When we returned to the village the day after, the community was adopting protective measures. This made me feel proud," he recalls.
First childbirth of a patient with COVID-19 in Guinea-Bissau- Aissato Ture Barai
During May 2020 the number of COVID-19 cases were rising in Guinea-Bissau. This put even more pressure on an already fragile health system. The situation was chaotic in the Hospital of Cumura, which is one of the three hospitals identified in the country to receive COVID-19 patients. An outbreak of COVID-19 started in the maternity ward and infected several health workers. The midwife Aissatu Ture Barai, working in Cumura for 7 years, told us that “the Hospital almost closed, with the health workers going to quarantine in their homes. For us that stayed it was a serious challenge: we didn’t have enough protective equipment, we worked several long hours, and yes, I can’t deny we were afraid, because this was a new disease and we didn’t have enough information”.
In the maternity ward of Cumura, R.S, a young lady almost 9 months pregnant started to show symptoms of COVID-19. The tests-results came two days later, she was infected with COVID-19, and the baby was expected to be born in the next days. It was also a high-risk pregnancy (pre-eclampsia). Later, the Cumura Hospital staff found out that R.S previously had been a COVID-19 patient at another hospital (one of the two other COVID-19 Centre) and, out of fear of COVID-19, left the hospital early.
Aissatu Ture Barai, was prompt in volunteering herself to assist in the childbirth. She told us, “I had no choice, I needed to assist in the childbirth, it was my duty as a health worker. I was very afraid, and my family and friends told me to not help her and that I would infect all of them. However, my husband, who is also a health worker, supported me in my decision.” On the 18th of May at 21:00 the first contractions started. Aissatu Ture Barai still remembers “when the childbirth started, all my fears of COVID-19 went way, the only thought that I had in my mind was to save the baby and this lady”. After a long labor, on the 19th of May at 17:40 R.S gave birth to a healthy boy, Julinho. R.S, with tears in her eyes, thanked the midway Aissatu Ture Barai.
Few days after, Aissató Ture was tested positive with COVID-19. Only 3 months later, she could come back to the hospital, the 3rd of August. Despite all the challenges, the risks and being infected with COVID-19, Aissatu still remembers this childbirth positively. “It was a special moment in my life, and I will never forget it. I was aware that I was taking part in the first childbirth of a patient with COVID-19 in Guinea-Bissau.”
22 Oct 2020, Placement of physical distance markers at Osvaldo Vieira International Airport.
In order to guarantee physical distance between passengers at Osvaldo Vieira International Airport, IOM proceeded with the elaboration and placement of markers approved by MoH and WHO on the airport's ground.
Photo 20 Physical distance markers at Osvaldo Vieira International Airport
Photo 21 Physical distance markers at Osvaldo Vieira International Airport

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Sustaining livelihoods in Guinea-Bissau under COVID-19 negative impacts on the most Vulnerable Amount: USD 500,000.00 | Overall Duration (months)
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-06-01
MPTF Office Project Reference Number: | 00121736 | Original End Date (dd.mm.yyyy) | 2020-12-01
Country | Guinea-Bissau | Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | WFP ($300K), UNICEF ($100K), UNDP($100K) | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
UNDP
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Under the COVID-19 MPTF, that UNDP, WFP and UNICEF joined forces in Guinea-Bissau and have worked together under the project “Sustaining livelihoods in Guinea-Bissau under COVID-19 negative impacts on the most vulnerable”. UNICEF, WFP and UNDP also used the project to Complement each other’s strength. The three agencies were able to successfully implement an integrated and inclusive social assistance programme, benefitting 1,587 of the most vulnerable households. While WFP supported the mechanism for transferring the cash to vulnerable families, UNICEF, building on its comparative advantage, used its expertise on social policy development to focus on the development of criteria for the target group, supporting the monitoring and evaluation system of the project and establishing a complaint and feedback system to be used as an end-user monitoring mechanism. UNDP’s intervention was guided by Outcome 2.2 “Support provided to vulnerable cashew crop growers in Cacheu and in Gabu regions”. The aim of this outcome was to ensure that, at least, 250 cashew crop growers (125/region) get necessary support to properly store their production until conditions for international trade were once again established. Due to the COVID-19 pandemic, international buyers, mainly from India, were not able to travel to Guinea-Bissau and carry out the purchase of cashew nuts. At the time of the drafting of the project, no organized national response was put in place to support small vulnerable farmers, who were suffering from the effects of the pandemic and related lockdown measures. Under Outcome 2.2 it was also planned an activity for geospatial mapping of the vulnerable producers and the provision of sanitary kits to those 250 cashew crop growers identified. To carry out these activities, UNDP partnered with Innovalab, local innovation and business organization, and with the Industrial Association of Guinea-Bissau (“AIGB” in the Portuguese acronym). Innovalab was responsible for the mapping of the vulnerable cashew producers and training of the local technical team in the regions, while AIGB focused on the purchase of storage equipment and sanitary kits as well as the transport of these materials to the regions.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | 1,587 households among the most affected by the COVID-19 were identified in 100 villages to benefit from the cash transfers. 250 cashew crop growers in Cacheu and Gabu regions (125 in Cacheu region; 125 in Gabu region). In Gabu, 5% were women and 95% were men. In Cacheu, 10% were women and 90%, men. Under the project's activities, 72 local technical team staff of the regions were trained in collecting data and using the digital questionnaire, produced by Innovalab, to map the cashew crop growers in the regions.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The support to the vulnerable populations at the local level was foreseen in UNDP strategic documents. Outcome 5 of the UNDAF “The most vulnerable population in the poorest regions have improved access to economic opportunities. A total of 250 vulnerable cashew crop growers in Guinea-Bissau benefitted from the MPTF project initiatives within the context of covid-19 pandemic in 2020. Of the 125 beneficiaries in Gabu region, only 5% were women and 95% men, whereas in Cacheu region 10% of the 125 beneficiaries were women and 90% men.
3.2 | Results: Output Level | Please include output level results achieved | Result 1: Establishment of sectors, village and household selection criteria. Selection of target communities and beneficiary enrolment, registration, and verification. Though UNICEF contribution, a targeting methodology has been elaborated and put in place with the support of the Government and NGOs. This methodology helped to identify 9 sectors that benefited from the project. Within the sectors 1,587 households among the most affected by the COVID-19 have been identified in 100 villages to benefit from the cash transfers. The funds have also supported cash transfer beneficiaries with 1200 mobile phones. CPD output Economic growth is inclusive and sustainable, promoting poverty reduction, decent work, food security, and the structural transformation of the economy. 250 cashew crop growers in Cacheu and in Gabu benefitted from storage equipment for their cashew production and sanitary kits in light of the COVID-19 pandemic. 72 local technical team staff of the regions were trained in data collection and on the usage of the digital questionnaire to map out the vulnerable cashew crop growers.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | One of the main challenges was the low coverage of the mobile network in some areas which made it difficult for beneficiaries as well as the programme team to follow cash transfer programme implementation as well as the cash disbursement. Further, the MPTF-project started with a bit of delay. It was predicted to start in July, but it was only able to be implemented in the beginning of August. Mainly due to the political situation and the UN system guidelines on the engagement with high level political staff, the field activities of the project were delayed. Also, the rainy season in Guinea-Bissau was also an impediment to the field activities. Some regions were not easily accessed by car and, in the case of São Domingos and Bigene, the delivery of the equipment and sanitary kits was delayed by almost a month until conditions were appropriate. Another challenge was the lack of technological infrastructure in the regions that would allow for a complete geospatial mapping of the cashew crop growers in Cacheu and in Gabu. As an alternative to that, UNDP and Innovalab (as the technical partner for the geospatial mapping) produced a georeferencing digital questionnaire to identify the vulnerable cashew crop growers, collecting data on their location and information related to their cashew production and household characteristics.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | One of the first lessons learnt is the need to have community engagement for behavior change supported by the cash transfer programme. The project really managed to have a strong engagement and commitment of implementing partners in the process, namely leaders at the community level, beneficiaries’ families, civil society organizations. The beneficiaries used the cash transfer to not only improve their nutritional status, but also to enroll children in school, acquire teaching materials, register children and even for medical assistance. The second lesson learnt is the fact that the cash used can go beyond families and help communities build their resilience. In UNDP's implementation, the project team initially carried out meetings with the regional delegates to agree on the questions to be adopted in the survey and how the vulnerability criteria is going to be used. The first talks regarding the project scope and areas of intervention for UNDP were carried out between the LED project team and the regional delegates of Cacheu and Gabu, given the political situation in the country and related guidelines of the UN system in Guinea-Bissau. The LED project team was involved in the elaboration of the MPTF-project since the structures identified and used for the identification of the vulnerable cashew producers and distribution of equipment were the ones implemented by the LED project. Bi-weekly zoom meetings with the regional delegates were organized to first discuss how the project could tackle the issues related to the vulnerable cashew producers. Once the project scope was finalized, the project team engaged in meetings with AIGB and with Innovalab to discuss partnership-issues for project implementation. Project team alongside regional delegates organized three Zoom meetings to discuss the vulnerability questionnaire as well as to identify what would be the vulnerability criteria. Once the project started its activities, bi-weekly Zoom meetings were organized with regional delegates and, then later, with Innovalab, to follow-up on field activities and on the mapping and identification of vulnerable cashew producers.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | As previously mentioned, UNDP partnered with Innovalab to carry out the geospatial mapping of the vulnerable cashew producers in the regions of Cacheu and Gabu. The modality of agreement with Innovalab was a “Micro-capital grant agreement” in the value of USD 9.900. The methodology adopted by Innovalab to carry out this mapping involved two main aspects: (i) survey in the selected communities and (ii) a georeferenced mapping exercise carried out by the regional delegates of Cacheu and Gabu, with the support of the structures of the Local Development Committees and the training of the local technical team, including regional delegates. Based on the survey provided by UNDP’s team in partnership with the regional delegates, Innovalab based its activities and developed an Android application to map and identify the most vulnerable cashew producers in Cacheu and in Gabu. Also, with AIGB, a “Micro-capital grant agreement” was signed. The amount for this agreement was CFA 29.090.775. Under this agreement, AIGB was responsible for the following activities: - Acquisition of storage equipment to the cashew producers; - Prepare a detailed budget alongside the regional delegates of Cacheu and Gabu related to the amount and type of storage material required; - Collect invoices related to the purchase of this equipment; - Prepare a workplan detailing how activities will be carried out. Also, beyond the MPTF-project scope, UNDP had partnered with AMAE in Guinea-Bissau to produce masks for COVID-19 protection. Some of these masks were produced in Cacheu and in Gabu and were also shared with the beneficiaries of the project and other vulnerable population identified by the CDLs in the regions. In total, 6000 masks were distributed to each region. In UNICEF's case, the funds were complemented by a Grant received from the Government of Portugal that partially supported Ccommunication For Development activities. The Portuguese Funds also partially supported the hiring of a national consultant that supported the complaints and feedback mechanism as well as the baseline line and end line studies. Some monitoring and evaluation missions were also supported.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | The project also trained a total of 72 local technical team members on the use of survey questionnaires to collect data in the communities in both Gabu and Cacheu regions. The results of this survey were used to conduct data entry via android applications tablets to generate the geospatial mapping of the communities to select the 250 vulnerable cashew crop growers in Gabu and Cacheu regions. The distribution of the cashew storage materials followed the selection of the vulnerable farmers in both regions
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | As mentioned above, a thorough geospatial mapping could not take place, as the regions did not possess the necessary technological infrastructure in the regions. After consultation with the two main Telecom companies in Guinea-Bissau (MTN and Orange), UNDP decided to continue to use technological means to geo-map the vulnerable cashew crop producers in a manner made possible in the country context.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | A total of 100,012 USD was made available by the MPTF for UNDP to support the vulnerable cashew crop growers in Gabu and Cacheu Regions. A total of 98,879 USD was spent with the delivery of 98.9%, leaving the balance of 1,133 USD. As far as procurement, a total of 2 partnerships were signed between UNDP and its local partners. UNDP signed agreement with Associacao Industrial da Guine-Bissau in the total amount of 50,157 USD to undertake the procurement process to procure and purchase cashew storage materials for 250 vulnerable cashew crop farmers in both Cacheu and Gabu regions. This process was successfully completed for both regions where the local Regional Delegates of SEPIR received the materials for eventual distribution to the vulnerable populations. On the other hand, UNDP signed agreement of 9,900 USD with the local high-tech company INNOVALAB to carry out the geospatial mapping of the communities to select the 250 vulnerable cashew producers. No additional resources were made available. In UNICEF's case, the Country office has spent $ 92,956.15 for this grant and all the funds have been used

## RBM-Final
|  | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 2: Most vulnerable girls, boys, women, and men in targeted communities have access to social and economic protection mechanisms
Indicator:
Baseline:
Planned Target:
Output 2.1 Most vulnerable girls, boys, women, and men in targeted regions have access to non-contributory emergency social protection schemes and are enabled to meet food and nutrition needs
Indicator 2.1a Proportion of households with acceptable Food Consumption Score disaggregated by sex | UNICEF/WFP |  |  | WFP Monitoring | WFP
Baseline: 62.3% |  | F=68.1% M=79.9%
Planned Target: >=80%
Indicator 2.1b Proportion of women between 15- and 29-years old meeting Minimum Dietary Diversity – Women | UNICEF/WFP | 20
Baseline: 17.9%
Planned Target: >=40%
Indicator 2.1c: Proportion of children 6–23 months of age who receive a minimum acceptable diet disaggregated by sex | UNICEF/WFP | F=8.30% M=8.50%
Baseline: 8.49%
Planned Target: >=20%
2.1.1a Number of households receiving cashbased transfers – disaggregated by sex | WFP | 1,587 families | The WFP has assumed the payments of the Remaining beneficiaries in the partnership for the joint implementation of the ct-mptf | MTN Paiment records on CT-MPTF Beneficiaries | UNICEF provided these responses
Baseline: n/a
Planned Target: 1200 (800 Women-Headed, 400 Male Headed)
2.1.1d Number households with women, men, boys and girls with disabilities receiving cashbased transfers | WFP | 540 | During the selection Process It was found that many head of households were living with disability so as it an humanitarian project aiming to help the most disadvantage households, we priveleged thease people that certeinly met the criteria
Baseline: n/a
Planned Target: 200
2.1.1e Proportion of assisted population receiving cash receive transfers through electronic delivery mechanisms (mobile money, electronic voucher) | WFP | 100% | N/A | N/A
Baseline: n/a
Planned Target: 100%
2.1.1f Number of people reached through C4D approaches using media – disaggregated by sex | UNICEF
Baseline: n/a
Planned Target:14000
2.1.1g Proportion of beneficiaries who are aware of the CFM mechanism and available communication channels– disaggregated by sex; | UNICEF/WFP | 22,2% of beneficiary interviwed in ednline study confirmed the knowledge of CFM mechanism | some C4D activities were not carried out during the program | C4D planned and realised activities on CT-MPTF | Unicef
Baseline: n/a
Planned Target: >=80%
2.1.1h Proportion of assisted people informed about the programme (who is included, what people will receive, length of assistance) – disaggregated by sex | UNICEF/WFP | 36,6% | C4D informative sessions were deemed insuficient, lessons learnt have been collected and discussed among the team to improve future similar interventions |  | Unicef
Baseline: n/a
Planned Target: >=80%
Output 2.2 Most vulnerable girls, boys, women, and men in targeted regions have access to non-contributory emergency social protection schemes and are enabled to meet food and nutrition needs
For the first two indicators, the geospatial mapping could not be fully undertaken, given the difficulties of Telcom infrastructure in the regions of Gabu and Cacheu. UNDP still managed to carry out a digital questionnaire that allowed the inclusion of georeferencing the farmers inquired, through a partnership with Innovalab, so that the 125 vulnerable farmers in each regions could be selected.
2.2.1.a Proportion of beneficiary farmers who were identified through geospatial mapping | UNDP |  |  |  | UNDP
Baseline: n/a
Planned Target: 90% |  | 100%
2.2.1.b Number of vulnerable cashew crop growers from selected regions of Guinea Bissau that are mapped for receiving support | UNDP |  |  |  | UNDP
Baseline: n/a
Planned Target: 100 |  | 2253 households inquired
2.2.1.c Number of vulnerable cashew crop growers that obtain support for harvesting, treating, packing, transporting and storing their products | UNDP |  |  | Reports from partners (Innovalab and AIGB) as well as receipts from the farmers that received the materials and respondents to the vulnerability mapping questionnaire. | UNDP
Baseline: n/a
Planned Target: 250 |  | 250
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Assisting Guinea-Bissau’s most vulnerable families during the COVID-19 pandemic
Cash transfer programme to reach 1, 587 vulnerable households across the country
Azevedo Gomes belongs to a village community inhabited by close to 500 people, some thirty kilometers south of the town of Cacheu. At 98 years of age, he remains firm and grows fruits and tubers in his farm and even recalls having been a seasonal migrant to The Gambia, where he worked as a stevedore. But with the onset of COVID-19 in Guinea-Bissau, Gomes, as many other agricultural workers in the country, has been negatively affected by mitigation measures put in place to prevent further transmission of the disease.
The state of emergency declared on March 27th, 2020, meant that borders and schools were closed, markets, where crops grown by farmers like Gomes would have been sold, faced drastic restrictions and movement across the different regions was limited. The introduction of COVID-19 in the country also coincided with the cashew campaign, which proved to be unsuccessful as global demand fell.
Gomes, and other vulnerable Bissau-Guineans, who depended on the revenue from cashews and the sale of other produce both nationally and internationally, were faced with increasing threats to their livelihoods and food insecurity.
In a bid to alleviate some of the pandemic’s worst consequences on Guinea-Bissau’s most vulnerable populations, UNICEF, supported by the Multi-Partner Trust Fund for COVID-19 and in coordination with WFP and UNDP, intervened to ensure that these households would have access to social and economic protection mechanisms, food security, and even support for cashew crop growers. One of the villages identified for the programme was Bianga, where Azevedo Gomes resides.
Recently awakened from his nap, he welcomed the programme implementation team smiling, and inquiring about where they travelled from. Overjoyed at receiving the cash transfer, equivalent to two thirds of the national minimum wage, Gomes expressed that it has helped to improve his diet, “I buy fish every day. I like fish, it’s my favorite”. He added that the fund also helped him to pay bills, including the school fees for his great-grandchildren.
His is one of 1,587 households that was supported across the country through the distribution of cash transfers. The programme was implemented by providing identified households with phones and SIM cards to allow families to access funds through mobile money. Mobile phones were also critical as they were used to conduct surveys to inform the baseline and end line data. Access to phones has also facilitated the feedback mechanism between UNICEF and the beneficiaries to enable them to provide feedback on the program and present claims. The program has also assessed its impact through measurements like the dietary diversity of women and children, demographics that are disproportionately affected by the pandemic. Of the households identified for the cash transfer program, 66% of them were headed by women and the vast majority had 5 or more dependents. With schools being closed under lockdown measures, additional stressors were placed on children’s principal caregivers.
But Gomes remains hopeful, “I had the happiness of living a long and productive life filled with experience”, he says. He hopes to pass it down to the younger generations just as he hopes to learn with them. Gomes is renewed with each new day, despite the precarities of the village that is isolated by treacherous roads and the hardship in the times of the pandemic. He is grateful to find a bit of support for his subsistence, so that he can continue surviving the worst consequences of COVID-19 and pass on his wisdom wherever he can.