## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | REINFORCING SURVEILLANCE AND CASE MANAGEMENT/INFECTION PREVENTION CONTROL IN SUPPORT TO MADAGASCAR NATIONAL RESPONSE PLAN AGAINST COVID-19 BY DECEMBER 2020. | Overall Duration (months) | 9 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 30.04.2020
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 29.01.2021
Country | Madagascar | Current End date(dd.mm.yyyy) | 29.01.2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF, UNIDO, WHO | National counterparts (government, private, NGOs & others) and other International Organizations
National counterparts: Ministry of Health (MoH), Ministry of Trades, Industry and Craft (MICA) and DRICA, Health and Environment Department (SSEnv) Beneficiaries Private sector: Eole. Air Liquide, Society of Anesthesia and Resuscitation of Madagascar (SARM), with the Malagasy Society of Pediatrics (SOMAPED), with the Society of Infectious Pathology of Madagascar (SPIM) Analamanga Region: KABALOO,MAHEFARIMANANA, Alaotra Mangoro Region: Promotion Feminine Moramanga, Atelier J4 Ambatondrazaka, Association VALITANANA Ambatondrazaka, Atsinanana Region: KOVAMPAMINA, Association APIM, Association ESPERANCE. Analanjirofo Region: Cooperative MAMIRATRA, Cooperative TNIM
Report Cleared By
o Name: | Issa Sanogo
o Title: | UN Resident Coordinator
o Email address: | issa.sanogo@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | WHO Investigation rate has grown from 75.9% to 84.3% due to the involvement of the Rapid Response Team (RRT) trained in 22 regions, they were based in the field to support interventions. Due to the reinforcement of testing capacities in making available GeneXpert network in regions, the testing has been improved: 100% of the suspected cases responding to clinical definition have been tested. As of 31 December, 10,223 suspected cases were tested either by RT PCR or GeneXpert with 17.6% positivity rate. As of this date, 17,931 confirmed cases were notified. In addition, 408 Emergency Response Team were trained to support activities at regional and district level Despite these results, for the data of the other suspected patients treated under syndromic approach, the information is not available and not shared by MoH because samples are not collected for dispatch to labs. By September, 228 health workers have been contaminated in 9 regions and have benefited from specific treatment. Among them, 163 have received treatment in hospital settings and 5 deaths have been registered; after this period, no information was shared on the situation. UNICEF The main activities were capacity building in resuscitation, management of pediatric cases and in infection prevention control measures and oxygen supply for managing severe cases. 175 health workers in resuscitation services from 46 CHU/CHRR/CHRD were trained on adult severe case management, 97 health workers in pediatric services from 30 Hospitals (CHU/CHRR/CHRD) were trained on pediatric severe case management and 874 Hygienists in large hospitals in 21 districts in 11 regions were trained on Infection Prevention Control. With the context of COVID-19, the number of participants in the various trainings was limited to 20 per session to respect infection control measures and behaviors. Oxygen supply has been ensured in all regions affected by the COVID-19 through 31 intensive care centres where 95,781 m3 of oxygen were provided till the end of December whereby 9,276 patients/day for moderate, severe and very severe patients benefitted from specialized care with oxygen therapy in these 31 intensive care centres. UNIDO UNIDO's rapid response intervention against the fight to COVID19 had as overall objective to manufacture and distribute 580,000 category 2 facemasks to local communities located in the regions and areas identified as being the most affected by COVID-19, while supporting the textile sector in these areas. In addition, the project aimed at supporting the Ministry of Industry, Trade and Craft (MICA) with the production of 20,000 facemasks for Ministries members and officials. In that regard, garment workshops were identified in three regions (Analamanga, Alaotra Mangoro, Atsinanana and Analanjirofo), and according to their respective needs and in relation to the project's baseline, equipment, subsidies and basic training were granted to them to produce category 2 masks.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The overall beneficiaries are primarily the populations of the 14 districts affected by Covid-19 since early March and the others Districts during the peak of mid-July to mid-August: 8,697,521 people in total, of which 4,240,046 men and 4,457,475 women. The MPTF funds contributed to support the implementation interventions covering the Human Resources capacity strengthening in hiring 8 epidemiologists, managing COVID-19 confirmed cases and provision of supplies and PPE for the protection of personnel involved. 17,931 (Male: 9,247 and female :8684) confirmed cases have been treated, of which 17,406 recovered from diseases, 265 deaths registered and identified 101,223 PCR tests realized. With regards to age distribution for the confirmed cases, the over 60 years old patients is the most affected representing (64.81% for male and 35.19% for female). For UNIDO in particular, the project has reached 2,565 beneficiaries, mainly vulnerable communities, located in the 10 workshops listed in Annex.
3.1 | Results: Outcome Level | Please include outcome level results achieved | • 84.3% investigations carried out: this investigation rate has grown from 75.9% to 84.3% due to the involvement of the Rapid Response Team (RRT) trained in 22 regions. These RRT contributed to investigation and contact identification and training at central and regional level during the reporting period. • 100% of suspected cases responding to clinical definition tested: due to the reinforcement of testing capacities in making available GeneXpert network in regions, the testing has been improved. As of 31 December 2020, 10,223 suspected cases were tested either by RT PCR or GeneXpert with 17.6% positivity rate. As of this date, 17,931 confirmed cases are notified. • 22 RRT are operational for the regions, the additional 19 RRT have been trained together with the district level, the total of 408 ERT members have been trained to support activities at regional and district level.
3.2 | Results: Output Level | Please include output level results achieved | • Capacity building in resuscitation: 29 CHU/CHRR, 17 CHRD (CHU: Centre Hospitalier Universitaire – CHRR/D: Centre Hospitalier de Reference Regional/District) • Management of pediatric cases: 14 CHU/CHRR, 10 CHRD • Infection prevention control measures: 19 CHU/CHRR. 10 CHRD • Oxygen Supply: 27 CHU/CHRR 4 CHRD • Masks produced: 400,000 (against 580,000 planned) due to Covid-19 supply chain restrictions (100,000 masks already delivered, the remaining quantities are being delivered by each workshop and according to the agreement they have with their respective DRICA). • 17,671 confirmed cases treated during the reporting period. • By September, 228 health workers have been contaminated in 9 regions and have benefited from specific treatment. Among them, 163 have received treatment in hospital settings and 5 deaths have been registered • 10 associations and companies have been targeted and supported by the production of masks (against 3 workshops planned), this include 2,565 beneficiaries including 1,500 women (against 2,200 beneficiaries including at least 1,340 women initially planned) • 6 workshops are led by women. • 02 fablab laser cutter have been provided by the project to improve workshops' capacities and to foster innovation and digitalization. • 75 industrial sewing machines for technical support and equipment of garment workshops have been provided to beneficiaries. •Trainings and capacity building sessions in Production and Quality of garment workshops have been organized by the project
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | • After the first training sessions for anesthesiologists and pediatricians, with the resurgence of the epidemic and a peak from July to August 2020, the restriction on the movements of trainers related to national confinement measures did not allow the extension of the training. Thus, virtual sessions were conducted and face-to-face training sessions were relaunched during September following the gradual deconfinement. During the same peak, the oxygen supply reached its maximum country capacity. Fortunately, the second O2 supplier was mobilized and was able to complement the first one. As a result, no rupture of O2 supply was experienced. A positive outcome of the O2 EMERGENCY supply was the possibility to mobilize more funds for a thorough renovation and equipping of O2 supply in all regional capitals of Madagascar that be implemented from 2021 onwards under the responsibility of the MoH. • From September to December 2020, there were no coordination strategic meetings (WHO, Institut Pasteur de Madagascar, World Bank, UNICEF and USAID), making harmonization of issues difficult between MoH and partners. The MoH took leadership not regular sharing the difficulties for clear interventions on one hand, one the other hand, the data were shared on irregular basis after the declaration of end of emergency. • With regards to surveillance, the testing strategy was not clearly defined in the country with a focus on syndromic approach and requirement of payment for some patients in some areas to benefit from health care. • The limited funding made the interventions of the RRT difficult to easily carry out all the expected activities • The delay in defining the distribution plans for the medical supplies exposing to the shortage risk for some areas. • The laboratory testing capacities were reduced due to the limited number of Tests and machines in country, the GeneXpert machine helped to increase the capacities in regions. • The number of ICU beds are reduced in the country, reducing the treatment capacities due to the situation requiring strong surveillance for based treatment of patients • There is not a clear visibility of the medical and non-medical supplies existing in country in support to COVID-19 response. • The garment workshops were not technically and materially equipped for manufacturing such important quantities: after a need assessment, the project considered it useful and necessary to add industrial equipment so that each workshop and association could work in a fair and efficient way. • Then, due to lack of resources and also in the actual crises of Covid-19 hitting the country, the workshops did not have the means to start the production. It was necessary to equip workshops with a subsidy in order to make the masks, otherwise the workshops would not have been able to cut the fabrics, sew the panels of fabric, etc. and deliver these masks to their respective DRICA. • Lack of health standard for facemasks production (such as AFNOR Specifications): since standards are not yet applied in Madagascar, it was necessary to carefully test the composition of the fabrics and pay a particular attention to the weight in order to make the compliant with the standard.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | • The involvement and leadership of the Ministry of Health were important. The gender dimension has been considered regarding the training of health workers. The indispensable O2 supply that saved many lives mobilized as an emergency allowed conscientization of donors to fund national rehabilitation of O2 supply in regional capitals. • Due to the urgency of the current Covid-19 situation, the project took a long time before starting the production of the masks, this was mainly due to the administrative procedures. In that regard, exceptional procedures with regard to public procurement rules and regulations commensurate with the urgency and specific type of intervention has been granted by the Organization. This specific procedures have already been replicated to similar Covid-19 rapid response projects. For future projects, and in order to improve the efficiency of interventions the following suggestions could be made: • Workshops identified by the Ministry should be subject to a preliminary assessment to define their needs and their productive capacity as well • The subsidy mode is always necessary when a project affects the production component in the workshops. Indeed, the small garment workshops do not have the financial means to start a production large enough. • Despite these difficulties, the team did its utmost to ensure the achievement of objectives and results. UNIDO's intervention put in place the necessary safeguards to enable the workshops to continue their activities even beyond the end of the project.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | • As part of capacity building in resuscitation and management of pediatric cases and in infection prevention control measures, collaboration has been developed with the Society of Anesthesia and Resuscitation of Madagascar (SARM), with the Malagasy Society of Pediatrics (SOMAPED), with the Society of Infectious Pathology of Madagascar (SPIM). These were for special intensive care but also with the national Medical Association for decentralized care of benign cases, with MEDAIR and the Health and Environment Department (SSEnv) for the hygienists' training. Training and monitoring tools have been developed for daily monitoring of O2 supply and consumption as well as for the decentralized care. • A partnership has also been established with companies supplying oxygen to hospitals, mainly EOLE and AIR LIQUIDE. WHO has been organizing weekly partner coordination meeting to ensure the harmonization of interventions and shared the updated policies related to the response strategies and SoPs. The coordination meeting contributed to update the 4W and share responsibilities based on the partner specific mandate. The joint donation activities were organized to respond to country expressed needs. • In order to allow installation of Fablab equipment and training of beneficiaries on them, despite the restrictions on movement and gatherings, the project set up a very innovative and digital scheme allowing distance learning trough smart and virtual reality eyewear. This has been made possible thanks to the project partner "Fablab en kits". The two trained workshops all benefited from this first innovation in the textile industry. • A practical training in Quality and Production was also necessary and to support the workshops and to allow them to understand the stakes in the production and also to make the most of the industrial machines they benefited from. • Despite the difficulties faced during the identification phase, the partnership with project's beneficiary workshops was finally much more efficient and productive once the project was launched. With a lot of exchanges and positive sharing, the beneficiaries expressed their wish to go into a much more professional and social evolution of their structures even beyond the project.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | • An evaluation might take place in 2021 of the severe cases hospitalized and benefitting of O2 supply to inform the future management of these cases as well as inform the policies for COVID-19 management. • An evaluation and expression of a demand for further trainings in Quality and Production was raised by the workshops, the need for technical support for the handling of industrial machinery was identified.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The project planned to manufacture 580,000 facemasks, but after a field assessment, supply chain related difficulties and considering the fact that the workshops needed more equipment and subsidy, the quantities of masks to be produced were finally adjusted to allow the workshops to produce facemasks that are AFNOR compliant, but more importantly to help them to develop their activities even beyond the end of the project and thus being sustainable.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | For UNICEF in particular, the programme mobilized additional resources from other partners to ensure the coverage of all the Districts affected as well as ensure complementarity with other donors and stakeholders

## RBM-Annual
OUTCOME/OUTPUT INDICATORS
Outcome 1. The structures of Ministry of Public Health at central, regional and District levels are able to ensure monitoring (surveillance) and case management/Infection prevention control
|  | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome Indicators (as in the approved ProDoc)
1.1.a - Percentage of COVID-19 confirmed cases investigated and contacts identified |  | 84.3% | The investigation rate has grown from 75.9% to 84.3% due to the involvement of the RRT trained in the 22 regions who are directly on field supporting interventions. These RRT (Rapid Response Teams contributed to investigation and contact identification and training at central and regional level during the reporting period. For the cases in regions, due to the number and the capacities and some communication challenges this was not possible to investigate the totality of cases. | Activity report WHO
Baseline: 100%
Planned target: 100%
1.1b - Percentage of suspected COVID-19 cases sampled and tested in laboratory |  | 100% | Due to the reinforcement of testing capacities in making available GeneXpert network in regions, the testing has been improved. As of 31 December 2020, 10, 223 suspected cases were tested either by RT PCR or GeneXpert with 17.6% positivity rate. As of this date, 17,931 confirmed cases are notified by Madagascar. Despite these results, for the data of the other suspected patients treated under syndromic approach, the information is not available and not shared by MoH because sampled not collected for dispatch to labs. | Activity report WHO
Baseline: -
Planned target: 100%
1.1.c - Number of rapid response teams functional 24/24 and 7/7 |  | 22 | The additional 19 RRT have been trained together with the district level. As such, the total of 408 ERT members have been trained to support activities at regional and district level | Activity report WHO
Baseline: 3
Planned target: 22
1.1.d - Percentage of patients who develop a severe form hospitalized in the resuscitation center taken care of by state of the resuscitation measures |  | 100% | By the end of December, 9,276 patients/day have benefitted from specialized care with oxygen therapy in intensive care centres | Activity Report
Baseline: -
Planned target: 100%
Description of results
1.1.1. The health structures at central, regional and District levels are equipped to monitor/manage the cases and implement the infection prevention control measures
1.1.2. The identified hospitals managing severe cases are equipped and have the capacity to ensure proper care to treat patients developing a severe form infected by COVID-19
1.1.3. The local actors (local authorities, traditional authorities, chiefs of Fokontany, possibly in collaboration with health workers) carry out actions to disseminate information and raise community awareness on prevention and response measures to COVID-19 (application of barrier measures) and on GBV/EAS reduction
Output Indicators (as in the approved ProDoc)
1.1.1a. Number of people treated in hospital settings |  | 17.671 | This represents the number of COVID-19 confirmed cases of patients developing moderate and severe form, they have been treated and confirmed with a final outcome either recovered or death as of December 31, 2021 | Hospital records report/ Sitrep WHO
Baseline: 212
Planned target: 1,000
1.1.1b - Number of health care workers contaminated by COVID-19 |  |  | By september, 228 health workers have been contaminated in 9 regions and have benefited from specific treatment. Among them, 163 have received treatment in hospital settings and 5 deaths have been registered. After this period no information was shared on the situation. | Hospital records WHO
Baseline: 212
Planned target: 0
1.1.1c - Number of treatment centers with shortages of essential equipment and supplies |  | 0 | All the 36 treatment centers have been provided with supplies depending on the expressed need from MoH. | Hospital records/ inventory report
Baseline:
Planned target:
1.1.2a - Number of COVID-19 hospitals Resuscitation teams equipped with theoretical and practical knowledge to ensure proper care to severe COVID-19 infected patients |  | 46 | The conjunction of other sources of funds allowed to overpass the overall targets - The 34 were achieved with MPTF funds | Refresher course report
Baseline: 4
Planned target: 34
1.1.2b - Number of hygienists in the three regions trained and implementing IPC measures to reduce COVID-19 transmission |  | 874 | Out of the total number of 874 Hygienists trained on IPC, 269 hygienists were achieved with MPTF funds and the other 605 hygienists were trained with other additionnal ressources. | Training report Monthly activity report
Baseline:
Target:
1.1.2c - Number of hospitals managing severe cases have Oxygen at their disposal without any discontinuity |  | 31 | 3 hospitals never requested O2 in view of no needs as no severe cases were admitted | O2 supply monthly report
Baseline: 4
Planned target: 34
1.1.3a - Number of textile companies trained, coached and producing masks |  | 10 |  | Business documents from companies / associations
Baseline: 0
Target: 3
1.1.3b - Number of masks produced locally |  | 400000 | 400.000 were feasible due to Covid-19 supply chain restrictions | Delivery notes to be sent to counterparts
Baseline: 0
Planned target: 580,000
1.1.3c- Number of jobs created/retained in the textile sector related to this activity
Baseline: 0 |  | 2565 |  | List of targeted beneficiaries working for companies / associations
Planned target: 2,200
- of which women jobs
Baseline: 0 |  | 1500 |  | List of targeted beneficiaries working for companies / associations
Planned target: 1,340

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
UNIDO TO PUT A STORY FROM THE FIELD HERE (video)
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
Link to UNICEF video: https://youtu.be/Vi3Gnng1-TM. A video documenting the activities implemented by UNICEF Madagascar in the field of health as part of the response to the COVID-19 pandemic was produced in August 2020, including strengthening the skills of health workers in case management. Another video on O2 support is being finalized
Link to UNIDO Communication materials: https://xfiles.unido.org/index.php/s/fTepETTe7LW68eB

## Annex
UNIDO Beneficiaries
1- KABALOO (1,860 employees in a multi-company group) Kaballo is a workshop member of the multi-company group, specialized in semi-industrial garments with added values in embroidery, silk screen printing and other special supports. KABALOO has actively contributed to the cutting of fabrics and provided the workshops located in the Provinces with panels of cut fabrics. 2- MAHEFARINAMANANA (110 employees) MAHEFARIMANANA workshop is a semi-industrial workshop located in Antananarivo, more oriented in knitwear but also in embroidery and screen printing. The MAHEFARIMANANA workshop has actively contributed to the cutting of fabrics and provided the workshops located in the Provinces with panels of cut fabrics. 3- Promotion Feminine (280 members). Promotion Feminine workshop is intervening in the field of women education through the provision of trainings in cutting and sewing. Managed by Catholic sisters, the aim of Promotion Feminine is to accompany young girls and also to help single mothers to find their path and professional orientation. The workshop is very artisana and the products are more oriented towards household linen and other basic textile products. 4- Atelier J4 (16 employees). This workshop aims to help young girls and mothers through the provision of vocational training in cutting and sewing in the Ambatondrazaka region. It has been established 10 years ago and has just moved to a larger premises to expand their activities and improve the workshop with the new industrial machineries provided by UNIDO 5- Association VALITANANA (30 members). The members of the association VALITANANA are doing charitable works in the city of Ambatondrazaka on a voluntarily. The sector of activity is very vast, from the training in restoration - kitchen and hotel trade to the craft industry. The association is leading very diversified activities, and started with textile related activities recently. After having designed washable sanitary pads and it is only since the beginning of the pandemic that the association decided to produce facemasks. 6- KOVAMPAMINA (156 members). KOVAMPAMINA also translates as Cooperative of the women of fishers is a cooperative that is working in crafts. The workshop and their commercial shop is located in Tamatave, mainly composed of women and young women. 7- Association for persons living with disabilities APIM (33 members). APIM or Association of Polio and Motor Infirm of Madagascar as its name indicates are people with motor problems but who work and earn their living with dignity through handicrafts and other industries such as handmade soap for example. 8- Association des Handicapés ESPERANCE (20 members). The association is also an association of people living with disabilities, the particularity of this workshop is that people are exclusively living from the local textile manufacturing industry in Tamatave. The member would like to work in the semi-industrial sector and required for technical and financial support to achieve their goal. 9- Cooperative MAMIRATRA (25 members). The cooperative is mainly composed of housewives who live from local sewing in the Fenerive East zone, these women also expressed support to widen their range of products and become more trained in access to market related issues 10- Cooperative TNIM (30 members). The cooperative lives from local clothing also by making aprons for students and all that is artisanal coverings. In addition to this local activity, the majority of the members are peasants and farmers.