## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Empowering Vulnerable and at-Risk Communities Adjust to the New Normal | Overall Duration (months) | 18 months
Programme Number (if applicable) | 123298 | Start Date (dd.mm.yyyy) | 2021-05-01
MPTF Office Project Reference Number: | 125952 | Original End Date (dd.mm.yyyy) | 2021-12-01
Country | Zambia | Current End date(dd.mm.yyyy) | 2021-12-01
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme |  | National counterparts (government, private, NGOs & others) and other International Organizations | ZFAWIB
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The objective of the project was to support the Governments efforts in reducing the risk of the spread of COVID 19 by providing standardised and certified masks to 20, 000 vulnerable at-risk communities and, to grow the domestic market for face masks which meet the certified standard, by targeting Lusaka-based tailors to establish the capacity to produce 50, 000 face masks. The project further aimed to provide an opportunity for the tailors to enhance their capacity to operate more effectively. To achieve this the project has identified the Zambia Federation of Women in Business (ZFAWIB) to implement the project activities. ZFAWIB has an extensive beneficiary network in the country's capital and has set up a catalytic revolving fund for women tailors that are participating in the production of masks to enhance their business resilience in light of the disruptive impact COVID- 19 has had on their businesses. ZAFWIB working through their partners also aims to ensure that all the members / tailors open individual mobile money accounts using mobile network operators (MNOs) of their choice. The mobile money accounts will strictly be used as channels for receipt of funds from the buyers of face masks. This will in turn increase their access to financial services as well as reduce risks of cash handling during and after the pandemic.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Through the Zambia Federation of Women in Business(ZFAWIB) that has been selected as the project's responsible party under the ongoing Business Reselinece Facility, ZFAWIB aims to target 500 women tailors in Lusaka city to produce 50,000 face masks. The project aims to secure 50,000 of these masks to distribute to atleast 20,000 vulnerable at risk populations through on going projects.
3.1 | Results: Outcome Level | Please include outcome level results achieved | RPA signed with implementing partner
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Sourcing 3 seperate groups posed a risk on coordinating activities and standardisation of face masks to be produced, to mitigate this risk one responsible party was chosen to coordinate the actitvities, this turned out to be beneficial as ZFAWIB had more female tailors than the proejct originally envisioned and had structured a revolving fund facility to empower it's members during and after the pandemic to have an accesible source of capital injection. the main difficulties encountered so far have been sorind onboaring ZFAWIB and allowing our partner to be accustomed to UNDP regulations and proceedures.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | A new partnership has been developed with ZFAWIB. ZFAWIB intends to use the funds of thre project to not only target the production of 50,000 masks across 500 women tailors but also create a revolving fund for the tailors that have had limited access to capital for their businesses. Half of the funds raised from the sale of face masks will be equally distributed among the 500 tailors as part of their initial working capital. The remaining funds will be kept under one common account, opened within a recommended bank of the tailors’ choice. The account will be controlled by ZFAWIB. The available funds in the account, will be a working capital loan fund and can be accessed by any of the tailors, who participated on the pilot in future. The project will initially aims to commence with one intervention focusing on the growth and resilience of one MSME segment, which is the tailors. After monitoring the pilot for three months, and depending on the progress, the project will be extended to the other lines of MSMEs segments
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] |  | Zambia Federation of Women in Business(ZFAWIB) was selected as the sole implementing partner due to their beneficiary coverage(500women tailors) and ongoing empowerment project with women that had their incomes disrupted by COVID 19. | ZFAWIB and UNDP RPA
Mitigate the Socioeconomic Impact and safeguard people and their livelihoods/ To increase income for small scale business enterprises through the production of 50, 000 cloth masks through the Zambia Bureau of Standards of which total production has been targeted specifically for women led MSMEs | 1
Indicator 1:2 women and 1 you led cooperative trained and mentored on the standardization of production of cloth masks by ZABS.
Baseline:0
Planned Target:3
Indicator 2:2 women-led and 1 youth-led cooperatives contracted to produce 50,000 of re-usable cloth masks according to defined ZABS standards. | 0 | ZFAWIB is due to begin project impmentation on 1 Septmenr 2021, when funds for implementation have been received. | N/A
Baseline:0
Planned Target:50000
Output 1.To contribute to the reduction in spread of COVID-19 amongst vulnerable hard to reach households | 0 | ZFAWIB is due to begin project impmentation on 1 Septmenr 2021, when funds for implementation have been received. | N/A
Indicator 1.1.1: Distribution of the 50,000 cloth masks produced distributed among over 20,000 vulnerable women across 3 provinces
Baseline:0
Planned Target:20000
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board