## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Leaving No One Behind in Timor-Leste's COVID-19 Response - Technical and Financial Support for the Implementation of the Cash Transfer Scheme for Low-Income Households | Overall Duration (months) | 8.5 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 20.05.2020
MPTF Office Project Reference Number: | 121445 | Original End Date (dd.mm.yyyy) | 30.11.2020
Country | Timor-Leste | Current End date(dd.mm.yyyy) | 29.01.2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | International Labour Organization (ILO) and | National counterparts (government, private, NGOs & others) and other International Organizations | Government of Timor-Leste, Ministry of Social Solidarity and Inclusion (MSSI), Australian Department of Foreign Affairs (DFAT), World Bank (WB), Catalpa, Rede Feto, ARCOIRIS
UN Women
Report Cleared By
o Name: | Hemansu Roy Trivedy
o Title: | Resident Coordinator
o Email address: | hemansu.trivedy@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Through the support from the COVID-19 MPTF-funded joint programme, the UN in Timor-Leste was able to support the Government’s COVID-19 social cash transfer scheme for low income households, which reached a total of 313,391 households - a total of 98 percent of all eligible households in the country, and 20 percent of which were female-headed. This was the first ever national cash transfer scheme in Timor-Leste, and the UN’s support was highly appreciated by the Government of Timor-Leste, not least because the UN’s support for this work was provided through the Government’s COVID-19 Response Fund (established by the Ministry of Finance). With the joint programme covering 68 percent of the operational costs of the first stage of the cash transfer scheme, the joint programme significantly contributed to the efficient implementation of the social cash transfer programme. Furthermore, the joint programme enabled civil society monitoring of the Government scheme, which strengthened the capacities of 14 women’s organizations to support evidence-based advocacy and conduct qualitative research to promote evidence-based advocacy. The work of the CSOs resulted in a set of recommendations that can inform future Government COVID-19 response and recovery programmes to make them more inclusive of marginalized groups, such as single women, LGBTI persons and people with disabilities. In a meeting with the Minister of Social Solidarity and Inclusion in early February 2021, the Minister appreciated the joint UN support – led by ILO and UN Women – to the COVID-19 social cash transfer scheme and recognized it as a catalytic support that enabled good collaboration and coordination amongst the development partners and civil society organizations in support of the Ministry. The RC/UNCT were able to use the opportunity to advocate to the Minister to convene more regular meetings with development partners and CSOs on social protection, so that development partners can provide more effective, coordinated support for social protection work in the country led by the Ministry.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The goal of the activities under this initiative was twofold: 1) Contribute to the operational costs of the Cash-Transfer Programme developed by the Government of Timor-Leste to mitigate the socio-economic impact of COVID-19 on the population. 2) Increase the engagement of the programme with civil society, in particular organizations representing more vulnerable groups (women, domestic workers, lesbian, bisexual women and transgender persons (LBT), etc.) which were a priori more likely to find barriers in accessing this programme. The contribution under point 1) covered 68% of the operational costs of the first stage of payments, which reached 313, 391, or a total of 98% of eligible households were reached. In the first stage of the cash transfer, 298,816 households were reached, 19% of which were led by women. In the second stage of the cash transfer, 14,582 households were reached, 36% of which were led by women . The contributions under point 2) supported a coalition of 14 women’s organizations led by National Women’s Network, Rede Feto Timor-Leste, to conduct qualitative research which directly engaged 1,594 people (1,499 women and 95 men, including 221 women (15% of respondents) with disabilities). The respondents were engaged through interviews and Focus Group Discussions across the country’s 12 municipalities and the Special Regional Authority of Oecusse-Ambeno. The findings have been presented in two workshops and via a television programme, which reached a wider audience. In total, 313,391 households were reached by the cash transfer programme (250,681 were male-headed households, 62,678 were female-headed households, and 31 were "other"). In the second stage of the cash transfer, for complaints only, 14,582 households were reached in total (9,343 were male-headed households, 5,224 were female-headed households and 15 were "other"). Note that these numbers are subject to very minor changes as the data reconciliation for the complaint payment process is being finalized.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The overall aim of the COVID-19 Social Cash Transfer, as per the Results Matrix, is that “By 31 December 2020, all the people of Timor-Leste, particularly the most vulnerable, including women and children, are relieved of the socio-economic impact of the COVID-19 pandemic” (Outcome 2.1). Overall, the COVID-19 Social Cash Transfer was successful in relieving the socio-economic impact of the COVID-19 pandemic for the people of Timor-Leste including the most vulnerable groups. The research supported by Rede Feto found that 96% of the 1,418 women from vulnerable groups had either directly collected the cash transfer (51%) or received through another household member (with 39% reporting the transfers were received by husbands, brothers, brother-in-laws or sons). Timor-Leste’s social protection programmes have historically lacked an overarching and coordinated framework, resulting in many gaps and people left without coverage and adequate support. The first outcome indicator which the COVID-19 Social Cash Transfer aimed to contribute to is the implementation a nationally appropriate social protection system (Outcome Indicator 2.1a, SDG Indicator 1.3). This was the first time in Timor-Leste’s history that the Government has implemented a nationwide programme such as this, successfully covering 98% of all eligible households. Most recipient households reported that they had found the support invaluable at a time when people had been made redundant due to business closures and market disruptions due to COVID-19. One key challenge in the implementation was that some vulnerable groups were not considered eligible for the cash transfer (either because they were not properly registered with the local authorities, had divorced from their partners or for other reasons) including some single women, widows, eligible women without access to the Family Record and some members of the LGBTI community. A key recommendation to Government from this programme is that future social protection programmes need to consider developing specific strategies, for example in their Standard Operating Procedures (SOPs), to guarantee that measures are put in place to reach those most vulnerable. Overall, there is an interest and demand for the cash transfer, as a study by the Asia Foundation in September – October 2020 showed that 46 % of households think that the Government should provide more cash to households. One of the most prevalent issues in Timor-Leste is the high rates of food insecurity and malnutrition, which are some of the highest in the world. The second outcome indicator which the programme aimed to improve was the food security status of the most vulnerable households of Timor-Leste (Outcome Indicator 2.2a, SDG Indicator 2.1.2). Prior to the pandemic, the percentage of the population that was moderately food insecure (Integrated Food Security Phase Classification, IPC level 3) was 21%, and after the pandemic, the Timor-Leste Food and Nutrition Survey 2020 (TLFNS), preliminary results show that the number increased to 34.8% (according to the Food Insecurity Experience Scale, FIES). The percentage of the population that experienced severe food insecurity was 15% (IPC level 4) and during COVID-19 severe food insecurity was 15.6% (FIES). (Please note here however that two different scales/classifications are were used to measure food security prior to and during COVID-19). The COVID-19 Socio-Economic Impact Assessment 2020 (SEIA) undertaken in June/July 2020 showed that 37.6% of the participating households were affected by moderate or severe food insecurity, i.e. at least one household member has been forced to reduce the quality of their diet due to lack of money or other resources. The SEIA showed that almost half of the most vulnerable households (47.7%) responded that lack of money or food was their biggest concern as a result of the COVID-19 pandemic. Similarly, the Rede Feto research found that 98% of respondents reported that the lack of ‘basic necessities’, particularly food, was the biggest challenge that many households faced. The importance of the cash transfer in alleviating the exacerbated issue of food security is reflected in the results of the Monitoring & Evaluation (M&E) report which showed that 95% of beneficiaries used the extra money to purchase food. Finally, the social cash transfer aimed to contribute to sustaining per capita economic growth in accordance with national circumstances in the least developed countries (Outcome Indicator 2.3 a, SDG Indicator 8.1). The World Bank projected that the GDP would contract by at least 5% in 2020, a sharp decline after an expansion of 3.4 % in 2019. Similarly, the Asian Development Bank (ADB) expects a decline of 6.3% in 2020. While official GDP data from the Ministry of Finance is not yet available for 2020, proxy data from the SEIA shows stark signs of a contraction in the economy. Eighty-one percent (81%) of Small and Medium Sized Enterprises (MSMEs) experienced a loss of earning, and for households, 56.6% had to survive without any revenue, compared to 18.3% prior to the pandemic. As per the ‘Theory of Change’ of this programme, it was anticipated that the cash transfer would help smooth out consumption, despite an increase in unemployment amongst households and increase aggregate demand in local food markets. Each eligible household in all of the 13 municipalities received a cash transfer of US$ 200, and surveys show that 95% of households planned to primarily spend the money on food consumption (which would amount to private consumption of US$ 63 million). If the planned spending reflects actual spending of the government cash transfer, it reinforces the aim laid out by the programme Theory of Change. Despite the expected fall in GDP, the cash transfer would have mitigated some of the adverse of effects on GDP, through increasing private consumption and aggregate demand. It is however worth to note here that private consumption in Timor-Leste generally has a lower weight on GDP than public consumption (World Bank Economic Report 2020).
3.2 | Results: Output Level | Please include output level results achieved | The COVID-19 Cash Transfer Results Matrix highlighted five outputs to which the programme aimed to achieve and contribute to. The first output indicator covered the number of households receiving cash transfers (Output Indicator 2.1.1a) where the target was all low-income households in Timor-Leste (318,257). The final progress was that 313,391 households received the cash, i.e. 98 % coverage. Almost half, or 47%, of those who collected the payment on behalf of the households were women. Some vulnerable groups were not considered eligible (as highlighted under Outcome Indicator 2.1a description), which is why one recommendation would be to develop an SOPs to ensure better compliance with the principle of Leaving No One Behind (LNOB). Secondly, the programme aimed to develop effective, accountable and transparent institutions at all levels (Output Indicator 2.1.b and SDG 16.6). Previous social security programmes have lacked financial and human resources, quality assurance, M&E and implementing capacity which resulted in poor quality of services delivered. Through strong partnerships between the UN agencies, MSSI and other development partners, this programme reached its target by establishing a feedback and grievance system with real time response. This grievance system was crucial in capturing groups that were overlooked, inputs to barriers were analyzed and proposed recommendations were shared with MSSI. In support of strengthening institutional feedback mechanisms, the Rede Feto raised awareness of at least 10 government and State institutions, civil society and development partners with its Advocacy Brief and Policy Recommendations, developed with support from UN Women and shared during two roundtable discussions. The recommendations also reached a wider audience via a televised panel discussion, which helped raise visibility of the barriers and improve social protection and gender mainstreaming within the ongoing COVID-19 responses and for future emergency responses. Thirdly, the cash transfer sought to ensure access to food (both economic and/or geographic access). According to the SEIA 2020, Timor-Leste’s food security profile suggests that food insecurity is often related to problems of accessibility to food, rather than overall food shortages. One key adverse effect of the State of Emergency (SoE) according to the SEIA, was households lack access to markets to buy and sell food (32%). One 32-year-old women from the community stated that: “We used to have fish because my father and brothers normally go fishing. I love fish. But during that time [SoE] we didn’t eat fish because my family wanted to go fishing but the police had forbidden them to do so. Instead we ate moringa, corn and papaya and only meat sometimes like chicken.” In late June, 70% of retailers noted that staple food prices remained the same, while 23% experienced an increase, in particular in the municipality of Oecusse (an enclave of Timor-Leste in western Timor, Indonesia) as higher transport feed influenced the commodity prices. As 95% of receiving households reported that they planned to use the cash to purchase food, this would entail that the cash transfer has increased primarily economic access to food. The Market Resilience Survey (2020) reflects an improvement in access to food, in that between May and July foods including grains, eggs, meat and fish, and agriculture products became less scarce. At the same time, 65% of Rede Feto research respondents noted the cash subsidy was helpful, but not sufficient. It is worth noting that 73% of respondents had between 4 to more than 11 family members in their household, with 68% of respondents having one to five household members economically dependent on them. The cash transfer also aimed to minimize the negative socio-economic effects of COVID-19 through the stimulation of aggregate demand and subduing the negative effects on unemployment (Output indicator 2.3.1a). Unemployment was 10.4% according to data from 2016, however according to the SEIA, 22% of all persons employed lost their work due to COVID-19. The unemployment level during the period June-July 2020 was found to be extremely high at 38.2% (almost the same for both sexes). Unemployment among young people under the age of 30 was 54.7%, and 83% of persons with disabilities were not economically active. These unemployment levels are much higher than the initial target in the Results Matrix. The World Bank notes that “…poor people [of Timor-Leste] are likely to be the hardest hit by…the economic consequences…in terms of business the main sectors affected will likely be wholesale and retail trade…and even agriculture…[I]t is therefore necessary to stop the vicious cycle of lower demand (caused by a decline in consumption) that contributes to lower supply (and eventually business closers), which in turn leads to job losses and a further drop in consumption) (World Bank, April 2020). The successful cash transfer therefore would be a key activity in mitigating the negative effects of the pandemic and SOE on unemployment”. Finally, the cash transfer also aimed to stimulate the functioning of the informal sector and local markets (Output indicator 2.3.1b). The SOE measures restricted the functionality of markets and accessibility between April and June. The majority of MSMEs reported a loss of income during COVID-19 due to a combination of limited market access, supply chain disruptions and changes in demand. As 95% of households planned to use the cash to purchase food, this should imply a temporary increase in demand to stimulate the functioning of local markets across all municipalities. The Rapid Market Resilience Assessment published in September 2020 by the Ministry of Agriculture and Fisheries (MAF) with support from WFP, Mercy Corps and Oxfam, showed that an average of 70 markets in rural areas in 12 municipalities were functioning, and basic commodities were available (although this indication of a return to normal operations is primarily attributable to lifting of SOE restrictions and the reduction in the perceived threat of COVID-19 in Timor-Leste).
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The risk identified in the ProDoc regarding delays in the implementation of the programme from the Government side did not materialize, in part because of the contribution to the operational costs of the programme through this project, which enabled the Government to accelerate its delivery. The programme also received visible high-level support from the political leaders in the country, which also led to its timely implementation. There were no security issues reported throughout the delivery of the cash-transfer programme. However, the Rede Feto research identified examples of conflicts related to the cash transfer scheme, which might not have been visible at the time of receipt. For example, one LBT community member who was also a vendor stated: “in my family, we faced a difficulty because my brother and his wife argued about who have the right to receive the subsidy. My brother wanted to receive the money, but his wife wanted it. So the two of them argued until they had a physical fight. In the end, the husband went to get the money.” There were indeed significant grievances from citizens regarding the programme. The Government provided payment stations with complaint forms for all citizens to use in order to submit their grievances. However, 37% (525 women) of respondents in the Rede Feto research said they were unaware of the complaints process, reinforcing the importance of greater information on the subsidy tailored to key groups in the population. In total, 15,746 complaints were received during the programme, of which 14,582 (93%) led to the payment of the monetary support in a second stage of payments where 5,224 payments were made to female led households and 9,434 payments were made to male led households between December of 2020 and January of 2021. There was no evidence of community transmission of COVID-19 during the period of payments of the programme, nor in the subsequent months, in the whole country. This suggests that some of the measures taken to control the pandemic (eg. ensuring functioning hand washing facilities at all stations, use of masks and other PPE equipment by staff implementing the programme, and observation of physical distancing protocols) during the implementation of the programme were successful.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The programme’s final report by the Government (forthcoming) and the Rede Feto research findings highlight several important lessons that can inform other programmes of similar nature. These include: • The value of using digital methods such as tablets to gather real-time data from the programme, even in contexts where digital methods have not been widely adopted, and the need to include disaggregation of data by sex, age and disability; • Inclusion of different levels of government (central, municipal, local) and working across sectors in deploying programmes which require a local physical presence, even when some of the entities are not traditionally involved in the deployment of social protection programmes; • The allocation of sufficient time for capacity development of teams that will be deployed to implement emergency programmes. This would mitigate the risk that they will not be able to assimilate and then properly adopt some of the key procedures of the programme (for instance, when it comes to different levels of data reporting). Further programmes should also work with civil society organizations to conduct awareness-raising to eliminate negative social norms about people with disabilities and LGBTI persons, as such negative social norms can unintentionally exclude vulnerable individuals and families. • The need to work with key vulnerable groups (such as isolated populations, single mothers, LGBTI persons or persons with a disability) in the design of responses, noting that many of these groups struggled to have access to the programme due to barriers related to social discrimination (e.g. lack of a clear definition for ‘household’ and subsequent impact on eligibility), lower levels of literacy, mobility and reach of social networks. It is important that future programmes integrate gender analysis, including budget analysis and develop specific strategies (for instance in reviewing definitions, eligibility criteria and SOPs) to guarantee that specific measures are in place to reach those most vulnerable. This should be informed by the persons most marginalized to ensure measures adequately address barriers to access the programme (e.g. inability to be physically at the payment stations, difficulty to prove eligibility, stigma by local authorities, etc). • Attention to operational constraints in the programme design. Issues such as registration of beneficiaries, eligibility criteria and methods of payment should be taken into account from their operational perspective and be considered and analysed before the programme design is finalized. This would mitigate the risk of operational constraints not allowing for an implementation that follows the initial design of the programme, and thus jeopardizing part of if its effectiveness. • The need to prioritize the development of banking systems to guarantee people’s wellbeing, not only from the angle of access to financial services, but also from a public health perspective. In a pandemic context, the lack of a well-developed banking system (be it in the traditional sense or through “new” methods such as mobile banking) that reaches most of the population leads to a significant increase of public health risks, due to an increase of physical contact between people and the large gatherings that they require. • The importance of investing in developing the capacities of women’s organizations and other marginalized groups in designing and rolling out qualitative research to monitor response programmes. This will better equip civil society organizations to partner with government and support the design, implementation and monitoring of more effective and efficient response measures. This was included as part of UN Women’s partnership with the 14 women’s organizations led by Rede Feto, where UN Women provided additional technical assistance to the organizations in each step of the monitoring process (e.g. in development of a methodological guide, workshops and learning sessions with social protection and gender specialists working both remotely and locally to ensure that language and technology are not barriers to the capacity development process.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The development partners, led by the ILO on the UN side, created a working group to provide support to MSSI in several areas during the programme’s implementation. The working group met regularly (usually once a week) virtually to identify areas of synergy and avoid overlapping of supporting efforts to MSSI. The group’s constant communication allowed each development partner to focus on its areas of expertise, making the support given to the Government of Timor-Leste both as efficient and agile as possible. This included joint efforts in several areas, as for instance the development of the programme’s SOPs, which was a document that took in inputs from several different development partners (including ILO, UN Women, UNICEF, WFP, DFAT and the World Bank). Through the partnership, UN Women supported Rede Feto to coordinate with 14 women’s organizations, comprising of 13 Rede Feto Members and the country’s only organization focused on the rights of LGBT persons (Arcoiris). This collaboration facilitated the monitoring of the cash transfer to focus on a wider range of stakeholders and was the first time the organizations conducted qualitative research to monitor a government programme. This was made possible through the COVID-19 Fund and grant of USD 106,780 from UN Women to Rede Feto members to utilize their respective networks and issue areas toward streamlined and evidence-based advocacy for women’s economic empowerment in COVID-19 recovery. The model of a consortium approach to joint monitoring by women’s groups and focus on stakeholders often most marginalized is already being considered by WFP. WFP is reviewing the Rede Feto questionnaires as part of their support to monitor the Government’s food basket/voucher programme. It can also be further adapted to the context of monitoring health-related or broader social protection outreach measures, and promoted as a more sustainable and inclusive approach to monitoring. Through the partnership, Rede Feto has gained space to present its findings and recommendations from the assessment with Government institutions and development partners such as the Ministry of State Administration, Ministry of Coordination of Economic Affairs, Office of the Provedoria for Human Rights and Justice, and development partners, including the UN, Australia and New Zealand. UN Women also facilitated the group to present its approach with the multi-stakeholder Gender and Protection Working Group, which UN Women chairs with UNICEF and brings together over 30 civil society, development partner and Government stakeholders to raise attention to gender and protection issues in COVID-19 response and facilitate coordination among stakeholders for better outcomes in the response. The research has also strengthened the connection between advocacy on COVID-19 and pre-existing gender equality commitments (such as the CEDAW Concluding Observations and the Maubisse Declaration II), which had been monitored by women’s organizations. Learning from the project, to sustain partnership with Rede Feto, UN Women will work to strengthen engagement with community groups and advocacy led by women in informal sectors and women with disabilities that face greater risks of exclusion and violence.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | In addition to the qualitative research undertaken by the 14 women’s organizations coordinated by Rede Feto, UN Women supported a gender-responsive budgeting analysis of the Government’s policy measures taken in response to COVID-19. The analysis highlighted a lack of attention to gender in the response plans and allocation of budgets. For example, there was no allocation for services supporting essential health, justice and social services to survivors of gender-based violence; subsidies of water and electricity exclude households without those basic services, employment benefits (deferral of taxes) benefit formal employees (a majority who are male) and economic support to private sector focused on formally-registered businesses, which are also majority male-owned. There was no sex-disaggregation of estimated beneficiaries and no targeted support for informal workers, many of whom are rural women. The analysis has been incorporated into the Rede Feto Policy Brief and highlights the importance of gender analysis in the design of response measures to ensure more equitable benefits for the population. In addition to the research supported by the UN, The Asia Foundation and Oxfam also supported analysis of the COVID-19 responses, which highlighted overall satisfaction with the Government response, but did not focus on barriers to accessing support.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | A two-month no-cost extension of the joint programme (through to the end of January 2021) was requested and approved, to enable the Rede Feto partnership to capture the full package of the cash transfer scheme (including those whose complaints that were approved) in its monitoring report recommendations. This resulted in the completion of two roundtable discussions on the findings of the research, as well as the development of three videos and the finalization of the Policy Recommendations and Advocacy Brief (to be available in English and Tetum).
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The transfer of funds from the ILO to the Government’s COVID-19 Fund was done through a Grant Agreement. The Government of Timor-Leste is expected to present a report to the ILO with its financial execution in the coming months, as per the Grant Agreement’s conditions. UN Women concluded a Partnership Cooperation Agreement with Rede Feto totaling USD 106,780 which facilitated the research coordinated by Rede Feto involving 14 women’s organizations. The final report on the agreement will be submitted in the coming months, as per the agreement terms. In addition to ILO and UN Women’s support to the Government’s social cash transfer programme, other UN agencies provided support including: transportation/vehicles for cash distribution (WFP, RCO and UNDP); COVID-19 safety measures implemented in distribution sites and printed materials about health and safety distributed to all households receiving payment (UNICEF); delivery of a 15 minute training session on social distancing and COVID-19 safety measures (WHO and UNICEF). From the development partners, as mentioned in previous sections, DFAT and the World Bank provided technical assistance as well as direct support to the programme by the acquisition and provision of several items necessary for the delivery of the programme.
Other

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 2.1 - By 31 December 2020, all the people of Timor-Leste, particularly the most vulnerable including women and children, are relieved of the socio-economic impact of the COVID-19 pandemic
Outcome 1[1] | Yes, social protection measures/system implemented. Number of households that received the CT subsidy: 313,359 (98% coverage rate). Number of eligible households: 318,257. Gender disaggregation breakdown: Male: 250,681 Female: 62,678 Other: 31 Total: 313,391 |  | MSSI, ILO
Outcome Indicator 2.1a Implement nationally appropriate social protection systems and measures for all, including floors and by 2030 achieve substantial coverage of the poor and the vulnerable (SDG Indicator 1.3)
Baseline: Bolsa da Mãe Programme and the Subsidy for the Support of the Elderly and Invalid (SAII)
Planned Target: Cash Transfer Scheme for all low-income families
Output 2.1.1 - By 31 December 2020, social protection mechanisms are strengthened technically and financially, in order to relieve the socio-economic burden of COVID-19, in particular for the most vulnerable, including women- and children-led households
Output Indicator 2.1.1a Number of households receiving cash transfers | A total of 313,359 households received the cash transfer (98 % coverage).
Baseline: No households
Planned Target: All low-income households in Timor-Leste - 318,257
Output Indicator 2.1.1b Develop effective, accountable and transparent institutions at all levels (SDG 16.6) | Inputs on barriers experienced by vulnerable groups and proposed recommendations shared with MSSI as part of monitoring report. Complaints received, gender disaggregation: Male: 9,343 Female: 5,224 Other: 15 Total: 14,582 |  | Government of Timor-Leste, Statistics report from MSSI
Baseline: Existing social security programmes lack financial and human resources, quality assurance, M&E and implementing capacity, resulting in poor service quality, irregular or unreliable benefit delivery, delays and interruptions in service provision and lower levels of protection for the population
Planned Target: Feedback/grievance system established with real-time response, ensuring that the most vulnerable are not overlooked
Outcome Indicator 2.2a Improve the food security status of the most vulnerable households of Timor-Leste (SDG Indicator 2.1.2) | 49 % food secure/mild food insecure; 34.8 % moderate food insecurity 15.6 % severe food insecurity (TLFNS 2020); 27.6 % of households affected by moderate or severe food insecurity (SEIA 2020) |  | Integrated Food Security Phase Classification (IPC) report 2019 provides baseline; Timor-Leste Food and Nutrition Survey (TLFNS) 2020, preliminary findings
Baseline: 36% of population moderate and severe chronic food insecurity (IPC level 3 and 4); 21% moderately food insecure; 15 % severe condition
Planned Target: TBD
Output 2.2.1 - By 31 December 2020, ensure households have access to food and nutrition, in particular the most vulnerable, including women and children.
Output Indicator 2.2.1a- Access to food (economic and/or geographical access to food) | Food markets were functioning again. Access to food markets was mentioned as a priority by 50.7 % of non-vulnerable households and 29.7 % vulnerable (SEIA 2020). Access to foods such as grains, egg, meat and agriculture products improved between May and July, reflected by the reduction in the scarcity of these foods (Market Resilience Survey). |  | SEIA 2020; Market Resilience Study 2020
Baseline: Food Insecurity Experience Scale (FIES 2020) or Socio-Economic Impact Assessment (SEIA 2020) to provide baseline
Planned Target: Yes, there is access and functioning of food markets
Outcome Indicator 2.3a Sustain per capita economic growth in accordance with national circumstances in the least developed countries (SDG Indicator 8.1) | Proxy: 81 % of Small and Medium Sized Enterprises MSMEs loss of earning; 56.6 % of all households survived without revenue vs 18.3 % before COVID-19 (SEIA 2020) |  | SEIA 2020
Baseline: 4.8% annual growth rate of real non-oil GDP (Data Source: IMF Country Report No. 19/124)
Planned Target: 1-5 % per year
Output 2.2.2 - By 31 December 2020, stabilization of aggregate demand will ensure that markets are sustained and has the capacity rebound.
Output Indicator 2.2.1a- Unemployment rate, by gender, age, persons with disabilities and municipality | The percentage of persons in the labour force who were unemployed was found to be 38.2 percent (almost the same for both sexes, 37.6 percent for males and 39 percent for females) which is extremely high. Unemployment among young people below the age of 30 is currently 54.7 percent in the study areas. People living with a disability usually have difficulty finding proper employment in the labour market. Among the working age population (15 to 64-year-olds), 83.0 percent of persons living with a disability are not economically active, compared The percentage of persons in the labour force who were unemployed was found to be 38.2 percent (almost the same for both sexes, 37.6 percent for males and 39 percent for females) which is extremely high. Unemployment among young people below the age of 30 is currently 54.7 percent in the study areas. People living with a disability usually have difficulty finding proper employment in the labour market. Among the working age population (15 to 64-year-olds), 83.0 percent of persons living with a disability are not economically active, compared to 57.8 percent of non-disabled persons. (SEIA 2020) This means that about 22 percent of all persons employed lost their work due to COVID-19. No notable differences were observed between males and females (22 percent and 22.2 percent respectively). |  | SEIA, Ministry of Finance, National Accounts
Baseline: 10.4% (Data Source: Mini LFS 2016)
Planned Target: Between 9.3 and 10.4 %
Output Indicator 2.3.1b Functioning of the informal sector and local markets | Rapid Market Resilience assessment report published with CSO partners (total 178 respondents, in 13 municipalities) Bi-weekly market monitoring reporting and distribution-going Average 70 markets in rural areas in 12 municipalities are functioning and basic commodities are available |  | Market Resilience Report Bi-weekly price monitoring report Full Market Functionality Index
Baseline: The State of Emergency measures restricted the functionality of markets and accessibility between April and June.
Planned Target: Conduct/support Market Resilience Survey (covering traditional markets and loja (kiosks) in 9 to 13 municipalities)

## Communication-Final
1. Impact Stories from the Field
"I will buy food, clothes, and books for children to continue their schooling": Filomena DeJesus, a beneficiary of the UN Timor-Leste supported Cash Transfer Programme June 2020 Filomena DeJesus, 34, mother of two, resident of Suco Dato/Liquica District, is a beneficiary of #TimorLeste COVID19 cash transfer programme. She would buy food, clothes, and books for children to continue their schooling, she exclaimed with joy on receiving USD200 cash subsidy. In second week of its implementation, more than 217,000 households in Timor-Leste have already received a subsidy of USD 43m from the Government under its COVID19 socio-economic response. United Nations #TimorLeste Country Team, through UNWomen, WFP, and ILO, is providing financial and technical support to Ministry of Social Solidarity and Inclusion (MSSI), Ministry of Finance, and related partners to implement the social protection programme that will assist low-income families in Timor-Leste during this difficult period of COVID19 pandemic. “I am delighted to see that a timely, speedy, and coordinated effort by the Government of Timor-Leste, United Nations County Team, and partners has helped reducing the devastating socio-economic impact of COVID19 on the lives of people. The United Nations is pleased to provide financial assistance and technical support extended through the International Labour Organisation (ILO), UN Women, World Food Programme, and other UN agencies to support the Ministry of Social Solidarity and Inclusion (MSSI), Ministry of Finance, and related partners to implement the social protection programme that has assisted more than 217,000 families by distributing USD43million so far in Timor-Leste during this difficult period”, said UN Resident Coordinator Roy Trivedy during his visit to cash distribution centres at Suco Dato and Tibar in District Liquica. He was accompanied by the Government and UN colleagues including Ministry of Finance DG Antonio Freitas, UN Women Head of Office Sunita Caminha, and ILO Protection Adviser Andre Gama.
2. Upload here: Communications and Visibility (OPTIONAL)
Filomena De Jesus, 34, mother of 2
National Council for Food Security, Food Sovereignty and Nutrition (KONSSATIL) Technical Meeting
Government Cash Transfer Agreement Signing Ceremony
“A timely, speedy, and coordinated response will help to reduce the devastating socio-economic impact of COVID-19”
WFP Supported Timor-Leste Government’s Cash Transfer in the Districts.
During October 2020 to January 2021, Rede Feto conducted two TV Talk shows to share research findings and recommendations with the government together with Oxfam Australia that supported research on COVID-19’s impact on women in informal sector. With support from the SG’s Fund, Rede Feto produced three videos on the experiences of marginalized women as part of the monitoring process:
Rede Feto posting on sessions https://twitter.com/Rede_Feto_tl/status/1308583850285477888 https://twitter.com/Rede_Feto_tl/status/1286102145532481536
- LBT persons: https://www.youtube.com/user/bellagalhos
- Women with disabilities: https://www.youtube.com/watch?v=cynZFPLahbU&feature=youtu.be
Domestic workers: https://www.youtube.com/watch?v=tzjHjz8S0L8&feature=youtu.be
Examples from social media (not comprehensive):
Twitter:
· https://twitter.com/SunitaCaminha/status/1349888289466011654
· https://twitter.com/Rede_Feto_tl/status/1349703856263872519
· https://twitter.com/Rede_Feto_tl/status/1341001018654355456
· https://twitter.com/Rede_Feto_tl/status/1339602891464556545
Facebook
· Rede Feto: To develop partners’ capacity in developing their advocacy strategy to take the recommendations forward and integrate in the Rede Feto Platform of Action, a briefing session organized with the Social Protection expert, 7 January 2021: https://free.facebook.com/story.php?story_fbid=3917711178253660&id=100000444484364&_rdc=1&_rdr
· https://free.facebook.com/story.php?story_fbid=3873194376038674&id=100000444484364&_rdc=1&_rdr
· https://free.facebook.com/story.php?story_fbid=3936469419711169&id=100000444484364&_rdc=1&_rdr
Policy Brief Recommendations available online:
· https://fokupers.org/latest-news/2021/1/20/policy-recommendation
· https://fokupers.org/latest-news/2021/1/20/social-protection-and-grb-during-the-covid-19-response
Videos
https://www.youtube.com/channel/UCj3zIyOBLhvrEzOw5B1sjBQ
https://www.youtube.com/user/bellagalhos
https://www.youtube.com/watch?v=tzjHjz8S0L8&feature=youtu.be
A widow and abandoned woman with four kids. An example of a family that does not have access to ficha familia and the Government's socio-economic support.
Photograph by: Helio Dearaujo, UN Women Timor-Leste
Please also see the mid-term report for more photos.