## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Improving the Livelihoods and Protection of Young Women and Men in Kenya | Overall Duration (months) | 12 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy)
Country | Kenya | Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF FAO UNWOMEN | National counterparts (government, private, NGOs & others) and other International Organizations | Advocates for Social Change Kenya (ADSOCK) Kenya Scouts Association (KSA) Kenya Girl Guides Association (KGGA) I Choose Life Ihlasoft
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The COVID-19 MPTF Program in Kenya has galvanized the broad and diverse expertise of UNICEF, FAO, and UNWomen in improving the livelihoods of young men and women in Kenya. At the onset of the program, the technical focal points from each agency met and developed work plans in consultation with young people, and a joint workshop was held in Turkana in July where county government officials, implementing partners, and young people shared the positive impact of the program to date. Planning meetings, mapping exercises, questionnaires, and needs assessments were conducted with youth-serving and disability-friendly organizations for a situational analysis in the target counties. Building on a partnership with FAO Technical Cooperation Project (TCP), 21 youth farmers, 21 county staff, and 2 private sector partners attended a two-week physical training on Farm Business School (FBS) enhancing their capacity in extension support. Site visits were conducted to reinforce classroom learning by making real-world connections as well as gaining practical experience in marketing their farm produce. To create awareness and sensitization of sexual and gender-based violence (SGBV), information, education, and communication (IEC) and behavior change communication (BCC) materials were developed through a consultative process with stakeholders to ensure ownership. 69 young women and men were supported, to prevent and respond to GBV in their communities through the Safe Spaces for Women and Girls Project that provides a formal or informal space where physical and emotional safety is offered. 745 young people have enrolled in the African Youth Marketplace (YOMA). As a result, the young people have created their digital CVs and have access to a suite of personalized courses and training and participated in community activities that include tree planting, cleaning, and painting schools. The youth engagement platform Yunitok has over 3,025 registered users. Polls and information sharing occurs monthly. Through the platform, Yunitokers provided feedback to support the national dialogue leading up to the United Nations Food Systems Summit 2021 (UNFSS) to ensure their thoughts and opinions were included. In addition, data collected from polls on nurturing innovation and entrepreneurship and supporting and protecting children and young people is being used to inform UNICEF and Generation Unlimited country programming. In Nairobi, Kisumu and Turkana, three innovation hubs have been contracted to provide incubation, coaching and mentoring services, financial linkages, and business growth opportunities for scaling offered to youth-led enterprises. In addition, 32 youth-led enterprises and groups with more than 120 young people responded to the expression of interest to be supported under this initiative from Nairobi, Kisumu and Turkana. Two youth-led enterprises have already begun the incubation programme in Nairobi, with the other counties set to begin in August. All activities continue to be implemented under strict adherence to the COVID-19 guidelines and protocols introduced by the government to contain the spread of the virus with agencies developing more synergies and innovative and inclusive solutions for joint implementation.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Kenya’s joint programme on Improving the Livelihoods and Protection of Young Women and Men in Kenya builds on existing youth programmes to connect young men and women to better livelihood opportunities while, increasing youth engagement in awareness raising initiatives to combat Gender Based Violence at the community level. During this reporting period, the programme through the Yunitok platform was able to reach 3,025 young people. Gender: 38% male and 62% women; Age: 23% [0-14]; 15% [15-19]; 35% [20-24];16% [25-30] and African Youth Marketplace (YOMA) 298 registered users.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1: Young women and men including youth with disabilities in rural areas, informal settlements, refugees and host communities are empowered economically.  Youth and disability-friendly sexual and gender-based violence (SGBV), information, education, and communication (IEC) and behavior change communication (BCC) were completed.  Draft Youth in Agribusiness Strategy in Kisumu county has been completed.  298 registered young people have completed self-development, training and skilling opportunities on YOMA and Farmer Business School. Outcome 2: Youth enhanced civic engagement and participation in decision-making and political processes and institutions  3,025 - (38% male and 62% women) youth champions and 75% of polls and information sharing in target communities highlight young peoples challenges on: entrepreneurship, nutrition and situation of children and young people. Outcome 3: Young women and men lead the promotion of favorable social norms, attitudes and behaviors to prevent GBV and COVID-19 at community and individual level.  69 direct beneficiaries engaged in the promotion of positive behavior change and access to credible information with several indirect beneficiaries and 6 behavior change initiatives were led by young men and women (3 in Turkana and 3 in Kisumu), through art, music, training and sensitization through the youth and disability-friendly BCC and IEC materials on GBV and disability inclusion.
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1: National and select county governments have strengthened institutions and policies to support decent employment and entrepreneurship opportunities for young women and men.  One out of six counties have completed the Youth in Agribusiness Strategy more specifically Kisumu. Output 1.2 Young women and men including those living with disabilities in the targeted counties have increased access to self-development opportunities and training in agriculture and agribusiness.  From the planned target of 1,000 a total of 298 young men and women have accessed and received training on YOMA and Farmer Business School. (256 on YOMA and 42 trained in Farmer Business Schools in Kisumu County) Output 1.3 Young women and men including those with disabilities in the targeted counties have improved access to GBV services  The development of youth and disability-friendly BCC and IEC messaging on GBV completed and will provide access to 2,000 young men and women when disseminated. Output 2.1 Youth civic engagement in social and political processes strengthened  A total of 255 from a planned target of 400 young people have been identified as Yunitok champions and lead innovative community initiatives. Output 2.2 Institutional and community awareness and agency around young people's challenges strengthened and improved access to information on comprehensive sexual reproductive health education, child abuse awareness, human rights education and safe spaces through U-Report and other digital platforms.  75% of the Yunitok polls and surveys have highlighted young people's challenges and issues from target communities, with findings used to inform UNICEF Kenya county programming.  317 of the targeted 2,000 young women and men enrolled on Yunitok have access to information on safe spaces, youth-friendly services and youth relevant information. Output 3.1 Young women and men are engaged as positive agents of change on prevention of GBV and COVID-19  69 direct beneficiaries from the targeted 2,000 have engaged in the promotion of positive behavior change and access to information on SGBV.  6 out of the 50 targeted behavior change initiatives (3 in Turkana and 3 in Kisumu) led through art, music, training and sensitization through the developed youth and disability-friendly BCC and IEC materials on GBV and disability inclusion.  2% of the 10% targeted innovations from young people pooled from GenU Youth Challenge, COVID-19 challenge and other youth networks have been supported to enhance youth livelihoods.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Following the government’s directive limiting movement within the western region; including Kisumu, one of the target counties to contain the spread of the COVID-19 virus, implementation of activities slowed down and all physical meetings and workshops put on hold in Kisumu. To ensure minimal delays in implementation, partners have adopted to virtual collaboration and networking through WhatsApp and other online platforms. These platforms are critical in ensuring continued engagement among the various stakeholders even amidst the various restrictions put in place by the government and UN agencies. In instances where physical meetings have been held, program implementation has continued under strict adherence to the safety protocols and guidelines issued by the Ministry of Health. Turkana is the 2nd largest county in Kenya 77,000 square km and its expansiveness has presented some challenges in reaching the remote counties due to the poor road infrastructure, security and harsh climate conditions. By leveraging on existing partnerships with community-based organizations working in remote areas, the program will maximize on the results of the activities implemented thus far to ensure no young person is left behind. The relationship between the host and refugee community in Turkana is fragile given the negative perception that the existing interventions have focused on the refugee population leaving out the host community. Managing this relationship and expectations is critical especially in the prevention and response to SGV to ensure that both host and refugee communities continue to peacefully coexist and can access services and opportunities for young people.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Initial engagements in the two counties revealed more collaboration is required between the UN agencies, civil society organizations (CSOs), development partners and stakeholders involved in youth engagement, livelihoods and SGBV prevention and response work in the communities. The joint workshop in Turkana was the first in-person meeting and provided the opportunity for all partners to meet and develop the rapport required for multi-sectoral collaboration and partnerships in all the programme areas. This will ensure coordinated implementation and minimize duplication of efforts and resources. Gender balance has been included and maintained across all program activities and meetings to guarantee conformity to the set guidelines as reflected in the program documents.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The programme has successfully achieved the results based on the timelines in the programme implementation plan, partnerships and engagement with various partners and government ministries. Some of the key partnerships include the Ministry of ICT, Innovation and Youth Affairs, State Department For Youth Affairs and National Youth Council (NYC): Leading and coordinating crucial youth initiatives supported by UNICEF, including Yunitok, YOMA and youth innovation challenges. This partnership builds on the vision of the Kenya Youth Policy 2019 that seeks to engage young people in identifying their needs and supporting them to amplify their voices to positively change their communities. The State Department is the chair of the Yunitok National Steering Committee in Kenya. Kenya Scouts Association (KSA) and Kenya Girl Guides Association (KGGA): Given their vast network, a comprehensive work plan has been developed with both organizations to mobilize young people for community service and engagement on Yunitok and youth entrepreneurship training as part of the YOMA platform. I Choose Life: a youth-focused organization that seeks to empower youth in Kenya and across Africa has mobilized over 3,000 young men and women in their network to enroll on the YOMA and Yunitok platforms through activation campaigns in target counties and youth networks.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | As part of understanding the programme design a partner mapping exercise was conducted with the information gathered analyzed in the programme counties to ensure that all activities aligned to the programme goals. A capacity gap assessment was also conducted to determine the specific intervention required for young farmers. Similarly, there is an ongoing joint baseline survey that is being conducted, led by the UN Women, FAO and other apex organizations under the MPTF-fund. Various partners identified during the mapping exercise alluded to ongoing studies, results of which will be shared. Based on the outcomes of these studies, and if necessary, adjustments in the programme implementation may be made accordingly while remaining within the confines of the programme mandate.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | No adjustments were done to the programme
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The programme mobilized additional resources through partnership with GIZ in Kisumu County to domesticate the youth in agribusiness strategy from the $20,000 from European Union for information sharing and youth engagement through the Yunitok platform to inform the 7 year EU programme cycle. There are ongoing discussions with World Food Program (WFP) to support domesticating of the Youth in Agribusiness Strategy in Turkana. Procurement of “choma or barbeque grills’’ for value addition of chicken to be distributed to 35 young men and women enabling them to earn an income of USD $ 8 per day from proceeds of the sales

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1: Young women and men including youth with disabilities in rural areas, informal settlements, refugees and host communities are empowered economically. Outcome Indicator 1: Proportion of young women and men engaged in economic empowerment activities
Output 1.1 : National and select county governments have strengthened institutions and policies to support decent employment and entrepreneurship opportunities for young women and men.
Indicator 1.1.1: # of counties supported to develop the youth empowerment policy implementation framework | Draft Youth in Agribusiness Strategy in Kisumu completed
Baseline: 0
Planned Target: 6
Output 1.2 Young women and men including those living with disabilities in the targeted counties have increased access to self-development opportunities and trainings in agriculture and agribusiness
Indicator 1.2.1: # of young people completing self development, training and skilling opportunities | 567 total (525 on YOMA and 42 trained in Farmer Business Schools in Kisumu County) | Capacity gap assessment in Turkana to identify the training needs and data analysis still ongoing | Registered users on YOMA (https://yoma.africa/) and Google analytics
Baseline: 0
Planned Target: 1,000
Indicator 1.2.2: # of young people demonstrating improved employment outcomes (e.g. placement in jobs, duration of unemployment, wages, retention, labor productivity)
Baseline: 0
Planned Target: 1,000
Output 1.3 Young women and men including those with disabilities in the targeted counties have improved access to GBV services
Indicator 1.3.1 # of young people accessing GBV information | Development of youth and disability friendly BCC and IEC messaging on GBV done.
Baseline: 0
Planned Target: 2,000
Indicator 1.3.2 # of young people accessing GBV services
Baseline: 0
Planned Target: 2,000
Output 1.4 Increased access to finance, ICT capacities related to business development and integration into markets for existing and emerging agribusinesses and SMEs of vulnerable young women and men.
Indicator 1.4.1. # of youth led agribusinesses and SMEs reporting increase in markets, sales, business linkages, expanded finance options | This is being collected
Baseline: 0
Planned Target: 50
Indicator 1.4.2 # of agribusinesses and SMEs established by young women and men | This is being collected
Baseline: 0
Planned Target: 50
Outcome 2: Youth enhanced civic engagement and participation in decision-making and political processes and institutions Outcome Indicator 2: # of policies and decision-making processes that young men and women influence
Output 2.1 Youth civic engagement in social and political processes strengthened
Indicator 2.1.1 # of young women and men U-Reporters from target communities who identify as champions and lead innovative community initiatives | 7,563 - (38% male and 62% women) (as at July 30, 2021) |  | https://www.yunitok.in/engagement/
Baseline: 0
Planned Target: 400
Output 2.2 Institutional and community awareness and agency around young people's challenges strengthened and improved access to information on comprehensive sexual reproductive health education, child abuse awareness, human rights education and safe spaces through U-Report and other digital platforms.
Indicator 2.2.1 Proportion of polls and surveys that highlight young people's challenges and issues from target communities | 30% |  | https://www.yunitok.in/opinion/2410/
Baseline: 0
Planned Target: 30 %
Indicator 2.2.2 # of young women and men connected to safe spaces, youth friendly services and youth relevant information through U-Report and other digital platforms | 7,563 - (38% male and 62% women) (as at July 30, 2021) |  | https://www.yunitok.in/engagement/
Baseline: 0
Planned Target: 2,000
Outcome 3: Young women and men lead the promotion of favorable social norms, attitudes and behaviors to prevent GBV and COVID-19 at community and individual level. Outcome indicator 3: # of women and men reached with advocacy messages on GBV and COVID-19 prevention
Output 3.1 Young women and men are engaged as positive agents of change on prevention of GBV and COVID-19
Indicator 3.1.1 # of young people engaged in promotion of positive behavior change and access to credible information | 69 direct beneficiaries and several indirect beneficiaries | Limited numbers of participants due to COIVD-19 guidelines reducing number of direct beneficiaries reached | Partner and youth group activity reports
Baseline: 0
Planned Target: 2,000
Indicator 3.1.2 # of behavior change initiatives led by young women and men | 6 initiatives (3 in Turkana and 3 in Kisumu), through art, music, training and sensitization through the developed youth and disability friendly BCC and IEC materials on GBV and disability inclusion | On course | Partner and youth group activity reports
Baseline: 0
Planned Target: 50
Output 3.2 Young women and men's social & economic innovations integrated in national and county COVID-19 and GBV responses through YOMA platform
Indicator 3.2.1 Proportion of innovations from young people pooled from GenU Youth Challenge, COVID-19 challenge and other youth networks supported to enhance COVID-19 and GBV response in target communities | 2% | Identification of other youth innovations ongoing
Baseline: 0
Planned Target: 10%
Output 3.3 Comprehensive Sexual Reproductive Health Education, child abuse awareness and Human Rights education promoted on UReport and YOMA Platform responding to adolescent mothers
Indicator
Baseline: 0
Planned Target: 2,000
Please include all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board