## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Reimagining Education for Marginalized Girls and Boys during and post COVID-19 in Bosnia and Herzegovina | Overall Duration (months) | 18 months
Programme Number (if applicable) | N/A | Start Date (dd.mm.yyyy) | 2020-10-13
MPTF Office Project Reference Number: | 00124305 | Original End Date (dd.mm.yyyy) | 2022-03-15
Country | Bosnia and Herzegovina | Current End date(dd.mm.yyyy) | N/A
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF, UNESCO, ILO | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Civil Affairs in Bosnia and Herzegovina, Ministry of Education and Science in Republika Srpska, Ministry of Scientific and Technological Development, Higher Education and Information Society in Republika Srpska, Ministry of Education, Culture, Science and Sports in West Herzegovina Canton, Ministry of Education, Culture, Science and Sports in Una Sana Canton
Report Cleared By
o Name: | Dr. Rownak Khan
o Title: | Representative, UNICEF
o Email address: | rkhan@unicef.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Upon preparing and sharing the Joint UN Programme overview for partners, the UN obtained the formal endorsements of the intervention of the state-level as well as the selected entity/cantonal education authorities. The designated UN agencies developed the joint work plan and hired the Joint UN Programme coordinator. Recruitment of United Nations Volunteers (UNVs) as local coordinators has been completed. Hence, the Joint UN Programme coordination structure is established and the induction phase is in the process of finalisation.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved | Educational Authorities are fully on board to prepare Guidelines on Standards for e-learning delivery in elementary, secondary (including TVET) and tertiary education.
3.2 | Results: Output Level | Please include output level results achieved | 1. Hygiene materials delivered to schools in three administrative units.2. Working group on ICT standards established and methodology in preparation phase. 3. Assessment of quality delivery of e-learning and blended learning for higher education completed.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | N/A for the reporting period
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Quality assessment of delivery of e-learning and blended learning was enlarged to cover the whole territory of Bosnia and Herzegovina, not just the three administrative units where projects is implementing activities as per the Project Document. This is due to recognition that this type of assessment should benefit all educational authorities in the country, regardless of lack of funding for follow up activities, i.e. trainings for teachers and procurement of ICT and assistive technologies. Rationalle for that decision was discussed and agreed upon by the Project's Steering Committee consisting of government partners in the selected administrative units.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | This Joint UN Programme established partnership mechanisms with the selected education authorities in Bosnia and Herzegovina. The kick-off meeting with Ministers of Education enabled further actions in establishing the Steering Committee with Assistant Minister level of representatives of all administrative units, and their active engagement in approving strategies and approaches in implementing the project. Regular communication and meetings were held to maximise national ownership of the project. The UN has obtained the formal endorsements of the intervention by five education authorities (Ministry of Civil Affairs in BiH, Ministry of Education and Science in Republika Srpska, Ministry of Scientific and Technological Development, Higher Education and Information Society in Republika Srpska, Ministry of Education, Culture, Science and Sports in West Herzegovina Canton, Ministry of Education, Culture, Science and Sports in Una Sana Canton) and has further identified the government institutions to be included in the specific areas of intervention (such as pedagogical institutes and universities). In addition, during the reporting period, UNESCO has initiated cooperation with other implementing partners, namely Microsoft within UNESCO Global Education Coalition and local training providers with the aim of catalysing additional support, as well as cooperating in the implementation of specific programme activities.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Assessment on the quality of higher education e-learning in Bosnia and Herzegovina and Assessment on the needs of teachers/trainers in e-learning delivery at higher education institutions in Bosnia and Herzegovina are completed. Assessment on the quality of e-learning at primary and secondary education level (including TVET) in Bosnia and Herzegovina and Assessment on the needs of teachers/trainers in e-learning delivery at primary and sedondary education level in Bosnia and Herzegovina are underway.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The no-cost extension of three months is envisaged to be communicated to the MPTF, due to delays at the beginning of the project, this will be treated separately via direct communication with relevant authorities. Outputs for the time being are kept as is, with previously described expansion on the work of the quality assessments to cover the territory of the whole country.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The UN Project Coordinator, 3 UNVs - Project Associates in three administrative units and 1 UNV - Project Officer were recruited in the reporting period. Potential donors are being discussed to advance the current project and expand on other administrative units. TO that end, RCO and RC took the coordinating role, and further resource mobilization is planned for the third quarter of the year.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]: Capabilities of education systems enhanced to manage continuity of learning during the COVID-19 pandemic
Indicator:
Baseline: N/A
Planned Target: N/A
Output 1.1: Gender-responsive crisis management, including legal frameworks, established to enable implementation of safe school operations and risk communication
Indicator 1.1.1: Percentage of education authorities equipped to ensure continuity of learning for all girls and boys during the COVID-19 pandemic and other disruptions | Currently all Education Authorities are on board and in process of implementing continuity of learning preparations for the new school year. | No variance | Project reports; Techincal Project Board Minutes
Baseline: 0%
Planned Target: 100%
Indicator 1.1.2: Percentage of education authorities prepared to endure possible new disruptions in learning | Currently all Education Authorities are on board and in process of implementing ativities that will ensure better preparedness of teachers and better equipped schools in case of new disruptions in learning. | No variance | TORs
Baseline: 0%
Planned Target: 100%
Indicator 1.1.3: Number of people equipped to follow epidemiological guidelines on COVID-19 prevention in schools/preschools, thus being able to participate in education process, disaggregated by sex, age group and at-risk population
Baseline: 0 | N/A | N/A
Planned Target: 6000
Output 1.2: Continuity of learning in BiH is supported for all vulnerable children and youth, girls and boys equally
Indicator 1.2.1: Percentage of education authorities capacitated for quality real time monitoring of school closure impact on children’s learning and well-being
Baseline: 0% | N/A | N/A
Planned Target: 100%
Indicator 1.2.2: Number of children able to continue schooling in case of school closure, disaggregated by sex and age
Baseline:105000 | N/A | N/A
Planned Target: 122000
Outcome 2: Resources and capacities of education systems strengthened to provide e-learning and blended learning for all | In progress
Indicator:
Baseline:N/A
Planned Target:N/A
Output 2.1: Education authorities are supported to implement quality inclusive e-learning and blended learning approaches
Indicator 2.1.1: Percentage of education authorities with new knowledge on advantages and shortfalls in providing quality e-learning and blended learning delivery
Baseline: 0% | N/A | N/A
Planned Target: 100%
Indicator 2.1.2: Standards/guidelines for quality inclusive blended learning developed (Y-N)
Baseline: Not available | In progress | N/A | Working group minutes, TORs, Project monthly reports
Planned Target: Standards/guidelines for quality inclusive blended learning developed
Indicator 2.1.3: Number of education government officials trained for effective and efficient information management system running, disaggregated by sex
Baseline: 0 | In progress | N/A | Working group minutes, TORs, Project monthly reports
Planned Target: 20
Indicator 2.1.4: Number of community volunteering activities which contribute to improving e-learning and blended learning
Baseline: 0 | N/A | N/A
Planned Target: 6
Indicator 2.1.5: Percentage of education authorities capacitated with resources to prevent online gender-based violence
Baseline: 0% | In progress | N/A | Implementing parter reports
Planned Target: 100%
Output 2.2: Teachers (women 68%) are empowered and have enhanced capacities for delivering quality e-learning and blended learning
Indicator 2.2.1: Analysis on professional development needs of teachers for quality e-learning and blended learning conducted (Y-N)
Baseline: N/A | In progress | N/A | TOR, Methodology
Planned Target: Analysis conducted
Indicator 2.2.2: Number of teachers with increased capabilities to teach online, disaggregated by sex and type of training
Baseline:0 |  | N/A | Lists of participants in trainings
Planned Target:4,250 (at least 2,890 women) | 321 (250 women)
Indicator 2.2.3: Analysis of the impact of school closure on female teachers' health and wellbeing completed (Y-N)
Baseline:N/A | In progress | N/A | TOR
Planned Target: Analysis on the impact of school closure on female teachers' wellbeing completed
Outcome 3: Management systems of TVET authorities and TVET teachers’ skills improved for knowledge transfer
Indicator:
Baseline:N/A
Planned Target:N/A
Output 3.1: Technical and Vocational Education and Training (TVET) authorities have enhanced capacities for delivering quality TVET e-learning and blended learning, including enhanced capacities for TVET teachers and instructors
Indicator 3.1.1: Standards/guidelines for TVET quality inclusive blended learning developed (Y-N)
Baseline:Not available | In progress | N/A | TORs, Final report
Planned Target: Standards/guidelines for TVET quality inclusive blended learning developed
Indicator 3.1.2: Number of key TVET occupations with blended and e-learning training plans and multi-media e-learning materials
Baseline:0 | In progress | N/A | TORs, E-Learning materials produced; E-learning plans available
Planned Target: 2
Indicator 3.1.3: Number of TVET providers, teachers and instructors who improved their e-teaching practices, disaggregated by sex | In progress |  | Outline of training course; completion rates of training course
Baseline:0 |  | N/A
Planned Target: 30
Indicator 3.1.4: Percentage of girls reached with career guidance on STEM skills as part of career guidance activities |  |  | Career Guidance materials on STEM skills
Baseline:0% | N/A | N/A
Planned Target: 80%
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Communication activities are being planned, pending finalisation of activities and pending interviews with final beneficiaries.
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board