## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Socio-Economic Empowerment of Vulnerable Women in Ghor Al Safi through Improving Access to Safe and Green Public Spaces | Overall Duration (months) | 12
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2021-01-28
MPTF Office Project Reference Number: | 22829-001 | Original End Date (dd.mm.yyyy) | 2022-01-14
Country | Jordan | Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN-Habitat, UNOPS, and ILO | National counterparts (government, private, NGOs & others) and other International Organizations | Zaha Cultural Centre, the Municipality of the Southern Valley, and Jordan River Foundation (implementing partner with ILO)
Report Cleared By
o Name: | Husam AlKayyali
o Title: | Partnerships & Development Finance Officer
o Email address: | husam.alkayyali@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | In response to the COVID-19 pandemic and the growing vulnerabilities among marginalized women in the Southern Jordan Valley, this programme (Socio-Economic Empowerment of Vulnerable Women in Ghor Al Safi through Improving Access to Safe and Green Public Spaces) aims to enhance the socio-economic conditions of vulnerable women living in Ghor Al Safi through the provision of a safe and green public space and the creation of livelihood opportunities. This will be achieved through the development of an enabling environment and tools which will assist women in developing and promoting their small businesses and achieve economic sustainability in a safe and inclusive environment. UN-Habitat, UNOPS, and ILO are responsible for delivering the outputs of the programme. After the implementation, Zaha Cultural Centre and the Municipality of the Southern Jordan Valley will manage the public space and community centre. The programme approach has followed the integrated method to public space developed by UN-Habitat to strengthen the participatory process in the design, implementation, and maintenance of the space. Through conducting a Site-Specific Assessment, the communities’ perceptions of the safety, accessibility, and inclusivity of the public space has been assessed. The Assessment activities included topographic surveying, exploratory walks of the site with the local community and stakeholders, site mapping, interviews with public space users and those residing within the walkable radius of the site, as well as meetings with local authorities and stakeholders. As part of this Assessment and to develop a gender-responsive and inclusive design, two community consultation sessions were held in Ghor Al Safi with the local community and organizations. The first consultation session was to validate the findings of the Site-Specific Assessment and listen to the community needs and aspiration from the project, whereas the second consultation session included a presentation of the conceptual design to receive community feedback, whereby all the participants expressed an overall positive response to the designs presented to them, with one calling the project, “every child’s dream.” Moreover, the package of services to be offered by the community centre is being developed, whereby a core component of these services will be related to livelihoods and business development. A community needs assessment was conducted through a digital survey conducted by Zaha Cultural Centre to develop the operational plan for the community centre, which included identification of the most desired training programs for women and children post-implementation. The Training of Trainers (ToT) has begun for selected staff and community members and the selection criteria for the “Women Do Business” (WDB) has been developed and participants were selected according to the developed criteria. Through this fund, this programme was able to follow a participatory approach that enabled the establishment of a communication platform between the participating UN agencies, the local community, the Southern Aghwar Municipality, Zaha Cultural Centre and the local CBOs in the area through the different activities and the fostering of partnerships to ensure that the outcomes and outputs of the programme are delivered.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | This programme will strive to reach out to the whole Ghor Al Safi population and the underserved neighbouring communities. The public space and community centre will directly benefit the 37,040 Ghor Al Safi inhabitants, of which 46% of the population are women. Post-implementation, the project will indirectly benefit at least 26,868 more people from the underserved communities of Al-Mazraa, Al-Maamoora, and Ghor Fifa. These communities are classified as poverty pockets and, like Ghor Al Safi, do not have adequate and safe public spaces. The direct and indirect beneficiaries of this project will be different groups of vulnerable women, Syrian refugees, vulnerable youth, people with disabilities, and women-headed microenterprises. The project will work closely with a local NGO to ensure a strong gender perspective of the deliverables and use their networks to reach the most vulnerable groups of society. The project will also directly work with the Municipality and local NGOs to provide them with the required capacity to target vulnerable and marginalized populations more effectively with their COVID-19 responses. It is expected, in the long term and post-implementation, that the whole of the Ghor Al Safi population and their underserved neighbouring communities will enjoy the improved access to safe, inclusive, and green public space and community center. It is expected that the public space itself will have at least 10,000 visitors per year. This will be ensured through the multiple events such as a minimum of 15 market fairs annually and 3 annual festivals. Additionally, Wadi Hasa, located on the outskirts of Ghor Al Safi, is a significant tourist attraction across Jordan, especially for those living in the nearby Amman. It could thus draw in more visitors to the nearby public space and the various events that will be held, which will create an opportunity for women in Ghor El Safi to promote and sell their products. During the reporting period, the programme has conducted a Site-Specific Assessment, which has directly engaged regular park users as well as those living within the walkable radius and held two community consultation session in Ghor Al Safi to develop the design and operational plan. Due to the high number of COVID-19 cases and gathering restrictions during Ramadan, the first community consultation session was attended by 8 participants from the Ghor Al Safi community, 4 women and 4 men. After Ramadan, the second community consultation session was attended by 66 participants from the Ghor Al Safi community, 49 women and 17 men, with approximately 34% were between the ages of 17-25 years old (Youth). Additionally, a community needs assessment conducted by Zaha Cultural Center engaged 55 community members, 31 females and 14 males, whereby 19 members were between the ages of 17-25, 12 between the ages 26-35, 13 between the ages of 36-45, 6 between the ages 46-55, and 2 between the ages 56-65. The recruited architectural firm has developed the detailed architectural design for the community center and the public space and currently working on the technical drawings and bidding documents. As part of outreaching for potential beneficiaries for WDB training. 132 Women from Ghor Al-Safi applied for Women Do Business training, whereby 125 to be selected from the applicants following the developed ILO criteria. Additionally, 28 trainers have been identified from Zaha Cultural Center and other NGOs in Ghor Al-Safi for the ToT training, of which 9 trainers, 5 females and 4 males, have completed the training. The Women Do Business training has been applied to by 132 Women from Ghor Al-Safi, whereby 125 to be selected from the applicants following the ILO selection criteria. Additionally, 25 trainers have been identified from Zaha Cultural Center and other NGOs in Ghor Al-Safi for the ToT training and 9 trainers, 5 females and 4 males, have completed the training.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The results of both outcomes will be achieved clearly in a later stage of the implementation and post-implementation since they are more focused on long term impact and results, which can’t be measured at the current stage of the project implementation.
3.2 | Results: Output Level | Please include output level results achieved | Results/deliverables under Output 1.1: Gender-inclusive, safe and accessible public space established in Ghor Al Safi: • Site-Specific Assessment was conducted to the project site and the report that includes the findings and recommendations under the five dimensions of Use and User, Accessibility, Amenities and Furniture, Comfort and Safety, and Green Environment based on community perceptions was produced (please find attached). The topographic survey for the site was conducted to document the exact levels in the site, and a Topographic Survey report was produced (attached). • A Community consultation session was held with the local community in Ghor El Safi on April 19th to listen to the community needs and aspiration from the project and also to validate the findings of the Site-Specific Assessment. Due to the high number of COVID-19 cases and gathering restrictions during Ramadan, 8 participants attended the session, 4 women and 4 men. • The Conceptual design of the public space and the community Centre was developed by the recruited architectural firm and presented to the Ghor Al Safi community. The received feedback from the local community was incorporated in the revised version of the design. • A second community consultation session was held with the local community on May 19th where the lead architect Dr. Rami Daher presented the design ideas and listened to the community’s feedback. The consultation session was attended by 66 participants from the Ghor Al Safi community, 49 women and 17 men, with approximately 34% were between the ages of 17-25 years old (Youth). Additionally, a community needs assessment conducted by Zaha Cultural Centre engaged 55 community members, 31 females and 14 males, whereby 19 members were between the ages of 17-25, 12 between the ages 26-35, 13 between the ages of 36-45, 6 between the ages 46-55, and 2 between the ages 56-65. • The Detailed design was developed and presented to implementing partners including the Southern Aghwar municipality and Zaha Cultural Centre, where their feedback is currently being incorporated in the revised version. The finalized version of the design will be reviewed by IPMG at UNOPS HQ Results/deliverables under Output 1.2: Market spaces and kiosks are developed and made available for women and people with disability to sell and promote their products: • Multi-use space was proposed in the developed detailed architectural design that can be dedicated to the market space and kiosk space. • Community needs assessment identified that a large portion of community want an E-Marketing training program as one of the micro project entrepreneurship trainings that should be provided. Results/deliverables under Output 2.1: Multi-service community centre is enhanced to train women and build capacities: • A community needs assessment was conducted by Zaha Cultural Centre to have a better understanding of the community needs and priorities in terms of the most desired programmes and trainings to be offered to women and children post implementation. A community needs assessment report that summarizes the identified needs and priorities of the different segments of the community including women, youth and children was produced (attached), and based on the findings of the assessment, an operational plan for the community centre will be developed. • ToT was conducted in Amman for 9 participants, in addition, 19 trainers from Ghor Al-Safi were identified to take part in the second ToT that is planned in July). • As part of outreaching for potential beneficiaries for WDB training. 132 Women from Ghor Al-Safi applied for Women Do Business training, whereby 125 to be selected from the applicants following the developed ILO criteria.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The main challenge encountered during the reporting period was the COVID-19 pandemic and the resulting safety concerns and Governmental mitigation measures. This was one of the risks identified in the Risk Management Matrix, whereby the extended COVID-19 measures and their socioeconomic impact may hinder project delivery and exacerbate social tensions, including the additional risk of contributing to the spread of COVID-19 during the planned activities. Due to Government restrictions, the team while conducting the site-specific assessment could not observe the project site in the evening or at night. Therefore, the assessment relied on interviews and focus groups to understand the average number of park users, the quality of artificial lighting, and daily activities prior to the pandemic. Moreover, the architectural team have contracted COVID-19 which impacted the planned activities and findings were delayed until the team recovered, to mitigate the risk of spreading the virus. Additionally, due to social distancing rules, safety concerns, and the Month of Ramadan, the first community consultation workshop had a limited number of community members but the second consultation workshop which was held shortly after the Month of Ramadan was well attended by the local community especially women from Ghor El Safi. During the different project activities, such as workshops, focus groups and interviews, and continuing throughout the remainder of the programme, safety measures including social distancing, provision of hygiene and sanitizers, and provision of masks was, and will be, ensured during any planned activity. Additionally, the ToT dates were shifted because of the time required for ILO to sign the implementation agreement with the ILO implementing partner (Jordan River Foundation), mainly due to the delay in receiving the approvals from JORISS. Moreover, ILO faced some difficulties reaching out and identifying trainers from Ghor Al-Safi who fit the selection criteria. Moreover, to mitigate the second perceived risk of deeply rooted social norms hindering the implementation of the intervention and leading to male community members not allowing women to start businesses or attend related trainings community workshop, the implementing partners ensured that both men and women from the community were involved in the community consultation workshops together to raise awareness amongst the community that can influence social change at the local level. Furthermore, at the current stage of the programme, the third identified risk, regarding the weak institutional capacity and limited local authorities’ capacity to support the implementation of the program, has been mitigated through the engagement of local authorities from the early stages of the programme and through the partnership and engagement of Zaha Cultural Centre as the operational organization from the start of the programme. At the end to ensure that the partners follow the “Do no Harm” approach and avoid exacerbating inequalities and vulnerabilities, the programme began with the Assessment to analyse the context, identify the stakeholders and their interactions with one another, and, accordingly, ascertain the suitable activities that will have the positive impact while increasing the participation and engagement of the local community (especially women and people with disabilities).
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The Site-Specific Assessment conducted generated findings on the five dimensions: use and user, accessibility, amenities and furniture, comfort and safety, and green environment that were analysed to develop a gender-sensitive, inclusive, and accessible public space. The findings from the Assessment has informed the design and ensured that the right solutions are in place for more inclusive, accessible, and safe public spaces. The Assessment offered a platform for dialogue between the community, professionals, and the local authority, leading to changing mindsets and attitudes towards a “collective responsibility” to public spaces. The developed Public Space Site-Specific Assessment Report will be disseminated in English and Arabic to programme stakeholders and planning entities in Jordan as the findings can provide a foundation whereby urban design becomes a solution to meet the community’s needs rather than simply beautification. Additionally, UN-Habitat, UNOPS, and ILO will continue to disseminate and share the results with governmental and non-governmental partners through follow-up meetings, workshops, and social media. The participatory approach of the project will be replicable throughout the different municipalities, with slight adaptations dependent on the needs of the communities and other stakeholders to achieve the short and long-term impacts successfully. Furthermore, the Site-Specific Assessment generates knowledge on the implementation of green architecture and permaculture assisting in harsh climates based on expert findings and community experience. This will be used to build the capacities of stakeholders, including representatives from the local community, on the techniques and methods of green infrastructure and permaculture design principles, which they can implement and replicate in other projects. Moreover, the community needs assessment conducted, generated knowledge on the training programs and opportunities desired by the community. Additionally, based on skills needs, local economic opportunities, market analysis skills development, and entrepreneurship training will be offered to women using ILO tools and methods such as ‘Women do Business’ (WDB) and ‘Start and Improve Your Business (SIYB). ILO entrepreneurship development programmes rely on a training of trainers' methodology whereby a network of capable and qualified BDS trainers is formed and trained by ILO certified Master Trainers. This ensures the scalability and sustainability of the intervention and allows institutionalisation of training programmes in existing BDS structures and monitoring of beneficiaries. The operational lessons and training programmes can inform and be adopted in future interventions across Jordan to equip young women and men with the necessary technical and entrepreneurial skills to enhance their socioeconomic conditions. The principal purpose of this programme is to advance gender equality through the establishment of a gender-inclusive and accessible public space in Ghor Al Safi, the development of market spaces and kiosks for women and people with disability to sell and promote their products, as well as the enhancement of a multi-service community centre to train women and build capacities. The expected outcomes of this programme are: firstly, the socioeconomic conditions and wellbeing of vulnerable women will be enhanced through the provision of green spaces and livelihood opportunities, and secondly, the transferable livelihood skills and economic opportunities for women in rural areas will be increased.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The UN-Habitat, ILO, and UNOPS have developed implementing and consultative partnerships with Zaha Cultural Centre, the Municipality of Southern Jordan Valley, Jordan River Foundation, Turath Architecture and Urban Design Consultants, and several local organizations in Ghor Al Safi. These partnerships have been developed to ensure that the programme outcomes are met, the sustainability of the programme post-implementation, and the catalytic impact of the programme, whereby the intervention can be replicated and expanded across Jordan post-implementation. Through this fund and its financial support, this programme was able to bridge the communication gap between local communities, governmental bodies, and private companies through the activities and the fostering of these partnerships. The participatory activities conducted between the different partners, consultants, and stakeholders allowed for a platform of exchange between the stakeholders to ensure that the outcomes and outputs of the programme are delivered. This programme is aligned with the response and priorities at the national level, including the “JNUP diagnosis report”, ‘Jordan 2025”, and the “UN Socio-Economic Framework for COVID-19 Response”. Additionally, this intervention, its participatory process, and its outcomes are aligned with the WHO COVID-19 Strategic Preparedness And Response Plan, which highlights the erosion of social cohesion, limited access to education, and reduced income and security communities have experienced as one of the key lessons for 2021. It additionally highlighted the disproportionate socioeconomic effect this pandemic has had on women. Furthermore, it is also aligned with the Global Humanitarian Response Plan, which takes into consideration the socioeconomic impact of COVID-19 on already-vulnerable population. This programme considers the short and long-term effects of this socioeconomic impact, how it can be mitigated for the vulnerable communities in Ghor Al Safi and, through replication, across Jordan, as well as recognizes, as the GHRP does, the effect this on achieving the Sustainable Development Goals. This programme model could be used for similar responses at country or global levels, especially for gender-responsive interventions that aim to enhance the skills and employability for vulnerable women.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | This programme has conducted a Public Space Site-Specific Assessment for Ghor Al Safi Park (the site) and the surrounding area. The programme has additionally conducted a topographic survey of the site to understand the levels and determine the location and elevations of selected ground points in order to plot the features (buildings, manhole, fence-lines, etc.) as well as show the differences in elevations from the ground surface. Furthermore, to develop the operational plan for the community centre and identify the training programs the community will most benefit from post-implementation, the programme has conducted a community needs assessment through a digital survey and produced a community needs assessment report. All he produced assessments and reports were translated into Arabic and English to disseminate and reach out to the wider audience of the project’s stakeholders. Currently, a soil test of the site is being conducted.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | This programme has had to revise the proposed timeline due to delays caused by the increasing cases of COVID-19 and the resulting governmental mitigation measures/restrictions as well as delays in signing implementation agreements. This revision affected the initial Site-Specific Assessment timeline, mainly due to the fact that the architectural team members conducting the Assessment contracting the virus during this time period, which delayed the activities. This additionally included limiting the number of participants in the first community consultation session held in Ghor Al Safi to ensure the safety of all attendees and the compliance with government restrictions. However, the participating agencies are working on mitigating this delay by revising the workplan and shifting some of the planned activities. There have not been any major adjustments to the planned strategies or outcomes and outputs of the programme.
5 | Resources (Optional) |  | Due to the limited fund, ILO has mobilized additional resources, noting that the total amount that can be proofed through supporting documents is 70,000 USD provided by RBTC ILO. In addition, ILO is supporting the implementation of this project through its existing staff recruited by other projects.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]: The socioeconomic conditions and wellbeing of vulnerable women are enhanced through the provision of a safe, gender-inclusive and green public spaces and livelihood opportunities. | This will be measured after the implementation of the project. |  | Will be verified through survey.
Indicator: Number of local community members demonstrating enhanced socio-economic conditions and social cohesion (disaggregated by gender, age, and nationality).
Baseline: 0
Planned Target: Direct beneficiaries: 37,040 inhabitants (where women represent 46% of the population) Indirect beneficiaries: > 26,868
Intermediate Outcomes: (I) Increased access to a safe, gender-inclusive, and green public space, community centre, and markets (II) Improved capacity of the target municipality and NGOs on the design of safe, gender-inclusive and green public spaces for women and people with disabilities | This will be measured after the implementation of the project. |  | Will be verified through post-implementation evaluation reports (by Zaha Cultural Centre), attendance sheets, and annual reports.
Indicators: (1) Number of Ghor Al-Safi population including persons with disabilities benefitting from the public space, community center and the local markets (disaggregated by gender and age). (2) Number of public spaces and community centers developed that enhance safety for women and persons with disabilities. (3) Number of Municipal staff and NGOs capacitated on the design of safe, gender-inclusive and green public spaces for women and people with disabilities
Baseline: 0
Planned Target: (1) 37, 040 (where women represent 46% of the population) (2) 1 pubic space and 1 community center designed and developed (3)10 participants
Output 1.1: Gender-inclusive, safe and accessible public space established in Ghor Al Safi | The first community consultation session/ workshop was attended by 16 participants, 8 women and 8 men, whereas the second community consultation session/workshop was attended by 66 participants from the Ghor Al Safi community, 49 women and 17 men. | Due to the Holy Month of Ramadan and the rising COVID-19 cases, the number of attendees from the local community attending the first session was low, but in the second consultation session the number of participants exceeded the planned target especially with the number of women participating in the session | Verified through attendance sheets, photos documenting the events, recorded contributions from participants
Indicator 1.1.1: Number of participants from the local community participated in sessions to design the public space (disaggregated by gender)
Baseline: 0
Planned Target: 65 participants (of which 50% women, 50% men, 25% youth, 10% refugees, 5% people with disabilities, and representatives from Ghor Al Safi Women’s Association for Social Development)
Indicator 1.1.2: Number of gender-responsive design alternatives for safe, inclusive and green public space developed through community engagement and participatory methodologies involving different stakeholders, including women’s groups. | Conceptual design alternatives have been developed and presented to the community for their feedback in the second community consultation session and, accoridngly, a detailed design has been developed and is currently being finalized amongst partners. |  | Verified through conceptual design report and detailed design report, will be further verified through design review report (UNOPs), and BoQ document upon approval.
Baseline: 0
Planned Target: 3 design alternatives and 1 detailed final design
Indicator 1.1.3: Number of gender-responsive, safe, inclusive and green public spaces and community centres rehabilitated/ made accessible for local communities | The public space and community centre design is being finalized and the construction will start in the next phase |  | Will be verified through building contracts, implementation progress reports and photos.
Baseline: 0
Planned Target: 1 public space and 1 community centre
Indicator 1.1.4: Number of green public spaces and community centres equipped with hygiene and sanitization items (COVID-19 response) | The public space and community centre design includes toilet/WASH facilities. Which will be provided once the public space and community center is constructed in the next phase |  | Will be verifiedthrough implementation progress reports and photos.
Baseline: 0
Planned Target: 1 public space and 1 community centre
Indicator 1.1.5: Number of users visiting the public space and community center (disaggregated by age and gender). | This will be measured after the implementation of the project. |  | Will be verified through the site-specific assessment questionnaires and post-implementation evaluation report
Baseline: 0
Planned Target: > 10,000 a year, of which 50% women, 20% men, 50% youth, 10% refugees, and 5% people with disabilities
Output 1.2: Market spaces and kiosks are developed and made available for women and people with disability to sell and promote their products | The design that is being finalized of the public space includes a multi-use area designated for the market space that will accommodate the stalls and additionally includes a kiosk. The second indicator will be measured after the implementation of the project. |  | Will be verfied through (1) design drawings, bidding docs, photos, events conducted and (2) survey
Indicator 1.2.1: (1) Number of stalls and display areas provided for economic and cultural activities. (2) % of increased income for women as a result of participating in the local market.
Baseline: 0
Planned Target: (1) 10 per event. (2) 25%
Indicator 1.2.2: % of increased income for persons with disablities running the provided kiosks. | This will be measured after the implementation of the project. |  | Will be verified through contract and survey.
Baseline: 0
Planned Target: 50%
Indicator 1.2.3: Number of local markets organized per year | This will be included in Zaha Cultural Centre's operational plan that is currently being developed. |  | Will be verified through operational plan, social media, photos, and post-implementation report.
Baseline: 0
Planned Target: >15 per year
Indicator 1.2.4: Number of women using the market space to sell their products | This will be measured after the implementation of the project. |  | Will be verified through submitted registration sheets and photos
Baseline: 0
Planned Target: >150 per year
Outcome 2: Increased economic opportunities for vulnerable women in rural areas. | This will be measured after the implementation of the project. |  | Will be verified through women surveyed
Indicator: % of increased income for women due to improved access to livelihoods opportunities
Baseline: 0
Planned Target: 25%
Intermediate Outcome: Increased transferrable livelihood skills for vulnerable women in rural areas. | This will be measured after the implementation of the project. |  | Will be verified through women surveyed
Indicator: Number of women, youth, elderly, persons with disability who are benefitting from livelihoods training and the services provided by the community centre.
Baseline: 0
Planned Target: 25%
Output 2.1: Multi-service community centre is enhanced to train women and build their capacities | 25 trainers were identified and 9 Participants participated in the ToT training | Training dates were shifted because of the time required to sign the implementation agreement with the implementing partner (Jordan River Foundation - JRF) mainly the delay in receiving the approvals from JORISS. In addition to the above, and following the ToT criteria, some difficulties were faced in the process of outreach and identify the trainers in the area of Ghor Al-Safi who fit the criteria. | Implemetation Agreement with Jordan River Foundation. Attendance sheets List of trainers Certificates (once issued)
Indicator 2.1.1: Number of BDS trainers trained by certified ILO trainers on the WDB programme
Baseline: 0
Planned Target: 25 of which at least 50% women
Indicator 2.1.2: Number of women trained on the Women Do Business programme (WDB). | Selection criteria developed, and 132 Women from Ghor Al-Safi applied for the WDB training. 125 to be selected from the applicants following the ILO criteria. | WDB training will be fininished in August (as scheduled) | List of participating applicants and their data
Baseline: 0
Planned Target: Direct beneficiaries: 125 women through 6 training workshops of 12 days including 20 – 25 women per workshop. Indirect beneficiaries: > 700
Indicator 2.1.3: Number of women-led businesses supported through submitted business plans selected for grants provision and coaching. | Not started. |  | Will be verfiied through project records
Baseline: 0
Planned Target: 10%-15% of business plans submitted are selected (an average of 17 business plans may be selected for grant provision and coaching)
Indicator 2.1.4: Number of business start-ups supported | Not started. |  | Will be verfiied through project records
Baseline: 0
Planned Target: 17 businesses
Indicator 2.1.5: Number of women trained on childcare provision and supported to set up childcare facility to serve the center. | Not started. This activity will be conducted after finishing the WDB training. This is to give women who are interested in daycare facilities (to be identified through the training) the opportunity to be part of this training |  | Will be verified through attendance sheet, training reports and photos.
Baseline: 0
Planned Target: > 4 women
Indicator 2.1.6: Number of trainees linked to existing employment information platforms and to trade unions during implementation. | Not started. |  | Will be verified through survey
Baseline: 0
Planned Target: Direct 125 women Indirect beneficiaries: > 700
Indicator 2.1.7: Number of women benefitting from the childcare facility per year. | This will be measured after the development of the community centre. |  | Will be verified through registration sheet and survey
Baseline: 0
Planned Target: > 70 women
Indicator 2.1.8:Number of Agreements signed to operate and maintain the public space and community centre with Zaha Cultural Centre and Municipality of the Southern Valley to ensure the sustainability of the project. | The agreement of coopreation between UN-Habitat and Zaha Cultural Centre is currently being finalized (has been signed by UN-Habitat's regional director and awaiting Zaha's signature). The agreement between the municipality of Souther Aghwar and Zaha Cutural Center is also being finalized and expected to be signed during the coming month. |  | Will be verified through signed agreements of cooperation (AoCs) and operational plan
Baseline: 0
Planned Target: 1 with Zaha Cultural Centre and 1 with the Municipality of the Southern Valley
Indicator 2.1.9: Number of permanent economic opportunities created for the community of Ghor Al-Safi to operate the public space and community centre. | This will be measured after the implementation of the project. It will be included in Zaha Cultural Centre's operational plan. |  | Will be verified through signed contracts
Baseline: 0
Planned Target: 3 staff members and 1 security guard
Indicator 2.1.10: Number of community members received ToT training on green infrastructure techniques | Not started - This will be measured after the implementation of the project. |  | Will be verified through attendance sheets and photos
Baseline: 0
Planned Target: 15 young men including at least 5 refugees
Indicator 2.1.11: Number of elected community committees established to oversee and support the operation of the community centre | Not started - This will be measured after the implementation of the project. The community consultation sessions showed that there is an interest in the community management of the public space. |  | Will be verified through community agreement with community representatives and agreement with Zaha Cultural Centre
Baseline: 0
Planned Target: 1 committee including at least 1 woman, 1 man, 1 youth from local community, 1 disabled person, 1 from refugees.
Indicator 2.1.12: Number of training programmes provided by Zaha Cultural Centre for women and children after the construction of the community center per year | Zaha Cultural Centre has conducted a community needs assessment and will develop an operational plan that includes the training programmes according to the community needs. |  | Will be verified through post implementation evaluation report, annual operational plan of the center
Baseline: 0
Planned Target: 25
Indicator 2.1.13: Number of community members and refugees benefiting from the community programmes by Zaha Cultural Centre per year | This will be measured after the implementation of the project. |  | Will be verified through post implementation evaluation report, annual operational plan of the center
Baseline: 0
Planned Target: > 3,000 per year, of which 50% women, 50% youth and 5% refugees.
Indicator 2.1.14: Number of disabled children benefiting from community center services provided by Zaha Cultural Centre after the construction of the community center per year | This will be measured after the implementation of the project. |  | Will be verified through post implementation evaluation report, annual operational plan of the center
Baseline: 0
Planned Target: At least 50 disabled children
Indicator 2.1.15: Number of visitors attending the 3 annual festivals organized by Zaha Cultural Centre | This will be measured after the implementation of the project. |  | Will be verified through photos, operational plan.
Baseline: 0
Planned Target: > 3,000 per festival
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
First Workshop Web Story: https://unhabitat.org/jordanian-women-call-for-a-playground-and-market-in-public-space-consultations
2. Upload here: Communications and Visibility (OPTIONAL)
UN-Habitat Twitter (Retweeted by UN Jordan Twitter): https://twitter.com/UNHABITAT/status/1384859282680725508?s=20 https://twitter.com/UNHABITAT/status/1390293380379332613?s=20 https://twitter.com/UNHABITAT/status/1400437448803487751?s=20 UN-Habitat Arabic Twitter: https://twitter.com/UNHabitat_Ar/status/1384831194186014721?s=20 https://twitter.com/UNHabitat_Ar/status/1399970137294376961?s=20 UN-Habitat Arabic Facebook https://www.facebook.com/UNHABITAT.Arabic/posts/4011909122197972 UN Habitat Facebook: https://www.facebook.com/UNHABITAT/posts/10158147927677444 UN Jordan Facebook: https://www.facebook.com/UnitedNationsJO/posts/2273356309473281 UN-Habitat Website: https://unhabitat.org/un-covid-19-response-and-recovery-fund-supports-a-project-to-alleviate-socio-economic-impact-of-the https://unhabitat.org/jordanian-women-call-for-a-playground-and-market-in-public-space-consultations The Jordan Times: http://jordantimes.com/news/local/un-covid-response-fund-support-vulnerable-women-ghor-al-safi Al Mamlaka News: https://www.almamlakatv.com/news/58134-مشروع-بقيمة-850-ألف-دولار-لتخفيف-أثر-كوفيد19-الاجتماعي-والاقتصادي-في-الأردن Roya News: https://en.royanews.tv/news/25943/2021-03-02 https://royanews.tv/news/239099 Jordan News Agency (Petra): https://petra.gov.jo/Include/InnerPage.jsp?ID=58246&lang=en&name=local_news https://www.petra.gov.jo/Include/InnerPage.jsp?ID=32745&lang=en&name=en_news
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board