## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Women Economic Empowerment Window (WEEW) | Overall Duration (months) | 12 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | November 2020
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | November 2021
Country | São Tomé and Principe | Current End date(dd.mm.yyyy) | November 2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | • UNDP • UNICEF • ILO | National counterparts (government, private, NGOs & others) and other International Organizations | • Ministry of Education, • Ministry in charge of Employment, Family and Vocational Training, • Ministry in charge of SMEs, • Ministry of Women's Promotion, • Ministry of Youth, • Direction of Social Protection, • Youth Interaction Centers • Departments responsible for the environment, urban health and community development, • The Chamber of Commerce, Industry, Crafts, • Civil society organizations (CSOs), • Partner NGOs working on education, • The social partners of the world of work.
Report Cleared By
o Name: | Katarzyna Wawiernia
o Title: | RC a.i.
o Email address: | kasia.wawiernia@undp.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The MPTF project kicked-off the implementation with the participatory definition of criteria and methodology for the selection of beneficiaries for each component, ensuring the women and girls most negatively affected by the pandemic are included. From one side, 259 women whose businesses (mostly informa) have been affected by the COVID-19, started the regular trainings on entrepreneurship with a focus on strengthening women business association. The participants are being capacitated to develop a business case for the expansion or recovery of their businesses. The best cases will be awarded with a grant. The trainings leveraged on two ongoing and successful initiatives: Emprende Jovem, supporting youth entrepreneurs on business management and grants and the ILO’s GERME methodology, supporting private sector entities in the country to identify qualified people. Even though the training process has not been completed, the beneficiaries have already experienced some positive changes in their business, in particular better organization of expenditure, recording of revenue, management of low wages and the usefulness of savings. To foster a network of women entrepreneurs which amplify the positive impact of the trainings to increase the number of competent business owned by women, a digital platform was developed. The platform serves as an intermediary between the companies that offer jobs and qualified candidates. MPTF project has supported the Ministry of Labor to set-up training and information center where women can access internet and computers as well as receiving online consultation on how to use the tool to find job and other income-generating opportunities. On the other hand, the MPFT projects is seeking to establish safety nets for women and adolescents, to increase their resilience to negative shock. Leveraging from funding provided by the Joint SDG fund, the back-to-school kit to ensure the continuity of school for children from vulnerable households has been amplified. The already developed kit, will be delivered to 1500 households led by women. All women with children participating on the entrepreneurship trainings will also receive this kit. In addition, safety nets were built in high schools to empower young and adolescent girls. 300 girls at risk of dropping out of school were identified in each high school. Small groups of girls were created and already 150 girls are currently receiving regular counselling to incentivize them to continue their education and stimulate their performance. The girls who participated on the counselling sessions confessed that the topics discussed boosted their self-esteem and encourage them to study and take the final school tests. In the coming month, the teachers of the selected high schools will receive training as well to avoid girls stigmatization and other ways of gender discrimination within schools. The school counselling content included topics on: i) Gender Equality; self-confidence and self-esteem; ii) Empathy, Women resilience and Empowerment; iii) the power of knowledge and service within their communities. The methodology is based on non-formal education techniques with dynamics, games individual and collective reflections, watching films and videos, sharing inspiring testimonies, etc. inspiring testimonies, etc.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | 239 beneficiaries for the training on business management and GERME. Attendance is high, above 90% in all classes. 85% of attendees own a small business, 15% without. The main sectors of businesses are informal restaurant (15%), hairdressing and beauty (10%), sewing (8%), bale (20%), fruit and/or vegetables selling (15%), agro-processing (15%), others (17%). 30% of the participants are between 18 to 24 years old; 25% 30-34, 25% 35-39, 20% 40-35. In total 150 (out of the selected 300) young and adolescent girls received school counselling. 12 (out of 36) school counselling sessions were delivered in 3 districts of Sao Tome and the Autonomous Region of Príncipe. The sessions were delivered in small groups (of maximum 20 participants) in each of the selected high school (3 sessions per group) also included capacity building topics for teachers.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1. Entrepreneurial technical capacity of start-ups and MSMEs led by women, particularly those in vulnerable situation: More than 240 women are being trained on business management and GERME; In addition, vulnerable girls and adolescents have been identified around the country and will participate to “life-skills” regular sessions at the Youth Interaction Centers in various districts of the country. The life skills sessions provide exposure to a set of learning opportunities, including social entrepreneurship, languages, and technical skills to empower them for the job market. Outcome 2. Increased access to funding for start-ups and MSMEs led by women particularly those in vulnerable situation: After the training sessions will be completed, the best business plans developed during the sessions will have access to microgrants of USD 5000 each. Outcome 3. Increased association of startups and MSMEs led by women, particularly those in vulnerable situation The digital platform on employment services and opportunities for women has been developed and the training rooms have been equipped at the Ministry of Labor. This tool aims at developing a network of women who owns business and qualified women who are seeking jobs. Outcome 4 - Increased education related safety nets available for adolescents’ girls and households led by women, particularly those in vulnerable situation The safety nets have been developed on two fronts: a) School counselling sessions in high-schools, for girls and adolescents at risk of dropping out-of-school due to socio-economic situations on topics such as self-steam, early pregnancy, knowledge opportunities, among others. The group session are fostering safe spaces where girls feel comfortable speaking-out and discussing personal aspirations and fears; b) A back-to-school kit to cover essential school cost such as uniforms for vulnerable households led by mothers who have been affected by the pandemic. The packages have been developed and 1500 mothers have been identified. Among these, women with children participating on trainings on entrepreneurship (outcome 1) will also receive the kit.
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1 – 100 out-of-school adolescent girls have been identified across the country through the youth interaction centers. In the coming weeks, these girls, will participate to the life-skills curriculum, which includes vocational learning, personal empowerment, employability, and active citizenship in the Youth Interaction Center. Output 1.2 – More than 240 women (mainly owning a business or willing to open one) are being trained, with the aim at increasing their technical capacity on entrepreneurship. Output 1.3 – More than 240 women are being trained by qualified trainers (GERME trainers) to increase their technical capacity on basic financial tools to access funding for micro and small business development. Output 2.1 – To start in August. Output 3.1 – A digital platform of public employment services has been designed and validated by the Ministry of Labor. The platform provides a tool to improve women access to decent job offers, business opportunities and other income generating activities. On the coming months, training and incentives to vulnerable women will be provided to ensure the appropriation and ownership of the platform by women who have lost their jobs or is looking to open up a new business. Output 4.1 – 1500 vulnerable households led by women, including women who are participating to the entrepreneurship trainings have been identified. Together with the Ministry of Education and in partnership with civil society organization and women led-NGOs, the back to school kits have been developed. In early September the kit will be distributed to the beneficiaries, to incentivize school attendance. Output 4.2 Secondary schools are now offering counselling sessions targeted to adolescent girls aimed at increasing their opportunities for learning, as well as providing psychological support on issues such as early pregnancy and gender-based violence. 12 (out of 36) school counselling sessions were delivered in 3 districts of Sao Tome and the Autonomous Region of Príncipe. Output 4.3 and 4.4 – will be implemented in the coming months. The communication at the community level will engage the identified out-of-school girls to support on the dissemination of messages and participating in the radio pod-cast.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Difficulties in targeting the most vulnerable women and girls –It has been challenging identifying the target audience as those most affected by the pandemic, are women that can barely write and read, although they are in business. In addition, difficulties in gathering reliable data on vulnerable families and beneficiaries were encountered, with the potential risk of excluding women who are most in need. Measure taken: To avoid excluding women who can’t write or read from the trainings, the methodology was adapted to the learning capacities of the target audience, providing trainers with additional support. To ensure the transparency on the selection of beneficiaries, clear selection criteria was jointly established and validated among the project key stakeholders. The project has increased its advocacy on the essential transparency and ethics for the selection process. Finally, data triangulation on the beneficiaries has been done at the district level. Risk of encountering internet and electricity disruptions. The country is going through a severe energy crisis, therefore the agencies are incurring in extra costs for logistics, such as fuel for the genset in the venues where the trainings are taking place, mostly provided without extra cost by the district authorities. Mitigation: proper planning and budgeting is being done to ensure the costs do not exceed the allocated budget. Lack of engagement and support by girls' families affecting girl’s attendance and participation in the activities. Some national authorities have raised concerns regarding the vulnerability criteria for the selection of the beneficiaries (e.g. single mother), stating that it might incentivize early-pregnancy among young and adolescent girls. Mitigation: a proper communication strategy is developed together with key development partners (i.e. World Bank) to mainstream key messages, based on evidence, on barriers faced by girls to stay in school or access quality and trainings. These barriers, alongside low self-steam in girls and low engagement on recreational activities accounts in part for the high rates of early pregnancy. Mass media communication (through radio and TV) will ensure this message is clear and based on evidence.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Country institutions and government engagement from the very conception and design of emergency intervention to ensure a better ownership by the implementing partners and to allow a smooth execution. Flexibility to reprogramme is key given the local context (limited human resources and availability of inputs in quantity and quality). Mainstreaming of digital tools: the implementation of the digital platform on employment services highlighted the need to digitalize interventions to increase the potential of the south-south cooperation and knowledge transfer. Ensuring adequate spaces for activities: During the implementation of this project we came across a lack of quality of safe places in some districts. It is essential to identify safe and welcoming places for women and girls to encourage them to continue learning. The demand is too high, as monitoring of activities is the only way we can guarantee the continuity of planned actions. Hence partnering with CSOs, NGOs and municipalities is key to ensure the proper logistics and conditions are provided.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | Partnerships that have been fostered by this project include: Increased involvement and empowerment of the Association of Women Entrepreneurs from the design of the project to the implementation and monitoring. Additional support from the Association to these women is being analyzed. Civil society engagement: in a context where human and financial resources are limited, a pandemic has a great impact on the government resilience. In such cases, the civil society plays a key role to support the government to deliver an adequate response. For the provision of safety nets to girls and women, the project has engaged NGOs and civil society organizations for the delivery of key outputs (back to school kit, and school counselling). This type of institutional partnership has proven to be very effective as it allows the traditional institutions to focus on a macro-level decision, with CSOs providing operational and logistic support. NGOs are also a great source of database which can inform the selection and engagement beneficiaries.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | None
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Only one output was revised: 4.2 – Instead of targeting all high-schools, the available funding allowed us to target only xx%. However the whole design of the trainings and the training of teachers is a way to ensure the up-scalability of this intervention.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | None so far.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1 - Increased entrepreneurial technical capacity of startups and MSMEs led by women, particularly those in vulnerable situation;
Indicator 1.1: Number of women, particularly those in vulnerable situation, benefiting from technical capacity building on entrepreneurship; | 239 | n/a | List of selected women available
Baseline: N/A
Planned Target: 500
Output 1.1 - Out-of-school adolescent girls, identified through community platforms, have increased skills on vocational learning, personal empowerment, employability and active citizenship trough the community-based entrepreneurship programme in the Youth Interaction Center.
Indicator 1.1.1: Percentage of out-of-school adolescent girls, have received monthly trainings on skills for vocational learning, personal empowerment, employability and active citizenship; | 0% | Due to Micro assessment to the implementing partner (youth institute), fund transfer was delayed. At this point, this institution is ready to receive the fund and carry on the planned activities | attendance list, field visits reports
Baseline: 0
Planned Target: 100% (of identified out-of-school)
Output 1.2 - Identifed women, particularly those in vulnerable situation, have increased technical capacity on enterpreneurship, cooperative/enterprise technics, and better conditions of work.
Indicator 1.2.1: Number of beneficiaries of training on enterprise/cooperative promotion tools and methods; | 239 (184 informal female workers) | n/a | List of selected women available (Training kits on the management of cooperatives provided to the women)
Baseline: 0
Planned Target: 150: 50 (informal young and female workers); 50 (female small enterprises holders); 50 (young and female informal workers)
Indicator 1.2.2: Number of beneficiaries of training on safety, health and hygiene at workplace; | 239 (184 informal female workers) | n/a | List of selected women available
Baseline: 0
Planned Target: 125: 75 (informal young and female workers); 50 (women workers)
Output 1.3 - Identifed women entrepreneurs, particularly those in vulnerable situation, have increased technical capacity on basic financial tools to allow access to funding for micro and small business development.
Indicator 1.3.1: Number of women benefiting training in business management through the network of incubators | 239 (49 with iinnovative ideiais) | The number of applications of women already in business was too large | List of selected ones
Baseline: 30
Planned Target: 130 (vulnerable women owners of innovative business ideas)
Outcome 2 - Increased access to funding for start-ups and MSMEs led by women particularly those in vulnerable situation
Indicator 2.1: Number of start ups and MSMEs led by women, particulary the most vulnerable, with access to finance. | Identification in progress, training phase to be completed at the end of July 2021 | n/a | List of grant beneficiaries
Baseline: 5
Planned Target: 35
Output 2.1 - Number of start ups and MSMEs led by women, particulary the most vulnerable, financed through micro grants.
Indicator 2.1.1: Number of start ups and MSMEs led by women, particulary the most vulnerable, financed through micro grants. | Identification in progress, training phase to be completed at the end of July 2021 | n/a | List of grant beneficiaries
Baseline: 0
Planned Target: 35
Outcome 3 - Increased association of start ups and MSMEs led by women , particularly those in vulnerable situation
Indicator 3.1: Number of new associtaion of women entrepreneurs. | 0 | On track but the result is expected by the end of the year | Data from the digital tool
Baseline: 0
Planned Target: 1
Output 3.1 - Identified groups of women entrepreneurs, particularly those in vulnerable situation, have the tools and incentives to associate, with the aim to improve their empowerment in terms of access to market, business and more decent jobs opportunities.
Indicator 3.1.1: Existence of a digital platform conducento to associtaion of women entrepreneurs. | 1 digital platform designed and available to the benefit of women entrepreneurs and job seekers | n/a | the platform is available at the level of the ministry of employment/ website: www.emprego.st
Baseline: 0 (not available to date)
Planned Target: 1
Outcome 4 - Increased education related safety nets available for adolescents’ girls and households led by women, particularly those in vulnerable situation.
Indicator 4.1: Percentage of vulnerable young girls and households led by women, with access to increased safety nets for the continued education of their children in pre-primary school. | 0% | The back to school programme will be launched in early september before the start of the school year, as a way to incentive registration of children on schools. | List of beneficiaries and signed vouchers
Baseline: 0
Planned Target: 100% (of WEEW beneficiaries)
Indicator 4.2: Percentage of secondary schools offering services for adolescent girls to increase opportunities for learning, and psychological support services on issues such as early pregnancy and gender-based violence. | 30% | In total the councelling will cover only 50% of the high-schools as costs for counselling and follow-up proved to be higher | Implementing partner reports
Baseline: 0
Planned Target: 100% (of secondary schools)
Output 4.1 - Adolescent girls and vulnerable female households receive a Back to School incentive package to support continuing education of their children.
Indicator 4.1.1: Number of children of adolescent girls and vulnerable female households received one back to school package. | 1500 backpacks, 1500 backpacks, 1500 notebooks, 1500 carbon pencils, 1500 erasers, 1500 sets, and 1500 pens.notebooks for preschool children from vulnerable families have already been purchased, and 400 uniforms have been made have been made for the boys. | n/a | Ministry of Education, and programmatic visit.
Baseline: 6000
Planned Target: 7500
Output 4.2 - All secondary schools integrate monthly counselling, training and vocational guidance sessions, and establish clinics led by public social workers for individualized support.
Indicator 4.2.1: Percentage of schools which integrated at least one counselling, training and vocational session and established a clinic with social workers for individualized counselling at least once per month during school time for adolescent girls. | 9 schools from the districts of Água Grande, Mé-Zóchi, Lobata and Cauê were covered with the training sessions, secondary schools and basic secondary schools, and 125 adolescent school dropouts | n/a | Ministry of Education, and programmatic visit.
Baseline: 0
Planned Target: 100% (of secondary schools)
Output 4.3 - Adolescent girls, attending schools and youth interactions centers, are better informed on existing professional opportunities, available trainings, early-pregnancy, HIV, through C4D campaigns.
Indicator 4.3.1: Number of communication and advocacy material developed quarterly for adolescent girls on existing professional opportunities, available trainings and sensibilization on early-pregnancy, HIV, abuse of substances and GBV | 0 | The communication and advocacy materials will only be developed and disseminated after the output 1.1 activities are finalized | Social media reports, national and local radio reports
Baseline: 0
Planned Target: 500
Output 4.4 - Adolescent girls develop and operationalize a radio program to widen the dialogue on women empowerment, entrepreneurship, out-of-school, gender based violence, and related issues.
Indicator 4.4.1: Number of radio sessions led by adolescent girls broadcasted in the national and community radios | 0 | The radio sessions and podcasts will be carried out by selected girls with notable performance during the capcity building sessions on output 1.1 | Social media sessions, national and local radio sessions
Baseline: 0
Planned Target: 35
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Story 1 Before I used to buy the food products in the city to sell in my shop in my area, but for me to set my prices I would first try to know what price other shops in my area are practicing, so I would also practice the same price. Now with the training I already know that for me to set the price of my products in my shop, I need to know first which price I bought each product. For example, when I buy 1 bag of rice for 390.00 dobras, as I will sell in kg and not in bag, and I know that each bag brings 25 kg of rice, then I have to know how much it cost me each kg of rice inside that bag. So I do a simple calculation. If a 25 kg bag of rice cost 390.00 dobras, then 1 bag cost me how many? 25 kg --------- 390.00 folds 1 kg ----------- x folds X= 1 kg x 390.00 folds / 25 kg X = 15,6 folds So I already know that each kg of rice cost me 15.6 folds. So I can never sell each kg of this rice of mine for 15.6 folds or less, so I will be at a loss. But another thing I already know is that this value is only for the purchase of rice, I also have to deduct the money from the motorbike, energy and rent for the space that I pay every month. Now I know the true value of the cost of 1 kg of rice, so I know what price I can put on each kg of rice so as not to make a loss. After that I can see what price the other shops nearby are charging and also try to know what price the people in the area are willing to pay for each kg of rice. Story 2: Before, I thought business was just about having space, having money to buy things that we will sell or use to produce something else, and knowing how to make these things and how to sell them. But now I have learned that if we want our business to be successful, we need to do many things to improve our business: before even starting our business, we have to study the market, know and study our competitors, our customers. We also have to analyse ourselves to know what we know how to do well and what our difficulties are. When we start our business, we have to know how to treat our customers well, be nice to our customers, be clean with ourselves and with our space. And we also have to try to do some innovation in our business to be different and better than others who already have the same business. If we take all these precautions our business will not be another one in the market that came and closed. We will have a better chance of succeeding and making more profit in our business to help our family.
Quotes from school girls after the trainings "For me today was a very fruitful and very interesting, because here I learn many things. I learned that a woman can be what she wants to be and what she wishes to be in society. [...] Today I leave here more confident of myself. I feel I can do anything I want. Idalmira , 19 years old "I enjoyed this training. I feel very happy. What struck me most about this training was empathy. We should not judge others before getting to know them. We should know others and we should also be nice/empathetic". Sara Nogeira. 15 years old Before I came for this training, I was a bit shy. Now I'm not anymore, I'm already open because those participating in my group have made me feel relieved. I no longer feel ashamed. I don't feel ashamed of anyone any more, I'm open with everyone. Idalécia Damião 15 years old I am part of the School Association, and after this sessions, I will convince the other members to talk mora about women's rights and other women’s issues. I will also talk to my physical education teache or the school headmaster so that we can form we form a girls' team in the school. Daniela, 17 years old
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board