## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Safety nets and revenue recovery for the poorest households and women informal workers in Cabo Verde | Overall Duration (months) | 7
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-06-01
MPTF Office Project Reference Number: | 121531 | Original End Date (dd.mm.yyyy) | 2020-12-31
Country | Cabo Verde | Current End date(dd.mm.yyyy) | 2020-12-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF ILO | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Foreign Affairs; Ministry of Finance; Ministry of Family and Social Inclusion
Report Cleared By
o Name: | Ana Graca
o Title: | Resident Coordinator
o Email address: | ana.graca@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project featured two complementary components: a direct support to social protection coverage, through the extension of an emergency cash-transfer to 1,000 households among the poorest in the country (during 3 months), namely the one headed by women; and a financial and technical support to 150 women informal business owners, from the most isolated islands/geographical areas, to promote the recovery and/or adaptation of their economic activity, within the framework of updated local economic development priorities. Component 1 contributed to minimize the effects of the crisis on the beneficiaries, selected trough the Social Register (Cadastro Social Único). A 5.500 CVE transfer, during 3 months, provided a minimum of survival to women heads of households, which were integrated in the social registry in the process. The payment modality was based on the mechanisms established by the government and was made through the bank account registered or created for each beneficiary. 100% of the 158,000 USD budget allocated was executed between June and December 2020. The second component was designed as an immediate/short-term response to the crisis created by the pandemic, with a limited timeframe of intervention, yet taking into account longer term perspective, and serving as a pilot for economic policy making for recovery and sustainable development. This component included an integrated package with financial support, two training packages (Get-ahead and Financial Education), financial and management services and guidance from partners’ NGOs and local consultants; and coaching for business recovery and formalization for 150 selected women in the islands of Fogo and Santo Antão, the country’s poorest and most isolated. The project was effective in contributing to the capacity building of selected women in the informal sector, giving them the opportunity to relaunch their business activities in an emergency context, supporting their economic recovery and the transition of 52% of these businesses towards formality. The beneficiaries’ selection criteria were clearly defined at the beginning of the process and the local authorities were strongly involved in the process. A wide local ownership of the project was ensured, despite the challenging context of COVID-19, through the implication via ZOOM conferences of the local platforms for SDG localization, which bring together local authorities, NGOs and private sector entities. Synergies with the municipalities were crucial to the success of the implementation as well the partnership and additional resources mobilized in amount of 10.200 USD from regular resources for UNICEF and UNDP. The planned activities were all successfully implemented within the budget’s framework and timeline, and synergies with existing projects and local partners were promoted to provide resources to support the implementation of the project activities. The beneficiaries scored the project 9,5 (on a 1 to 10 scale), stressing the relevance of technical and financial support received as important means to recover their businesses and build resilience. The combination of financial and non-financial services was key to supporting the sustainable recovery of businesses and their transition to formality. 100% of the 300.000 USD budget was executed between June and December 2020.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Purpose of the component 1 : Aims at providing lifesaving/relief assistance to 1.000 households among the most vulnerable and poorer in the country - namely the ones with at least a child under 15, an elderly, or a person with disability at charge. Out of the 1,000 households, 998 were headed by women. Purpose of component 2: Supporting women informal entrepreneurs in reactivating/recovering their businesses, while facilitating their transition to formal economy. Direct beneficiaries: 150 women informal entrepreneurs from the two poorest islands of Cabo Verde - Fogo and Santo Antao (40% of the women have between 25-34 years old, immediately followed by the range 35-44 with 31%; women aged between 45-54 represented 17% of the total; the same pattern was observed for both island if analysed separately)
3.1 | Results: Outcome Level | Please include outcome level results achieved | 100% of the beneficiaries selected at national level of the first component received the cash transfer. 52% of the project beneficiaries transitioned towards formal economy (78 beneficiaries out of 150: 38 in Fogo and 40 in Santo Antão) against a target of 20%; 100% of the project beneficiaries that transitioned towards formal economy were women.
3.2 | Results: Output Level | Please include output level results achieved | 1.000 households among the most vulnerable and poorest in the country benefited from the social transfer in an amount of 5.500 CVE each one. 150 women benefited from technical and financial support to recover their businesses on the islands of Fogo (70 women) and Santo Antão (80 women), in line with local economic development priorities as expressed in the Municipal Sustainable Development Plans (elaborated with the support of the SDG Localization Platforms).
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Although the main risk identified in the project risk register was the impossibility to deliver project activities due to COVID-19 specific circumstances (lockdown, etc.), the project was in general not highly affected by the materialization of this risk. The activities of component 1 involving work on the field (identifying the beneficiaries, open bank accounts for them when needed, registering them in the CSU, etc.), was done by local authroities and representatives of the Ministry of Family and Social Inclusion. The activities of component 2 were locally implemented on both islands by ILO national consultants, project partners and trainers; and the COVID-19 prevention measures did not have a strong impact on the activities. For the component 1, at the begining there was some difficulty in contacting some of the potential beneficiaries due to the change of address and telephone contacts, however this risk was overcome with the strong engagement of the municipalities which has made possible to reach all the beneficiaries. Some of the beneficiaries also did not have a bank account, but the bank accounts were opened and some payments were made by post on presentation of identification documents. For component 2, some difficulties were encountered in the availability of trainers on the islands of intervention, which affected the planned implementation timeline due to travel restrictions. Another challenge that was identified during the project implementation was the municipal elections that took place in late October 2020, which affected the availability of the municipalities’ staff and their engagement with the project, especially at the stage of the beneficiaries’ selection process. However, overall, apart from minor delays, these constraints did not result in shortcomings in the project expected results, neither in terms of quality nor quantity, partly thanks to a good local ownership from local authorities and beneficiaries.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | 1. The use of the Single registry in the identification of the potential beneficiaries, allowed not only to allocate the benefit on the basis of efficient targeting mechanisms, but also to identify duplicate beneficiaries avoiding double payment. 2.The strong partnership with Cape Verde's municipalities and post offices facilitated the process of identification and payment of benefits to households; 3. The awareness raising and communication campaigns carried out were also an important vehicle to inform the beneficiaries 4. The combination of the training and coaching/follow up services with the financial support is important to ensure an efficient business recovery as well as to increase its resilience in the face of shocks and crisis. 5. The involvement of the national and local partners, as well as synergies with other ongoing projects, brought valuable contributions to enable a swift and sustainable implementation of activities, facilitating the achievement of the proposed objectives. 6. The sensitization of informal entrepreneurs regarding the process and advantages of formalization is a very effective measure to overcome misinformation and promote transition to formality within vulnerable groups. Overall, the project's approach allowed, at one hand, for piloting a business recovery solution for the informal sector that can be afterwards scaled up and applied to other contexts in the post-pandemic background. As such, a similar intervention (“productive inclusion project”) is being developed by the Ministry of Family and Social Inclusion, with support from the World Bank in 2021, for which this pilot project will provide recommendations and lessons learned.On the other hand, it promoted the use of work instruments and delivery mechanisms already in place, used by the national social protection institutions, thus reinforcing local and central capacity.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | For Component 1, considering that the amount of 158.000 USD allowed to cover only 942 households out of 1000 planned beneficiaries, UNICEF was able to cover the remaining 58 beneficiaries with its own resources and additional resources mobilized from UNDP, thus allowing the project to cover the 1.000 beneficiaries as planned. Component 2 leveraged the creation of synergies with other existing projects on the islands of Fogo and Santo Antão, such as the Jov@Emprego Program, and the Local Development Platforms, in order to maximize resources and avoid overlapping of the different interventions. As such, the trainings were facilitated by the local antennas of Program Jov@Emprego, building upon existing ILO instruments, such as the Get Ahead and the Financial Education training tools, ensuring its feasibility in such a short time-frame. Furthermore, the participatory approach of the project, that involved the Ministry of Family and Social Inclusion, the Ministry of Finance, two NGOs (Morabi and OMCV), six municipalities on both islands, and the antennas of Jov@Emprego, was very important to ensure the project’s sustainability and to obtain the necessary support to ensure an effective local implementation of the planned activities within such a challenging timeline.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | An evaluation exercise carried out with a random sample of project beneficiaries from both islands emphasized the relevance of the project’s response to their most urgent needs as a result from the pandemic. Most of them mentioned the impact that COVID-19 and lockdown measures had on their sales, forcing them to halt their economic activities. The beneficiaries scored the project’s support with 9,4 (on a 1 to 10 scale), stating that they were thankful for both the financial support and the training received, which is helping them to recover their businesses and become more resilient. The beneficiaries also stated the relevance of the training to teach them how to better run their business, the benefits of formalization and the opportunities to eventually expand their business in the future, as well as the usefulness of the small grant in enabling them to take the first steps towards recovering their businesses.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | /
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Overall Budget Analysis: The planned budget for the implementation of the project’s first component for the period of June-December 2020 was 158.000 USD USD and 100% of the budget allocated to provide lifesaving/relief assistance to 1.000 households among the most vulnerable and poorer in the country. The beneficiaries were selected through the Single registry (Cadastro Social Unico).The payment modality was based on the mechanisms established by the government to manage payments to beneficiaries but in close concertation with UNICEF via un agreement (LOA) signed with the DGPOG-MFISS, and was made into the registered bank account of each beneficiary. Each beneficiary received an amount of 5.500 CVE, during 3 months. The expected results in terms of financial execution achieved as the financial executions was 100%. Synergies with the municipalities were crucial in providing support in the contact with the potentials beneficiaries identified in through the Single registry at local level. The planned budget for the implementation of the project’s second component for the period of June-December 2020 was 130.540 USD, with 24% of the budget pertaining to supplies, commodities and materials, including the national and international consultants and other subcontracts; and 73% allocated to transfers and grants. The latter budget line was divided between both islands, with the amount of 42.000 USD allocated to 70 women in Fogo and 48.000 USD for 80 women in Santo Antão. Each beneficiary received up to 600 USD to support their business recovery (amount defined with the Ministry of Family and Social Inclusion based on the average loan that women ask to relaunch their activities, and the amount that the Productivity Inclusion project of the World Bank is expected to pay for a similar intervention that will start later on this year, but in different municipalities. There were no significant differences between planned and spent expenditure. The project’s second component was efficient in terms of the adequacy of resources for the implementation of the activities and the achievement of the expected results in terms of financial execution. The planned activities were all implemented within the allocated budget and the financial execution was 100%. Synergies with existing projects, such as Jov@Emprego, and with the municipalities were crucial in providing resources to support the implementation of the project activities. The training courses on financial education and Get Ahead were provided within the framework of Jov@Emprego; whereas the municipalities supported activities by providing logistic support, such as venues for training and interviews as well as transportation for the beneficiaries.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator: 2.1 Proportion of extremely poor households covered by the Social Inclusion Income (RSI) and RSI Emergency (RSI/E) at national level (3 months) | 100% |  | Management Information System
Baseline: 30%
Planned Target: 100%
Indicator: 2.1b Proportion of women headed households that benefit from RSI and RSI/E
Baseline: TBD | 98% |  | Management Information System
Planned Target: 60%
Indicator: 2.2 Number of informal businesses accompanied in their transition toward formality | 52% | The combination of financial and non-financial services was key to support the sustainable recovery of businesses and their transition to formality. | Management Information System
Baseline: 0%
Planned Target: 20%
Indicator: 2.2b Proportion of women among them | 100% | Selection specifically targeted female beneficiaries, especially those with children and coming from single parent households | Management Information System
Baseline: NA
Planned Target: 60%
Output 2.1.1 The poorest, most vulnerable and most isolated households are included in the social registry (CSU)
Indicator 2.2.1 Number of households covered by the extension of the emergency social inclusion income (3 months) | 1, 000 |  | Management Inf.System
Baseline: 2,788
Planned Target: 3,788
Output 2.2.1 Women informal workers from the most isolated islands/geographical areas benefit from support to economic activity recovery, with a view to adapt their business to the new situation, in the framework of updated local economic development priorities | 150 | / | Management Information System
Indicator 2.2.1 Number of women benefitting from support to economic recovery
Baseline: 0
Planned Target: 150
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
A video on the project, together with two or three written stories from the field, are being finalised, and are expected to be received in the coming weeks. The fact that the producers had to do two missions to the islands (and within the pandemic) had an impact in terms of time delivery.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board