## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Increasing Access to COVID-19 Diagnostic and Treatment Centres in The Gambia | Overall Duration (months) | 9 months
Programme Number (if applicable) | 22662-001 | Start Date (dd.mm.yyyy) | 2020-06-01
MPTF Office Project Reference Number: | 22662-001 | Original End Date (dd.mm.yyyy) | 2020-12-31
Country | The Gambia | Current End date(dd.mm.yyyy) | 2021-03-30
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA, UNICEF, UNOPS | National counterparts (government, private, NGOs & others) and other International Organizations | Government of The Gambia
Report Cleared By
o Name: | Seraphine Wakana
o Title: | UN Resident Coordinator
o Email address: | seraphine.wakana@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Since the commencement of the MPTF COVID-19 Project in June 2020, results achieved include construction of three (3) COVID-19 Treatment centers sites, followed by procurement and fabrication of containers, construction of access ramps, procurement of 60 beds, 60 IV stands and 60 mattresses. All internal works including electricals, installation of extractor fans, painting, plumbing, smoke alarms, and internal partioning works have been completed. The construction of all the 3 COVID-19 Treatment centers strictly complied to the SARI Design Guidelines. UNICEF worked in collaboration with UNOPS, Department of Water Resources and Ministry of Health to install prefabricated sanitation facilities at three COVID-19 Treatment centers sites. This innovative technique made it possible to quickly start the work and to have permanent infrastructure to be easily replicated for other needs. In addition to the sanitation facilities in treatment centers, UNICEF has installed 4 additional containers to set up 16 toilet cabins including 8 cabins for male and 8 cabins for female in Lumo, Wassu, Janjanbureh and Lamin Koto. UNICEF with UNOPS support and in collaboration with Department of Water Resources constructed 3 new boreholes equipped with solar pumping system, to reduce energy consumption (and also operating cost) and make the project more sustainable and more ecological, in order to cover permanently the essential water needs of the COVID -19 treatment centers in Essau, Bansang and Soma . In addition to that UNICEF also rehabilitated the borehole in Soma Health Facility. To support in running of the COVID-19 treatment centers, UNICEF purchased non-food items (NFIs) for hygiene including soap, chlorine, bleach, individual hygiene kits to facilitate disinfection of centers, water treatment, and ensure the hygiene of patients and front-line health workers. UNICEF in collaboration with the MoH developed training modules on Infection Prevention and Control (IPC). This training in addition to allowing a systematic response to COVID-19, will also make it possible to stop or reduce nosocomial transmissions and good management of medical waste. UNFPA launched the National GBV Helpline in June to respond to the needs of survivors by providing them with Psycho First Aid and referring them to other services to cater for their immediate needs. So far, 2619 survivors used the Helpline356 survivors received Psycho Social Support and GBV case management services, 33 persons were referred to the shelter for children and integrating them back to their normal lives. A GBV referral pathway has been developed to link services and standard operating procedures was also developed for the management of the One-stop centers. Through this project, UNFPA with MoH supported the expansion of 4 one-stop center in Soma Health center, Lower River Region, Bansang Hospital, Central River Region, Basse Health center, URR and Brikama Health Facility. In addition to this, a shelter to support GBV survivors with basic and immediate needs was also established together with the Ministry of Gender, Children and Social Welfare. It is important to note that this is the first time the Gambia has such a service specifically catered for GBV survivors.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The main focus and purpose of the joint MPTF COVID-19 project was to tackle the health emergency; focus on the social impact, and the economic response and recovery; and help the country to recover better. The combined populations of the North Bank and Central River regions of the Gambia constitutes the ‘catchment area’ for the health centers, and therefore with the target population of 447,072 people or 22.35% of the entire population (based on 2013 census). In addition to the beneficiaries popualtion of North Bank and central river Region of the Gambia, UNICEF as part of capacity building, trained 300 health workers on IPC, including 221 male and 79 female
3.1 | Results: Outcome Level | Please include outcome level results achieved | The continuation of health service delivery for women and people with disability through the provision of primary health care by preventing the disruption of routine services in poor and rural areas as a result of COVID-19 Response. The provision of GBV services and response mechanisms to support survivors of GBV and reintegrating them back to their normal lives.
3.2 | Results: Output Level | Please include output level results achieved | -The availability of standard treatment facilities for the affected population that will reduce risk of the spread of the disease to the rest of the population especially to poor and deprived social groups. -Ease of access to COVID-19 treatment hospitals for rural communities in The Gambia. -The establishment of a first GBV Helpline in the Gambia, expansion of 4 one-stop centers in 3 regions of the country and 1 municipality. -Establishment of the GBV shelter to support GBV survivors across the country. -Access to safe and sustainable water supply for 3 facilities and vulnerable communities -Access to adequate sanitation and adoption of good hygiene practices in 3 facilities and among vulnerable communities. -Community capacity in awareness for change of behavior is built to sustainably prepare, respond and recover from Public Health Emergencies and other forms of disasters.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Weak inter-ministerial and inter agency coordination and weakness of contractor capacity for the project delivery remained valid throughout the project. Regular UNCT meetings with government stakeholders were held to improve dialogue and concerted efforts to deliver the project successfully. Regular contractor management including intensive monitoring and handholding through the outposting of UNOPS engineers and administrative support staff to remote project sites mitigated contractor tardiness. To resolve shortcomings UNICEF also held 3 technical meetings with the various partners in charge of the implementation. One issue has been the lack of showers in treatment centers. Indeed, it would also be necessary to have showers for patients in the treatment center; in the light of the discussions with the contractor, UNICEF will be able to propose an adequate solution going forward. The fact that comprehensive GBV programming is new to the Gambia, there exist limited capacity of partners to implement GBV case management programmes. In ensuring a timely and broad based Programme delivery on GBV targeting and reaching the furthest behind, there is a need to have a pool of partners with the technical capacity to execute and deliver certain programmes tailored to GBV whilst reflecting on the survivor centered approach. However, this is lacking in the Gambia due to the limited number of CSO’s and NGO’s with the requisite expertise to implement GBV activities. This poses a challenge for UNFPA to roll out and launch multiple GBV Programme activities. Furthermore, the establishment of shelters and safe spaces for GBV survivors is also new in the Gambia and due to the socio-cultural norms and sensitivity of GBV in the country, and hitherto, most survivors prefer settling their issues within the family to avoid stigmatisation within the community and will go to the extent of withdrawing cases from the police thus this limits the effectiveness of managing GBV cases. However, measures to counter these problems were taken by UNFPA and this was done through engaging the Gambia Police Force. The Gender and Child Welfare Unit were supported to conduct thorough investigations on GBV cases, awareness raising activities, train Police Officers, Local authorities and community leaders on issues affecting women and children in relation to GBV throughout the country as they are the most affected groups in our society. Although, there exist limited partners in GBV programming, UNFPA was able to conduct two partner capacity assessment and engage these partners to support the programme. One of these partners is managing the Helpline and the other is coordinating the service delivery at the one-stop centers.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Operational lesson 1: need to plan and account for additional resources for active project site monitoring and supervision and support of local contractors to maintain implementation schedules. Operational lesson 2: improve coordination with government for site selection, as original site alloted was inaccesible during heavy rainfall, which led to construction start-up delays. UNICEF through this project has demonstrated to strengthen the health system in The Gambia with innovative techniques and to strengthen the capacity of health workers on IPC and waste management in the health environment. This project also, starts from the innovation that comes with it (a technique of using a container) which can be duplicated everywhere in The Gambia, also contributing to the preservation of the environment with the use of solar pumping system and the construction of latrines in public places to avoid open defecation and thus also avoid faecal diseases.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UNOPS is showcasing this project and the indigenous capacity for delivering prefabricated container treatment centers that are being built for this project with selected donors and soliciting funding in the same line of intervention for emergency COVID-19 response. The facility is 3 out of 9 that the government proposes to build in response to COVID-19 pandemic, and the local capacities built through this project will be leveraged for replication and scale up. UNICEF together with the commitment of the communities will preserve the environment through this project with latrines in highly frequented public places. These latrines will be fully managed by the beneficiary communities. UNFPA together with the Ministry of Gender, Children and Social Welfare partnered with Paradise Foundation to establish the GBV Helpline 1313. As they are currently managing the COVID-19 Helpline on behalf of the Ministry of Health, together with their experience and interest in GBV, UNFPA sought to leverage on their expertise for a fruitful engagement in having them manage the GBV Helpline on behalf of the Ministry of Gender, Children and Social Welfare. Another partnership that was fostered was with the Network Against Gender Based Violence. On the basis through this partnership, a GBV Referral Pathway was developed together with the Standard Operating Procedures for the management and operations of the one-stop centers.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | None - still early for assessments; this is an emergency project and usage is just commencing.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | None- still early for assessments; this is an emergency project and usage is just commencing. The target of reaching 16,000 survivors through the GBV helpline for psychosocial support and GBV case management services was ambitious. This is due to the fact that such services are “first of its kind” in The Gambia and service uptake is expected to be lower in the first few months of the commencement. In addition to this, the socio-cultural barriers that exist in the country it will take some time to navigate. As a result of this, UNFPA requested for the revision of the targets during the mid-term reporting and this was approved, as part of the no-cost extension.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Additional resource mobilization is ongoing as the government has expressed interest in additional containerized nurse stations and back up solar power.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1.1 Ensure the continuity of health service delivery including for women and people with disability through primary health care by preventing the disruption of routine services in poor and rural areas as a result of COVID-19 Response.
Indicator: International Health Regulations (IHR) capacity and health emergency preparedness (% increase in number of hospital beds available for forecasted critical cases of COVID-19) |  |  | Number of hospital beds available
Baseline: 10.2%
Planned Target: 16% | 16%
Output 1.1 Ensure the availability of standard treatment facilities for the affected population that will reduce risk of the spread of the disease to the rest of the population especially to poor and deprived social groups
Indicator 1.1.1: Availability of 3 functional treatment centres in the poorest regions of the country to ensure each of the 7 health regions of the country have a treatment centre for COVID-19 | 3 COVID-19 treament centers in place |  | Assessment report on Functionality of Treatment centres
Baseline: 0 | 3
Planned Target: 42% | 100%
Outcome 1.2 Increased protection and safeguarding of women, children, elderly and persons with disabilities from stress, fear, stigma, gender based violence through a systematic psychosocial support system and multi-sectoral GBV referral pathway in the Gambia
Indicator 1.2.a:# of women, girls, boys and men, persons with disabilities and elderly received PFA services through hotlines & physical services. |  |  | Service Data Registrar and hotline call registrar
Baseline: Not Available
Planned Target: 15000 Revosed: 2000 | 2616
Indicator 1.2.b:# of women and girls received PSS & GBV Case Management Services to |  |  | Service Data Registrar
Baseline: 0
Planned Target: 2000 Revised 250 | 356
Output 1.2.1. Strengthened remote service delivery through hotlines and technology to ensure women, girls, boys, elderly, person with disability have the access to information, referral and basic psychological first aid services
Indicator 1.2.1a. # of women, girls, boys, elderly, persons with disability and marginalized people received PFA services, referral & follow up of services quality through hotlines |  |  | Service Data Registrar and hotline call registrar
Baseline: not available
Planned Target: 15000 Revised target: 2000 | 2616
Indicator 1.2.1b. # of women and girls received PSS & GBV Case Management Services |  |  | Service Data Registrar
Baseline: not available
Planned Target: 15000 Revised Target: 250 | 356
Output 1.2.2. Strengthened GBV case management services with specialized Psychosocial Programmes for women and girls who are the survivors of GBV or at risks of GBV (both remote and physical services)
Indicator: 1.2.2.a # of women & girls received GBV case management services tailored with psycho-social services that includes shelter and re-integration into normal lives through multi-sectoral referral pathway. |  |  | Service Data Registrar and hotline call registrar
Baseline: 0
Planned Target; 1000 revised target: 100 | 33
Indicator: 1.2.2.b # of Women’s Multipurpose center is establish to provide integrated GBV and PSS services to survivors, women and girls, persons with disabilities.
Baseline: 0
Planned Target: 2 | 1 |  | Service Data Registrar
Indicator: 1.2.2.c # of health care providers received PSS/GBV services
Baseline: Not available
Planned Target: 4000 Revised: 150 | 604 |  | Service Data Registrar
Outcome 1.3.Three holding/treatment centers, catchment areas populations have improved and equitable access to and utilize safe drinking water and sanitation services and adopt improved hygiene practices and behaviors
Indicator: 1.3a Proportion of the population using an improved source of drinking water and access to latrine
Baseline: 90%
Planned Target: 91% | 91% |  | MICS Reports
Output 1.3.1 Increased equitable access to safe and sustainable water supply for 3 facilities and vulnerable communities
Indicator: 1.3.1a: Number of safe water facilities constructed /rehabilitated
Baseline: 0
Planned Target: 3 | 4 | Fully Achieved : 3 newly contructed and equiped boreholes ; 1 rehabilitated borehole in Soma health facility | Report and field visit
Output 1.3.2 Increased access to adequate sanitation and adoption of good hygiene practices observed at 3 facilities and among vulnerable communities
Indicator: 1.3.2b: Number of gender and disability inclusive sanitation facilities constructed
Baseline: 0
Planned Taget: 5 | 4 | Fully Achieved: 16 toilet cabins (4 containers) including 8 cabins for male and 8 cabins for female in Lumo, Wassu ,Janjanbureh and Lamin Koto are available- all are disability sensitive | Report and field visit
Output: 1.3.3 Improved community capacity and awareness for change of behavior to sustainably prepare, respond and recover from Public Health Emergencies and other forms of disasters.
Indicator: 1.3.3.c: Number of trained community structures on water Management, water safety planning, waste management, operation and maintenance of WASH facilities for sustainability of WASH interventions.
Baseline: 0
Planned Target: 24 | 24 | Fully achieved: 90 female and 60 male were trained to make the 24 water mismanagement committees fully operational | Training report and field visit
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Supporting One-Stop Centers to strengthen The Gambia’s GBV response mechanism Gender-Based Violence (GBV) negatively impacts the health, wellbeing and dignity of its victims and survivors. Because of its horrific nature, survivors of GBV are exposed to among other issues, sexual and reproductive health challenges such as sexually transmissible infections including HIV, unwanted pregnancies which may lead to unsafe abortions, among others. As such, there is always a need for a holistic approach in addressing this human rights violation and mitigating its impact on lives and livelihoods. In The Gambia, at least 3 in every 4 women and girls aged 15 to 49 have undergone Female Genital Mutilation while 49.9 percent of women within the same age bracket believe that their husbands/intimate partners can beat them. In responding to these and all other forms of GBV happening in Gambian communities, there is a strong need for a comprehensive response package that provides survivors with health, legal and psychosocial support services. This is the idea behind the One-Stop Centers. In The Gambia, the One-Stop Centers are health facility-based centres positioned in major government hospitals and are best-suited for achieving the broadest range of health and legal outcomes, through the support of a multi-disciplinary team of staff working to ensure the best health and wellbeing outcomes for survivors and victims. However, the One-Stop Centres currently operating in The Gambia have been faced with numerous challenges over the years, ranging from inadequate hospital supplies/equipment, dedicated hospital personnel (doctors and nurses), social workers, police and legal aid personnel to effectively operate the centres as well as to collect data for effective response and programming. These challenges have resulted in an uncoordinated approach in dealing with survivors, thus hampering the centres’ goal to effectively deliver quality care. In order to support the government of The Gambia address these challenges and ensure a fully functional GBV response in the country, especially during the COVID-19 pandemic due to the projected increase in incidences of GBV across the globe, UNFPA with support from the UN Multi-Partner Trust Fund (MPTF) funded project aimed at mitigating the impact of COVID-19 in The Gambia, is supporting the establishment and renovation of 3 One-Stop Centres at the Essau District Hospital, Soma District Hospital and Bansang General Hospital. The support towards these centres will help ensure the delivery of holistic health, legal and psychosocial support services to survivors of GBV, thus strengthening the country’s GBV response mechanism and promoting the wellbeing, health and dignity of all survivors, especially women and girls. In order to ensure the provision of the above services, an assessment was conducted by UNFPA and Ministry of Health personnel, in order to gauge facility readiness for the operationalisation of the centres and the response services they will deliver. UNFPA remains committed to continue to support the government and people of the Gambia in addressing GBV and its resulting impact, through investments in gender equality and women’s empowerment programmes, strengthening the institutional capacity of government and other partners to provide a comprehensive and coordinated response and supporting community sensitisation programmes that influence positive change in behaviours and perceptions regarding GBV.
1. https://gambia.unfpa.org/en/news/supporting-one-stop-centers-strengthen-gambias-gbv-response-mechanism 2. https://gambia.unfpa.org/en/news/effective-gbv-case-management-ease-access-emergency-care-services-victims-and-survivors 3. https://gambia.unfpa.org/en/news/national-psychosocial-support-services-referral-pathway-advance-mental-health-and-wellness 4. https://gambia.unfpa.org/en/news/first-lady-gambia-launches-2020-swop-report-and-national-gender-based-violence-helpline 5.https://twitter.com/UNGambia/status/1274327942114488322 6. https://twitter.com/UNGambia/status/1300537523232559106 7. https://twitter.com/UNGambia/status/1300551617775886337 8. https://twitter.com/UNFPATheGambia/status/1270755590718083074
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
https://drive.google.com/drive/u/1/folders/1QT5g8-cQFBza8sTzoCFRndjzo7GtKmlV
https://drive.google.com/drive/folders/1aj-JMLAZagpkoDwYRbwvXEB3rZmM3RZD
https://drive.google.com/drive/folders/1f8DvXAaDOwcShXCsAZWCGtm0C2-ahxRq
Please provide links to any videos that have been produced during implementation.
https://www.youtube.com/watch?v=LM2KGmdfcEc
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board