## RBM-Annual (2)
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Outcome 1.1: Maintain continuity of essential health services and related supply chain for the direct public health response to the pandemic
Baseline:
Planned Target:
| 13237 |  | MOHSPP report www.covid.tj
Indicator 1.1a: Number of patients tested positive for COVID-19 with severe symptoms who receive treatment in hospital
Baseline: 0
Planned Target: 12,500
Indicator 1.1b: Number of hospitals equipped with lifesaving pharmaceutical drugs and equipment | 100 |  | UNICEF Report
Baseline: 0
Planned Target: 35
| 91 | UNFPA covered all RH facilities providing SRH/FP services to ensure services are available throughout the country | MoHSP /UNFPA report
Indicator 1.3a: # of healthcare facilities able to maintain alternate delivery of SRH services in case of COVID-19
Baseline: 0
Planned Target: 80
| Yes | Over 60,000 leaflets along with 200 posters have been distributed throughout the country along with awareness raising campaigns.
Indicator 1.3b: Education materials for pregnant women/families on SRH and basic hygiene practices
Baseline: No
Planned Target: Yes
| 64 | UNFPA covered National, Oblast and District level RH facilities to ensure referrals of clients in need of pshycosocial support services are well established throughout the country | MoHSPP/UNFPA report
Indicator 1.3c: # of health service providers trained on psychosocial services for pregnant women, women and girls subjected to violence
Baseline: 0
Planned Target: 60
Output 1.3.1: Strengthen national and local health system capacity to ensure continuity and access to SRH and GBV services for women and girls in the context of Covid-19 | 91 | UNFPA/MoHSP trained 91 RH service providers throughout the country to ensure client/service provider interaction is well established | MoHSPP/ UNFPA report
Indicator 1.3.1: # of SRH specialists trained on alternate SRH service provision in case of COVID-19 outbreak
Baseline: 0
Planned Target: 80
Indicator 1.3.2: # of hotline points established at National and Regional Levels on alternate SRH and GBV related services | 5 | Initially it was planned to establish 4 hotline points at National and Regional level RH facilities. However, based on MoHSP request additional hotline point was established in GBAO region in view of language requirements. | MoHSPP/UNFPA report
Baseline: 0
Planned Target: 4
Indicator 1.3.3: # of remote online consultations of SRH and GBV related aspects provided | 19400 | An estimated 19,400 women of reproductive age received remote online consultations of SRH and GBV related aspects provided. In view of delays caused by supply chain interruption, the telehealth services became functional in October 2020. Taking into account uncertaintees with further developments around pandemic, UNFPA took decision to extend the project by June 2021 with its own technical and financial assistance. | MoHSPP/UNFPA report
Baseline: 0
Planned Target: 93000
Indicator 1.3.4: # of women of reproductive age receive quality information on SRH and basic hygiene including related to COVID-19. | Over 1 mln. women of reproductive age | Video PSA (public service announcement) was aired at National and Regional TV media resources with 152 airtimes and over 2 mln people coverage including 200,000 pregnant women and 800,000 women using modern contraceptives | MoHSPP/UNFPA report
Baseline: 250000
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | STRENGTHENING THE HEALTH SYSTEM IN TAJIKISTAN TO PREPARE AND RESPOND TO COVID-19 | Overall Duration (months) | 8 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-05-01
MPTF Office Project Reference Number: | 00121615 | Original End Date (dd.mm.yyyy) | 2020-12-01
Country | Tajikistan | Current End date(dd.mm.yyyy) | extended until end of March 2021
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF, UNFPA | National counterparts (government, private, NGOs & others) and other International Organizations | MOH&SPP, TFPA
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The COVID-19 pandemic has tested health systems globally. Tajikistan’s health system has been overwhelmed by the efforts dedicated to pandemic management and has had difficulty in provision of medicines, medical equipment and supplies, ensuring routine health services, in particular those related to sexual and reproductive health (SRH) care, including integral components such as the provision of antenatal care (ANC), family planning (FP) and psychosocial assistance as part of GBV prevention services. Addressing these immediate needs is the main objective of the “Strengthening the health system in Tajikistan to prepare and respond to COVID-19” launched in May 2020, implemented by UNICEF and UNFPA. To support national preparedness for the surge of patients amid the coronavirus pandemic, the project in consultation with the Ministry of Health and Social Protection of Population (MoHSPP) agreed on the priority list of 13 types of pharmaceutical medication and 12 kinds of equipment to procure and provide for the intensive care units of 35 hospitals selected to treat patients suffering from COVID-19. With the supply and procurement being a comparative advantage globally, the project/UNICEF played a lead role in the procurement and provision of vital supplies for healthcare facilities across the country. The procurement process was led by UNICEF through its Supply Division and local procurement mechanisms. In response to urgent request of the MoHSPP, five ventilators, 20 oxygen concentrators and 5 Analyzers have been delivered, installed in the health facilities to ensure access to life-saving health services. Tailored training sessions have been provided for health staff on how to operate this medical equipment. In total, more than 100 hospitals /primary health care facilities across the country benefited/will benefit from the procurement of essential supplies as per the approved MoHSPP’s Distribution Plan. UNFPA led introduction of the new alternative ways of service provision using telehealth technologies to minimize direct patient contact in non-urgent situations in an attempt to minimize the spread of COVID-19. Different MoHSP affiliated structures such as the National Reproductive Health Center, Republican Clinical Family Medicine Center along with experts from the Academy of Health Sciences were engaged in the adaptation and development of temporary counseling protocols on SRH (ANC/FP) during Covid-19. Adjustments to the standard ANC, FP and psychosocial support service schedules were tested so that some appointments are conducted using phone or video chat, to ensure that there is no disruption in service or breakdown in women’s maternity care. This was basically the first-time practical experience to introduce alternative ways of SRH service provision in the country.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The COVID-19 pandemic has tested health systems globally. Tajikistan’s health system has been overwhelmed by the efforts dedicated to pandemic management and has had difficulty in provision of medicines, medical equipment and supplies, ensuring routine health services, in particular those related to sexual and reproductive health (SRH) care, including integral components such as the provision of antenatal care (ANC), family planning (FP) and psychosocial assistance as part of GBV prevention services.
3.1 | Results: Outcome Level | Please include outcome level results achieved | •As of December 31, 2020, five ventilators, 20 (10L) units of Oxygen Concentrator and 5 Analyzers were delivered and distributed by UNICEF. This equipment was distributed to hospitals chosen to receive COVID-19 patients based on a distribution list provided by the MoHSPP. The installation of the equipment has been completed in all designated hospitals, and ICU staff have been trained on the equipment’s use and maintenance. Partial distribution of the procured pharmaceutical items and medical equipment was carried out jointly with the MoHSPP. •Availability of life-saving equipment and medicines during the spike of the outbreak, helped the Government limit the spread of the virus into the community, to lower rates of infection and mortality, and in turn reduced the overall strain on hospital resources nationwide. This intervention was complemented by establishment of a telehealth system to minimize direct patient contact in non-urgent situations in an attempt to minimize the spread of COVID-19 and a series of below interventions for front-line healthcare workers in infection prevention and control conducted by UNFPA: •Telehealth equipment procured, tested and handed over to National and 4 Regional RH Centers of MoHSP with 22 SRH service providers selected to maintain alternative ANC, FP and psychosocial support services. •3 temporary protocols on ANC, FP and psychosocial protection were developed by the national experts group of MoHSP that were integrated at RH facilities throughout the country. All protocols are developed based on WHO/UNFPA technical guidance notes on maternal care during Covid-19 and tested at the National RH Clinic. •Based on MoHSP Order, three cascade trainings were conducted at National and 2 Regional levels covering 91 RH service providers on application of temporary counseling protocols on AN/FP and 64 RH service providers on rendering psychosocial support services during Covid-19. •Over 60,000 leaflets along with 200 posters have already been distributed throughout the country along with awareness raising campaigns. Video PSA (public service announcement) is currently aired at National and Regional TV media resources with 152 airtimes and over 2 mln people coverage including 200,000 pregnant women and 800,000 women using modern contraceptives.
3.2 | Results: Output Level | Please include output level results achieved | • Originally, it was planned to establish 4 hotline points at the National and 3 at regional levels, however based on request of MoHSP additional hotline point was established to cover GBAO region. The choice of centers was made based on geographical locations of RH clinics to expand the coverage with alternative SRH services. 22 dedicated phone numbers along with stable Internet connection was provided for all RH clinics using telehealth system. • Three cascade trainings on provision of online SRH services based on temporary counseling protocols conducted for 91 SRH specialists along with 64 SRH service providers trained to provide psychosocial support services. • An estimated 19,400 women of reproductive age received remote online consultations of SRH and GBV related aspects provided. In view of delays caused by supply chain interruption, the telehealth services became functional in October 2020. In view on uncertaintees with further developments around pandemic, UNFPA took decision to extend the project by June 2021 with technical and financial assistance of UNFPA. • Over 60,000 leaflets along with 200 posters have already been distributed throughout the country along with awareness raising campaigns. Video PSA (public service announcement) is currently aired at National and Regional TV media resources with 152 airtimes and over 2 mln people coverage including 200,000 pregnant women and 800,000 women using modern contraceptives.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | One of the first and apparent impacts of Covid-19 is disruption in supply chains and logistics due to the lockdown measures applied throughout the world and delays with procurement and delivery of the equipment and medicines. UNFPA was able to place an order for telehealth equipment however due to shipment issues no supplier was able to guarantee swift delivery. This resulted in delayed delivery of equipment and overall launch of the telehealth system. UNICEF has procured and arranged a shipment of some medicines to Tashkent/Uzbekistan by plane and from Tashkent to Dushanbe by road. Oxygen concentrators were brought to Bishkek by plane and delivered to Dushanbe by truck. The challenges of air shipment were discussed with the UNICEF Supply Division and currently considering the options of bringing more of the supplies by road. The other factor affecting the overall project is due to deployment of health care providers towards responding to Covid-19. The national experts group established by MoHSPP for the adaptation and development of temporary counseling protocols on SRH and psychosocial assistance was also engaged in other critical interventions related to Covid-19 response. This has also delayed implementation of capacity building events. Finally, limited opportunity to present and observe project based interventions related to maintenance of telehealth equipment, development and practical test of protocols, capacity-building events, participation at various experts’ group meetings is the challenge that affects the overall project management efforts. Finally, limited opportunity to present and observe project based interventions related to maintenance of telehealth equipment, development and practical test of protocols, capacity-building events, participation at various experts’ group meetings is the challenge that affects the overall project management efforts.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The current situation with Covid-19 pandemic has shown that the impact of an epidemic on sexual and reproductive health often goes unnoticed as it does not have a direct impact rather has a long term nature that leads to indirect consequences of overloaded health care systems, interruption in care and redirected resources. To this date, it is unknown how the pandemic will affect women’s SRH needs and preferences in the long term; however it is already observed that women in Central Asian region are facing different challenges. The inability to get regular antenatal care services or preferred method of contraception, women and girls might instead go for self-care practice or use less effective traditional methods, or may discontinue contraceptive use entirely and expose themselves to maternal complications and unwanted pregnancies and abortions. Although no official statistics on the impact of Covid-19 on SRH was available in the country the regional comparative analysis of SRH statistics by districts in-between six months of 2019 and 2020 have shown significant drop down in ANC coverage (81,6% in 2019 vs 68,9% in 2020) and in Contraceptive Prevalence Rate (33,1% in 2019 vs 19,8% in 2020). Pandemic has also affected Maternal Mortality Rate in the region with an increase by 40% from 15,1 per 100,000 in 2019 to 18 per 100,000 in six months of 2020. Although there are no clear statistics on abortion, the report provides increase in abortions from 419 women in 2019 to 500 women in 2020 that used medical abortion. In addition, the official public statistics on the impact of COVID-19 pandemic on GBV is not quite clear, however provided numbers report on increased levels of violence against women. Until June 2020, 310 crimes involving domestic violence were recorded (Committee on Women and Family Affairs - CoWFA informed that it is 42 cases less than the last year, 2019, which does not add up with the 115 cases provided in the 2019) . 545 people reported cases of violence through the national hotline located at CoWFA (January - February, mid-May - June 2020), out of them 493 women and 52 men. Although not confirmed, the effects of stay-at-home orders and movement restrictions might be accounted for increased women’s exposure to violent partners. Household tensions mount and economic stresses also may play a role. These changes increase the need to reconsider country based contingency plans now including epidemiological situations such as Covid-19 pandemic. Since it will take considerable time to understand the epidemiology of Covid-19 it is reasonable now to use the long-standing model of pandemic influenzas studied for decades but not applied today. With the development of new technologies, Tajikistan should learn and apply alternative ways of providing health care services such as telehealth in order to render access to quality information and safe services for its population at times of emergencies like Covid-19. Tajikistan should also consider development of distance learning opportunities especially targeting emergency preparedness and response interventions.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The project is built on the agreed pillars of the Country COVID-19 Response Plan which was developed by multi stakeholder technical working group led by WHO as UN support to Country preparedness and response. Programmatic efforts particularly target on pillars: 2) Risk communications and community engagement, 5) Case investigation and rapid response and 7) Infection prevention and control. UNICEF collaborated with the WHO, UNFPA, GIZ, RCST and other development partners including the World Bank, KfW, SDC, MSF, AKDN, ADB, and IsDB who are supporting the MoHSPP in the response to COVID-19. With EU support, UNICEF aims to implement an Infection Prevention and Control Project, part of the immediate response to COVID-19, that also includes the provision of PPE and ventilators. Through the financial support from SDC, UNICEF has provided the MoHSPP with PPE and hygiene-related supplies, and also built the capacity of health workers on COVID-19 management and risk communication. To ensure proper and prompt distribution of procured supplies and that supply reach the intended end users, UNICEF established a monitoring mechanism through a cooperation agreement with “the Tajik Red Crescent Society” and a contractual agreement with “Z-Analytics” (a local company). Red Crescent Society and Z-Analytics experts have been monitoring supplies procured with EU and other donors’ support, including ventilators, and provided timely feedback to UNICEF to this effect. Regular phone call interviews conducted by and “Z-Analytics” confirmed that 95% of the provided ventilators were in use. Based on gaps in shortage of oxygen in the majority of hospitals by UNICEF third party monitoring established, the MoHSPP has engaged other donors for support ensure a constant oxygen supply at the hospitals. In response, the WB, KfW, ISDB and JICA have expressed their commitment in supporting the MoHSPP to establish oxygen generating stations in 47 hospitals across the country. In partnership with the Committee on Women and Family Affaires, UNFPA and MoHSPP adopted temporary counseling protocol on Psychosocial assistance and referral of survivors of GBV to the Women support rooms established in 21 maternity rooms across the country. Such Women support rooms were first established by UNFPA and expanded through the ongoing Spotlight initiative - a Joint EU-UN Initiative to Eliminate Violence against Women and Girls. Thus, the project contributes to the elimination of Sexual and Gender based violence (SGBV) by responding to the needs of women and girls and addressing the underlying causes of violence against women and girls during Covid-19 pandemic. Different MoHSPP affiliated structures such as the National Reproductive Health Center, Republican Clinical Family Medicine Center along with experts from the Academy of Health Sciences were engaged in the adaptation and development of temporary counseling protocols on SRH (ANC/FP) during Covid-19. In addition, the protocols include WHO/UNFPA technical guidance notes on maternity services during Covid-19.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Rapid assessment of impact of COVID19 on MMR in the countries of Central Asia
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | UNFPA will continue capacity building activities for service provision beyond project's implementation period.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | No budget revisions were conducted during the reporting period.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Outcome 1.1: Maintain continuity of essential health services and related supply chain for the direct public health response to the pandemic
Baseline:
Planned Target:
| 13237 |  | MOHSPP report www.covid.tj
Indicator 1.1a: Number of patients tested positive for COVID-19 with severe symptoms who receive treatment in hospital
Baseline: 0
Planned Target: 12,500
Indicator 1.1b: Number of hospitals equipped with lifesaving pharmaceutical drugs and equipment | 100 |  | UNICEF Report
Baseline: 0
Planned Target: 35
| 91 | UNFPA covered all RH facilities providing SRH/FP services to ensure services are available throughout the country | MoHSP /UNFPA report
Indicator 1.3a: # of healthcare facilities able to maintain alternate delivery of SRH services in case of COVID-19
Baseline: 0
Planned Target: 80
| Yes | Over 60,000 leaflets along with 200 posters have been distributed throughout the country along with awareness raising campaigns.
Indicator 1.3b: Education materials for pregnant women/families on SRH and basic hygiene practices
Baseline: No
Planned Target: Yes
| 64 | UNFPA covered National, Oblast and District level RH facilities to ensure referrals of clients in need of pshycosocial support services are well established throughout the country | MoHSPP/UNFPA report
Indicator 1.3c: # of health service providers trained on psychosocial services for pregnant women, women and girls subjected to violence
Baseline: 0
Planned Target: 60
Output 1.3.1: Strengthen national and local health system capacity to ensure continuity and access to SRH and GBV services for women and girls in the context of Covid-19 | 91 | UNFPA/MoHSP trained 91 RH service providers throughout the country to ensure client/service provider interaction is well established | MoHSPP/ UNFPA report
Indicator 1.3.1: # of SRH specialists trained on alternate SRH service provision in case of COVID-19 outbreak
Baseline: 0
Planned Target: 80
Indicator 1.3.2: # of hotline points established at National and Regional Levels on alternate SRH and GBV related services | 5 | Initially it was planned to establish 4 hotline points at National and Regional level RH facilities. However, based on MoHSP request additional hotline point was established in GBAO region in view of language requirements. | MoHSPP/UNFPA report
Baseline: 0
Planned Target: 4
Indicator 1.3.3: # of remote online consultations of SRH and GBV related aspects provided | 19400 | An estimated 19,400 women of reproductive age received remote online consultations of SRH and GBV related aspects provided. In view of delays caused by supply chain interruption, the telehealth services became functional in October 2020. Taking into account uncertaintees with further developments around pandemic, UNFPA took decision to extend the project by June 2021 with its own technical and financial assistance. | MoHSPP/UNFPA report
Baseline: 0
Planned Target: 93000
Indicator 1.3.4: # of women of reproductive age receive quality information on SRH and basic hygiene including related to COVID-19. | Over 1 mln. women of reproductive age | Video PSA (public service announcement) was aired at National and Regional TV media resources with 152 airtimes and over 2 mln people coverage including 200,000 pregnant women and 800,000 women using modern contraceptives | MoHSPP/UNFPA report
Baseline: 250000
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
More than 2,200 women of reproductive age have already taken advantage of the telehealth programme, which will be extended through June 2021 with technical and financial support from UNFPA. A total of 80 sexual and reproductive health service providers have been trained in the provision of alternative antenatal care, family planning and psychosocial support services following UNFPA technical guidance and WHO recommendations. This includes 22 service providers with dedicated mobile numbers and web-based applications developed for this purpose. An awareness-raising campaign including posters, leaflets and video PSAs has reached more than 2 million people in the country, including 200,000 pregnant women and 800,000 women who use modern contraceptives.
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | STRENGTHENING THE HEALTH SYSTEM IN TAJIKISTAN TO PREPARE AND RESPOND TO COVID-19 | Overall Duration (months) | 8 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-05-01
MPTF Office Project Reference Number: | 00121615 | Original End Date (dd.mm.yyyy) | 2020-12-01
Country | Tajikistan | Current End date(dd.mm.yyyy) | 2021-03-01
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF, UNFPA | National counterparts (government, private, NGOs & others) and other International Organizations | MOH&SPP, TFPA
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The COVID-19 pandemic has tested health systems globally. Tajikistan’s health system has been overwhelmed by the efforts dedicated to pandemic management and has had difficulty in provision of medicines, medical equipment and supplies, ensuring routine health services, in particular those related to sexual and reproductive health (SRH) care, including integral components such as the provision of antenatal care (ANC), family planning (FP) and psychosocial assistance as part of GBV prevention services. Addressing these immediate needs is the main objective of the “Strengthening the health system in Tajikistan to prepare and respond to COVID-19” launched in May 2020, implemented by UNICEF and UNFPA. To support national preparedness for the surge of patients amid the coronavirus pandemic, the project in consultation with the Ministry of Health and Social Protection of Population (MoHSPP) agreed on the priority list of 13 types of pharmaceutical medication and 12 kinds of equipment to procure and provide for the intensive care units of 35 hospitals selected to treat patients suffering from COVID-19. With the supply and procurement being a comparative advantage globally, the project/UNICEF played a lead role in the procurement and provision of vital supplies for healthcare facilities across the country. The procurement process was led by UNICEF through its Supply Division and local procurement mechanisms. In response to urgent request of the MoHSPP, five ventilators, 20 oxygen concentrators and 5 Analyzers have been delivered, installed in the health facilities to ensure access to life-saving health services. Tailored training sessions have been provided for health staff on how to operate this medical equipment. In total, more than 100 hospitals /primary health care facilities across the country benefited/will benefit from the procurement of essential supplies as per the approved MoHSPP’s Distribution Plan. UNFPA led introduction of the new alternative ways of service provision using telehealth technologies to minimize direct patient contact in non-urgent situations in an attempt to minimize the spread of COVID-19. Different MoHSP affiliated structures such as the National Reproductive Health Center, Republican Clinical Family Medicine Center along with experts from the Academy of Health Sciences were engaged in the adaptation and development of temporary counseling protocols on SRH (ANC/FP) during Covid-19. Adjustments to the standard ANC, FP and psychosocial support service schedules were tested so that some appointments are conducted using phone or video chat, to ensure that there is no disruption in service or breakdown in women’s maternity care. This was basically the first-time practical experience to introduce alternative ways of SRH service provision in the country.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The COVID-19 pandemic has tested health systems globally. Tajikistan’s health system has been overwhelmed by the efforts dedicated to pandemic management and has had difficulty in provision of medicines, medical equipment and supplies, ensuring routine health services, in particular those related to sexual and reproductive health (SRH) care, including integral components such as the provision of antenatal care (ANC), family planning (FP) and psychosocial assistance as part of GBV prevention services.
3.1 | Results: Outcome Level | Please include outcome level results achieved | •As of December 31, 2020, five ventilators, 20 (10L) units of Oxygen Concentrator and 5 Analyzers were delivered and distributed by UNICEF. This equipment was distributed to hospitals chosen to receive COVID-19 patients based on a distribution list provided by the MoHSPP. The installation of the equipment has been completed in all designated hospitals, and ICU staff have been trained on the equipment’s use and maintenance. Partial distribution of the procured pharmaceutical items and medical equipment was carried out jointly with the MoHSPP. •Availability of life-saving equipment and medicines during the spike of the outbreak, helped the Government limit the spread of the virus into the community, to lower rates of infection and mortality, and in turn reduced the overall strain on hospital resources nationwide. This intervention was complemented by establishment of a telehealth system to minimize direct patient contact in non-urgent situations in an attempt to minimize the spread of COVID-19 and a series of below interventions for front-line healthcare workers in infection prevention and control conducted by UNFPA: •Telehealth equipment procured, tested and handed over to National and 4 Regional RH Centers of MoHSP with 22 SRH service providers selected to maintain alternative ANC, FP and psychosocial support services. •3 temporary protocols on ANC, FP and psychosocial protection were developed by the national experts group of MoHSP that were integrated at RH facilities throughout the country. All protocols are developed based on WHO/UNFPA technical guidance notes on maternal care during Covid-19 and tested at the National RH Clinic. •Based on MoHSP Order, three cascade trainings were conducted at National and 2 Regional levels covering 91 RH service providers on application of temporary counseling protocols on AN/FP and 64 RH service providers on rendering psychosocial support services during Covid-19. •Over 60,000 leaflets along with 200 posters have already been distributed throughout the country along with awareness raising campaigns. Video PSA (public service announcement) is currently aired at National and Regional TV media resources with 152 airtimes and over 2 mln people coverage including 200,000 pregnant women and 800,000 women using modern contraceptives.
3.2 | Results: Output Level | Please include output level results achieved | • Originally, it was planned to establish 4 hotline points at the National and 3 at regional levels, however based on request of MoHSP additional hotline point was established to cover GBAO region. The choice of centers was made based on geographical locations of RH clinics to expand the coverage with alternative SRH services. 22 dedicated phone numbers along with stable Internet connection was provided for all RH clinics using telehealth system. • Three cascade trainings on provision of online SRH services based on temporary counseling protocols conducted for 91 SRH specialists along with 64 SRH service providers trained to provide psychosocial support services. • An estimated 19,400 women of reproductive age received remote online consultations of SRH and GBV related aspects provided. In view of delays caused by supply chain interruption, the telehealth services became functional in October 2020. In view on uncertaintees with further developments around pandemic, UNFPA took decision to extend the project by June 2021 with technical and financial assistance of UNFPA. • Over 60,000 leaflets along with 200 posters have already been distributed throughout the country along with awareness raising campaigns. Video PSA (public service announcement) is currently aired at National and Regional TV media resources with 152 airtimes and over 2 mln people coverage including 200,000 pregnant women and 800,000 women using modern contraceptives.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | One of the first and apparent impacts of Covid-19 is disruption in supply chains and logistics due to the lockdown measures applied throughout the world and delays with procurement and delivery of the equipment and medicines. UNFPA was able to place an order for telehealth equipment however due to shipment issues no supplier was able to guarantee swift delivery. This resulted in delayed delivery of equipment and overall launch of the telehealth system. UNICEF has procured and arranged a shipment of some medicines to Tashkent/Uzbekistan by plane and from Tashkent to Dushanbe by road. Oxygen concentrators were brought to Bishkek by plane and delivered to Dushanbe by truck. The challenges of air shipment were discussed with the UNICEF Supply Division and currently considering the options of bringing more of the supplies by road. The other factor affecting the overall project is due to deployment of health care providers towards responding to Covid-19. The national experts group established by MoHSPP for the adaptation and development of temporary counseling protocols on SRH and psychosocial assistance was also engaged in other critical interventions related to Covid-19 response. This has also delayed implementation of capacity building events. Finally, limited opportunity to present and observe project based interventions related to maintenance of telehealth equipment, development and practical test of protocols, capacity-building events, participation at various experts’ group meetings is the challenge that affects the overall project management efforts. Finally, limited opportunity to present and observe project based interventions related to maintenance of telehealth equipment, development and practical test of protocols, capacity-building events, participation at various experts’ group meetings is the challenge that affects the overall project management efforts.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The current situation with Covid-19 pandemic has shown that the impact of an epidemic on sexual and reproductive health often goes unnoticed as it does not have a direct impact rather has a long term nature that leads to indirect consequences of overloaded health care systems, interruption in care and redirected resources. To this date, it is unknown how the pandemic will affect women’s SRH needs and preferences in the long term; however it is already observed that women in Central Asian region are facing different challenges. The inability to get regular antenatal care services or preferred method of contraception, women and girls might instead go for self-care practice or use less effective traditional methods, or may discontinue contraceptive use entirely and expose themselves to maternal complications and unwanted pregnancies and abortions. Although no official statistics on the impact of Covid-19 on SRH was available in the country the regional comparative analysis of SRH statistics by districts in-between six months of 2019 and 2020 have shown significant drop down in ANC coverage (81,6% in 2019 vs 68,9% in 2020) and in Contraceptive Prevalence Rate (33,1% in 2019 vs 19,8% in 2020). Pandemic has also affected Maternal Mortality Rate in the region with an increase by 40% from 15,1 per 100,000 in 2019 to 18 per 100,000 in six months of 2020. Although there are no clear statistics on abortion, the report provides increase in abortions from 419 women in 2019 to 500 women in 2020 that used medical abortion. In addition, the official public statistics on the impact of COVID-19 pandemic on GBV is not quite clear, however provided numbers report on increased levels of violence against women. Until June 2020, 310 crimes involving domestic violence were recorded (Committee on Women and Family Affairs - CoWFA informed that it is 42 cases less than the last year, 2019, which does not add up with the 115 cases provided in the 2019) . 545 people reported cases of violence through the national hotline located at CoWFA (January - February, mid-May - June 2020), out of them 493 women and 52 men. Although not confirmed, the effects of stay-at-home orders and movement restrictions might be accounted for increased women’s exposure to violent partners. Household tensions mount and economic stresses also may play a role. These changes increase the need to reconsider country based contingency plans now including epidemiological situations such as Covid-19 pandemic. Since it will take considerable time to understand the epidemiology of Covid-19 it is reasonable now to use the long-standing model of pandemic influenzas studied for decades but not applied today. With the development of new technologies, Tajikistan should learn and apply alternative ways of providing health care services such as telehealth in order to render access to quality information and safe services for its population at times of emergencies like Covid-19. Tajikistan should also consider development of distance learning opportunities especially targeting emergency preparedness and response interventions.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The project is built on the agreed pillars of the Country COVID-19 Response Plan which was developed by multi stakeholder technical working group led by WHO as UN support to Country preparedness and response. Programmatic efforts particularly target on pillars: 2) Risk communications and community engagement, 5) Case investigation and rapid response and 7) Infection prevention and control. UNICEF collaborated with the WHO, UNFPA, GIZ, RCST and other development partners including the World Bank, KfW, SDC, MSF, AKDN, ADB, and IsDB who are supporting the MoHSPP in the response to COVID-19. With EU support, UNICEF aims to implement an Infection Prevention and Control Project, part of the immediate response to COVID-19, that also includes the provision of PPE and ventilators. Through the financial support from SDC, UNICEF has provided the MoHSPP with PPE and hygiene-related supplies, and also built the capacity of health workers on COVID-19 management and risk communication. To ensure proper and prompt distribution of procured supplies and that supply reach the intended end users, UNICEF established a monitoring mechanism through a cooperation agreement with “the Tajik Red Crescent Society” and a contractual agreement with “Z-Analytics” (a local company). Red Crescent Society and Z-Analytics experts have been monitoring supplies procured with EU and other donors’ support, including ventilators, and provided timely feedback to UNICEF to this effect. Regular phone call interviews conducted by and “Z-Analytics” confirmed that 95% of the provided ventilators were in use. Based on gaps in shortage of oxygen in the majority of hospitals by UNICEF third party monitoring established, the MoHSPP has engaged other donors for support ensure a constant oxygen supply at the hospitals. In response, the WB, KfW, ISDB and JICA have expressed their commitment in supporting the MoHSPP to establish oxygen generating stations in 47 hospitals across the country. In partnership with the Committee on Women and Family Affaires, UNFPA and MoHSPP adopted temporary counseling protocol on Psychosocial assistance and referral of survivors of GBV to the Women support rooms established in 21 maternity rooms across the country. Such Women support rooms were first established by UNFPA and expanded through the ongoing Spotlight initiative - a Joint EU-UN Initiative to Eliminate Violence against Women and Girls. Thus, the project contributes to the elimination of Sexual and Gender based violence (SGBV) by responding to the needs of women and girls and addressing the underlying causes of violence against women and girls during Covid-19 pandemic. Different MoHSPP affiliated structures such as the National Reproductive Health Center, Republican Clinical Family Medicine Center along with experts from the Academy of Health Sciences were engaged in the adaptation and development of temporary counseling protocols on SRH (ANC/FP) during Covid-19. In addition, the protocols include WHO/UNFPA technical guidance notes on maternity services during Covid-19.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Rapid assessment of impact of COVID19 on MMR in the countries of Central Asia
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | UNFPA will continue capacity building activities for service provision beyond project's implementation period.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | No budget revisions were conducted during the reporting period.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Outcome 1.1: Maintain continuity of essential health services and related supply chain for the direct public health response to the pandemic
Baseline:
Planned Target:
| 13237 |  | MOHSPP report www.covid.tj
Indicator 1.1a: Number of patients tested positive for COVID-19 with severe symptoms who receive treatment in hospital
Baseline: 0
Planned Target: 12,500
Indicator 1.1b: Number of hospitals equipped with lifesaving pharmaceutical drugs and equipment | 100 |  | UNICEF Report
Baseline: 0
Planned Target: 35
UNFPA covered all RH facilities providing SRH/FP services to ensure services are available throughout the country
| 91 |  | MoHSP /UNFPA report
Indicator 1.3a: # of healthcare facilities able to maintain alternate delivery of SRH services in case of COVID-19
Baseline: 0
Planned Target: 80
| Yes | Over 60,000 leaflets along with 200 posters have been distributed throughout the country along with awareness raising campaigns.
Indicator 1.3b: Education materials for pregnant women/families on SRH and basic hygiene practices
Baseline: No
Planned Target: Yes
| 64 | UNFPA covered National, Oblast and District level RH facilities to ensure referrals of clients in need of pshycosocial support services are well established throughout the country | MoHSPP/UNFPA report
Indicator 1.3c: # of health service providers trained on psychosocial services for pregnant women, women and girls subjected to violence
Baseline: 0
Planned Target: 60
Output 1.3.1: Strengthen national and local health system capacity to ensure continuity and access to SRH and GBV services for women and girls in the context of Covid-19 | 91 | UNFPA/MoHSP trained 91 RH service providers throughout the country to ensure client/service provider interaction is well established | MoHSPP/ UNFPA report
Indicator 1.3.1: # of SRH specialists trained on alternate SRH service provision in case of COVID-19 outbreak
Baseline: 0
Planned Target: 80
Indicator 1.3.2: # of hotline points established at National and Regional Levels on alternate SRH and GBV related services | 5 | Initially it was planned to establish 4 hotline points at National and Regional level RH facilities. However, based on MoHSP request additional hotline point was established in GBAO region in view of language requirements. | MoHSPP/UNFPA report
Baseline: 0
Planned Target: 4
Indicator 1.3.3: # of remote online consultations of SRH and GBV related aspects provided | 40780 | An estimated 40,780 women of reproductive age received remote online consultations of SRH and GBV related aspects from when the telehealth system was launched in Oct 2020 until 31 March 2021. UNFPA will continue to invest technical and financial assistane into the remote service provision until end of June 2021 and even further if it will be possible to reach the original targeted number of individuals. Due to the delay in procuring the telehealth hardware the system was only functional in October 2020 and not already during the summer of 2020 as originally planned. | MoHSPP/UNFPA report
Baseline: 0
Planned Target: 93000
Indicator 1.3.4: # of women of reproductive age receive quality information on SRH and basic hygiene including related to COVID-19. | Over 1 mln. women of reproductive age | Video PSA (public service announcement) was aired at National and Regional TV media resources with 152 airtimes and over 2 mln people coverage including 200,000 pregnant women and 800,000 women using modern contraceptives | MoHSPP/UNFPA report
Baseline: 250000
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Please see the annual report - all the same results.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board