## OVERALL REPORTING INSTRUCTIONS (hidden)
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual (hidden)
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual (hidden)
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | 8002 direct beneficiaries reached with the immediate supplies (e.g. food and sanitizers) in response to the COVID -19 pandemic situation. Roma- 923; transnistria region-1800 women leaving with HIV- 3145; elderly- 1626; women with disability- 108; survivors of domestic violence- 295; volunteers - 265;service providers- 505. 707 Indirect beneficiaries - roma 462; transnistria region -179; women with disability- 25;survivors of domestic violence -41. About 34 NGOs working withte vulnerable groups and involved in teh distribution of the suplies to the beneficiaries also benefited from PPE.
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved | 7939 vulnerable and marginalized women, young girls and their dependents accesse and benefit from immediate and preventive suplies, as food and hygiene package. Roma- 923; transnistria region-1800 women leaving with HIV- 3145; elderly- 1626; women with disability- 108; survivors of domestic violence- 336.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | International procurement of PPE was influenced negatively by the increased market price to all PPE and additional changes were made in the number of PPE procured for Moldova. An additional challenge was the extremely limited transportation routes to ensure timely provision of PPE from China. Hence, there are considerable freight charges incurred, funds that would have ordinarily been used for procuring additional PPEs. In addition, having in mind the “leaving no one behind” principle, the provided support by UN Women aimed to cover the most in need women out of women from vulnerable groups. Local NGOs working in the field of women’s rights and rights of people from vulnerable groups provided relevant support to identify the potential beneficiaries and their needs. Due to difficult socio-economic situation encountered by direct beneficiaries, the project had limitations when it comes to respond fully to the identified needs. Thus, only primary needs, like food, PPEs and hygienic and cleaning products could be delivered to beneficiaries, although the requests were covering the products like clothes as well. The relevant explanation related to limitations to cover other requirements, as clothes, was provided to beneficiaries and the NGOs. Besides this, although the initial target related to number of vulnerable women, girls including their dependents receiving immediate and preventive supplies (food package, sanitizers, etc.) was achieved and there were selected only the most in need people, the project couldn’t cover all the potential beneficiaries who were be identified and who would require support. In this respect, due to envisaged money savings after the finalization of the delivery, UN Women initiated the identification of additional beneficiaries to be covered. At this stage the instructions and templates were shared with the NGO helping in outreach work which save the time and the process of data collection on needs. The envisioned risk related to the delayed distribution of items to the final beneficiaries has a high impact at the beginning of transportation to the Transnistria region due to the long-lasting check procedures at the cross-river points. After the issues was brought at High level discussion a solution was identified as “red corridor” for the supplies under COVID 19 related support.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Implementing the planned procurement and programmatic actions during the emergency meant that partnerships had to be managed effectively and timely so as to ensure the achievement of planned results and positively impact the targeted communities. What has worked particularly well, which can potentially inform similar responses, are the following:  Make use of flexible programming strategies and tools during humanitarian/emergency situations. UNICEF was able to make adjustments to existing workplans with the government entities and CSOs to modify planned actions, redirect funds and revise timelines rather quickly, taking advantage of the flexible partnership modalities in times of emergencies. The ability to adapt and quickly adjust to new reality is key for the UN system as a whole, in order to be effective in fulfilling our mandate.  Embed contingency planning and programming in standard programme documents with partners. These contingency provisions could be activated rather quickly at the onset of a crisis, and they can prove essential under tight deadlines and in a resource constrained environment. The absence of these provisions delays the implementation process and subsequently can add to the cost.  Coordination with development partners, government entities and CSOs is a sine-qua-non for the success of any humanitarian operation, including the activities funded through the MPTF. All three implementing agencies under this MPTF funding have a solid track record of setting up, managing and coordinating multisectoral and multilevel partnerships. Furthermore, under the coordination of the Resident Coordinator, thematic task force groups within the UN system, donor coordination meetings and the government line ministries’ coordination mechanisms were very effective in ensuing timely identification of needs, quantity of supplies, most vulnerable communities, and distribution modalities. Timely and careful planning is essential if we’re to ensure that support reaches the most vulnerable communities on the left back of the Nistru river, a key objective of the project. Communication with beneficiaries and with NGOs, especially with NGO partners, is essential in terms of providing information about the needs to be covered and the selection of beneficiaries. Visibility serves not only to provide information about the project and the achieved results, but also is a tool to prove that the support achieved its primary objective. In the process of the procurement of the relevant support, UN Women emphasized the importance to support the local service providers and vendors. In this respect, one on the most important selection criteria of the vendors to provide PPEs, cleaning and hygienic products, served the fact that they are local manufacturers and retailers, especially if they are managed/owned by women, which is an important support to women affected by the economic consequences of the COVID-19 pandemic.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UN Women in partnerships with local NGOs with work experience in gender equality field and/or working with people from underrepresented groups, in order to provide support in identification of the beneficiaries and their primary needs. Thus, before deciding on the type and quantity of support to be procured by UN Women, the partners submitted lists with information about the number of beneficiaries and types of required aid to be distributed. Also, NGOs and local volunteers were involved in ensuring the delivery of goods to the beneficiaries. Having in mind the logistical aspects necessary to reach beneficiaries from across the country, UN Women signed two contracts with two NGOs, one of them being from the left bank of river Dniester, to provide support in delivery the aid directly to beneficiaries- multidisciplinary teams and Roma population from the norther districts of Moldova and to beneficiaries from the Transnistrian Region. Within the Roma communities the role of Roma community mediators plays important role in coordination with the local authorities the distributions of the packages to the most in needs members of the community.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Due to some savings created after the first procurements of food and prortection products due to some facilities offrered by retailers and voluntary support UN Women manage to have a second procurement lots and covered more than 7000 women and girls and their dependents (initially targeted 3500)
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | In the process of the procurement of the relevant support, UN Women emphasized the importance to support the local service providers and vendors. In this respect, one on the most important selection criteria of the vendors to provide PPEs, cleaning and hygienic products, served the fact that they are local manufacturers and retailers, especially if they are managed/owned by women, which is an important support to women affected by the economic consequences of the COVID-19 pandemic.

## Communication-Annual (hidden)
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | STRENGTHENING THE REPUBLIC OF MOLDOVA’S NATIONAL RESPONSE TO THE COVID-19 CRISIS | Overall Duration (months) | MAY to NOVEMBER 2020
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-05-01
MPTF Office Project Reference Number: | 00121444 | Original End Date (dd.mm.yyyy) | 2020-11-01
Country | Republic of Moldova | Current End date(dd.mm.yyyy) | 2020-11-01
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN Moldova: UNICEF, UN Women, IOM | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health, Labour and Social Protection, General Inspectorate for Border Police, Department of Penitentiary Institution NGOs
Report Cleared By
o Name: | Laura Fiorotto
o Title: | RCO Moldova Team Leader
o Email address: | laura.fiorotto@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The overall objective of the project was to ensure effective and accessible health services for COVID-19 control in Moldova, with a focus on vulnerable groups. The objective was achieved by improving the access to personal protective equipment (PPEs) for front line workers in the health system and non-health agencies as well as provision of humanitarian support for specified critically vulnerable groups. Through the project the participating UN agencies (UNICEF, UN Women and IOM) were able to make considerable contributions to the country response to COVID-19 in the Republic of Moldova. The project managed to enhance the protection capacity of frontline workers, to improve the situation of vulnerable women in a very critical moment as well as enhance the capacities of the Border Police to better handle the infection control at the points of entry in the country. The response was focused on providing support, such as supplies, equipment and capacity building, to key frontline medical workers, police, border police, social workers and vulnerable communities, especially Roma, women from underrepresented groups, persons with disabilities, and other at-risk communities. Each participating agency was able to target specific groups of service providers, essential workers and vulnerable communities to avoid duplication, ensure coherence and maximize efficiency by leveraging existing networks and partnerships. The response was coordinated with government partners. UNICEF provided support to the national health system to strengthen its capacity for infection prevention and control. UNICEF focused primarily on ensuring the delivery of Personal Protective Equipment (PPE) to health facilities that experienced severe of essential PPE while facing continuously growing infection and hospitalization rates. In coordination with the Ministry of Health, Labor and Social Protection (MHLSP), using its global supply networks and with the support from the UNICEF Supply Division in Copenhagen, PPE were procured and delivered to all planned 58 health facilities in the country, border police facilities and all penitentiaries. IOM ensured infection control and prevention of COVID-19 at 12 Points of Entry (PoEs) into the country with the highest traffic, through updating and dissemination of PoEs-specific Standard Operating Procedures (SOPs) for detection, notification, isolation, management and referral of travelers infected with COVID-19, in full compliance with international human rights law and other relevant standards and practices. Furthermore, IOM supported the development and implementation of training curricula, and delivery of trainings to Border Police front-line staff. Additionally, IOM assessed the needs and gaps in PoE infrastructure, upgraded hygiene, water and sanitation facilities and waste management, and provided necessary supplies for screening to help prevent the spread of the disease. Finally, IOM supported the emergency response of the national institutions through production of up-to-date data and analysis, and on the numbers and profiles of the returning migrants using rapid surveying solutions. The actions implemented by UN Women were aimed at addressing the immediate needs of vulnerable women during the COVID-19 pandemic and strengthening the national and subnational efforts to sustain these interventions. A total 8709 direct beneficiaries from both banks of the river Nistru (8332 women and 377 men from vulnerable groups), 707 indirect beneficiaries, 34 NGOs and 505 members of multidisciplinary support teams were targeted by UN Women’s actions. UN Women distributed food supplies and PPE to women affected by domestic violence, women living in shelters, HIV positive women and women with disabilities. The support provided to the multidisciplinary teams, enabled the continuous provision of services to victims of domestic violence in the north of the country.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Direct beneficiaries: - Front line health workers from all the 58 health facilities that provide treatment to COVID-19 patients; - Front line border police workers - 200, (80 women,120 men); - A total of 8709 direct beneficiaries reached with the immediate supplies (e.g. food and sanitizers) in response to the COVID -19 pandemic, including: + Roma- 923; + Transnistria region residents -1800; + Women leaving with HIV- 3145; + Elderly people- 1426; + Women with disability/vulnerable- 109; + Survivors of domestic violence- 336; + Volunteers - 265; + Temporary placement/shleter in Balti - 200 people; + Service providers- 505. Indirect beneficiaries: - Patients that benefited from health services in 58 health facilities supported with PPE; - 707 beneficiaries of UN Women Programmes, including Roma (462) ;Transnistrian region residents (179); women with disabilities (25); survivors of domestic violence (41); - About 34 NGOs working with vulnerable groups and involved in the distribution of supplies to the beneficiaries also benefited from PPE for their staff; - People that crossed the border during the period May - December 2020.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The project planned outcome was to ensure effective and accessible health services for COVID-19 control in Moldova, with a focus on vulnerable groups. The project managed to make a considerable contribution to the country response to COVID-19 in the Republic of Moldova. With the support from the UN COVID-19 TF, we succeeded to enhance the capacities of health and non-health institutions in controlling the transmission of COVID-19 among frontline workers and service providers, specifically the staff at healthcare facilities involved in the COVID-19 response, social workers, NGOs working with vulnerable groups of population on both bank of the Nistru River, border police, penitentiary institutions as well as alleviation of the critical situation of vulnerable groups of population (Roma women, women with disabilities, survivors of domestic violence, women leaving with HIV, elderly etc.). The project exceeded the number of planned health facilities that were to be supported with PPEs (58 against the planned 50). However, despite this, and despite the full achievement of all output level indicators, the target to reach a COVID-19 incidence level of 20 per 100,000 population, was not achieved. This target proved to be unrealistic, and efforts to achieve it were further undermined by factors beyond the control of the implementing partners, such as the very intensive community spread of SARS-CoV-2, limited knowledge on SARS-CoV-2, limited capacities to respond to pandemic and expectations on pandemic evolving in the beginning of the COVID19 crises in Moldova and at the global level.
3.2 | Results: Output Level | Please include output level results achieved | Output 1. Enhance the capacity of the National System to protect front line workers during the COVID-19 pandemic and provide health care to all COVID-19 patients The capacity for immediate protection of the frontline workers was considerably enhanced through efficient international procurement and distribution of PPEs to health care facilities, Border Police and penitentiary institutions: Surgical masks -252,000; Masks N95 - 98,400; Face shields- 34,500; aprons/gowns-20,198; gloves- 1,050,000; thermometers- 100. Additionally, the project procured locally and delivered PPEs to Border Police staff: Coverall - 1,000; Gowns - 2,000; Thermo-scanners - 2 Output 2. Assist most vulnerable populations by providing immediate and preventive supplies to women from underrepresented groups The project provided immediate humanitarian support to vulnerable women in a very critical moment. In this context, 8709 vulnerable and marginalized women, young girls and their dependents accessed and benefited from immediate and preventive supplies, as food and hygiene package. Roma- 923; Transnistria region-1800 women leaving with HIV- 3145; elderly- 1426; women with disability- 108; survivors of domestic violence- 336. In the gross, over 41 tons of products were efficiently procured and delivered to beneficiaries across the country, including to 70 multidisciplinary teams providing social services to people from vulnerable groups. Output 3. Improved readiness and response measures at Moldova’s points of entry. The project contributed considerably to the consolidation of capacity of the Border Police to better handle the infection control at the Points of Entry (PoEs). The project supported the assessment of the WASH and Isolation infrastructure, facilities and equipment at 12 Moldovan Points of Entry. To address the need for basic WASH supplies and equipment, the following supplies have been procured and distributed for the 12 PoEs: 2000 liters of disinfectant solution; 8 thermal scanners; 12 UVC Germicidal lamps; 5 nebulizers, 7 back-pack sprayers; 10 Bio trash bins and 23 Automatic/non-contact hand sanitizer dispensers; 30 Mini Safe Step Carpets; 35 liters Biocidal solution, Lysoformin 3000; 10 Table water coolers and 30 water bottles have been procured; 16,750 masks. PoE-specific SOPs for detection, notification, isolation, management and referral of travelers with COVID-19 infection were updated and developed by IOM. Over 200 Border front line staff have been trained on the usage of updated PoE SOPs, and 500 brochures were provided in three languages (Romanian, Russian and English) to all frontline border police staff. Almost all the 200 suspected cases (70 migrants, 70 asylum seekers and 60 border police front line staff), were referred for COVID-19 testing. Additionally, IOM Moldova implemented a Displacement Tracking Matrix (DTM) assessment through comprehensive surveying of returning migrants and their host communities.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | International procurement of PPEs was influenced negatively by the increased market price of all PPEs, requiring the revision and adjustment of the numbers of planned PPE to be procured for Moldova. An additional challenge were the very limited options for transportation routes to ensure timely provision of PPEs from China due to disruptions on quarantine. Hence, considerable additional freight charges were incurred, funds that would have ordinarily been used for procuring additional PPEs. In accordance with the “leave no one behind” principle, the support provided by UN aimed to cover the most-in-need women from within the group of vulnerable women. Local NGOs working in the field of women’s rights and rights of people from vulnerable groups helped identify the potential beneficiaries and their needs. Due to the extremely difficult socio-economic situation encountered by the beneficiaries, the project had limitations when it came to respond fully to the identified needs. Thus, only primary needs, like food, PPEs and hygiene and cleaning products could be delivered to beneficiaries, although the requests included items like clothing as well. These challenges were explained to the beneficiaries by the NGO partners. The project incurred savings that were channeled to support additional beneficiaries that were identified subsequently, thus additional procurement processes were conducted. Finally, the envisioned risk related to possible delays in the distribution of items to the final beneficiaries in the Transnistrian region (breakaway enclave) due to the long and complex checks at the river cross-points had a negative impact on the timing. To settle the project brought the issue to the attention of the authorities and a high-level agreement was concluded to institute a “red corridor” for the supplies under COVID 19 related support.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Implementing the planned procurements and programmatic actions during the emergency meant that partnerships and logistics had to be managed effectively and timely established, so as to ensure the achievement of planned results and positively impact the targeted communities in time. Several approaches worked particularly well and can potentially inform similar situations in the future: 1) Make use of flexible programming strategies and tools during humanitarian/emergency situations. UNICEF was able to make adjustments to existing workplans with the government entities and CSOs to modify planned actions, redirect funds and revise timelines rather quickly, taking advantage of the flexible partnership modalities in times of emergencies. The ability to adapt and quickly adjust to new reality is key for the UN system, in order to be effective in fulfilling our mandate. 2) Embed contingency planning and programming in standard programme documents with partners. These contingency provisions could be activated rather quickly at the onset of a crisis, and they can prove essential under tight deadlines and in a resource constrained environment. The absence of these provisions delays the implementation process and subsequently can add to the cost. 3) Coordination with development partners, government entities and CSOs is a sine-qua-non for the success of any humanitarian operation, including the activities funded through this specific MPTF. All three implementing agencies under this MPTF funding have a solid track record of setting up, managing and coordinating multisectoral and multilevel partnerships. Furthermore, under the coordination of the Resident Coordinator, thematic task force groups within the UN system, donor coordination meetings and the government line ministries’ coordination mechanisms were very effective in ensuing timely identification of needs, quantity of supplies, most vulnerable communities, and distribution modalities. 4) Timely and careful planning is essential if we’re to ensure that support reaches the most vulnerable communities on the left back of the Nistru river, a key objective of the project. 5) Communication with beneficiaries and with NGOs, especially with NGO partners, is essential in terms of providing information about the needs to be covered and the selection of beneficiaries. Visibility serves not only to provide information about the project and the achieved results, but also is a tool to prove that the support achieved its primary objective. 6) In the process of the procurement of the relevant support, UN Women emphasized the importance to support the local service providers and vendors. In this respect, one on the most important selection criteria of the vendors to provide PPEs, cleaning and hygienic products, was that they are local manufacturers and retailers, especially if they are managed/owned by women, which is an important support to women affected by the economic consequences of the COVID-19 pandemic. 7) Coordination with other UN Agencies (OHCHR and UNODC in particular) to better identify and target the most vulnerable groups and those that are exposed the most in those circumstances proved to be a very good practice. UN Agencies have a wealth of knowledge that could easily be accessed on the situation of various groups, channels to target them and get access so that the support is delivered in the most inclusive way and to those who need it most.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UNICEF worked closely with the Ministry of Health, Labor and Social Protection (MHLSP), Border Police and the Department of Penitentiary Institutions to identify the needs and ensure proper distribution of the supplies. In addition, UNICEF advocated at the level of MHLSP (the main recipient of PPE) for the distribution of PPE to front line workers from non-medical entities that were in greatest need (police, border police and workers in penitentiaries). As a result, 10% out of internationally procured PPEs were distributed to Border Police and Department of Penitentiary Institutions. In addition, the MPTF funding helped catalyze additional funds for WASH supplies and other non-PPE supplies (education kits, school equipment) for the most vulnerable communities. Namely, based on needs assessments and successful partnerships leveraged within the MPTF grant, USAID increased its original grant to UNICEF by an additional $US 1 million, to support the procurement of WASH and hygiene products to all education institutions and facilities, as well as health facilities in the country, reaching over 470,000 beneficiaries. These products were accompanied by communication materials and capacity building, which complemented all PPE procurement under the MPTF grant. UN Women worked in close partnership with local NGOs with work experience in the field of gender equality, or working with people from underrepresented groups, in order to identify beneficiaries and their primary needs. Thus, before deciding on the type and quantity of support to be procured by UN Women, the partners submitted lists with information about the number of beneficiaries and types of required aid to be distributed. Also, NGOs and local volunteers were involved in ensuring the delivery of goods to the beneficiaries. Having in mind the logistical aspects necessary to reach beneficiaries from across the country, UN Women signed two contracts with two NGOs, one of them being from the left bank of river Dniester, to provide support in delivery the aid directly to beneficiaries- multidisciplinary teams and the Roma population from the northern districts of Moldova and to beneficiaries from the Transnistrian Region. Within the Roma communities the role of Roma community mediators played an important role in coordination with the local authorities the distribution of packages to the most in need members of the community. The General Inspectorate of the Border Police (GIBP) as IOM’s key partner, has been instrumental in the implementation of all activities such as: involvement in all aspects of the program according to their mandate, setting-up of the necessary administrative and formal arrangements, coordination and cooperation between relevant GIBP personnel to facilitate timely and efficient implementation of project activities, approval of the relevant project implementation instruments, and provision of access to all necessary information and resources. The GIBP and IOM provided technical advisory services in developing and implementing the envisaged activities. UN Women worked in partnership with local networks of NGOs (Gender Equality Platform, Human Rights Task Force, Roma Women and Girls network), NGO Artemita, Zdorovie, Participation.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | IOM Moldova Assessment Report on Water Supply, Sanitation, Hygiene and Insolation infrastructure, facilities and equipment present at Moldovan Border Crossing Points in the context of COVID-19 outbreak
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | As a result of savings incurred after the initial procurements of food and protection supplies resulting from discounts offered by retailers and volunteer support, UN Women was able to conduct an additional procurement covering more than 7000 women and girls and their dependents (in addition to the initially targeted 3500) that received supplies.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | In the process of the procurement of the relevant support, UN Women emphasized the importance to support the local service providers and vendors. In this respect, one on the most important selection criteria of the vendors to provide PPEs, cleaning and hygienic products, was that they are local manufacturers and retailers, especially targeting those that are managed/owned by women, which is an important support to women negatively affected by the economic impact of the COVID-19 pandemic.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1.1 Improved capacities of the healthcare system and other relevant authorities and stakeholders in Moldova to provide a rapid response to the needs of the population during the COVID-19 pandemic
Indicator:1.1a # of supported COVID-19 healthcare facilities improved capacity for infection control and prevention | Staff from 58 medical care facilities were covered with PPE for IPC | Outcome 1 indicator 1.1.a' results exceeded the proposed targets and PPE was distributed to 58 health facilities, as per MHLSP adjusted needs | Reception notes, communications with the MHLSP, MHLSP orders on PPE distribution
Baseline: 2
Planned Target: 50
Indicator:1.1b # of new COVID-19 infections per 100,000 uninfected population, by sex, age and key populations | Crude Cumulative Incidence: 3,786.8 per 100,000 population Last 14 days Incidence: 168.3 per 100,000 population (-35%) Last 7 days Incidence: 85.3 per 100,000 population (+3%) | The planned target to reach a COVID19 incidence level of 20 per 100,000 population, was not achieved. This target proved to be unrealistic, and efforts to achieve it were further undermined by factors beyond the control of the implementing partners, such as the very intensive community spread of SARS-CoV-2, limited knowledge on SARS-CoV-2, limited capacities to respond to pandemic and expectations on pandemic evolving in the beginning of the COVID19 crises in Moldova and at the global level.. | WHO European Region, 20 January 2021
Baseline: 88
Planned Target: ~20
Output 1.1 Healthcare facilities staff and non-health front line workers provided with Personal Protective Equipment (PPE) for infection control, prevention and case management.
Indicator 1.1.1: # Personal Protective Equipment (PPE) for infection control and prevention procured for health facilities staff, police, penitentiaries, border police staff, and health facilities staff in Transnistria Region. | In total 933,098 units of PPE were procured: Surgical masks -252,000 Masks N95 - 98,400 Face shields- 34,500 aprons/gowns-22,198 Coverall - 1,000 gloves- 1,050,000 (525,000 pairs) thermometers- 100 thermo scanners - 2 | Output 1.1 indicator target was exceeded | Reception notes, MHLSP’ orders on PPE distribution
Baseline: 40,320
Planned Target: 250,000
Output 1.2 Vulnerable and marginalized women, young girls and their dependents access and benefit from immediate and preventive supplies during the country lockdown.
Indicator 1.2.1:vulnerable women, girls including their dependents receiving immediate and preventive supplies (food package, sanitizers, etc.), by groups of vulnerability | 7939 vulnerable and marginalized women, young girls and their dependents accessed and benefit from immediate and preventive supplies, as food and hygiene package. Roma- 923; Transnistria region-1800 women leaving with HIV- 3145; elderly- 1626; women with disability- 108; survivors of domestic violence- 336 | As a result of savings incurred after the initial procurements of food and protection supplies stemming from rebates offered by retailers and volunteer support, UN Women was able to initiate an additional procurement covering more than 7000 women and girls and their dependents (in addition to the initially targeted 3500) . Based on consultations with NGOs working with women from various underrepresented and vulnerable groups, as those living with HIV, sex workers, drug users, elderly, survivors of violence, UN Women was able to identify additopnal 1900 women from these categories, including from the left bank of the Nistru river. | UN Women, implementing partners reports
Baseline: 250 Planned Target: 3500
Indicator 1.2.2: #of members of the MDTs- equipped with personal protective equipment (social workers and social assistants is the baseline) | 500 members of 70 multidisciplinary teams from 6 districts (Ocnita, Telenesti, Drochia, Glodeni, Rascani, Donduseni) | n/a | UN Women, implementing partners reports
Baseline:3279
Planned Target: 500
Output 1.1.3 National health-related emergency response at points of entry is enhanced, including through the upgrading of border infrastructure
Indicator 1.1.3 a: # SOPs up-dated | The PoE-specific Standard Operating Procedures (SOPs) document, for detection, notification, isolation, management and referral of sick travelers with COVID-19 infection, has been updated and developed by IOM. Available instructions, working steps, necessary forms and responsibilities to ensure detection and management of persons with suspected COVID – 19 infection. Assessment of the Water Supply, Sanitation, Hygiene and Isolation infrastructure, facilities and equipment present at 12 (twelve) target PoEs (air, railway, river and road border crossings) was conducted The 12 PoEs received 2000 liters of disinfectant solution, 8 thermoscanners, 12 UVC Germicidal lamps, 5 nebulizers, 7 back-pack sprayers, 10 Bio trash bins and 23 Automatic/non-contact hand sanitizer dispensers, 30 Mini Safe Step Carpets, 35 liters Biocidal solution, Lysoformin 3000, 10 Table water coolers and 30 water bottles have been procured |  | IOM reports
Baseline: 0 Planned Target: 1
Indicator 1.1.3 b:
# existence of a training curricula on the use of the up-dated SOPs and other relevant topics; | Training course on the use of the updated SOPs has been updated and developed; |  | Available online information on the use of PoE SOP
Baseline: 0
Planned Target:1
# of copies of the printed SOPs and training curricula; | 500 copies of PoE SOP have been printed in three languages RO, RU and ENG and distributed among border police front line staff |  | PoE SOP document available as hard copies and online on e-learning platform of GIBP
Baseline: 0
Planned Target: 250
# of front-line border police staff who receive training by a commissioned expert on the use of the up-dated SOPs and other relevant topics for Front-line Border Officials at the PoEs in Response to COVID-19 Outbreak | 200 border police front-line staff benefited out of 4 online trainings on the use of the updated PoE SOPs in response to COVID-19 outbreak |  | e-learning platform of GIBP; PPT presentation
Baseline: 0
Planned Target: 200
Indicator 1.1.3 c: # of returned migrants who benefit from enhanced access to disease prevention services and efficient health screening; | 764,380 individuals benefited from the health screening at the POEs, out of which 200 suspected cases (60 border police front-line staff, 70 migrants and 70 asylum seekers) have been referred to COVID-19 testing |  | GIBP statistical reports, Referral letters; Service agreements
Baseline: 0
Planned Target: 10000
Indicator 1.1.3 d: Existence of enhanced and up-to-date gender disaggregated data on the numbers and profiles of the returning migrants | Displacement Tracking Matrix assessment executed through comprehensive surveying of returning migrants and their host communities. A report developed on the mobility-driven impact of COVID-19, numbers and profiles of the returning migrants as well as specific vulnerabilities of groups affected by the decrease of remittances containing an overview and analysis of the initial findings drafted and submitted.
Baseline: No up-to date gender disaggregated data on the numbers and profiles of the returning migrants Planned Target: Available up-to date gender disaggregated data on the numbers and profiles of the returning migrants |  |  | Report on the mobility-driven impact of COVID-19, based on the executed Displacement Tracking Matrix assessment.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Pictures and videos uploaded
Human Story:
https://moldova.unwomen.org/en/noutati-si-evenimente/noutati/2020/06/mptf
https://www.investigatii.md/ro/investigatii/drepturile-copilului/reportaj-multimedia-copiii-care-dau-lectii-de-curaj-medicilor-in-pandemie
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
All Pictures and Videos uploaded to Sharepoint

## RBM-Annual (hidden)
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification | PUNO in charge
Outcome 1[1]
Improved capacities of the healthcare system and other relevant authorities and stakeholders in Moldova to provide a rapid response to the needs of the population during the COVID-19 pandemic' | Staff from 58 medical care facilities and Border Police and Penitentiary institution benefited out of PPE for infection prevention and control
Indicator: 1.1a # of supported COVID-19 healthcare facilities improved capacity for infection control and prevention | 58 |  | Reception notes, communications with the MHLSP | UNICEF
Baseline: 2
Planned Target: 50
Indicator: 1.1b # Number of new COVID-19 infections per 100,000 uninfected population, by sex, age and key populations | 14 days incidence 155.5/100,000 population, Crude Cumulative Incidence - 1,068.6 per 100,000 population |  |  | UNICEF, IOM, UN Women
Baseline: 88
Planned Target: ~20
Output 1.1.1 Healthcare facilities staff and non-health front line workers provided with Personal Protective Equipment (PPE) for infection control, prevention and case management. |  |  | Ministry of Health, Labour and Social Protection (MoHLSP)
Indicator 1.1.1: # Personal Protective Equipment (PPE) for infection control and prevention procured for health facilities staff, police, penitentiaries, border police staff, and health facilities staff in Transnistria Region. | PPE were procured through UNICEF SD in Copenhagen and were distributed to 58 health facilities, Border Police and penitentiary institutions: Surgical masks -252,000 Masks N95 - 98,400 Face shields- 34,500 aprons/gowns-20,198 gloves- 1,050,000 thermometers- 100 In addition, PPE were procured locally for Border Police staff: Coverall - 1,000 Gowns - 2,000 Thermoscaners - 2 |  |  | UNICEF
Baseline: 40320
Planned Target: 250000
Output 1.1.2 Vulnerable and marginalized women, young girls and their dependents access and benefit from immediate and preventive supplies during the country lockdown. | 7939 vulnerable and marginalized women, young girls and their dependents accesse and benefit from immediate and preventive suplies, as food and hygiene package. Roma- 923; transnistria region-1800 women leaving with HIV- 3145; elderly- 1626; women with disability- 108; survivors of domestic violence- 336. In the gross, over 41 tons of products were delivered to beneficiaries across the country, including to 70 multidisciplinary teams providing social services to people from vulnerable groups. |  | IP reports, UNW reports, delivery report | UN Women
Indicator 1.1.2 a # vulnerable women, girls including their dependents receiving immediate and preventive supplies (food package, sanitizers, etc.), by groups of vulnerability | 7502 (7125 women and 377 men) direct beneficiaries from both banks of the river Nistru, out of which 461 Roma people, 1621 beneficiaries from the Transnistrian Region and security zone, 3145 women living with HIV, sex workers and drug users; 200 people with disabilities and elderly living in Temporary placement center for people with disabilities and elderly from Balti; 83 women with disabilities from across the country; 295 survivors of domestic violence; 1427 elderly; 265 volunteers and 5 staff of public department. Within this total number 8 women with no income from ATU Gagauzia and 14 staff of NGO Vesta from ATU Gagauzia was also covered. 34 NGOs working in the field received also disinfection products. Indirect beneficiaries accounted of about 707 people. | Having been able to achieve efficiency savings during the procurement process was possible to procure additional food packs, masks gloves, hand sanitizers and sanitizing products and thermometers. Based on consultations with NGOs working with women from various underrepresented and vulnerable groups, as those living with HIV, sex workers, drug users, elderly, survivors of violence, UN Women was able to identify additional around 1900 women from this categores, including from the left bank of the Nistru river. | Solicitations submitted by NGOs, lists provided by NGOs | UN Women
Baseline: 250
Planned Target: 3500
Indicator 1.1.2 b # of members of the MDTs- equipped with personal protective equipment (social workers and social assistants is the baseline) | 500 members of 70 multidisciplinary teams from 6 localities from Ocnita district,15 localities from Telenesti district, 28 localities from Drochia district, 6 localities from Glodeni district, 11 localities from Rascani district, 4 localities from Donduseni district |  | Solicitations submitted by NGOs, lists provided by NGOs | UN Women
Baseline: 3279
Planned Target: 500
Output 1.1.3 National health-related emergency response at points of entry is enhanced, including through the upgrading of border infrastructure | The PoE-specific Standard Operating Procedures (SOPs) document, for detection, notification, isolation, management and referral of sick travelers with COVID-19 infection, has been updated and developed by IOM. Available instructions, working steps, necessary forms and responsibilities to ensure detection and management of persons with suspected COVID – 19 infection. Assessment of the Water Supply, Sanitation, Hygiene and Isolation infrastructure, facilities and equipment present at 12 (twelve) target PoEs (air, railway, river and road border crossings) was conducted The 12 PoEs received 2000 liters of disinfectant solution, 8 thermoscanners, 12 UVC Germicidal lamps, 5 nebulizers, 7 back-pack sprayers, 10 Bio trash bins and 23 Automatic/non-contact hand sanitizer dispensers, 30 Mini Safe Step Carpets, 35 liters Biocidal solution, Lysoformin 3000, 10 Table water coolers and 30 water bottles have been procured
Indicator 1.1.3 a: # SOPs up-dated;
Baseline: 0
Planned Target: 1
Indicator 1.1.3 b:
# existence of a training curricula on the use of the up-dated SOPs and other relevant topics; | Training course on the use of the updated SOPs has been updated and developed; |  | Available online information on the use of PoE SOP | IOM
Baseline: 0
Planned Target:1
# of copies of the printed SOPs and training curricula; | 500 copies of PoE SOP have been printed in three languages RO, RU and ENG and distributed among border police front line staff |  | PoE SOP document available as hard copies and online on e-learning platform of GIBP | IOM
Baseline: 0
Planned Target: 250
# of front-line border police staff who receive training by a commissioned expert on the use of the up-dated SOPs and other relevant topics for Front-line Border Officials at the PoEs in Response to COVID-19 Outbreak | 200 border police front-line staff benefited out of 4 online trainings on the use of the updated PoE SOPs in response to COVID-19 outbreak |  | e-learning platform of GIBP; PPT presentation
Baseline: 0
Planned Target: 200
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.