## Global activities
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget by recipient organization (not including staff, general operating costs and indirect fee) - IOM Liberia | Level of expenditure in USD (to provide at time of project progress reporting): IOM | Commitments/PO in USD - IOM | Level of expenditure/PO in % to date | Budget by recipient organization (not including staff, general operating costs and indirect fee) - UNDP Côte d'Ivoire | Level of expenditure in USD (to provide at time of project progress reporting): UNDP | Commitments/PO in USD - UNDP | Level of expenditure/PO in % to date | Budget by recipient organization (not including staff, general operating costs and indirect fee) - IOM Liberia | Level of expenditure in USD (to provide at time of project progress reporting): IOM | Commitments/PO in USD - IOM | Level of expenditure/PO in % to date | Budget by recipient organization (not including staff, general operating costs and indirect fee) - UNDP Liberia | Level of expenditure in USD (to provide at time of project progress reporting): UNDP | Commitments/PO in USD - UNDP | Level of expenditure/PO in % to date | Total for both countries Liberia | Both countries expenditure and committments in USD (to provide at time of project progress reporting): Côte d'Ivoire & Liberia | Both countries expenditure/PO in % to date
OUTCOME 1: Enhanced capacities for conflict prevention and level of trust between state institutions and target communities of the cross-border areas
Output 1.1: | Reduced tensions and increased promotion of social cohesion through strengthened and institutionalized civil-state collaboration mechanisms | 79500 | 13598.97 | 8549.28 | 27.86% | 112500 | 38596.67 | 0 | 34.31% | 72000 | 10000 | 19885 | 41.51% | 105740 | 51390 | 19290 | 66.84% | 369740 | 161309.92 | 43.63%
Activity 1.1.1: | Conduct a baseline study of all targeted communities and security forces on their perceptions/assessments of the levels of border security, cross-border cooperation and social cohesion; | 11500 | 11500 |  | 100% | 7500 |  |  | 0% | 10000 | 10000 |  | 100% |  |  |  |  | 29000 | 21500 | 74.14%
Activity 1.1.2: | Establish or reinforce Civil-Military Committees (CMC) for Cote d’Ivoire or County Security Council (CSC) for Liberia; | 0 |  |  |  | 50000 | 38596.67 |  | 77.19% |  |  |  |  | 35740 | 20500 |  | 57.36% | 85740 | 59096.67 | 68.93%
Activity 1.1.3: | Regularize inclusive dialogue sessions of CMCs and CSCs in respective countries and between CMCs and CSCs of mirroring communities in the two countries | 0 |  |  |  | 30000 |  |  | 0% |  |  |  |  | 70000 | 30890 | 19290 | 71.69% | 100000 | 50180 | 50.18%
Activity 1.1.4: | Reinforce the linkage to the existing early warning systems as well as their capacities to report on the issues related to cross-border area to CMCs and CSCs. | 0 |  |  |  | 25000 |  |  | 0% | [8 empty] | 25000 | 0 | 0%
Activity 1.1.5: | Organize a potential crisis simulation at the border to establish humanitarian corridors and ensure the maintenance of essential economic needs. | 68000 | 2098.97 | 8549.28 | 15.66% |  |  |  | #DIV/0! | 62000 |  | 19885 | 32.07% |  |  |  |  | 130000 | 30533.25 | 23.49%
Output 1.2: | Improved capacities of local authorities, security forces, border management officials and key government actors for border management with a view to preventing conflicts. | 338036.5405 | 49355.82 | 59591.18 | 32.23% | 40000 | 0 | 0 | 0% | 355000 | 241633.68 | 47865.56 | 81.55% | 110000 | 20942.5 | 0 | 19.04% | 843036.5405 | 419388.74 | 49.75%
Activity 1.2.1: | Conduct a capacity assessment. | 10000 | 7618.38 |  | 76.18% |  |  |  | #DIV/0! | 10000 | 10000.02 |  | 100% | 25000 | 20942.5 |  | 83.77% | 45000 | 38560.9 | 85.69%
Activity 1.2.2: | Carry out rehabilitation works in border posts providing the necessary equipment to enhance key actors’ capacities as well as to respond needs of women. | 126536.5405 | 21147.81 |  | 16.71% |  |  |  | #DIV/0! | 140000 | 120334.88 | 9375.56 | 92.65% |  |  |  |  | 266536.5405 | 150858.25 | 56.6%
Activity 1.2.3: | Provide basic skill trainings to use computers and other electronics to input and manage data. | 21500 | 2660.2 | 15566.94 | 84.78% |  |  |  | #DIV/0! | 20000 | 11400.12 | 8500 | 99.5% | 20000 |  |  | 0% | 61500 | 38127.26 | 62%
Activity 1.2.4 | Organize trainings in border management for administrative authorities, security forces/agencies and communities’ leader. | 45000 | 9708.44 | 27016.71 | 81.61% | 5750 |  |  | 0% | 47000 | 47000 |  | 100% |  |  |  |  | 97750 | 83725.15 | 85.65%
Activity 1.2.5 | Facilitate the organization and institutionalization of joint and cross-border patrols by the security agencies of both countries at the local level. | 90000 | 3413.83 | 17007.53 | 22.69% |  |  |  | #DIV/0! | 90000 | 38420 |  | 42.69% |  |  |  |  | 180000 | 58841.36 | 32.69%
Activity 1.2.6 | Organize two high-level meetings between relevant authorities of both countries. | 45000 | 4807.16 |  | 10.68% | 34250 |  |  | 0% | 48000 | 14478.66 | 29990 | 92.64% | 65000 |  |  | 0% | 192250 | 49275.82 | 25.63%
TOTAL $ FOR OUTCOME 1: |  | 417536.5405 | 62954.79 | 68140.46 |  | 152500 | 38596.67 | 0 | 25.31% | 427000 | 251633.68 | 67750.56 |  | 215740 | 72332.5 | 19290 |  | 1212776.5405 | 580698.66 | 47.88%
OUTCOME 2: Improved peaceful co-existence and social cohesion between the target communities of the cross-border areas
Output 2.1: | Strengthened conflict prevention and dispute resolution platforms for dialogue, joint problem-solving and cooperation, including women, youth and refugees, at community level | 17000 | 2390.55 | 12025.21 | 84.8% | 72036.54 | 65769.79 | 0 | 91.3% |  |  |  |  | 105000 | 52925.4 | 6671 | 56.76% | 194036.54 | 139781.95 | 72.04%
Activity 2.1.1: | Establish or consolidate the community conflict prevention and management mechanisms in the target communities. | 0 |  |  |  | 30000 | 30000 |  | 100% |  |  |  |  | 20000 | 17925.4 |  | 89.63% | 50000 | 47925.4 | 95.85%
Activity 2.1.2: | Strengthen capacities of CPPCs and CPCs to effectively mitigate disputes and conflicts in their respective communities. | 0 |  |  |  | 32036.54 | 32000 |  | 99.89% |  |  |  |  | 40000 | 20000 |  | 50% | 72036.54 | 52000 | 72.19%
Activity 2.1.3: | Facilitate the organization of CPPCs and CPCs on a quarterly basis. | 0 |  |  |  | 10000 | 3769.79 |  | 37.7% |  |  |  |  | 25000 | 15000 | 6671 | 86.68% | 35000 | 25440.79 | 72.69%
Activity 2.1.4: | Organize Joint Committee meetings between respective mirroring communities. | 17000 | 2390.55 | 12025.21 | 84.8% |  |  |  | #DIV/0! |  |  |  |  | 20000 |  |  | 0% | 37000 | 14415.76 | 38.96%
Output 2.2: | Improved social cohesion and stability among cross-border communities through joint social, cultural and economic initiatives | 140000 | 27891.37 | 104826.44 | 94.8% | 350000 | 239537.79 | 0 | 68.44% | 123062.45 | 105062.76 | 8665.12 | 92.41% | 280000 | 157261.35 | 75000 | 82.95% | 893062.45 | 718244.83 | 80.42%
Activity 2.2.1: | Provide and/or reinforce basic community infrastructure. | 100000 | 11972.85 | 72183.32 | 84.16% | 105000 | 98775 |  | 94.07% | 123062.45 | 105062.76 | 8665.12 | 92.41% | 75000 |  | 75000 | 100% | 403062.45 | 371659.05 | 92.21%
Activity 2.2.2: | Support cross-border women initiative to promote women's rights, fight against SGBV, community development, and social economic exchanges. | 0 |  |  |  | 30000 | 40100 |  | 133.7% |  |  |  |  | 20000 | 10000 |  | 50% | 50000 | 50100 | 100.2%
Activity 2.2.3: | Organize sensitization and awareness campaigns related to social cohesion of cross-border areas and elections through the ECOWAS radio broadcasts and IEC materials. | 40000 | 15918.52 | 32643.12 | 121.4% | 60000 | 20000 |  | 33.33% |  |  |  |  | 80000 | 78671.4 |  | 98.34% | 180000 | 147233.04 | 81.8%
Activity 2.2.4: | Facilitate to organize cultural, sport, and economic activities with a view to improving social cohesion. | 0 |  |  |  | 155000 | 80662.79 |  | 52.04% |  |  |  |  | 105000 | 68589.95 |  | 65.32% | 260000 | 149252.74 | 57.4%
TOTAL $ FOR OUTCOME 2: |  | 157000 | 30281.92 | 116851.65 |  | 422036.54 | 305307.58 | 0 | 72.34% | 123062.45 | 105062.76 | 8665.12 |  | 385000 | 210186.75 | 81671 |  | 1087098.99 | 858026.78 | 78.93%
TOTAL OUTCOME 1 & 2 |  | 574536.5405 | 93236.71 | 184992.11 |  | 574536.54 | 343904.25 | 0 | 59.86% | 550062.45 | 356696.44 | 76415.68 |  | 600740 | 282519.25 | 100961 |  | 2299875.5305 | 1438725.44 | 62.56%
Project personnel costs if not included in activities above |  | 103416.576 | 83449.37 |  | 80.69% | 68944.38 | 17749.74 |  | 25.75% | 86180.48 | 50394.83 |  | 58.48% | 86180.48 | 56032.86 |  | 65.02% | 344721.916 | 207626.8 | 60.23%
Project operational costs if not included in activities above | [6 empty] | 68659.39 |  | #DIV/0! | [8 empty] | 0 | 68659.39 | #DIV/0!
Project M&E budget |  | 48261.072 |  |  | 0% | 32174.05 | 20000 |  | 62.16% | 36654.27 | 5520 | 2025 | 20.58% | 42051.48 | 27705.39 |  | 65.88% | 159140.872 | 55250.39 | 34.72%
SUB-TOTAL PROJECT BUDGET: |  | 726214.1885 | 176686.08 | 184992.11 |  | 675654.97 | 450313.38 | 0 | 66.65% | 672897.2 | 412611.27 | 78440.68 |  | 728971.96 | 366257.5 | 100961 |  | 2803738.3185 | 1770262.02 | 63.14%
Indirect support costs (7%): |  | 50834.9932 | 11721.43 | 12949.41 | 48.53% | 47295.85 | 24474.8798 |  | 51.75% | 47102.804 | 16215.9739 | 5490.84 |  | 51028.0372 | 32705.25 | 0 | 64.09% | 196261.6844 | 103557.7837 | 52.77%
TOTAL PROJECT BUDGET: |  | 777049.1817 | 188407.51 | 197941.52 | 49.72% | 722950.82 | 474788.2598 | 0 | 65.67% | 720000.004 | 428827.2439 | 83931.52 | 71.22% | 779999.9972 | 398962.75 | 100961 | 64.09% | 3000000.0029 | 1873819.8037 | 62.46%
[11 empty] | 1873819.8037 | [6 empty] | 0.62461

## Activities Cote D`Ivoire
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget by recipient organization (not including staff, general operating costs and indirect fee) - IOM Côte d'Ivoire | Level of expenditure in USD (to provide at time of project progress reporting): IOM | Commitments/PO in USD - IOM | Level of expenditure/PO in % to date | Budget by recipient organization (not including staff, general operating costs and indirect fee) - UNDP Côte d'Ivoire | Level of expenditure in USD (to provide at time of project progress reporting): UNDP | Commitments/PO in USD - UNDP | Level of expenditure/PO in % to date | Total per country Côte d'Ivoire | Level of country expenditure and committments in USD (to provide at time of project progress reporting): Côte d'Ivoire | Level of country expenditure/PO in % to date
OUTCOME 1: Enhanced capacities for conflict prevention and level of trust between state institutions and target communities of the cross-border areas
Output 1.1: | Reduced tensions and increased promotion of social cohesion through strengthened and institutionalized civil-state collaboration mechanisms | 79500 | 13598.97 | 8549.28 | 27.86% | 112500 | 38596.7 | 0 | 34.31% | 192000 | 60744.95 | 31.64%
Activity 1.1.1: | Conduct a baseline study of all targeted communities and security forces on their perceptions/assessments of the levels of border security, cross-border cooperation and social cohesion; | 11500 | 11500 |  | 100% | 7500 |  |  |  | 19000 | 11500 | 60.53%
Activity 1.1.2: | Establish or reinforce Civil-Military Committees (CMC) for Cote d’Ivoire or County Security Council (CSC) for Liberia; | 0 |  |  |  | 50000 | 38596.7 |  | 77.19% | 50000 | 38596.7 | 77.19%
Activity 1.1.3: | Regularize inclusive dialogue sessions of CMCs and CSCs in respective countries and between CMCs and CSCs of mirroring communities in the two countries | 0 |  |  |  | 30000 |  |  | 0% | 30000 | 0 | 0%
Activity 1.1.4: | Reinforce the linkage to the existing early warning systems as well as their capacities to report on the issues related to cross-border area to CMCs and CSCs. | 0 |  |  |  | 25000 |  |  |  | 25000 | 0 | 0%
Activity 1.1.5: | Organize a potential crisis simulation at the border to establish humanitarian corridors and ensure the maintenance of essential economic needs. | 68000 | 2098.97 | 8549.28 | 15.66% |  |  |  |  | 68000 | 10648.25 | 15.66%
Output 1.2: | Improved capacities of local authorities, security forces, border management officials and key government actors for border management with a view to preventing conflicts. | 338036.5405 | 49355.82 | 59591.18 | 32.23% | 40000 | 0 | 0 | 0% | 378036.5405 | 108947 | 28.82%
Activity 1.2.1: | Conduct a capacity assessment. | 10000 | 7618.38 |  | 76.18% |  |  |  | #DIV/0! | 10000 | 7618.38 | 76.18%
Activity 1.2.2: | Carry out rehabilitation works in border posts providing the necessary equipment to enhance key actors’ capacities as well as to respond needs of women. | 126536.5405 | 21147.81 |  | 16.71% |  |  |  |  | 126536.5405 | 21147.81 | 16.71%
Activity 1.2.3: | Provide basic skill trainings to use computers and other electronics to input and manage data. | 21500 | 7467.36 | 15566.94 | 107.1% |  |  |  | #DIV/0! | 21500 | 23034.3 | 107.1%
Activity 1.2.4 | Organize trainings in border management for administrative authorities, security forces/agencies and communities’ leader. | 45000 | 9708.44 | 27016.71 | 81.61% | 5750 |  |  |  | 50750 | 36725.15 | 72.36%
Activity 1.2.5 | Facilitate the organization and institutionalization of joint and cross-border patrols by the security agencies of both countries at the local level. | 90000 | 3413.83 | 17007.53 | 22.69% |  |  |  |  | 90000 | 20421.36 | 22.69%
Activity 1.2.6 | Organize two high-level meetings between relevant authorities of both countries. | 45000 |  |  | 0% | 34250 |  |  | 0% | 79250 | 0 | 0%
TOTAL $ FOR OUTCOME 1: |  | 417536.5405 | 62954.79 | 68140.46 |  | 152500 | 38596.7 | 0 |  | 570036.5405 | 169691.95 | 29.77%
OUTCOME 2: Improved peaceful co-existence and social cohesion between the target communities of the cross-border areas
Output 2.1: | Strengthened conflict prevention and dispute resolution platforms for dialogue, joint problem-solving and cooperation, including women, youth and refugees, at community level | 17000 | 2390.55 | 12025.21 | 84.8% | 72036.54 | 65770 |  | 91.3% | 89036.54 | 80185.76 | 90.06%
Activity 2.1.1: | Establish or consolidate the community conflict prevention and management mechanisms in the target communities. | 0 |  |  |  | 30000 | 30000 |  | 100% | 30000 | 30000 | 100%
Activity 2.1.2: | Strengthen capacities of CPPCs and CPCs to effectively mitigate disputes and conflicts in their respective communities. | 0 |  |  |  | 32036.54 | 32000 |  | 99.89% | 32036.54 | 32000 | 99.89%
Activity 2.1.3: | Facilitate the organization of CPPCs and CPCs on a quarterly basis. | 0 |  |  |  | 10000 | 3770 |  | 37.7% | 10000 | 3770 | 37.7%
Activity 2.1.4: | Organize Joint Committee meetings between respective mirroring communities. | 17000 | 2390.55 | 12025.21 | 84.8% |  |  |  | #DIV/0! | 17000 | 14415.76 | 84.8%
Output 2.2: | Improved social cohesion and stability among cross-border communities through joint social, cultural and economic initiatives | 140000 | 27891.37 | 104826.44 | 94.8% | 350000 | 239538 | 0 | 68.44% | 490000 | 372255.81 | 75.97%
Activity 2.2.1: | Provide and/or reinforce basic community infrastructure. | 100000 | 11972.85 | 72183.32 | 84.16% | 105000 | 98775 |  | 94.07% | 205000 | 182931.17 | 89.23%
Activity 2.2.2: | Support cross-border women initiative to promote women's rights, fight against SGBV, community development, and social economic exchanges. | 0 |  |  |  | 30000 | 40100 |  | 133.7% | 30000 | 40100 | 133.7%
Activity 2.2.3: | Organize sensitization and awareness campaigns related to social cohesion of cross-border areas and elections through the ECOWAS radio broadcasts and IEC materials. | 40000 | 15918.52 | 32643.12 | 121.4% | 60000 | 20000 |  | 33.33% | 100000 | 68561.64 | 68.56%
Activity 2.2.4: | Facilitate to organize cultural, sport, and economic activities with a view to improving social cohesion. | 0 |  |  |  | 155000 | 80663 |  | 52.04% | 155000 | 80663 | 52.04%
TOTAL $ FOR OUTCOME 2: |  | 157000 | 30281.92 | 116851.65 |  | 422036.54 | 305308 | 0 |  | 579036.54 | 452441.57 | 78.14%
TOTAL OUTCOME 1 & 2 |  | 574536.5405 | 93236.71 | 184992.11 |  | 574536.54 | 343904.7 | 0 | 59.86% | 1149073.0805 | 622133.52 | 54.14%
Project personnel costs if not included in activities above |  | 103416.576 | 83449.37 |  | 80.69% | 68944.38 | 17749.74 |  | 25.75% | 172360.956 | 101199.11 | 58.71%
Project operational costs if not included in activities above | [6 empty] | 68659.39 |  |  | 0 | 68659.39 | #DIV/0!
Project M&E budget |  | 48261.072 |  |  | 0% | 32174.05 | 20000 |  | 62.16% | 80435.122 | 20000 | 24.86%
SUB-TOTAL PROJECT BUDGET: |  | 726214.1885 | 176686.08 | 184992.11 | 49.8% | 675654.97 | 450313.83 | 0 | 66.65% | 1401869.1585 | 811992.02 | 57.92%
Indirect support costs (7%): |  | 50834.9932 | 11721.43 | 12949.41 | 48.53% | 47295.8479 | 24474.88 |  | 51.75% | 98130.8411 | 49145.72 | 50.08%
TOTAL PROJECT BUDGET: |  | 777049.1817 | 188407.51 | 197941.52 | 49.72% | 722950.8179 | 474788.71 | 0 | 65.67% | 1499999.9996 | 861137.74 | 57.41%

## Activities Liberia
Annex D - PBF project budget
Note: If this is a budget revision, insert extra columns to show budget changes.
Table 1 - PBF project budget by Outcome, output and activity
Outcome/ Output number | Outcome/ output/ activity formulation: | Budget by recipient organization (not including staff, general operating costs and indirect fee) - IOM Liberia | Level of expenditure in USD (to provide at time of project progress reporting): IOM | Commitments/PO in USD - IOM | Level of expenditure/PO in % to date | Budget by recipient organization (not including staff, general operating costs and indirect fee) - UNDP Liberia | Level of expenditure in USD (to provide at time of project progress reporting): UNDP | Commitments/PO in USD - UNDP | Level of expenditure/PO in % to date | Total per country Liberia | Percent of budget for each output reserved for direct action on gender equality (if any): | Any remarks (e.g. on types of inputs provided or budget justification, for example if high TA or travel costs) | GEWE Calculation
OUTCOME 1: Enhanced capacities for conflict prevention and level of trust between state institutions and target communities of the cross-border areas
Output 1.1: | Reduced tensions and increased promotion of social cohesion through strengthened and institutionalized civil-state collaboration mechanisms | 72000 | 10000 | 19885 | 41.51% | 105740 | 51390 | 19290 | 66.84% | 177740
Activity 1.1.1: | Conduct a baseline study of all targeted communities and security forces on their perceptions/assessments of the levels of border security, cross-border cooperation and social cohesion; | 10000 | 10000 |  | 100% |  |  |  |  | 10000 | 50% | The baseline study has been completed at 100% delivrable | 14500
Activity 1.1.2: | Establish or reinforce Civil-Military Committees (CMC) for Cote d’Ivoire or County Security Council (CSC) for Liberia; |  |  |  |  | 35740 | 20500 |  | 57.36% | 35740 | 30% | Dialogue sessions will focus on issues affecting women as well as ways forward; special measures will be taken to ensure women's participation, including provision of transportation and child care. | 25722
Activity 1.1.3: | Regularize inclusive dialogue sessions of CMCs and CSCs in respective countries and between CMCs and CSCs of mirroring communities in the two countries |  |  |  |  | 70000 | 30890 | 19290 | 71.69% | 70000 | 50% | Dialogue sessions will focus on issues affecting women as well as ways forward; special measures will be taken to ensure women's participation, including provision of transportation and child care. | 50000
Activity 1.1.4: | Reinforce the linkage to the existing early warning systems as well as their capacities to report on the issues related to cross-border area to CMCs and CSCs. | [8 empty] | 0 | 30% | This includes training on SGBV and gender issues as well as techniques for women to report in safety; special measures will be taken to ensure women's participation, including provision of transportation and child care. | 7500
Activity 1.1.5: | Organize a potential crisis simulation at the border to establish humanitarian corridors and ensure the maintenance of essential economic needs. | 62000 |  | 19885 | 32.07% |  |  |  |  | 62000 | 50% | There is an ongoing preparation to bring authorities from both countries together for the crisis simulation activities. This will done in 2021 | 65000
Output 1.2: | Improved capacities of local authorities, security forces, border management officials and key government actors for border management with a view to preventing conflicts. | 355000 | 241633.68 | 47865.56 | 81.55% | 110000 | 20942.5 | 0 | 19.04% | 465000
Activity 1.2.1: | Conduct a capacity assessment. | 10000 | 10000.02 |  | 100% | 25000 | 20942.5 |  | 83.77% | 35000 | 50% | This activity has been completed at 100% | 22500
Activity 1.2.2: | Carry out rehabilitation works in border posts providing the necessary equipment to enhance key actors’ capacities as well as to respond needs of women. | 140000 | 120334.88 | 9375.56 | 92.65% |  |  |  |  | 140000 | 50% | Constructions are currently ongoing at the the 4 administrative border posts | 133268.27
Activity 1.2.3: | Provide basic skill trainings to use computers and other electronics to input and manage data. | 20000 | 11400.12 | 8500 | 99.5% | 20000 |  |  | 0% | 40000 |  | Computer training of Joint Security Actors is currently ongoing in Nimba & Grand Gedeh
Activity 1.2.4 | Organize trainings in border management for administrative authorities, security forces/agencies and communities’ leader. | 47000 | 47000 |  | 100% |  |  |  |  | 47000 | 30% | This activity has been completed at 100% | 29325
Activity 1.2.5 | Facilitate the organization and institutionalization of joint and cross-border patrols by the security agencies of both countries at the local level. | 90000 | 38420 |  | 42.69% |  |  |  |  | 90000 |  | Planning meetings between security and relevant authorities of both countries is ongoing for the final preparation of the joint patrol
Activity 1.2.6 | Organize two high-level meetings between relevant authorities of both countries. | 48000 | 14478.66 | 29990 | 92.64% | 65000 |  |  | 0% | 113000 | 30% | Activity is scheduled for July 2021 at high level meeting of the two authorities of Liberia & Cote d'Ivoire | 57675
TOTAL $ FOR OUTCOME 1: |  | 427000 | 251633.68 | 67750.56 |  | 215740 | 72332.5 | 19290 |  | 642740
OUTCOME 2: Improved peaceful co-existence and social cohesion between the target communities of the cross-border areas
Output 2.1: | Strengthened conflict prevention and dispute resolution platforms for dialogue, joint problem-solving and cooperation, including women, youth and refugees, at community level |  |  |  |  | 105000 | 52925.4 | 6671 | 56.76% | 105000
Activity 2.1.1: | Establish or consolidate the community conflict prevention and management mechanisms in the target communities. |  |  |  |  | 20000 | 17925.4 |  | 89.63% | 20000 | 50% | Committees will comprise leaders of women's associations as well as take into account conflict prevention and management mechanisms driven by women. | 25000
Activity 2.1.2: | Strengthen capacities of CPPCs and CPCs to effectively mitigate disputes and conflicts in their respective communities. |  |  |  |  | 40000 | 20000 |  | 50% | 40000 | 50% | Trainings will implicate leaders of women's associations and included tailored techniques to women's role in mitigation processes; special measures will be taken to ensure participation, such as child care provision | 38518.27
Activity 2.1.3: | Facilitate the organization of CPPCs and CPCs on a quarterly basis. |  |  |  |  | 25000 | 15000 | 6671 | 86.68% | 25000 | 30% | As part of quarterly meetings, a separate meeting held by women for women will be included; special measures will be taken to ensure participation, such as child care provision | 12000
Activity 2.1.4: | Organize Joint Committee meetings between respective mirroring communities. |  |  |  |  | 20000 |  |  | 0% | 20000 | 30% | Meetings will include a focus on issues and challenges specific to women in cross-border communities. | 12600
Output 2.2: | Improved social cohesion and stability among cross-border communities through joint social, cultural and economic initiatives | 123062.45 | 105062.76 | 8665.12 | 92.41% | 280000 | 157261.35 | 75000 | 82.95% | 403062.45
Activity 2.2.1: | Provide and/or reinforce basic community infrastructure. | 123062.45 | 105062.76 | 8665.12 | 92.41% | 75000 |  | 75000 | 100% | 198062.45 | 50% | Constructions are ongoing for the 4 hand pumps to support community engagement scheduled to finished by June 2021 | 201531.225
Activity 2.2.2: | Support cross-border women initiative to promote women's rights, fight against SGBV, community development, and social economic exchanges. |  |  |  |  | 20000 | 10000 |  | 50% | 20000 | 100% |  | #REF!
Activity 2.2.3: | Organize sensitization and awareness campaigns related to social cohesion of cross-border areas and elections through the ECOWAS radio broadcasts and IEC materials. |  |  |  |  | 80000 | 78671.4 |  | 98.34% | 80000 | 50% | Broadcasts will include specific thematics/segments related to women, their role in local societies as well as challenges and ways forward | 90000
Activity 2.2.4: | Facilitate to organize cultural, sport, and economic activities with a view to improving social cohesion. |  |  |  |  | 105000 | 68589.95 |  | 65.32% | 105000 | 50% | At least half of proposed activities will specifically target women; specific provisions will be made to ensure women's participation (such as provision of transportation and child care). | 130000
TOTAL $ FOR OUTCOME 2: |  | 123062.45 | 105062.76 | 8665.12 |  | 385000 | 210186.75 | 81671 |  | 508062.45
TOTAL OUTCOME 1 & 2 |  | 550062.45 | 356696.44 | 76415.68 |  | 600740 | 282519.25 | 100961 |  | 1150802.45 |  |  | #REF!
Project personnel costs if not included in activities above |  | 86180.48 | 50394.83 |  | 58.48% | 86180.48 | 56032.86 |  | 65.02% | 172360.96
Project operational costs if not included in activities above | [9 empty] | 0
Project M&E budget |  | 36654.27 | 5520 | 2025 | 20.58% | 42051.48 | 27705.39 |  | 65.88% | 78705.75
SUB-TOTAL PROJECT BUDGET: |  | 672897.2 | 412611.27 | 78440.68 | 72.98% | 728971.96 | 366257.5 | 100961 |  | 1401869.16
Indirect support costs (7%): |  | 47102.804 | 16215.9739 | 5490.84 | 46.08% | 51028.0372 | 32705.25 | 0 | 64.09% | 98130.8412
TOTAL PROJECT BUDGET: |  | 720000.004 | 428827.2439 | 83931.52 | 71.22% | 779999.9972 | 398962.75 | 100961 |  | 1500000.0012

## Category Liberia
Table 2 - PBF project budget by UN cost category
Note: If this is a budget revision, insert extra columns to show budget changes.
CATEGORIES | Amount Recipient Agency IOM Liberia | [5 empty] | Amount Recipient Agency UNDP Liberia | [5 empty] | Total tranche 1 (70%) | Total tranche 2 (30%) | PROJECT TOTAL | Overall Expenses | Overall PO | Overall Del (%)
| Tranche 1 (70%) | Tranche 2 (30%) | Total | Expenses | PO | Del (%) | Tranche 1 (70%) | Tranche 2 (30%) | Total | Expenses | PO | Del (%)
1. Staff and other personnel | 60326.336 | 25854.144 | 86180.48 | 50394.83 |  | 83.54% | 60326.336 | 25854.144 | 86180.48 | 56032.68 |  | 92.88% | 120652.672 | 51708.288 | 172360.96 | 106427.51 | 0 | 88.21%
2. Supplies, Commodities, Materials | 22717.5792 | 9736.1054 | 32453.6845 | 11951.79 | 5521.53 | 76.92% | 8410.36 | 3604.44 | 12014.8 | 8318.24 |  | 98.9% | 31127.9392 | 13340.5454 | 44468.4846 | 20270.03 | 5521.53 | 82.86%
3. Equipment, Vehicles, and Furniture (including Depreciation) | 36359.5047 | 15582.6449 | 51942.1496 | 26628.48 | 141.6 | 73.63% | 29436.26 | 12615.54 | 42051.8 | 4953.63 |  | 16.83% | 65795.7647 | 28198.1849 | 93993.9496 | 31582.11 | 141.6 | 48.22%
4. Contractual services | 73158.3058 | 31353.5596 | 104511.8655 | 50850.26 | 2025 | 72.28% | 105129.5 | 45055.5 | 150185 | 0 | 100961 | 96.03% | 178287.8059 | 76409.0596 | 254696.8655 | 50850.26 | 102986 | 86.29%
5.Travel | 30803.4972 | 13201.4988 | 44004.996 | 31493.1 | 4048 | 115.4% | 29436.26 | 12615.54 | 42051.8 | 27705.39 |  | 94.12% | 60239.7572 | 25817.0388 | 86056.796 | 59198.49 | 4048 | 105%
6. Transfers and Grants to Counterparts | 152092.2674 | 65182.4003 | 217274.6677 | 147955.16 | 66540.11 | 141% | 168207.2 | 72088.8 | 240296 | 168207.2 |  | 100% | 320299.4674 | 137271.2003 | 457570.6677 | 316162.36 | 66540.11 | 119.5%
7. General Operating and other Direct Costs | 95570.552 | 40958.808 | 136529.36 | 81499.5 | 164.43 | 85.45% | 109334.46 | 46857.62 | 156192.08 | 101040.36 |  | 92.41% | 204905.012 | 87816.428 | 292721.44 | 182539.86 | 164.43 | 89.17%
Sub-Total Project Costs | 471028.04 | 201869.16 | 672897.2034 | 400773.12 | 78440.67 | 101.7% | 510280.376 | 218691.584 | 728971.96 | 366257.5 | 100961 | 91.56% | 981308.4184 | 420560.745 | 1401869.1634 | 767030.62 | 179401.67 | 96.45%
8. Indirect Support Costs (must be 7%) | 32971.9628 | 14130.8412 | 47102.804 | 28054.1184 | 5490.8469 | 101.7% | 35719.626 | 15308.4112 | 51028.0372 | 32705.25 |  | 91.56% | 68691.5893 | 29439.2522 | 98130.8414 | 60759.3684 | 5490.8469 | 96.45%
TOTAL | 504000.0028 | 216000.0012 | 720000.0074 | 428827.2384 | 83931.5169 | 101.7% | 546000.002 | 233999.9952 | 779999.9972 | 398962.75 | 100961 | 91.56% | 1050000.0077 | 449999.9972 | 1500000.0049 | 827789.9884 | 184892.5169 | 96.45%