## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Building Forward Better: A Resilient Women and Youth Centred and Digitally Enhanced Value Chain Development in Vietnam | Overall Duration (months) | 15 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | Feb. 2021
MPTF Office Project Reference Number: | MPTF_00209_00089 | Original End Date (dd.mm.yyyy) | 2022-04-01
Country | Vietnam | Current End date(dd.mm.yyyy) | Sept 2022 (if starting from the approval government date in July 2021)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | IFAD and UNIDO | National counterparts (government, private, NGOs & others) and other International Organizations | - Ministry of Agriculture and Rural Development - Provincial People's Committees of Dong Thap province and Ben Tre province - Fruit enterprise associations - Farmers groups, Women’s Union, Youth Union, Farmers’ Union - Private sector - R&D and technological institutions
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project aims to rebuild and digitally enhance an agricultural value chain in order to serve as a model for wider scaling out. The proposed approach of the project would place rural women and youth and their empowerment through digital means as the core target groups by pursuing the following outcomes: Outcome 1. Women and youth centered business enabling environment Outcome 2. Enhanced competitiveness, safety and sustainability of women and youth-led value chains (VCs) Outcome 3. Improved access to new markets for women and youth When receiving the fund transfer in Feb. 2021 from the MPTF, IFAD needs to complete the internal approval process. At the same time, UNIDO and IFAD started to develop two full project documents (UNIDO) and two financing agreements (IFAD) with the two partner provinces of Ben Tre and Dong Thap and worked with the government for the project registration/approval according to ODA management decree 56. The fast-track government approval was completed in June (for UNIDO) and in July (for IFAD) to enable the project to officially start its implementation. The project has started preparatory activities in parallel to ensure that it could be implemented at full speed once the project documents are approved and signed by the project counterparts. This includes (1) consultation meetings with the two provinces and the Ministry of Agricultrue and Rural Development (MARD), (2) review of past/ongoing projects to identify synergies, (3) develop a detailed workplan and (4) identify service providers.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Women and youth in Dong Thap and Ben Tre provinces working along the mango and pomelo value chains are the core target beneficiaries and intended change agents of the project. Moreover, rural small and medium enterprises including wholesalers, transportation, storage and local input suppliers will also benefit from the outputs of the proposed project. Since the project is at the preparatory phase, it has not yet reached to the beneficiaries.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1. Women and youth centered business enabling environment: no outcome level result achieved yet Outcome 2. Enhanced competitiveness, safety and sustainability of women and youth-led VCs: no outcome level result achieved yet Outcome 3. Improved access to new markets for women and youth: no outcome level result achieved yet
3.2 | Results: Output Level | Please include output level results achieved | Output 1.1 Women led farmer groups mobilized and strengthened: Two value chains of mango and pomelo were chosen for project intervention after consultation with the two provinces. PMUs have identified a list of women-led farmer's groups which are developed earlier by the IFAD-supported AMD project in Ben Tre and the UNIDO-supported mango value chain development project in Dong Thap. Such model of the groups will be multipled in coming period. Output 1.2 Enhanced capacity and accessibility of women and youth-focused support services (ICT, finance, extension, business advisory, etc.). IFAD and UNIDO have linked the provinces with the OCOP management in order to utilize the ICT-based marketing application developed by IFAD for this project. PMUs are ready to organize provincial workshops on mobilization of private sectors to sign farming contracts with the women-led fermer's groups. However due to COVID the activities are pending. The conceptualization of a digital ecosystem that could model the physical value chain and provide supporting services was developed and the contratual negotiation with a service provider is on-going Output 1.3 Policy and advocacy platform for (a) the promotion and scaling up of women and youth centered value chains; (b) promotion of women’s leadership roles in economic development; and (c) the promotion of social norm change on gender roles in sharing the housework. A plan for the policy and advocacy activities has been developed for each province. Output 2.1 COVID-19 safe food standards, good practices and technologies developed/promoted along the value chain. PMUs have reviewed and selected good practices and technologies for promotion under this project. Output 2.2 Women and youth centered value chain established and upgraded. This output is expected at a later stage. Output 3.1 Women and youth led innovation through value addition, branding, promotion and e-commerce. This output is expected at a later stage Output 3.2 Farm-enterprise, enterprise to enterprise contracts established. This output is expected at a later stage
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Limited local travel and no travel of international experts due to COVID-19 hampered the mission to the project sites. The project therefore had to organize virtual discussion in stead of in-person meeting. More decentralization to field office was also made to facilitate.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Even though digitalized agriculture sector and rural areas are of government's top priorities, the implementation is fragmented due to lack of coordination, resources and technical capability of the government institutions, business development service providers and the value chain actors. The application of digital technology along the value chain should aim to bring benefits to all the stakeholders (i.e. bringing more profit and business opportunities to the farmers and SMEs, supporting Government management and decision making, improving the transperancy and tracebility of the value chains/produce). The project is working to create such digitized value chain model for policy advocacy and replication.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | Partnerships are envisaged during implementation with both national and international institutions such as: (i) National Coordination Office for NTP-NRD and OCOP; (ii) Central Committee for Ethnic Minorities (CEM) for integration with the NTP-EMD; (iii) the Mekong Delta Coordination Committee (MDCC) established by the Prime Minister Decision on 12 June 2020; (iv) the Ministry of Agriculture and Rural Development (MARD) and the development partners under the International Mekong Delta Working Group (MDWG) for implementation of the Mekong Delta Agriculture Transformation Programme; (v) the World Bank’s Mekong Delta Integrated Climate Resilience and Sustainable Livelihoods Project working in both Ben Tre and Dong Thap provinces; the project “Green Innovation Centres for the Agriculture and Food Sector” (GIZ), the project “Enhancing Global Competitiveness of Vietnam’s dragon fruit through Improving Quality Infrastructure in the Value chain” (IFC), the project “Improving smallholder farmer incomes through strategic market development in mango supply chains in southern Vietnam” (ACIAR), the project "Traceability development for export" (DFAT), and the project "Safe food for growth" (Canada). In addition, the project’s scope is catalytic but fully compatible with the other country programs of IFAD and UNIDO in Vietnam. The IFAD funded Adaptation in the Mekong Delta project (AMD) in Ben Tre and Tra Vinh provinces in the Mekong Delta provide the basis and experience to develop and modernize the proposed value chain. IFAD through the AMD promoted climate smart, pro-poor value chain development including value chain finance approaches. UNIDO has established a Center of Excellence for mango harvesting, packing operations, storage and transport in the Mekong River Delta. In addition, UNIDO is providing technical assistance to increase the quality and standards compliance of the mango value chain in the region through Global Quality and Standards Programme (GQSP). In response to the Covid-19 challenges – and in line with the government’s dual goals (response and recovery) – the Ministry of Agriculture and Rural Development (MARD) foresees a continued restructuring of agriculture, utilizing cutting edge technology, empowering its position in the supply chain, increasing the value-added and enhancing the competitiveness of Vietnamese agricultural products. A partnership model of 4 partners including the Ministry of Agriculture and Rural Development (MARD), the Women's Union, the Farmers' Union, and the Youth Union was established to facilitate agriculture products consumption. This has been a successful model to connect demand and supply in the context of the complicated development of the COVID-19 epidemic. The project could this model and facilitate it better. The Government has specific policies for the transformation of the rural economy and to render it climate resilient and compatible with food export markets. The project outcomes thus also have high potential to serve as a springboard and be replicated by other larger investment programmes sponsored by Government and IFIs. The focus on women and youth through ICT is highly innovative and in fact a prerequisite for the enhancement of their social and economic development. The private sector will be closely involved from the beginning as they will lead the identification of training needs, required technology and equipment, and farm inputs. These aspects would ensure that the farmer groups’ produce respond to market demand, especially in terms of product quality and delivery. Private enterprises operating in logistics, payment, IT and data security and E-commerce platforms (Shopee, Lazada, etc.) will be mobilized for stakeholder dialogues to provide a strong foundation and promote increased e-commerce adoption among farmers and SMEs, with the ultimate goal of improving long-term trust among actors in online fruit-related businesses.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | The PMUs have conducted a review of experience and lessons learnt from completed and on-going projects/programs in Ben Tre and Dong Thap provinces. The Project Completion Report (PCR) of the IFAD-supported Climate Change Adaptation in Mekong Delta (AMD) is a resourceful assessment of the on-going initiatives for the women and youth development.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | So far no adjustment of the project strategy, targets and key results is proposed by the target provinces.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The Government and IFAD have approved a continued IFAD investment to the Mekong Delta, the Climate Smart Agriculture Transformation in Ben Tre and Tra Vinh provinces (CSAT), which will be implemented from early 2022 and maximize impacts of the MPTF support from the UN. The MPTF project activities will be integrated with the CSAT programme which has mobilized partnership with DFCD, SNV and IDH. In additon a complimentary project is proposed for co-financing by the Adaptation Fund.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1 Women and youth centred digitally enhanced business enabling environment | The project has establshed a M&E system. However since the project implementation has just started the data are not available yet |  | Project report
Indicator: District agencies pursue and support women and youth centred business in at least one fruit value chain
Baseline:
Planned Target: Twelve Districts report concerted efforts by agencies in at least one fruit value chain
Output 1.1 Women led farmer groups mobilized and strengthened through digital communication tools | Not available yet |  | Project report
Indicator 1.1.1: Number of organised women and youth partaking in the programme
Baseline:
Planned Target: 2,000 female and/or young fruit producers participate in the model value chain support programme by the end of 2021
Output 1.2 Enhanced capacity and digital accessibility of women and youth-focused support services (ICT, finance, extension, business advisory, skills development, etc.) | Not available yet |  | Project report
Indicator 1.2.1: Frequency of using digital platforms to establish, maintain or use value chain relations
Baseline:
Planned Target: 80% of groups report using the digital platforms at least weekly
Output 1.3 Policy and advocacy platform for (a) the promotion and scaling up of women and youth centred value chains; (b) promotion of women’s leadership roles in economic development; and (c) the promotion of social norm change on gender roles in sharing housework | Not available yet |  | Project report
Indicator 1.3.1: # of significant Provincial Resolutions promoting women and youth centred value chains
Baseline: |  |  | Project report
Planned Target: One Provincial Resolution (per Province) articulating steps for promoting women and youth centred value chains
Outcome 2 Enhanced competitiveness, safety and sustainability of women and youth-led value chains
Indicator: $ of sales, % increase is sales volume and value |  |  | Project report
Baseline:
Planned Target: Target increase in $ of sales to be determined 30% increase in sales volume/value
Output 2.1
Indicator 2.1.1: COVID-19 safe food standards, good practices and technologies developed/ digitally promoted along the value chain | Not available yet |  | Project report
Baseline:
Planned Target: # of good practices, pre-and post-harvest technologies applied by the value chain operators
Output 2.2 Women and youth centred digitally enhanced value chain upgraded
Indicator 2.2.1: # of value chains upgraded/created to explicitly benefiting women and youth producers |  |  | Project report
Baseline:
Planned target: 1 model fruit value chain established | Not available yet
Outcome 3 Improved digital access to new markets for women and youth
Indicator: # of beneficiaries using digital access technologies |  |  | Project report
Baseline:
Planned Target: 5 enterprises
Output 3.1 Women and youth led innovation through increased digital access to value addition, branding, promotion and e-commerce
Indicator 3.1.1: # of diversified primary products / product market combinations | Not available yet |  | Project report
Baseline:
Planned Target: 2 innovated primary products accessed to the markets
Output 3.2 Farm-enterprise, enterprise to enterprise contracts digitally facilitated and established
Indicator 3.2.1: # of producer – enterprise business relationships per producer group established digitally | Not available yet |  | Project report
Baseline:
Planned target: 3 digitally facilitated business relationships with growth potential per producer group
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
- Signing Ceremony of the Joint Delaration on the project Press release https://nongnghiep.vn/nang-cao-nang-luc-tuan-thu-cac-quy-dinh-doi-voi-xoai-xuat-khau-d288237.html https://baophapluat.vn/tieu-dung-va-du-luan/thi-truong-xuat-khau-xoai-cua-viet-nam-con-rat-lon-583490.html
- The 1st Coordination Meeting Press release: https://vietnam.un.org/en/129976-unido-and-ifad-join-hands-launch-new-project-develop-fruit-value-chain-mekong-river-delta
Representatives of UNIDO, IFAD, MARD, Dong Thap province and Ben Tre province signed the JD of the project