## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE: 13 August 2021
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Safe and Innovative Health Services in Times of COVID-19 | Overall Duration (months) | 15
Programme Number (if applicable) | 00125740 | Start Date (dd.mm.yyyy) | 31.12.2020
MPTF Office Project Reference Number: | 00125740 | Original End Date (dd.mm.yyyy) | 31.03.2022
Country | North Macedonia | Current End date(dd.mm.yyyy) | 31.03.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA UNICEF WHO | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health, Ministry of Labor and Social Policy, E-health Directorate, Association of Gynecologists and Obstetricians, Committee on Safe Motherhood and Healthy Newborn, Macedonian Medical Association, Macedonian Association of Nurses and Midwives, University Clinic of Psychiatry and civil society organizations.
Report Cleared By
o Name: | Sébastien Fahrni
o Title: | Associate Coordination Officer (RCO)
o Email address: | sebastien.fahrni@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project achieved important results, especially in terms of pre-setup of mobile gynaecological clinics and stepping up of capacities for Covid-19 immunisation and addressing vaccine hesitancy. In terms of the mobile gynaecological clinics, a Protocol for provision of sexual and reproductive health (SRH) services through mobile clinics was updated and SRH commodities procurement was initiated. Optimal modality for integration of the two mobile gynaecological clinics in the e-Health system was identified through several consultations, enabling secure data management and avoiding paper-based reporting and/or misreporting. A communications campaign on prevention of cervical cancer (a national priority theme in SRH) has been prepared to promote cervical cancer screening, inter alia, through mobile gynaecological clinics. In terms of immunisation, the project provided support on two main fronts – addressing Covid-19 and overall vaccine hesitancy and strengthening the capacities of health care system to efficiently roll out Covid-19 immunisation. A multi-media vaccine trust campaign was developed and carried out and contributed to a positive shift in attitudes towards COVID-19 immunisation. The campaign had a significant outreach (reached 77% of population over 18 years at least once and 62% at least three times via TV, and on average 75,000 people per post on social media, with average 21,000 people engaging with content (campaign ran on all social media channels). The campaign had measurable impact – based on WHO Behavioural Insights Surveys, the belief of population in immunisation as an effective Covid-19 control measure jumped from 56% in Dec 2020 to 69% in June 2021. In addition, behavioural study and on drivers of MMR vaccine hesitancy as well as training of five master trainers were completed, in preparation for roll out of an awareness campaign on the benefits of MMR vaccination. Furthermore, the project supported the strengthening of capacity of the health care system for Covid-19 immunisation roll-out and immunisation in general. The project supported the development of national e-immunisation registry to provide accurate and timely data on immunization and address lack of regular immunization check-ups. Furthermore, 420 health care workers completed courses on Covid-19 vaccination, which were adapted and accredited with the project support (Open WHO courses COVID-19 vaccination training for immediate needs of health workers and Orientation and planning for COVID – 19 vaccination). Mapping of human resources, capacity development of front-line healthcare professionals in immunization teams and performance support on how to plan and implement COVID-19 vaccination - supply chain management, cold chain vaccine administration and communication - created a solid and sustainable base of experts, skilled to administer different types of vaccines and address vaccine hesitancy. Implementation of qualitative formative study on health workers perceptions and behaviours related to COVID – 19 vaccination has also been completed (focus discussions and online interviews) . All aforementioned activities were implemented in close collaboration with Ministry of Health and other key stakeholders. Facilitating the provision of social and child protection to social risk families in close collaboration with the centres for social work have been initiated, through a remapping effort, by strengthening referral and response mechanisms.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | In terms of the Covid-19 vaccine trust communication campaign, the outreach was to the overall/general population. In addition, behavioral interventions for MMR1 vaccine had an outreach to 10.000 parents with children aged 13 months (based on annual number of births/year). Immunization trinaings have reached 1152 health care workers (512 nurses, 228 doctors, and 412 health professionals). Digital modules have reached general population. 25 families at social risk have been reached in order to support provision of social protection, and ensure referral if other social risk issues are identified.
3.1 | Results: Outcome Level | Please include outcome level results achieved | n.a,
3.2 | Results: Output Level | Please include output level results achieved | In preparation for mobile gynaecological clinics, UNFPA signed Implementing Partner Agreements with the Macedonian Medical Association and the Red Cross of the Republic of North Macedonia. Working groups comprising of heatlh professionals in various fields (cervical cancer, maternal health, family planning, GBV, E-Health), have been established, to review the existing Protocol for provision of SRH sevices through mobile clinics (initially developed in the course of the refugee/migrant crisis), and update it, to reflect the COVID-19 reality and context. Based on the assessment of the needs of the health facilities with regards to SRH commodities, the Procurement Plan has been developed and procurement through the UNFPA global procurement office has been initated. Technical solution to integrate the two mobile gynaecological clinics in the e-Health system has been identified, to ensure that data related to services provided in the mobile clinics is captured and recorded in the national e-Health system. As prevention of Cervical Cancer was identified as one of the prioroty SRH interventions, the UNFPA and Ministry of Health communications team have worked closely together on the development of a communications campaign, to increase public awareness, promote cervical cancer screening in general, but also through the mobile gynaecological clinics. In terms of addressing Covid-19 vaccination hesitancy and building publc trust, a multi-media campaign was developed and implemented in collaboration between UNICEF and the Ministry of Health. The campaign reached 77% of the population over 18 years of age at least once and 62% at least three times on television. On social media, while the campaign ran on all channels, on Facebook it included 30 posts which on average reached on average some 75,000 people by post and engaged some 21,000 people by post. 3 posters, reminder tent and leaflet designed for roll-out around the country. The outreach work of the mobile teams in five cities have been initiated, aimed at facilitating the provision of social protection to social risk families in close collaboration with the centers for social work. The teams consist of lawyers and social workers to support the centers for social work in mapping, targeting, providing legal support to vulnerable children and families, and identifying and referring cases of violence and abuse, including gender-based violence. The teams have already reached out to 25 families. In addition, networking between social workers and local CSOs is being facilitated to extend the support to families at social risk. In terms of the e-Immunisation, new digital modules for the national e-Health system were developed with WHO support: 1. Module for integration of all data about children vaccination status from the National e-Health system in the e-Register for Immunization. 2. Module for coverage reports on national and local levels for regular immunization and submodule for coverage reports on national and local levels for Covid19 vaccination. 3. Upgrading the Module for mass notification (SMS and mail) for sending reminders to parents about next vaccination date. 4. Development of training modules for mid – level immunisation managers and in-practice immunization and training sessions: • Online trainings for vaccination teams from Health Homes, Epidemiological Services in the Public Health Centers, Agency for medicine and medical devices, State Sanitary and Health Inspectorate • Four online trainings for General practitioners/ Family doctors • Training for cold chain monitoring from Health Home Skopje and Institute of transfusiology (Pfizer – BioNTech vaccine and Gam – COVID – VAC) • Training for vaccination teams from Health Home Skopje for vaccination with Gam – COVID – VAC - Trainings for administering Pfizer’s vaccine for vaccination teams from Health Homes in Tetovo, Gostivar, Ohrid, Struga, Bitola, Prilep, Kavadarci, Strumica, Kumanovo and Shtip and for the Mass vaccination sites (13). 5. Website www.kovid19vakcinacija.mk has been developped 6. Adapted and accredited 2 OpenWHO training courses : COVID-19 vaccination training for health workers (https://openwho.org/courses/covid-19-vaccination-healthworkers-mk) and Orientation and planning for COVID – 19 vaccination ( https://openwho.org/courses/covid-19-ndvp-mk ); 6. The adaptation of WHO mid-level management training (MLM) 6 modules and Adaptation of the in-service practice immunization training and development of the electronic versions of the trainings are in progress. 7.Qualitative formative study on health workers perceptions and behaviours related to COVID – 19 vaccination
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | In light of the COVID-19 pandemic, the efforts of the national counterparts throughout 2021 remained organizing the health system in a way to address the COVID-19 related emergencies and saving lives of COVID-19 patients. Thus, the process for operationalization of the mobile gynaecological services took longer than initially expected, as well as the internal review by the Ministry of Health of their SRH facilities, capacities and distribution of morbidity and mortality, in order to define the most burning points. Regular coordination and follow up with the national counterparts were in place throughout the year. COVID-19 restrictions for face-to-face design of behavioural interventions have required modification of the methodology to on-line modality. Involvement of policy makers and health professionals in COVID-19 response made it challenging to provide sufficient number of participants in the on-line consultations when developing prototypes. Due to travel restrictions, national consultant was hired to perform observations and interviews at the three pilot healthcare facilities. The need to start implementation of communication efforts to build trust in vaccines before hiring Communication for Development Officer was managed by assigning additional responsibilities to existing human resources. Delays in arrivals of vaccines and uncertainties in the type of vaccine and their distribution to different sites, were decided on ad hoc bases and requiring ad hoc training plan. Due to this many trainings which were planned to be undertaken online have been replaced with face-to-face training at vaccination sites. This immediate intervention of the national team of experts fastened the process and enabled uninterrupted vaccination process. Coverage reports for vaccination from the calendar of vaccination and Covid-19 vaccination are developed for regional health centres and the Institute of public health, however due to the limited number of personnel the reports were still completed with delay.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | It is crucial to ensure that relevant counterparts are involved from the very start of the project - in the case of this project, we have been implementing the activites in close consultation with the Ministry of Health, the Association of Gynaecologists and Obstetricians, the Association of Nurses and Midwifes, the E-Health Directorate, staff from the Sexual Assault Referral Centers, the Red Cross and others. Behavioral insight study has identified 12 barriers to the uptake of MMR1 vaccination in North Macedonia, grouped under barriers for caregivers (unsure of risks and benefits, lack of trust and confidence in doctors’ recommendations about vaccinations, misinformation, unsatisfactory appointments, waiting time uncertainty and no reminders) and barriers for clinicians involved in vaccination (fear of caregiver reprisals if something goes wrong following vaccination, fear of creating hesitancy, ill-informed about the benefits and risks of the MMR vaccine, poor interpersonal communication skills and lack of experience and motivation). Implementation of qualitative formative research to inform policies for engaging health workers is advantageous to ensure successful uptake of COVID-19 vaccination. All the health workers reported they would recommend a COVID-19 vaccine to their patients.Over half thought their patients would have some questions, concerns and maybe some hesitancy about COVID-19 vaccination. Particularly family doctors anticipated questions about safety (e.g. long term, for those planning pregnancy), contraindications for certain vaccines (e.g. anti-coagulant therapy for Astra Zeneca vaccine, hypertension, diabetes, allergies) and post-infection vaccination. A few offered a view on which groups of patients were likely to be hesitant.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UNFPA established partnership with the Macedonian Medical Association and the Red Cross of the Republic of North Macedonia. The establishment of these partnerships has been initiated within the framework and for the implementation of this project, but these will continue even beyond the project duration, and provide a framework for cooperation in the period 2021-2025. The Macedonian Medical Association brings together organizations of health professionals from various fields and fosters exchange of experience, professional development, and promotion of evidence-based medicine. The Red Cross of the Republic of North Macedonia is a reliable partner that has the most extensive network of volunteers and activists on local level and is the first responder in the event of emergency. By working closely with the Ministry of Health, the Macedonian Medical Association, and the Red Cross, we ensure that the health services are delivered to the women and girls in the priority locations. Under the overall coordination by UNICEF Regional Office, UNICEF Country Office has partnered with Behavioural Insights Team UK for the behavioural study on immunization. Under the leadership of the Ministry of Health, UNICEF vaccine trust communication campaign has been developed in coordination with WHO and compliments the overall Government vaccine deployment plan and contribute to national COVID19 risk communication and community engagement efforts. Additional coordination with the Delegation of the European Union has ensured efforts are complementary. The WHO Country Office has coordinated the digitalization of the immunization system, partnering with the e-Health Directorate and the Institute for Public Health, under the leadership of the Ministry of Health. The digitalization of the immunization services as part of this project contributes to upgrading the level of implementation of the activities within the annual immunization programme. E-Health Directorate contributed with its available IT structures and trained personnel and ensures embedding in the already functional national e-Health system “Moj Termin”. Partnering with the Institute of Public Health and the Centre for Family Medicine-Faculty of Medicine Ss Cyril and Methodius Skopje, enabled establishment of a team of experts, who developed the National vaccine deployment plan, guided by the WHO EURO and implemented the trainings. Collaboration with the Institute of Family Medicine and the Faculty of Medicine has contributed to the scientific adaptation of the WHO new immunization practice courses. WHO will continue to follow and monitor the performance of the trainings. Continuous coordination with UNICEF, UNFPA and with the Delegation of the European Union enabled the synchronization of activities.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Internal review by the Ministry of Health of their SRH facilities, capacities and distribution of morbiditiy and mortality, in order to define the most burning points. Rapid assessment of self-efficacy, perceptions and practices of healthcare workers on routine immunization (ongoing)
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Qualitative formative research to inform policies for engaging health workers to ensure successful uptake of COVID-19 vaccination experience of the COVID-19 pandemi, was additionaly implemented withint this project.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The procurement of SRH commodities is done through the UNFPA Global Procurement Services Branch based in Copenhagen, thus ensuring the quality of the SRH commodities procured and cost efficiency. Additional set-aside funding has been secured by UNICEF Regional Office in support of roll-out of behavioral interventions, that were developed and tested with MPTF funding. Additional HAC funding has been also secured for inter-personal communication skills capacity development for health workers. Recruitment of C4D officer ongoing. Additional funding has been secured through the WHO Western Balkan EU Project for additional upgrading of the immunization electronic system with flexible algorithm for booking vaccination appointments for vaccination upon urgent governments request.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1: Mobile services equipped with skilled teams and tools to provide timely sexual and reproductive health and immunization services utilized by women and girls, and children from vulnerable families, in hard-to-reach and under-served areas.
Indicator 1.1.1: Number of people accessing (with UN support) essential (non-COVID-19 related) sexual and reproductive health services, disaggregated by sex, age group and at-risk populations | 0 | Activities will follow in the coming period.
Baseline: 0
Planned Target: 1800
Indicator 1.1.2: Number of health service providers trained to provide SRH services in the mobile clinics | 0 | The trainings of the service providers will follow once the Protocol for provision of SRH services through the mobile clinics is finalized, and this is dependant upon the finalization of the internal review of the Ministry of Health of their SRH facilities, capacities and distribution of morbiditiy and mortality, in order to define the most burning points.
Baseline: 0
Planned Target: 50
Indicator 1.1.3: Number of services provided at the mobile clinics | 0 | The process for setting the infrastructure for provision of SRH services through the mobile clinics took longer than envisaged, thus delaying the deployment of the clinics in the field.
Baseline: 0
Planned Target: 4
Indicator 1.1.4: Number of women and girls aged 15-49 Reached through multi media campaigns | 0 | The communications activities will follow in the coming period.
Baseline: 0
Planned Target: 50'000
Output 1.2: Capacity developed for essential health workforce necessary to provide safe, effective and quality immunization services and national digital/electronic immunization registry developed to provide accurate and timely data on immunization and awareness raised on benefits of immunization.
Indicator 1.2.1: Number of health workers trained with the newly established training course on safe vaccination practices | 412 online trianing courses ; 512 nurses and 228 doctors Vaccination administrators | Development and adaptation of WHO Mid-level management training (MLM) to national context | E-health directorate/Moj termin and Final report from the national Experts for Immunziation
Baseline: 0
Planned Target: 2000
Indicator 1.2.2: Number of new digital immunization modules established | 4 |  | e-health/Moj termin
Baseline: 0
Planned Target:
Indicator 1.2.3: Number of master trainers trained in IPCS | 5 | In collaboration with Drexel University, 5 master trainers were trained in IPCS | Training records
Baseline: 0
Planned Target: 10
Indicator 1.2.4: Number of immunization teams trained in IPCS | 0 | Based on the rapid assessment, modules on IPCS will be selected and trainings rolled-out late September | Training records
Baseline: 0
Planned Target: 30
Indicator 1.2.5: Number of people reached through immunization campaign | 806000 |  | Advertising agency reports with indicator reflecting the number of adult population reached through television at least 3 times (62% of 1.3 mill adult population)
Baseline: 0
Planned Target: 500'000
Indicator 1.2.6: Number of people engaged with messages from the immunization campaign | 21000 | 30 posts on social media engaged some 630K people. The inndicator is based on average number of people reached by post as opposed to total engagement to avoid double counting | UNICEF social media analytics based on average number of people engaged by post
Baseline: 0
Planned Target: 45'000
Output 1.3: Developed system for recognition, reporting, referral and response of gender-based violence cases, targeting under-served areas and groups.
Indicator 1.3.1: Safe services in place to address gender- based violence (GBV) during the COVID-19 pandemic
Baseline: No
Planned Target: Yes
Indicator 1.3.2: Number of social service workforce trained provide immediate and continuous support to children and families, and ensure access to GBV services
Baseline: 0
Planned Target: 100
Indicator 1.3.3: Number of persons provided with support through helplines
Baseline: 344
Planned Target: 1000
Indicator 1.3.4: Number of PHC clinics screening for ACEs | 0 | Contract with Macedonian Medical Association signed in August. Screening will start in September
Baseline: 1
Planned Target: 3
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Vaccines save lives - trust the facts, ask before you assume https://www.unicef.org/northmacedonia/vaccines-save-lives
Communications campaign for cervical cancer prevention developed - to be implemented in the coming period
http://www.euro.who.int/en/countries/north-macedonia
2. Upload here: Communications and Visibility (OPTIONAL)
Links to videos from Covid-19 vaccination hesitancy campaign: https://www.unicef.org/northmacedonia/vaccines-save-lives