## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | SUPPORT TO JOBS, THE RESILIENCE OF THE SMALL ENTERPRISES AND INFORMAL WORKERS DURING AND BEYOND THE COVID19 IN CAMEROON | Overall Duration (months) | 12
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | January 2021
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | December 2021
Country | CAMEROON | Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | ILO UNHABITAT UNESCO UNFPA | National counterparts (government, private, NGOs & others) and other International Organizations |  The Ministry of Employment and Vocational Training (MINEFOP)  The National Employment Fund (FNE),  The Ministry of SMEs (MINPMEESA)  The Ministry of Women and Family Promotion(MINPROFF)  Ministry of Housing and Urban Development (MINHDU)  The Ministry of Public Health (MoH)  The Ministry of Youth and Civic Education (MINJEC)  The Ministry of Scientific Research (MINRESI)  The Ministry of Environment, Nature Protection and Sustainable Development (MINEPDDED)  The Ministry of Arts and Culture (MINAC)  Ministry of Communication (MINCOM)  Ministry of Territorial Administration (MINAT)  The municipalities  FEICOM  Employers' organizations  Workers' organizations  Civil society organizations (CSOs), Women Associations (National Chapter of the Organization for Women in Science for the Developing World), youth associations and networks (PAYNCoP, LOYOC, Youth National Council, Youth Connekt Cameroon, StrawAcademy, Accord Parfait, AfricAvenir-G54, DMJ)  Media, community radios; Research institutions: Panafrican Development Institute; Universities of Douala, Yaoundé 1 and Dschang; National Statistical Institute; National Population Census Bureau, National Institute of Cartography Local Authorities: Douala, Yaoundé and Bafoussam Councils, Municipalities, Associations of Residents, traders and women, Prison and Markets Administration, UN agencies: UNDP, UNECA, UNWOMEN, UNHRC and IOM, UNESCO, UNICEF Civil Society Organizations: Traders associations, Professional Associations"
Report Cleared By
o Name: | ALI MADAÏ BOUKAR
o Title: | Subregional Specialist of Employment and Development-ILO DWT Central Africa
o Email address: | madai@ilo.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | In collaboration with the Ministry of Employment and the municipalities of Douala 4 and Yaoundé 2, a sample of women micro-entrepreneurs in the green economy was selected on the basis of objective criteria. The 100 women were selected from the database of the Integrated Programme of the Informal Sector (PIAASI), coordinated by the Ministry of Employment. The training modules for the empowerment of these women were prepared by PIAASI in collaboration with the ILO. Technical training workshops for vulnerable women are planned for the month of August. As part of the strengthening of employment services to improve the quality and offer of services for vulnerable women's populations in the context of COVID19, the project instituted a collaboration between the ILO, the National Employment Fund (NEF) and the municipalities of Yaoundé and Douala. To this end, municipal counsellors, jobs and enterprises counsellors (from NEF), and social partner organizations have been trained on the e-employment platform, which is a tool helping vulnerable populations (such as women and young people) to better access employment and business opportunities offered by companies. Municipal counsellors, employment service counsellors and social partners have a better understanding of the usefulness of the platform, which facilitates relations between companies and job seekers and business opportunities seekers. Better still, two technical training workshops including women, took place in Yaoundé and Douala, to train the employment services and municipalities of these 2 regions of Cameroon, on the usefulness of the job terminals being installed as part of the project. These employment kiosks are relays of the NEF's general employment platform, at the decentralized level.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The MPTFII project aims to enhance the economic empowerment of vulnerable women in 2 municipalities of Cameroon. To this end, regarding the output 1.1, 100 women identified on the basis of objective targeting, based on consensual criteria, were selected from an official data base of the ministry of employment and vocational training. Of these women, 25 will be selected to receive a small grant for the improvment of theirs activities in order to create jobs as well. Their age ranges from 17 to 40 years. Regarding the process of implementation of job terminals in the 2 selected municipalities of yaounde and Douala (output 1.2), 40 beneficiaries (job consellors, municipalities consellors, social partners), have received technical tools, informations, in order to better advice and train the women job seekers and those who are planned to create their own small enterprise;
3.1 | Results: Outcome Level | Please include outcome level results achieved | Promoting the creation of quick (based on high Labour Intensive activities-HLIA) and sustainable jobs based on more enhanced and effective labour market institutions (Public job services, Cooperatives, SMSEs) for the most vulnerable women and young people Indicator: Number of vulnerable women/young, benefiting from socioeconomic recovery based on quick sustainable jobs and small grant 40 women are empowered in the employment services tools in douala and yaounde
3.2 | Results: Output Level | Please include output level results achieved | nef
For the Outcome 1, output 1.2, 40 job consellors and municipalities officials and social partners, were trained on the digital services provided by the employment platform (e emploi of the National Employment fund). 2 municipalities are enhanced on the employment services promotion tools
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | the main difficulty is related to the context of the health crisis which has limited face-to-face meetings in some extent in order to speed up the start of certain activities with the national stakeholders of the project. To address this issue, the webinars were organized despite the low quality of the internet connection in Cameroon.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | one relevant finding of the project is the good linkage of the MPTF project to the national green jobs programme in Cameroon. One of the component of the project will serv as pilot initiative to boost the green job programme in the area of empowering small enterprises managed by women in this area. this approach wil sustain the process of resource mobilization to implement the national green jobs programme led by the ministry of employment;
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | we have a good potential to improve the partnership around this project given that it is linked to the national green job programme which has an operational resource mobilization plan. The working approach was participatory and all the partners (municipalities of Yaoundé 2, Bafoussam 3 and Douala 4) responded positively to our approach by providing us with facilities to be able to reach the populations, local authorities and all other components of civil society.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | instead of 3 municipalities, given that the north of Cameroon remains insecure and requires resources beyond the available fund of the MPTF project, we worked on 2 municipalities (yaounde 2 and Douala 4)
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | 3 UN volunteers and 5 UGP members are mobilized for the success of the project

## Feuil1
Outcomes
Outcomes | Output | Description
Outcome 1 |  | Promote the creation of quick and sustainable jobs based on labour-intensive activities and enhanced intermediation, counselling and empowerment services for women, youth, cooperatives, MSMEs
| Output 1.1 | The technical and financial capacities of women, vulnerable young people, cooperatives, are enhanced in order to enhance the creation of quick and decent jobs, in pilot municipalities
| Output 1.2 | Tools and micro grant to facilitate the promotion of innovative sustainable enterprises and employment services (information, intermediation and placement) for vulnerable women, small business holders and young job seekers, are being developed and applied in pilot municipalities
Outcome 2 |  | Strengthening the technical and professional skills of self-employment and the professional integration of vulnerable women and young people most affected by the pandemic
| Output 2.1 | Targeted tools and approaches to skills development for self-employment and professional integration are being applied for vulnerable women and youth at pilot sites
Outcome 3 |  | Strengthening life skills and human protection for greater empowerment of the most vulnerable and stigmatized women and youth in crisis
| Output 3.1 | Women and youth's abilities are promoted in life skills for greater empowerment during and after COVID-19
| Output 3.2 | The capacity of decentralized institutions/actors to promote women is strengthened in terms of support for empowerment, social promotion and protection from violence and stigma during the pandemic
Manage Indicators
Indicator Title | Description | Baseline Value | Max Value | Outcomes | Outputs
Outcome indicator 1 | Number of vulnerable women/young, benefiting from socioeconomic recovery based on quick sustainable jobs and small grant | 0 | 300 (150 women, 150 young people) | outcome 1
Output indicator 1.1 | Number of rapid and sustained decent jobs created by High intensive Labour Approach in pilot communes | 0 | 150 (100 women, 50 young people) |  | output 1.1
| Number of beneficiaries of training on safety, health and hygiene at workplace; | 0 | 150 : 100 (informal young and female workers); 50 (women workers)
Output indicator 1.2 | Number of start ups and MSMEs led by women, particulary the most vulnerable, financed through micro grants. | 0 | 15 small business women particularly those operating in the green economy promotion |  | output 1.2
| Number of pilot communes enhanced by the modern and digital employment services for vulnerable women and young job seekers | 0 | 3
Outcome indicator 2 | Number of women, particularly those in vulnerable situation, benefiting from technical and professionnal skills of self employment | 0 | 150 | outcome 2
Output indicator 2.1 | Number of women/young NEET empowered | 0 | 100 (50 women, 50 young people) |  | output 2.1
| Number of TVET programmes and centers enhanced | 0 | 15
Outcome indicator 3 | Number of women and young, particularly those stigmatized and in vulnerable situation, benefiting from lifeskills and human protection | 24697 (14 818 adolescents girls and 9 879 boys) | 30 000 (75% adolescent girls, 25% boys) | outcome3
Output indicator 3.1 | Number of women and youth's benefiting from life skills for greater empowerment during and after COVID-19 | 96862 (77 490 adolescents girls and 19 372 boys) | 110 000 (75% adolescents girls, 25% boys) |  | output 3.1
Output indicator 3.2 | Number of decentralized institutions/actors trained and become able to promote women conditions | 0 institutions/0 actor | 3 institutions/20 actors |  | output 3.2

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] |  | in progress | Activity reports; Field monitoring records Monthly report; Monitoring report; Notes from local authorities; Minutes of dialogue
Promote the creation of quick and sustainable jobs based on labour-intensive activities and enhanced intermediation, counselling and empowerment services for women, youth, cooperatives, MSMEs
Indicator:Number of vulnerable women/young, benefiting from socioeconomic recovery based on quick sustainable jobs and small grant
Baseline: 0
Planned Target: 300
Output 1.1 The technical and financial capacities of women, vulnerable young people, cooperatives, are enhanced in order to enhance the creation of quick and decent jobs, in pilot municipalities | ongoing (100 women were already selected based on competitive criterias) | Ongoing (the process is implementing in collaboration with UN Habitat and the 2 municipalities of Yaounde 2 and Douala 4)
Indicator 1.1.1: Number of rapid and sustained decent jobs created by High intensive Labour Approach in pilot communes
Baseline: 0
Planned Target: 150 (100 women, 50 young in informal sector)
Indicator 1.1.2: Number of beneficiaries of training on safety, health and hygiene at workplace; |  | Ongoing
Baseline: 0
Planned Target: 150 (100 women and 50 young in informal sector)
Output 1.2 Tools and micro grant to facilitate the promotion of innovative sustainable enterprises and employment services (information, intermediation and placement) for vulnerable women, small business holders and young job seekers, are being developed and applied in pilot municipalities | ongoing (100 women small business holder were already selected based on competitive criterias)/25 of them will received the Grant folowing the test planned in august | it remains possible to exceed the target of 15 small business women, based on consultations with the ministry of employment | list of selected small business women
Indicator 1.2.1: Number of start ups and MSMEs led by women, particulary the most vulnerable, financed through micro grants.
Baseline: 0
Planned Target: 15 small business women in green economy
Indicator 1.2.2: Number of pilot communes enhanced by the modern and digital employment services for vulnerable women and young job seekers |  | 2 pilot communes (yaounde 2 and Douala 4) were already enhanced (the implementation of the jobs terminal in these 2 municipalities will end the process in august) | technical workshop reports from National Employment fund and ILO
Baseline: 0
Planned Target: 3
Output 1.2,4 Tools and means to facilitate access to innovative sustainable employment services (information, intermediation and placement) for vulnerable jobseekers, including women, are being developed and implemented in the pilot municipalities |  |  | Activity reports; Field monitoring records Monthly report; Monitoring report; Notes from local authorities; Minutes of dialogue
Indicator 1.2.4 : Strengthen the skills of mayors and municipal staff in developing and deploying community engagement, communication and risk recovery plans through online training workshops and the use of advanced technologies
Baseline: 0
Planned Target:
Indicator 1.2.5: Integrate the municipal recovery plan in place, using state-of-the-art technologies (internet, tablets, open GIS software) to better monitor COVID-19 trends and responses from public and private actors |  |  | Activity reports; Field monitoring records Monthly report; Monitoring report; Notes from local authorities; Minutes of dialogue
Baseline: 0
Planned Target: 3
Indicator 1.2.6: Purchase of technical and digital tools and equipment to support the extension of employment services, testing of labour intensive activities, training tools
Baseline: 0
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board