## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | ENHANCING FOOD SECURITY, NUTRITION AND RESILIENCE IN KIRIBATI | Overall Duration (months) | 7 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 8.05.2020
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | Kiribati | Current End date(dd.mm.yyyy) | 31.12.2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF & FAO | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health and Medical Services, Ministry of Agriculture, Minisitry of Fisheries
Report Cleared By
o Name: | Mohammed Mozeem
o Title: | Partnerships Specialist, RCO
o Email address: | mohammed.mozeem@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Focus of UNICEF interventions remained on strengthening essential nutrition services, nutrition counselling for pregnant women and lactating mothers, mobilization of prepositioned essential nutrition commodities and procurement of essential supplies. In addition, UNICEF promoted engagement with and mobilization of different local and national level stakeholders to promote nutrition messages and healthy eating in context of COVID-19. Some key activities undertaken are as per below: Screening, Referral and Treatment of Children for Acute Malnutrition A house to house screening campaign for actue malnutrition was conducted by 184 trained community volunteers and nurse-aides. The intensified screening efforts sought to ensure that no child was being left behind in routine child health sessions, and flag at-risk children for ongoing monitoring by the health facility. A total of 10,884 children (5609 boys and 5275 girls) were screened. Data collected identified 57 cases of moderate acute malnutrition (25 Male and 32 Female) and 28 Cases (14 Male and 14 Female) of Severe Malnutrition referred to health facilities for treatment and follow up. In order to overcome logistical challenges with implementation faced during the COVID-19 pandemic remote guidance to health facility staff was provided via telephone to enable assessments to be conducted in outer islands which could not be visited by plane. Supplementation of micronutrients To ensure mothers and children have continued access to adequate micronutrient supplementation during COVID-19, prepositioning and distribution of Vitamin A for children 6-59 months and Iron Folic Acid for pregnant women has been completed reaching a total of 1,385 children (6 – 12 Months) and 10,834 children (13 – 59 month), with distribution in some communities ongoing. Capacity building of the health workers to ensure continuous delivery of quality nutrition services 29 Medical Assistants and 37 Public Health Nurses were trained on High Impact Nutrition Interventions, including counselling skills, MUAC assessments and how to conduct community-based food/cooking demonstrations. The ‘how to guides’, a community engagement tool for health workers has recently been developed by UNICEF/MHMS to strengthen engagement of health workers through home visits, outreach, community dialogues, demonstrations and campaigns. Health workers can utilize this tool and their skills developed on nutrition counseling to expand their engagement on nutrition with caregivers and the wider community. Social and Behaviour Change and Community Engagement At the community level, eleven church denominations and six non-governmental organizations (622 community volunteers) have been orientated on nutrition including the provision of localized advice for maintaining a healthy diet in the context of COVID-19. Follow up visits were conducted with church denominations who developed action plans for how these messages can be integrated into their routine activities. Media channels including roadshows, radio broadcasts and SMS messages were used to reinforce key messages accross a national scale. The interventions of FAO focused on strengthening the capacities for the production and marketing of safe local agriculture and fish products to improve local food security through the conduct of various trainings and distribution of materials and equipment. FAO established partnerships to better implement the activities of the project. Some of the key activities undertaken were: Enabling safe small-scale community fish processing and value adding The establishment of a fully operational small-scale community fish processing facility aids in the manufacturing of novel tuna products for domestic sales in South Tarawa. The product development conducted is to perfect shelf stable tuna products for commercial production within The projects planned initiatives for Arorae, Tamana and North Tarawa CBFM community processing locations. It is also an initiative to stimulate market opportunities to neighboring islands for the outer island community fish processing centers. The project developed innovative designs for portable 'hand pushed'' fish hygiene trolley to assist road side fish vendors in improving hygiene and food safety within the identified major food risk unregulated practice. Molded fiberglass tops manufactured overseas are currently being procured while locally manufactured trolleys have been designed in the country. Improving access and training for nearshore pelagic fishing New fishing gears were manufactured with locally available low-cost materials in order to commence some training prior to larger orders coming from overseas. Training of trainers also commenced for the improvement of onboard handling of fish at point of capture. New mid water fishing technologies were also introduced to assist small scale tuna fishers in improving efficiencies within existing artisanal fishing operations, which are also suitable for inclusion within present vessel operational parameters to ensure safety at sea is not compromised. The project also helped develop innovative designs for portable 'hand pushed'' fish hygiene trolley to assist road side fish vendors in improving hygiene and food safety within the identified major food risk unregulated practice. Molded fiberglass tops manufactured overseas are currently being procured while locally manufactured trolleys have been procured in the country. Fisheries and agriculture collaboration for improved soils The FAO Kiribati team developed process systems to utilize the large volumes of seaweed polluting South Tarawa beaches. Locally manufactured water tanks were procured as composting containers. The communities involved in the below agriculture trainings are also trialling the seaweed compost technique. Trainings on local production of vegetables and fruits and restoration of traditional fruit trees An increase of both conventional and household production for vegetables and fruits and restoration of traditional fruit trees was the focus in South Tarawa, due to the complexity of travel to the outer islands and that most of the Kiribati population are concentrated in South Tarawa. In cooperation with ALD-MELAD staff, the project trained community members in techniques for improving their household gardening. Trainings include propagation of plants through cuttings, seed and air-layering expansion of home gardens with local materials, soil improvements including how to make or prepare their compost and liquid fertilizer to improve the quality of the soil and production of vegetable and marketing of those. The training will be expanded to outer islands when further inputs including the shipment of seeds arrive and travel is possible so that households can continue to grow safe & nutritious foods. During project implementation, due to the limitations for materials available in Kiribati, local solutions were used to encourage beneficiaries to create home gardening using tins, coconut husks, local trees, extracting seeds from local fruits and planting them. Use of organic materials such as dried leaves, used cardboard, coconut husks, and seaweed empty and used tin cans which are available in abundance for growing seedlings, was encouraged. Local trees and vegetables food crops that grow and well adapted to Kiribati condition were also promoted and distributed. Community members were also trained how to extracting seeds from local fruits and encouraged to share their planting materials in order to increase and sustain their home garden production Improved practices and awareness on agriculture production In collaboration with ALD-MELAD, instructional pamphlets were also developed for all the training techniques taught to the beneficiaries and were distributed to the communities for future reference. In addition, two (2) electrical water pumps were purchased for the ALD nurseries in Kiritimati Island, (7) seven solar powered water pumps purchased for the ALD nurseries located in seven (7) outer islands, 100 sets of Tamana/Marakei pump purchased for the outer islands beneficiaries and 120 Kg of seeds (seven (7) different varieties) were purchased and pending of reception. beneficiaries and 120 Kg of seeds (of seven (7) different varieties) were purchased and pending of reception. Diverse planting materials and tools (biodegradable nursery plant grow bags (50,000 pcs), pruning shears (100 pcs), seedlings tray (1000 sets), peat moss pellets (25000 pcs), peat moss (5000 L), polycarbonate corrugated roofing (15 pcs) were purchased to improve the ALD nurseries to be more resilient and prepare to support the local farmers in the future, but are still in transit.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The purposed of the proposed interventions was to strenghthen access to nutrition services and promote positive nutrition practices during COVID-19.Overall 19,155 pregnant women and children under 5 were reached with essential nutrition services such as Vitamin A and Iron Folic Acid during the COVID-19 pandemic period. Nearly 50,000 community members received messages on infant and young child feeding practices via a range of media and community based platforms such as radio talkback, SMS, roadshows, practical cooking demonstrations and promotion through churches and NGO's. The agriculture interventions have trained a total of 423 direct beneficiaries with 2,538 indirect beneficiaries, 25% of which are women. This will be expanded to include a total of 1000 direct beneficiaries in South Tarawa and 100% of farmers in the outer islands of Banaba, Teraina, Taburaean, Maki, Marakei and Kuria. For the fisheries harvest trainers have been skilled up to continue training for additional fishers (120 in South Tarawa, and 12 in Abaiang, Maina, Aruanuka, and Kuria) once the delivery of the materials and equipment are completed. Additionally 24 women and 4 men were trained in fish processing and a target of 40 fish processors will be reached within the first quarter of 2021, these processors will supply novel tuna products to thousands of I-Kiribati on outer islands and urban markets.
3.1 | Results: Outcome Level | Please include outcome level results achieved | 1.1 12219 children under 5 have access to essential nutrition services such as Vitamin A supplementation. 1.2 49,557 people reached with nutrition messages through multi-modal platforms. (see RBM) 2.1 100% of farmers in the outer islands of Banaba, Teraina, Taburaen, Makin, Marakei and Kuria and 65 % of farmers in South Tarawa will have strengthened capacity for production and/or marketing of agriculture. In addition, 12 fishers in Abaiang, Maiana, Aranuka and Kuria as well as 120 fishers in South Tarawa will be enabled to strengthen fisheries production while at least 48 vendors will be trained in improved safety for fish handling and production of value-added tuna products enabling supply novel tuna products to thousands of I-Kiribati on outer islands and urban markets.
3.2 | Results: Output Level | Please include output level results achieved | The following out put level results were achieved: 1.1.1 29 Medical Assistants were trained on High Impact Nutrition Interventions, including counselling skills and how to conduct community-based food/cooking demonstrations. 1.1.2 10,884 children screened for severe acute malnutrition. 1.1.3 57 cases of moderate acute malnutrition and 28 cases of severe acute malnutrition were detected and treated. 1.1.4 12,219 children recieve vitamin A supplementation (1,385 6-12 months, 10,843 13-59 months). 1.1.5 6936 pregnant women receved iron folic acid supplementation. 1.1.6 11 church groups were orientated including 622 trained volunteers on Infant young child feeding and maintaining a balance diet. 1.1.7 a six-weeks radio program on nutrition aired daily in the morning and evening on Radio Kiribati with a likely (KSDIS, 2018-19) 36.3% (Male) and 35.1% (Female) coverage of the adult population in both rural and urban settings. (See RBM) 2.1.1 Communities trained and supplied with necessary resources (including local seaweed for compost) for local and traditional vegetable and fruit production. In cooperation with ALD-MELAD, a total of 423 community members, mostly in South Tarawa, were trained for the different techniques for improving their household gardening. Trainings were adapted depending on the level of knowledge of the beneficiaries from not having knowledge on basic gardening techniques to already experiencing home gardening. Once materials arrive, all farmers the outer islands of Banaba, Teraina, Taburaean, Maki, Marakei and Kuria will benefit from seeds, planting materials and training. In addition, the above outer islands have all been enable to increase production through provision of pumps for water (solar, electric and hand depending on the beneficiary) 2.1.2 Pilot trainings were initially conducted with locally purchased equipment as the larger volumes of fishing equipment are still in transit. Training of trainers was also conducted to enable trainings to continue beyond the life of the project. By the end of Q1 2021, 120 fishers in South Tarawa and 12 from each of the following outer islands will be trained – Abaiang, Maina, Aruanuka, and Kuria. Trainings will be roll-out once the delivery of the fishing equipment is completed. 2.1.3 Due to procurement delays, the output was expanded to include value adding to products for fish sellers to increase revenue generating activities and support the sustainability of the hygiene trolleys. Manufactured home-made sausage extruder were made a and solar convection drier unit with a heater back-up system (coconut husks) was developed. Fish sellers as well as trainers were trained to enable the commercial production of value-added tuna products. These technologies in Kiribati will assist communities with sustainable revenue generating activities, including improved hygiene and food safe practices. Support is being developed with detailed pictorial guides and training videos which will be disseminated to all beneficiaries. At least six (6) women fish seller groups in South Tarawa and Betio will be provided with access to common fish cleaning facility during the first quarter of 2021 once the delivery of equipment procured overseas is completed.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Financial processing: Delays in disbursements of funds rippled into delays in starting of activities as planned. To overcome this, continuous follow up and starting implementation of activities that did not require financial resources. Available in country funds from other programs were also utilised where necessary. These were reimbursed upon receipt of programme funds in September enabling completion of activities despite some delays in the beginning. Monitoring of programme activities: Limited internal flight options and infrequent flights availability in Kiribati has restricted the selection of and number of outer islands visited. Currently there is only one plane operating the domestic flights route. In order to mitigate this, the team has only travelled to islands possible to visit by boat and conducted remote monitoring via telephone calls. Human resources: Limited human resource capacity made it difficult to follow up and to provide technical backup to clinics during their rollout of training on MUAC. It also made it difficult to follow up on trained volunteers beyond the project cycle minimizing the potential to ensure continuous and sustainable dissemination of correct messaging on positive nutrition practices. Comunication and coordination: Difficulties in reaching focal persons from the NGOs and Faith based institutions through telecommunication resulted in slight delay in initiating the trainings. This was overcome by physically visiting offices across South Tarawa. International procurements were identified as another difficult challenge encountered. As not all the needed interventions such as planting materials and fishing equipment are available in the country, the purchasing of seeds and fishing equipment that meet the technical specifications were done overseas. However, delays in the delivery were experienced due to the supply shortages and movement restrictions imposed due to the global pandemic. The effects of the delays were mitigated through the procurement of locally available seeds and equipment to be used as training and demonstration materials while waiting for the completion of the delivery of the necessary materials.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Data collection and gender markers: The programme reinforced the need for expansion of the current Health Information System to capture more inclusive information, enabling dissagregation of indicators by sex and age. Innovative procurement options for small businesses: With the worldwide lockdown and reduction in freight lines, materials to be purchased outside of the country can take a very long time to arrive (up to two or three times more than the average time), hence, it is important to use local materials available in the local stores. Creating systems that allow the organization (UN) to deal with small businesses that don´t have access to internet or regular banking systems, but do have the materials, would overall, increase local transactions and create more opportuntiies for income generation in the country. Social behaviour change: Use of mass media campaigns such as SMS and Radio talk show is an important avenue available for a nationwide access that includes hard to reach Islands for dissemination of critical nutrition messaging. Tripartite partnerships between the Nutrition Department, NGOs and Faith based institutions can facilitate a quick and large scale dissemination of knowledge on positive nutrition practices in urban setting. Opportunities for remote training and monitoring in areas of low internet connectivity: Unavailability of flights to some islands required the to use telecommunications to facilitate remote training and guidance to health facility staff. This approach was a useful and feasible alternative in light of restrictions to mobility. Future remote trainings should embed over the phone knowledge assessments and/or participant feedback to act as a comparison to in-person training sessions. Lots of new things were learnt along the way. Age does not matter with some communities especially those who are already engaged in home gardening and have greatly benefited from their own activity. It is also a good learning opportunity for both trainers and trainees to share their own experiences and exchange of planting materials. As noted with issue of receiving fund for training and for imported seeds, as their great appreciation for the content of the training and sharing some new propagation methods (simple but new to them, such as propagating tomato from cuttings, air-layering of papaya trees) communities were happy to share their planting materials freely to their fellow neighbours and as well as committed their own resources by providing their own meal, transport and committed throughout the training. It is also interested to learn that some of the active home gardeners have already used seaweed as their ingredient in their composting, but need more proper information on how best to utilized the seaweed. The Youth in Agriculture Sport is another initiative from ALD that this project was very active to support. ALD will run a sport with a reward for wining team as first price of $1000 second by $750 and third by $500. In order for youth team to participate they must plant certain amount of identified (10 selected crops such: 50 cabbages or spinach, 12 tomatoes, 20 nambere, 8 papaya, 6 banana, 4 pumpkin, 20 kangkong, 20 cassava, 10 amaranthese, and 20 sweet potatoes) vegetables at their Home or started their HG for those who have not yet started and this must be properly check to confirm those who are ready to enter the soccer and volleyball competition. This initiative resulted in flooded a number of household involved in HG at their own cost. The project will assisted in providing seedlings for those that are not available. There is community empowerment and youth commitment when they are involved in such important activities.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The programme facilitated the development of opportunistic partnerships for behaviour change in nutrition through engagament with faith based organisations and NGO's. Recognising human resource constraints in the capacity of the health promotion departments, these partnerships facilitated the widespread dissemination of information on nutrition at the community level. Opportunities for the strengthening and formalisation of these partnerships for the ongoing sustainability of the programmes objectives are vast. A recommendation arising from the implementation of this programme included the development of a tripartriate agreement between the MHMS, NGO and FBO's to facilitate greater reach, distribution of resources and coordinated messaging during emergency and non-emergency situations. The programme further facilitated the inclusion of local governance structures (Island and Urban Councils) in programme implementation. These visits included a chance to meet with the Island Councils and the Island COVID-19 taskforce to reinforce the importance of ensuring adequate nutrition and healthy diets are incorporated within COVID-19, island level response efforts.There is still scope for strengthening the partnerships between the relevant ministries, Ministry of Health and Medical Services and Ministry of Agriculture during programming. This includes alignment of timelines and location of implementation activities so that interventions are coordinated especially for outer-island visits. Improved communication and coordination between these ministries will ensure a unified and targeted response to COVID-19 related food security and nutrition challenges. Partnerships were formed to achieve the objectives of the project. As the interventions in agriculture was based on the COVID-19 response prepared by ALD-MELAD. FAO supported the request to improve the ALD nurseries with planting materials and seeds, so it can become more resilient and less dependent in case of any similar emergency situations. With the provision of such materials, seeds and water pumps, the nurseries will be more productive and able to provide seedlings to the local farmers and outer islands. With the experience of the ALD officers, local materials available in South Tarawa were used for demonstrations during the trainings. These is way to recycle materials and reuse existing resources on the country. The project has also established partnerships with a community-based fisheries management (CBFM) community initiative within Buariki, North Tarawa, with an NZ funded project in Tamana and Arorae and with a Government Ministry "Fish for Life" programme. In all cases, the partners are able to build longevity with all initiatives and can assist in the sustainability of the project objectives. The distribution of materials and equipment once delivered will be part of the complementary support to the project from FAO and other partners. On the other hand by way of direct interaction and conversion with any community good information and ideas can be generated which then can be used to design the most appropriate and cost effective actions to address their specific issues. Betio Community is a very large community consisted of more than 100 active small communities and each community consisted of 15 to 25 members. It is guided and monitored by the Police Community Services and run a three weeks consultation with different ministries and sectors to address some of the burning issues including; youth unemployment, waste pollution, overcrowded, youth alcohol behavior, unhealthy living condition and other issues that are of interest to the Community. Participants age ranged from young as under 21 years old to over 60 years. There were 60 participants in total who represented the three zones for Betio; 20 from Temakin, 20 from Nuuka and 20 from Takoronga. It was anticipated that the 20 representatives from each zone will share their learnt skills and knowledges to their respective communities upon completion of their three weeks training but most importantly to start their home garden at their respective homes. The agricultural expert for the UN COVID 19 Recovery Response project together with the support from ALD through the Extension and Livestock Section participated in the two days training workshop assigned for ALD. The training gave an insight to the ALD staff and NAO on assessing the level of participants knowledge and understanding on basic skills and management on home gardening. The training started with basic skills on home gardening. Participants were given information on how to select the type of crops to grow and most importantly it is important to understand the growing nature and physiology of a plant you select to grow in your garden. Start your home garden with what resources available at your own area is the key message given to Betio Community participants. The team encouraged them to start with cut flowers grown in empty tin cans which are always in abundance at their area. If participants can grow 100 flowers or more flowers using those tins and can sell those at $1.00 or $2.00 each, they can earn that much from only flowers using waste tin cans. Participants were challenged not to be idle or making excuses like, I do not have garden tools, or I do not have seed, or I do not have the skill. It is important that participants must allocate one or two hours each day if they are going to reach the benefit from Home gardening.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | No formal assessments or evaluations were conducted during the programme cycle. The MHMS and UNICEF completed a joint report to assess implementation of activites, lessons learnt and areas for further action and cooperation. Qualitative feedback was gathered from participants and beneficiaries throughout implementation to inform progress towards desired results. An informal assessment on the availability and cost of fruit and vegetables in market the was conducted in July to determine variety of local seeds available and market prices.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Revision to output 1. - Number of children admitted for treatment of SAM- results of the SAM assessment indicated that initial targets for estimated cases identified for treatment were lower than expected. Difficulties collecting data by gender due to lack of gender disagregation in HMIS required revision of output 1.2.4 nto exclude gender markers. Disagregation was conducted based on age. The target for outcome 2.1 [50% of population with strengthened capacities for the production and/or marketing of safe local agriculture and/or fish products by December 2020] was also revised to reflect the target communities and islands identified at the beginning of project implementation. Revised outcome target: 100% of farmers in the outer islands of Banaba, Teraina, Taburaen, Makin, Marakei and Kuria and 65 % of farmers in South Tarawa will have strengthened capacity for production and/or marketing of agriculture. In addition, 12 fishers in Abaiang, Maiana, Aranuka and Kuria as well as 120 fishers in South Tarawa will be enabled to strengthen fisheries production while at least 48 vendors will be trained in improved safety for fish handling and production of value-added tuna products enabling supply novel tuna products to thousands of I-Kiribati on outer islands and urban markets. Revision to output 2.1.3 – Target is “At least 6 women fish seller groups in South Tarawa and Betio with access to common fish cleaning facility by December 2020”. This includes 48 individual fish sellers, 28 of which have now received training in value adding techniques. However the full output will be achieved by March 2021 due to the delay in the arrival of materials and continuation of the work through a complementary project.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UNICEF received US$ 150,000 under the grant SM200375 from UNSG-MPTF. As of December 2020, the total expenditure under this grant has been US$ 152,107.09, which is 100% expenditure, although some funds is still with Ministry of Health and Medical Services as Cash Advance and Prepayments. Of the total programmable expenditure of 142156.16, US$ 30,625.41 have incurred under the category Supplies, Commodities, Materials and US$ 111530.75 has been transferred to Ministry of Health and Medical Services as Transfers and Grants to Counterparts. No expenditures have incurred under the Budget Lines of Staff and other personnel; Equipment, Vehicles, and Furniture, incl. Depreciation; Contractual services; Travel; and General Operating and other Direct Costs. FAO received USD 150,000 from UNSG-MPTF to implement project activities related to COVID-19 response in Kiribati. Approximately 95% of the total amount received will be spent to achieved targeted project outputs. This can be explained by the variable nature of some of the procurement costs. The final total expenditure will be determined once project deliverables have been completed. A national agriculture officer was recruited for the implementation of this project.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1: 1.1 Children, pregnant and breastfeeding women have improved access and receive essential nutrition services (screening for malnutrition, treatment of children with SAM, IYCF counselling and support, micronutrient supplementation such as Vitamin A or MNPs for children) during the COVID-19 pandemic period. | 12,219 (78.8%) | Due to logistical constraints and geographical remoteness of some islands, nutrition commodities have only reached 5 out of the 6 districts in Kiribati. | HMIS
Indicator 1.1.1: Number of children that have access to essential nutrition services during the Covid-19 pandemic period
Baseline: N/A
Planned Target: 15,500
Indicator 1.1.2: Number of people reached with nutrition messages in the context of Covid-19 | 49,557 82.6% | Reporting does not take into account number of beneficiaries by NGO/FBO representatives | Media coverage/MHMS report
Baseline: N/A
Planned Target: 60,000
Output 1.2 | 29 |  | MHMS Report
Indicator 1.2.1: Number of Medical Assistants trained on IYCF Counselling
Baseline: 0
Planned Target: 30
Indicator 1.2.2: Number of children under five years screened for Severe Acute Malnutrition disaggregated by sex | 10,884 (5609 boys, 5272 girls) (72%) | Due to logistical constraints the SAM asssessment only covered 5 out of the 6 districts in Kiribati. | MHMS Report
Baseline: 0
Planned Target: 15,000
Indicator 1.2.3: Number of children under five admitted for treatment of Severe Acute Malnutrition disaggregated by sex | 57 cases of Moderate acute malnutrition (25 Male and 32 Female) and 28 Cases (14 Male and 14 Female) of Severe Malnutrition identified and treated. | Of 10,884 children screened only 28 cases of SAM were identified. Nutrition supplies will be continue to be utilised for treatment of complicated SAM identified through routine assessments. | MHMS Report
Baseline:69
Planned Target: 400
Indicator 1.2.4: Number of children 6-59 months with routine supplementation of Vitamin A disaggregated by sex | 12,219 (1,385 6-12 months, 10,843 13-59 months) | Due to logistical constraints and geographical remoteness of some islands, nutrition commodities have only reached 5 out of the 6 districts in Kiribati. Disaggregation could not be achieved as this is not captured in HMIS. | HMIS
Baseline: 6,000
Planned Target: 14,000
Indicator 1.2.5: Number of pregnant women supplemented with Iron Folic Acid | 6936 |  | HMIS
Baseline: N/A
Planned Target: 2,750
Indicator 1.2.6: Number of church groups orientated | 11 (622 volunteers from FBO's and NGO's trained) |  | MHMS report
Baseline: 0
Planned Target: 10
Indicator 1.2.7: Number of radio panel discussion aired | Daily radio panel discussion aired for 6 weeks |  | MHMS report
Baseline: 0
Planned Target: 6
Outcome: Strengthened capacities for the production and marketing of safe local agriculture and fish products | 100% of farmers in the outer islands of Banaba, Teraina, Taburaen, Makin, Marakei and Kuria and 65 % of farmers in South Tarawa will have strengthened capacity for production and/or marketing of agriculture. In addition, 12 fishers in each island - Abaiang, Maiana, Aranuka and Kuria - as well as 120 fishers in South Tarawa will be enabled to strengthen fisheries production while at least 48 vendors will be trained in improved safety for fish handling and production of value-added tuna products enabling supply novel tuna products to thousands of I-Kiribati on outer islands and urban markets | The variance was caused by the delays in the delivery of resources and materials because of the shortage in supplies and restrictions in movement of both supplies and personnel | Project Reports / training reports
Indicator: Percentage of population with strengthened capacities for the production and marketing of safe local agriculture and fish products
Baseline:
Planned Target: 50% of population with strengthened capacities for the production and/or marketing of safe local agriculture and/or fish products by December 2020
Output 1.1 Communities trained and supplied with necessary resources (including local seaweed for compost) for local and traditional vegetable and fruit production | A total of 423 direct beneficiaries with 2538 indirect beneficiaries, 25% of which are women, have been reached by the project through different trainings and mentoring. Once materials arrive, all farmers the outer islands of Banaba, Teraina, Taburaean, Maki, Marakei and Kuria will benefit from seeds, planting materials and training. In addition, the above outer islands have all been enable to increase production through provision of pumps for water (solar, electric and hand depending on the beneficiary) | The variance was caused by the delays in the delivery of resources and materials because of the restrictions in movement of both supplies and personnel | Training Reports
Indicator 1.1.1: Number of farmers (at least 40% women) in South Tarawa and outer islands who received training and planting materials for local and traditional fruit and vegetable production
Baseline:
Planned Target: At least 1500 farmers in South Tarawa and 500 in outer islands received training and planting materials for local and traditional fruit and vegetable production by December 2020
Output 1.2. Fishers in selected locations trained on improved fishing techniques to supply South Tarawa market | Trainers in South Tarawa have been enabled through the trainings conducted including trainings for improved onboard handling and new vertical longline fishing techniques. By the end of Q1 2021, 120 fishers in South Tarawa and 12 from each of the following outer islands will be trained – Abaiang, Maina, Aruanuka, and Kuria. Trainings will be roll-out once the delivery of the fishing equipment is completed. | The variance was caused by the delays in the delivery of resources and materials because of the shortage of supply as well as restrictions in movement of both supplies and personnel | Project Reports
Indicator 1.2.1: Number of local commercial fishers in selected locations who received training on improved fishing techniques
Baseline:
Planned Target: At least 70% of local commercial fishers in South Tarawa, Abaiang, Maiana, Aranuka and Kuria islands received training on tuna or snapper fishing techniques by December 2020
Output 1.3. Common fish cleaning facility established for women fish seller groups in South Tarawa and Betio | Training in post-harvest techniques for women’s groups have been completed. The project is currently waiting of the completion of deliveries of the materials ordered for provision of the fish hygiene trolleys.
Indicator 1.3.1: Number of women fish seller groups in South Tarawa and Betio with access to common fish cleaning facility |  | The planned target remains the same. The variance was caused by the delays in the delivery of resources and materials because of the restrictions in movement of both supplies and personnel | Project Reports
Baseline:
Planned Target: At least 6 women fish seller groups in South Tarawa and Betio with access to common fish cleaning facility by December 2020
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Photos from agriculture interventions are attached.
New initiative develops tuna products in Pacific Island countries: http://www.fao.org/in-action/sustainable-nearshore-fisheries-improves-livelihoods-pacific/news/details/en/c/1365506/
Strengthening livelihoods and nutrition resilience during COVID-19. Kiribati is a Micronesian independent republic that consists of 33 islands, 21 of which are inhabited. The islands are dispersed over 3 million km2 of the Pacific Ocean. The generally poor agricultural quality of the flat and low- lying islands, limits the supply of diverse, nutritious food sources for consumption. Families largely rely on fish and rice as their primary food sources. Caregivers have low levels of awareness of what are appropriate dietary practices for infants and as a result, only 9% of Kiribati children receive a minimum acceptable diet.The socio-economic impacts of COVID-19 threaten to further exacerbate these food security and dietary challenges. Families in Kiribati may find it more difficult to afford the costs of food and other goods as they are less likely to receive remittances from overseas, and experience increased unemployment. Travel and mobility restrictions could also result in a decreased capacity of the health system to deliver essential health and nutrition supplies and services. Under the COVID-19 MPTF funded programme, UNICEF and FAO have partnered to jointly address these challenges and enhance foods security, nutrition and resilience in Kiribati during COVID-19. As part of this programme, UNICEF and FAO are committed to ensure mothers have the knowledge and capacity to provide nutritious, diverse diets to their children during COVID-19. Communities were made aware of cost-effective actions to protect their children through the promotion of appropriate breastfeeding practices along with home-gardening and planting techniques to increase supply of diverse foods for their families. Multiple platforms were utilized to engage all caregivers include high risk and hard to reach households including, community roadshows and drama’s, radio and SMS broadcasts and engagement with local councils. Luisa Taninga is a mother of two children in the community of Temaiku, Kiribati. Recently she witnessed a road show from the Health Promotion department on nutrition, making her aware of actions she can take to keep her family healthy during the COVID-19 pandemic period. She remarked, “We will start planting fruits and vegetables, my husband to cut toddy and to maintain breastfeeding of my younger child.” To strengthen access to essential nutrition services, UNICEF and the Ministry of Health and Medical Services (MHMS) also mobilized 170 community volunteers to conduct house to house visits to identify and refer children with moderate or severe acute malnutrition. During the screening campaign one of Luisa’s two children was detected for severe acute malnutrition and referred to the hospital for life-saving treatment. “It was a good experience because it helped me know the status of my children. My younger son is healthy except my older son who is malnourished (SAM). I felt sad at first, but then encouraged myself to aim to make my older son become healthy like his brother, which is what I have been doing until now.” As a result of the screening campaign 10,886 children were screened for severe acute malnutrition, enabling the referral of malnourished children to health facilities and hospitals for life-saving support. Buriita Tioti the Medical Assistant in Tamaiku is committed to ensuring all children in her community continue to receive an adequate diet. “Malnutrition is a challenge to us in our line of work, but we want to fight against it and eliminate it from our communities. We have found one way to reach out to all our communities in Temaiku and that is to work with the Mother Community. We will have nutrition awareness and cooking demonstrations and the Mother Community is responsible to disseminate the information and lessons learned to all of the communities. We want our clinic to have zero malnutrition case because in this way we are sure that our children are well taken cared of and are healthy.”
Luisa Taninga, and her son Teeruka Kabuta (1yr) in Temuiku, Kiribati.
MHMS Health Promotion and Nutrition community drama in Temaiku, South Tarawa
Cooking Demonstration With Faith Based organisations

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board