## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Protecting women & children: digitalizing & streamlining social services, and creating a unified platform for national care | Overall Duration (months) | 12 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-10-15
MPTF Office Project Reference Number: | 124359 | Original End Date (dd.mm.yyyy) | 2021-11-01
Country | Maldives | Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA, UNDP, UNICEF | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Gender Family and Social Services (MoGFSS), Ministry of Communication, Science and Technology (MCST), National Social Protection Agency (NSPA), CSOs
Report Cleared By
o Name: | Ms. Catherine Haswell
o Title: | Resident Coordinator
o Email address: | catherine.haswell@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Preparatory work including partnerships and agreement on expectations of the digitizing as well as policy work was carried out during the first half of the project period. Progress on implementation of the planned interventions was delayed with the recent emergence of the COVID-19 Delta variant, the country experienced a third wave of cases. Government partners moved to working from home which had a significant impact on the timeliness of implementation. Activities aimed at social norm change to address violence against women and children under Output 1 were completed. Planning for the implementation of strategic interventions are in progress. Preparatory work, which included multi stakeholder meetings and consultations continued in the reporting period on developing a digital platform for the Ministry of Gender, Family and Social Services (MOGFSS) to provide services for GBV survivors, and enable multi-sectoral support and facilitate a survivor-centered tracking system. During this period, through the digitalization support provided, business continuity of key agencies catering to the vulnerable population such as MoGFSS and National Social Protection Agency (NSPA) was facilitated. Technical and ICT support was provided to the Local Government Authority (LGA) to upgrade their online portal with data on vulnerable populations to support effective service provision by MoGFSS and NSPA. Through project support, the Business Corporation Centre of Maldives is working towards launching a series of localized training programmes in September through the creation of several informative training programmes targeted towards MSMEs, for both physical and virtual delivery, to adapt to the challenges of the situation, and increase outreach.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Institutional capacities of key agencies, namely LGA, MOGFSS and NSPA, working towards social protection were built in terms of understanding and assessing gaps and needs, which can be addressed through digitalization support to ensure continued service provision. During the first half of the year, planning and preparatory work was undertaken and too early to report on beneficiaries reached.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The outcome of the project is to have beneficiaries accessing national social protection services/schemes through the digitized systems developed under the project. Since the digitized systems are not in place as of yet due to delays as outlined in the challenges section, no outcome level results to be reported at this time.
3.2 | Results: Output Level | Please include output level results achieved | Output 1: Consultations were held with the government, UN and CSO stakeholders to better conceptualize social norm change strategies. A concept and a TOC is developed and work underway to start planning on selected GBV prevention activities Output 2: Under the expansion of essential public services through digital solutions in particular GBV, a mobile application for seeking quick help for GBV survivors including reporting, tracking of cases, data generation and multi-agency support for an expanded referral support system which includes, health, psychosocial, shelter, legal, economic and other national support for GBV survivors is ongoing. Before the IT developers come on-board, background work on documenting and mapping the existing referral mechanism including mapping of service provider stakeholders, and development of relevant Standard operating procedures (SOPs) is on-going. Work is underway to ensure adequate mechanisms for quality assurance and survivor centred and rights based services through the digital platform. A TOR for a technical expert on Gender is developed to ensure the mobile application is survivor centred and in line with GBV Guiding Principles. The consultant will be on board during August and the work is expected to be completed by end of November 2021. With the delays in finalization of the TOR in line with the UN Guiding Principles, survivor centred background work including data confidentiality protocols, the process of getting the mobile application developer on board is delayed. Hence the expected results of this activity will be revised to have the mobile application developed by the end of the project period adhering to the UN Guiding Principles on GBV. Given LGA’s key role in strengthening data collection systems at the grassroot level per their mandate, the project has included strengthening the existing online portal ‘GEMEN’ (Local Government Authority Maldives (www.lga.gov.mv) to enable effective data gathering from island councils. During this period, support was provided to strengthen the data collection systems used by island councils, and providing technical advice and ICT equipment to enhance the current capacities at the LGA. The digital equipment provided to LGA were two optimized computer systems which is able to support the operationalizing of the online portal ‘Gemen’, along with an operational training to the relevant focal points at LGA Mandated with the responsibility to support the needs of micro, small and medium sized enterprises, the Business Corporation Centre (BCC), UNDP is working on developing localised and accessible training materials for advocacy and dissemination on social media and mainstream media. These training materials can be accessed virtually to assist target groups, especially women and youth in setting up a business, running the business as well as scaling up. A lot of this information was available when accessing services at the centre physically but given the current COVID-19 circumstances and to ensure uninterrupted support for businesses in need during this time, going online provides equal access to all regardless of their location in the country, and reduces barriers to entry in these areas. The trainings will focus on sustainability, financial skills, managerial skills, digital marketing and solutions and e-commerce. Consultations with various departments of the Ministry of Gender, Family and Social Services, including the National Social Protection Agency (NSPA), Child and Family Protection Services, Local Government Authority and National Bureau of Statistics were completed. The main focus of the consultation was to look at the challenges faced by vulnerable families, or groups in accessing social protection services. A cleared understanding on how a mobile application can be used by these vulnerable families at an island level was sought in the discussion. Based on these discussions and inputs a term of reference for the development of a mobile application for easier access to social protection services was developed and is currently under review by the partners. Hiring of a mobile application developer is slightly delayed, until mid-August, with the work expected to be completed by December 2021. . With the delays in finalisation of the ToR and hiring of the consultant, it is anticipated that the whole process will take more time than planned. Measures, such as clear and realistic revised timeline and close monitoring of progress, will be put in place to ensure that the mobile application is launched and available to use The need for building capacity of government partners and civil society organizations to use communication for development was identified through consultation with key stakeholders. The training launched for registration in late March. However, the number of applicants were very low and the deadline for registration was extended. The training was further postponed upon request from some of the partners due to the increase in the cases of COVID-19. A date for initiation of the training is yet to be finalised pending a decline in case numbers. The National Social Protection Agency (NSPA) with the assistance from the World Bank and in accordance with the Government’s Strategic Action Plan (SAP) is developing a National Social Protection Framework for the Maldives. Discussions are underway with NSPA to bring about the required changes to the National Social Protection Act or Policy. An agreement is being negotiated to move ahead with identification of the required inputs to the policy document with milestones and timeline defined. Some delayed are expected, however harmonisation of different task in developing the National Social Protection Framework and subsequently working on the required changes to the policy documents is absolutely critical, to achieve the indented results.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The onset of the third wave of the Covid-19 pandemic and the subsequent lockdown delayed the initiation and also became challenging to engage government partners. In the absence of a documented multi-sectoral referral and coordinated referral mechanism for the GBV survivors, the development of the terms of reference for mobile application was delayed. Several precautionary measures including sensitive data sharing protocols had to be scheduled before the development of the application. In addition, the lack of clarity and the need to manage expectations on how the project interventions support and complement the government’s plan for the national digitizing platforms contributed to further delays. At the onset of the project, there was a willingness from the government to create an overarching system for harmonizing the digital platforms to be created under this project with the existing systems. However, the overlapping mandates pertaining to this area and change in key institutions such as the dissolution of Ministry of Communications, Science and Technology and the merger of this portfolio in another Ministry’s mandate has delayed this process. Discussions have been held with partners to undertake these development processes concurrently to avoid further delay. Business Centre Corporation, like many other organisations, faced difficulties in adapting to work from home modality during a lockdown. With some adjustments to their working modality, and discussions between the partners, timelines have been finalised and communicated.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The Theory of Change developed for the social norm change to end GBV highlighted areas for systemic change beyond the scope of the project. Most noteworthy lessons are; current response to GBV is more from a punitive approach towards both women and men rather than response to the survivor and rehabilitation of the perpetrator through a public health approach; need to integrate skills and awareness in school system and parenting and the critical function to bridge mainstream education, skills and labour market are some important lessons identified in the process. . One critical lesson learned was the need to ensure that the scope and interventions of the project are completely understood and owned by all relevant stakeholders, in addition to the lead agency with the direct mandates. This is due to the cross-cutting nature of this wide-ranging thematic area and specifically since this project envisages the introduction of digital approaches towards social protection. It is therefore imperative that all future interventions have collective policy level onboarding with regards to stakeholder roles and mandates, as well as considers alternative programming at the programme formulation stage with partners, to ensure timely and effective utilization of resources. Lesson Learned: • Government’s response to COVID pandemic has mainly been from a health perspective. This has challenged the rollout of other projects/programmes. • Limited human resource capacity at the MoGFSS and weak intersectoral coordination, combined with lengthy decision-making processes has to be considered in future programmes planning.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | In addition to the partnerships identified in the project proposal the following partners were engaged in the implementation of the activities during the reporting period: - Local Government Authority (LGA): LGA is a state institution established under the Decentralisation Act to regulate, oversee, and develop the local governance system of Maldives as envisioned in the Constitution. They are vital to bridge the gap between the efforts to reach out to the vulnerable groups in various parts of the country through the respective local councils and therefore, coordination was commenced with LGA along with NSPA and MOGFFS, and roles of LGA for activity implementation were identified and agreed to as well - Consultations were held with the gender focal points at sectoral ministries as well as civil society actors who will become critical stakeholders for the implementation of the project. Similarly, the President Office will play an important role to integrate all the digital functions in the national system.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | N/A
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The scope of project intervention on activity 1.2.1 is revised to the existence of the mobile application on GBV because there will be no time to promote the usage of the platform within the project timeframe. No other revisions were made to the approved proposal.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | No additional resources were mobilized during this period.

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]: National protection system is shock responsive and government's ability to identify the vulnerable groups increased | Ongoing work with partners to strengthen the National protection system responsive enabling Government ability to identify vulnerable groups.
Indicator: % of beneficiaries accessing NSP services/schemes disaggregated by type and sex
Baseline: 20%
Planned Target: 75% disaggregated by type and by sex
Output 1.1: Strengthened capacity of national stakeholders to take action in changing social norms to prevent GBV and increase access to reproductive health and economic opportunities and empowerment of women | Ongoing planning work and too early to report
Indicator 1.1.1:Number of people reached with messages on social protection services
Baseline: 0
Planned Target: 100,000
Indicator 1.1.2: Number of sessions lead by men and boys publicly on gender equality and prevention of violence against children and women | Ongoing planning work and too early to report
Baseline: lead by boys = 0 lead by men= 0
Planned Target: lead by boys = 12 lead by men = 12
Output 1.2: Increased access to digital technology and platform for the most vulnerable populations including the children, elderly, persons with disability, people with mental illness and women and poor and strengthen data collection at all levels | Ongoing planning work and too early to report | Propose to change the indicator to existence of a GBV digital platform Baseline: No Target: Platform developed and launched
Indicator 1.2.1: Percentage of people reported GBV digital platform
Baseline: 0
Planned Target: 75%
Indicator 1.2.2: Single entry digital platform established | Expected to launch the platform in 2021
Baseline: No
Planned Target: Yes
Indicator 1.2.3: Percentage of people downloaded mobile app | Work initiated, too early to report
Baseline: 0
Planned Target:75%
Indicator 1.2.4: Proportion of women using digital platforms to access social protection services | Work initiated, too early to report
Baseline: 0
Planned Target: 45%
Indicator 1.2.5: Number of people trained to use communication for development as a tool for social norm change | Work initiated, too early to report
Baseline: 0
Planned Target: 25
Output 1.3: Consolidate and build an integrated, efficient, inclusive, and sustainable social protection system based on the principles of universal basic income (UBI) towards a reformed, expanded, streamlined and digitized national social protection policy in support of the Government’s recovery plan. | Work initiated, too early to report
Indicator 1.3.1: Revised National Social Protection Policy published
Baseline: Social Protection legislation exist, No policy in place
Planned Target: published
Indicator 1.3.2: Number policymakers engaged on human rights based social protection | In progress, to be implemented in Q3
Baseline: 0
Planned Target: 6
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Given the initiatives are still in progress, human interest stories will be developed towards the end of the project period.
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board