## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Protecting women & children: digitalizing & streamlining social services, and creating a unified platform for national care | Overall Duration (months) | 12 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-10-15
MPTF Office Project Reference Number: | 124359 | Original End Date (dd.mm.yyyy) | 2021-11-01
Country | Maldives | Current End date(dd.mm.yyyy) | 2021-11-01
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA, UNDP, UNICEF | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Gender Family and Social Services (MoGFSS), Ministry of Communication, Science and Technology (MCST), National Social Protection Agency (NSPA), CSOs
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Strengthening resilience of the most vulnerable to future shocks in the Maldives | Overall Duration (months) | 6 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 29.05. 2020
MPTF Office Project Reference Number: | 121912 | Original End Date (dd.mm.yyyy) | 03.10.2020
Country | Maldives | Current End date(dd.mm.yyyy) | 31.12.2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | WHO UNICEF | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Gender, Family and Social Services, Ministry of Health, Center for Mental Health, IGMH, Home for Persons with Special Needs, Maldivian Red Crescent (MRC), Society for Health Education (SHE), and Blue Hearts, as well as indirect partnership from Advocating for the Rights of the Child and Ministry of Education.
Report Cleared By
o Name: | Ms. Catherine Haswell
o Title: | Resident Coordinator
o Email address: | catherine.haswell@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Mental Health and Psychosocial Support Services (MHPSS) have been provided to nearly 7000 individuals (teachers, MHPSS volunteers), and the capacity to deliver community-based Psychosocial Support (PSS) was increased. Access to MHPSS support was expanded, with 6995 people directly benefitting from the psychosocial helpline. In addition, over 4000 people received specialized mental health services from the Centre for Mental Health (CMH). In part a result of the increase in service availability, and the messaging regarding the universal challenges from COVID-19, there has been a notable shift in community sentiments towards the acceptability of mental health services. Prevention and awareness activities conducted with the MRC, CMH, and NGOs continued to disseminate key messages on promoting mental health and psychosocial well-being and encouraging self-care and tips to manage stress. A total of 132 mental health related messaging posts were disseminated via social media by UNICEF and its partners (SHE, ARC, MRC, CMH, Blue Heart) during the reporting period, with a combined estimated reach to 1,546,227 people. This support has been instrumental in expanding critical MHPSS services across the four layers of MHPSS services, covering different kinds of services in the spectrum. The interventions cover community-level support (including remote ones) and work their way up to specialized care, with different agencies and civil society agencies providing services as per their expertise area. These are further explained in Outcome level results section of the report. The project has been instrumental in leveraging UNICEF’s existing partnerships and building new ones to improve access to quality MHPSS services – as the project has four civil society organizations and four Government agencies. The Home for People with Special Needs (HPSN) caters for the most vulnerable populations needing psychiatric and geriatric care. This project has contributed to strengthening the emergency preparedness at the Home. Medical equipment provided to set up an intensive care unit (ICU) will be installed in collaboration with Indhira Gandhi Memorial Hospital (IGMH) in 2021. The ICU will cater to the patients in need of critical care in emergency situations, and when transfer (by sea) to a higher-level health facility is not feasible. In addition to the medical equipment much needed drugs and care items, personal hygiene items were also provided to ensure that the occupants of the HPSN were adequately taken care of during the pandemic lock down. As not all the requirements for care items and medical equipment could not be met with the project funds, WHO used its own funds to meet the gaps. Technical support was also provided to strengthen the overall programme at HPSN. A local consultant was engaged to review the current SOPs used at HSPN and develop SOPs targeting care workers on handling patients and management and supervision of care. These SOPs are awaiting finalization from relevant government stakeholders. Once complete, WHO will further engage the consultant to produce a development plan for the service that ensures the delivery of high quality, clinically informed practice and co-ordinate and monitor casework and administrative functions of the home and evaluate standards of performance. These activities have already been agreed with HPSN to continue the work started through this project and further strengthen the services provided by HPSN.
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The total number of individuals who received direct MHPSS services and interventions from all providers reach over 16,000. In addition, the prevention messaging and awareness sessions combined had reached nearly 250,000 people. (details provided in relevant sections below) The Home for People with Special Needs (HPSN) is currently caring for a total of 192 (161 psychiatric patients and 31 geriatric patients). All 192 will benefit from quality improvement in the services. After the operationalizing of ICU facility, all patients at a time in need of critical care, when transfer to facilities in Male’ may not be feasible, will be cared in the residential facility. With adequate training, HPSN staff will be in a better position to mitigate the spread of the virus in the Centre and in the island. HPSN currently employees 169 staff with 108 staff working as care workers. All 108 care workers will be trained by the end of 2021.
3.1 | Results: Outcome Level | Please include outcome level results achieved | The collective effort of NGO’s, MRC, SHE, ARC and blue hearts during the reporting period amplified to strengthen and expand the prevention of mental health and Psychosocial Support, thereby increasing the resilience of the most vulnerable groups in the country. The interventions and services are integrated across the four layers. At the highest tier (L-1), where specialized MH services are provided, CMH was the lead partner. Counseling therapy, student referral to counseling through ARC was supported at tier 2 by SHE, with focused care provision. Further, community based psychosocial support was supported by MRC, blue hearts and ARC which includes prevention activities surrounding MHPSS, at the fourth tier. Outcome 1: The resilience of most at-risk persons affected by the collateral impact of the COVID-19 pandemic in the Maldives is improved as a result of the expanded capacity of service providers to deliver timely and quality mental health and psychosocial support services Overall outcome results have increased access and capacity of service providers to provide MHPSS support to those affected by the COVID-19 pandemic and associated issues. Activities supporting these results include: a. Level - 1- Specialized mental health services (CMH) From June to December of 2020, CMH provided specialized mental health and psychological services which directly benefited 11,826 individuals and their families. These services include psychiatry services, psychological and psychotherapy services, social work services, occupational therapy services, and family protection unit services. The increased demand for MHPSS services resulting from the Covid-19 pandemic was seen during the reporting period. The specialized MHPSS services provided by CMH has been strengthened through the project, by increasing human resource capacity to meet the increased demand for MH services during the Covid-19 pandemic. A clinical psychologist and senior social service worker were hired as full-time staff, to work within a multidisciplinary team and provide quality, evidence-based care to people living with mental health conditions, and their families. Recruiting two international consultants to provide remote clinical supervision to psychologists and counselors, and social workers enhanced the quality of specialized MHPSS services. The clinical supervisors provide ongoing individual clinical supervision and group supervision for the team, in order to strengthen performance standards and, technical skills and psychological competencies of the service providers. In order to meet the demand for increased mental health services, two additional clinical staff enabled more clients or beneficiaries seeking services at the center. Program coordinators hired by CMH and SHE continue to support interagency coordination efforts and strengthen the MHPSS program of their respective agencies. A research consultant was provided to CMH to strengthen data analysis, research, and knowledge management of CMH. Key performance indicators of CMH have been developed, and education sessions on research and statistics have been conducted, with CMH staff beginning individual and group research on mental health in individuals, families, and community. The research done by CMH from this program will provide much needed information on mental health in the Maldives, which can be used to strengthen mental health care and drive evidence-based policy making in relevant sectors. b. Level - 2- Early PSS services and individual interventions (NGO SHE) By expanding and strengthening focused and professional MHPSS services provided at SHE, 279 telephone counselling sessions were provided to 173 clients (21 males, 152 females) from June to December of 2020. An additional 28 clients (14 males, 14 females) are also being provided with regular MHPSS support through the hotline. Blue Heart provided online chat-based psychosocial support to 306 individuals during the reporting period, majority of whom were under 25 years of age. Blue Hearts is launching a mobile application (on both IOS and Android platforms) that will offer online MHPSS services comprising of paid counselling services from a licensed counsellor and free psychosocial support from trained first responders. This application will be the first of its kind in the Maldives to offer a full customer experience when it comes to online counselling service provision; the application can facilitate client registration, online payments, along with appointment scheduling and counselling service provision. The application is currently in the beta test phase; it is scheduled to launch in early March 2021. c. Level – 3 Community-level PSS (MRC, Blue hearts, and ARC) The MHPSS services provided by MRC was significantly strengthened. This includes increased training capacity, that enabled MRC to act as a learning resource centre, providing training sessions to other sectors on PSS, as well as expand the remote community-based PSS support through the PSS helpline. Summary of reach: • PSS helpline 871 • Outreach 369 • Training 6845 Psychological First Aid training of trainers was conducted to build a pool of committed and competent volunteer trainers in the MRC Male’ branch as part of engaging volunteer trainers in PFA training and capacity development works. Human resource capacity was also enhanced, enabling the recruitment of Psychological First Aid (PFA) trainers. As part of COVID-19 operations, MRC conducted PFA training and orientations to MRC volunteers and staff, and individuals from other organizations responding in the COVID-19 operations. This significantly supported to build the PSS capacity at both an individual level and at the organizational level. In order to build the capacity of volunteers to facilitate the PFA, MRC also conducted PFA training to MRC Branches targeting staff and volunteers in outer islands. Psychological First Aid (Training of Trainers) increased the capacity of volunteers at sub-national or island level to facilitate PFA sessions themselves on the ground. This has contributed to the sustainability of the pool of volunteers by engaging them in branch level PSS activities. MRC in collaboration supported the Ministry of Education to deliver training programmes for teachers on Psychological First Aid. An additional group of teachers undertook high-level training to deliver PFA for Children The MHPSS component of the project also contributed to the hosting of online webinar sessions surrounding MHPSS. The support to strengthen the learning resources and platforms significantly contributed to the efficient roll-out of the training across the country, especially during restrict travel periods. The combined engagement of all learning sessions is estimated to be 9103 users. MRC led PSS Helpline: During the reporting period, the COVID-19 MPTF-Joint Programme for mental health and psychosocial support services (MHPSS) has increased capacity to deliver community-based PSS support and expanded access MHPSS support to a large part of the population. MRC established a call center to provide psychosocial support to people affected during the Covid-19 response. This is being institutionalized and extended during peacetime as well. The funding enables the organization to onboard dedicated part-time staff to respond to the helpline calls during extended hours. MHPSS promotion engagement sessions Adolescents: The Covid-19 pandemic and consequent socio-economic issues have been particularly hard on children and adolescents. Having to stay in their homes, without regular school or any other extracurricular activities, not being able to meet their family member and friends have created a mental strain in most children. To address this specific need, the UNICEF extended the partnership to NGO ARC, to engage directly with adolescents to promote their mental and emotional health and well-being. ARC, through an extended collaboration with private psychologists, conducted 19 online sessions on mental health, reaching 370 students from secondary grades and above. The sessions raised awareness on common mental health issues and provided the adolescents with tips and strategies to address them. The topics ranged from: o Covid-19 and mental health; o Mental health: interpersonal relationships; o Coping strategies for stress and anxiety; o Mental health: anger and frustrations; o Relaxation techniques and mindfulness d. Level – 4 - MHPSS well-being promotion and awareness creation (all partners) During the reporting period, prevention and promotion efforts included key messages on mental health in partnership with government agencies and local NGOs. Combined, 132 mental health related messaging posts were disseminated via social media by UNICEF and its partners (SHE, ARC, MRC, CMH, BH) during the reporting period, with an estimated reach of 1,546,227. A key focus of the MHPSS prevention messages by MRC was to build psychosocial resilience in individuals and communities by promoting and normalizing help-seeking behaviors, self-help strategies, and promoting our psychosocial support service 1425. Society for Health Education (SHE) disseminated positive messaging on mental health and psychosocial wellbeing by conducting education/awareness sessions on a variety of topics ranging from stress management to conscious parenting to mental well-being. These sessions had purposeful messages targeted towards key populations including vulnerable groups, such as adolescents, parents with young children, parents of children with special needs, fathers, school counsellors, teachers, and care workers. SHE also conducted MHPSS messaging (in the form of posts, illustrations, GIFs) through mass media and social media, which helped to reduce and prevent the risk of long-term repercussions on community well-being, and enhanced individual and community capacity to cope with stress and adversity. These efforts helped to tackle the stigma on mental health problems in the community. ARC also developed a series of child-friendly IEC resources on MHPSS, with the theme of “you are not alone”, to reassure children that many others are experiencing stress and anxiety, and to helping young people to create their toolkit of coping strategies. All partners came together to commemorate the World Mental Health Day on 10th October, which amplified the preventive and awareness messages on MHPSS. Maldivian Red Crescent (MRC) conducted several training sessions in the reported period, targeting their volunteers as well as other sectors, particularly the teachers and staff in the school setting. Responding to emerging needs of building PSS capacity for front line workers, several targeted sessions were conducted for staff from different sectors. In this regard, a series of various levels of virtual Psychological First Aid (PFA) training were conducted: PFA Orientation and PFA training for schoolteachers as well as to social workers, and counselors from the Ministry of Gender Family and Social Support (MoGFSS), and the National Drug Agency. To date, MRC conducted 89 sessions of PFA orientation, resulting in 6,332 teachers completing PFA orientation. The PFA training of teachers helped sensitize the teachers to psychosocial aspects of children and increase the skills of school staff to provide support to students. An additional PFA for children, a certified training of 9 contact hours led to 194 teachers and counselors having improved skills to deliver psychological first aid to children in distress., and 166 counsellors and teachers (31 Male, 135 Female) completed PFA for children. Several batches of the volunteer training session were also conducted, including 20 MHPSS volunteers completing the 20 hours of comprehensive training on providing psychosocial support in emergencies. Further, 19 of the MHPSS call center staff completed Gender-based violence sensitization training. Outcome 2.: Critical care capability increased within HPSN during a potential COVID-19 outbreak, and any potential future health crises, to cater for vulnerable people in society including geriatric patients Critical care capability of HPSN will be strengthened with the establishment of the ICU within the Facility. The setup of this ICU will strengthen the capacity of HPSN to respond to any future health crisis/pandemic. The development of guidelines and SOPs and the ensuing trainings will improve the human resource capacity of HPSN resulting is much better quality of care for the elderly and geriatric patients at the facility. In continuation of this project a monitoring and evaluation mechanism will also be set up at the facility to ensure accountability and proper programme implementation. It is expected that the SOPs, guidelines and monitoring and evaluation mechanism will be in place before end of 2021. WHO is already working with MoGFSS with support of a technical consultant of development of these documents. At the very onset of the pandemic visitation was stopped at the facility and infection prevention and control measures were increased. With the strong measures taken for the safety of the patients at HPSN no cases of COVID have been seen so far at the facility. Thus, no mortality has been recorded.
3.2 | Results: Output Level | Please include output level results achieved | Output indicator 1.1a.1 At-risk women, elderly persons, children (girls/boys) and young people (girls/boys), migrant community, persons with disabilities and persons at risk access quality community-based mental health and psychosocial support services in a gender and age sensitive manner Gender disaggregated data (September – December 2020) of specialized services provided at CMH indicate that a larger proportion of women seek mental health care and services; this is similar to data provided by SHE for the reporting period (June – December 2020) with 83% of 201 clients of SHE being women and young girls. CMH provided a total of 1242 specialized psychological and psychotherapy sessions (Sept-Dec 2020), with 75.9% of those sessions provided to women and young girls. Similarly, 1997 psychiatry consultations (Sept-Dec 2020) were provided by CMH, with 63.5% of those consultations provided for females. Among the 64 clients of social workers of CMH (Sept-Dec 2020), 38 were females. Patients who are triaged by CMH for emergency services amount to 1043 patients (Sept-Dec 2020), with 651 female and 392 male patients. In converse, males predominantly received occupational therapy, with 131 males out of the 175 patients provided OT services. Several messages were posted from UNICEF and partners (MRC, HPA, CMH, and NGOs) on MHPSS areas and topics, which ranged from identifying feelings, coping with new normal, stress, anxiety, suicide, to help-seeking behavior. More than 130 posts mental health related topics had a combined reach of 1,546,227 reach on Facebook and Instagram (posts, comics, videos, GIFs, illustrations). On Twitter, engagement averaged 200 for each post. Specifically, SHE reached an estimated 104,587 people through the dissemination of mental health-related messaging and session on mass media and social media platforms. Both the social media posts and FB Live and Zoom sessions helped to provide strategies to individuals and communities to respond to their problems and emerging needs in mental health. Key messaging by Blue Hearts on social media reached an estimated 10,935 individuals. Additionally, MH promotion and self-care messages circulated by CMH reached an estimated 4967 individuals. Output indicator 1.1b.1: At-risk women, elderly persons, children and young people, migrant community, persons with disabilities and persons at risk receive tailored mental health and psychosocial care messages and have adequate avenues to give feedback on received services During the reporting period from June to December, 86.4% of callers seeking MHPSS services received immediate support i.e., within 5 seconds of being connected to a call agent’s queue. Blue Hearts provided prompt support to all help seekers, with 100% attended within 24hr benchmark. The 1425 PSS helpline service hours were increased, and the part-time staff recruited helped to expand access to the services. The helpline is often used by individuals living in the Atolls as well as in Male. The PSS helpline set by MRC provided PFA to nearly 1500 callers during the reporting period, for problems ranging from stress, anxiety to suicide, to help-seeking behavior. Among those who provided personal information, several individuals from different vulnerable groups were identified during the reporting period: • At-risk women (*) 11 • Elderly persons 14 • Children and young people 53 • Migrants 11 • PWDs 17 (*) Women who reported issues of domestic/SGBV. These are the number of calls and not individuals. In addition, individuals in quarantine facilities and front-line workers and were provided regular PFA support and “check-ins”. These outreach services were provided to 2066 individuals. People from all walks of life sought MHPSS services, peaking in July and early August, and tapering down later in the year. This trend in demand for MHPSS services correlates with the COVID-19 infection trend in the country vis-a vi change in policies such as ease of restrictive measures. Further, with the policy change, all COVID-19 positive cases have been home quarantined, and a substantive number of positive cases are isolated at home. There is a separate mechanism established at HEOC where staff is calling in and “checking-in” with people quarantined and isolated at home, with a purpose of maintaining contact with cases, identifying risk factors and deterioration of health conditions, as well as obtaining information on well-being and well-fare of individuals at home. PSS helpline is designated with the provision of PSS services to these individuals. People from all walks of life sought MHPSS services, peaking in July and early August, and is currently tapering down. This trend in demand for MHPSS services correlates with the COVID-19 infection trend in the country. The PSS helpline received several calls from vulnerable groups (at-risk women / GBV – 11, elderly persons - 60, children/adolescents - 224, migrants -11, people with disabilities - 17). Moreover, through the hospital-based multi-specialty specialized mental health team, nearly 4000 individuals received face-to-face sessions, while 1043 received support through the virtual triage set-up. Further, with the change in policy, all COVID-19 positive cases have been home quarantined, and a substantive number of positive cases are isolated at home. There is a separate mechanism established at HEOC where staff are calling in and “checking-in” with people quarantined and isolated at home, with a purpose of maintaining contact with cases, identifying risk factors and deterioration of health conditions, as well as obtaining information on well-being and well-fare of individuals at home. SHE provided MHPSS services to 281 vulnerable clients (i.e., women and children), along with 30 at-risk clients attended to by trained mental health practitioners on GBV and Sexual Abuse related, and suicide-related cases. CMH provided specialized mental health services in a multidisciplinary setting for 11,826 individuals from June to December 2020, with 2595 individuals receiving immediate services through the tele and online triage set-up during this period. MRC, CMH, and UNICEF, and SHE key agencies that worked at the committee level in the Mental Health cluster of the National Emergency Operations Centre (NEOC), to coordinate and strengthen MHPSS services and systems as part of the Covid-19 response. This interagency coordination and collaboration helped to streamline prevention and promotion messaging, establish referral mechanisms, and strengthen service provision Online- Chat based PSS targeting Young people: The expansion of community-based MHPSS services in Blue Hearts has directly benefited 306 people within the reporting period, from which an estimated 60 percent of service seekers are within the 16 - 25 age range. Service seekers at Blue Hearts are guaranteed anonymity through online MHPSS services provided by eight trained first responders. As such, demographic information on the clientele of Blue Hearts is not available for this report; the new mobile application and renovated website to be launched in March 2021 through the Covid-19 MPTF-funded program will support improved documentation of such data. As part of prevention and promotion of mental health, the mobile application developed by Blue Hearts will act as a repository of information on mental well-being and self-care, along with a directory of available MHPSS services nationwide. Both social media posts and articles (for the application) have been developed on a range of topics including emotional regulation, relaxation and sleep guides, and myth-busters on mental health, to increase awareness and reduce stigma on mental health. The mobile application also provides a journaling feature for users, as a tool for self-care which will promote the positive mental health of individuals. Output Indicator: 2.2a.1 COVID-19 prevention and management services established in HPSN Once the intensive care unit set up is operational in the HPSN, it will enable management of patients at the facility instead of transfer of patients to Male’ for tertiary care. The SOPs and guidelines developed under the technical consultancy would further strengthen the programmes conducted at the facility. Some of the documents already in draft stage are; • SOP for care workers on handling patients, • SOP for care for children and adolescents, • Guideline on management and supervision of care workers. • Guideline on coordination and monitoring of casework and administrative functions of the home and evaluate standard of performance.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | 1. Limited availability of technical MHPSS expertise in the country: Partner agencies and UNICEF faced difficulty in recruiting technical people due to the limited pool of trained personnel in the country. The Project Coordinator Terms of Reference (ToR) was advertised three times, and no competent applications were received. The ToR was reviewed, scaled-down and recruitment was eventually completed in August 2020, and since then, onboard. 2. Need to re-strategize the concept and activities due to new support by UN agencies outside of the project: After the MPTF proposal was submitted in May 2020, outside of the project, UNDP obtained resources to support the expansion of mental health services offered by the same partners included in the MPTF proposal. Resolving this and reaching an agreement on roles and responsibilities for each agency took some time. UNICEF and UNDP discussed and identified ways of harmonizing the support to the partners to collectively contribute to the attainment of the desired results. UNICEF realized the need to bring in additional NGOs to expand the pool of service providers and to ensure adequate fund absorption capacity. The process of resolving this situation and finding new partners delayed the initiating of the project and affected the timeline at the front end. 3. Finding alternatives to voice recording: UNICEF proposed the introduction of quality control measures to the hotline services. Audio-recording and auditing of the calls were one of the proposed quality assurance measures. However, the partners and technical experts had reservations in setting up voice recording of the conversation between the call center staff and callers due to the sensitivity of the callers and cultural acceptance issues. The partners felt that audio-recording would discourage help-seeking behavior. MHPSS experts recommended alternatives, such as stringent documentation through standardized written record-keeping of calls. 4. Restrictions due to COVIF-19 affected the initial plans: Physical training session at sub-national level had to be reprogrammed and re-strategized due to COVID-19 travel and movement restrictions. The funding allocated to that was reallocated to expand awareness activities and helpline. 5. Availability of trained professionals: The biggest challenge at HPSN is the limited human resources available at the facility. Though a medical officer and nurse are present at the facility they are not trained to deliver specialized care. In addition to medical staff the staff that provide day to day care to the patients including the staff providing palliative care are not fully trained. The facility has an agreement with IGMH to train their medical staff on using the specialized medical equipment provided through this project. The technical consultant engaged under this project supported in drafting SOPs and guidelines for the other staff to provide different types and different levels of care. Once the SOPs and guidelines are finalized the technical consultant will also conduct necessary trainings which is planned to be completed before end of 2021.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | One of the key lessons learned during the operationalization of the project is the need for closer coordination and information sharing among the stakeholders. Moreover, time taken to form a consensus among partners and diversion of funds within the scope of the project affected the implementation timeline. This may have partially been due to the short lead time due to the emergency nature of the intervention and the efficiency of MPTF approval and disbursement. Another learning is recognizing the necessity for flexibility and being able to respond to emerging needs. For example, the need for international supervision support has been identified as a key need to provide quality services at Center for Mental Health, and the project is addressing this critical need. It was also realized that obtaining prescribed information on set targets may not be feasible (such as the desegregation of social media reach). Some targets were set relatively high and requires adjustment. Emerging needs related to technical support was identified by the CMH, in the form of shortage in clinical supervision of the expanding multi-disciplinary team at the centre. UNICEF has supported this through recruitment of clinical supervisors who provide remote support to the team, on a regular basis. This has led to improved quality of overall services, and capacity building of the staff at the center. The nature of MHPSS work is more beneficial when interventions are planned with a long-term view a time period of at least a year. For example, recruiting personnel for a few weeks were faced with challenges. UNICEF addressed such challenges by entering into one year partnerships and committing additional funds from own resources. The capacity building needs of HPSN and the need for development of SOPs were identified during the designing of this project. For the effective and efficient running of the facility there is need for adequately trained health professionals and care workers. Through this project a technical consultant was hired to support in development of SOPs, guidelines and to conduct training for doctors, nurses and care workers in the facility. However, not having adequate number of medical staff still remains a challenge. WHO will continue to support the technical consultant to ensure that all the documents are in place and trainings completed before end of 2021.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The Project has been instrumental in expanding the UN partnership with NGOs expanding MHPSS in the country. Maldivian Red Crescent (MRC), Society for Health Education (SHE), and Blue Hearts, and Advocating the Right of Children (ARC) were critical non-governmental partners, ensuring that the project was able to support all levels of the mental health and psychosocial support pyramid. The partnership included public sector institutions such as the Centre for Mental Health (CMH) and the Ministry of Education (MOE) teachers and school counsellors. The MPTF funding provided these partners with a unique opportunity to deliver on their mandates and further enhance their service provision and management systems. For example, the partnership established with MRC led to the training of over 6,300 teachers in PFA. The new partnerships established with NGOs are bringing innovative approaches and expanding access to young people in a more youth-friendly manner. For example, the internet-based chat service provided by NGO Blue Hearts through the project, is being strengthened by development of an interactive app. In addition, the new partnerships have created a platform for the partners to work together collectively. A good example of the collective effort is one of the NGOs (SHE) providing free counselling session for those who cannot afford expensive counselling sessions. UNICEF’s emergency funds received through HQs and bilateral donors were allocated to meet the funding shortfall due to the expansion of partnerships. For example, towards formal partnerships with NGOs, UNICEF contributed an estimated USD 150,00. As a result, access to specialized MHPSS as well as community-based psychosocial support services has increased. Further, due to the nature of the mental health and psychosocial interventions, a medium to long-term perspective on planning provided added value to all stakeholders. Hence, given the necessity to plan beyond 6 months, UNICEF contributed resources from the organization’s budget and secured a one-year partnership with the respective agencies. The layered system of complementary supports recognizes that different people require different levels of support and facilitates the help seekers to avail relevant kinds of support. It also recognizes that certain groups, such as adolescents require different strategies, and builds on existing service providers niche to provide adolescent and youth-friendly, technology-based MHPSS. The different partners of the project add value to achieve these specific targets. WHO has been working with MoGFSS on elderly health, disability and gender based violence as part of the WHO regular workplan programmes. On several occasion strengthening of services at HPSN has been discussed prior to this project, however not much headway had been made for various reasons. This project gave the opportunity to build a relationship directly with HPSN through MoGFSS, and through this relationship it is believed that WHO has more opportunity to expand both the elderly care and disability programme activities.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The initial design of the program had to be re-strategized mid-way due to new support from another UN agency outside of the joint UN project which saw a shifting of resources to maximize the expertise and contributions of all agencies to reach a greater number of recipients. This also required bringing new NGOs on board to expand the pool of service providers and increase the fund absorption capacity of the national partners committing UNICEF core funds to complement the expansion.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | 100% utilization of the fund. To support continuation of critical activities for one year, UNICEF committed an additional USD 150,000 and will continue supporting partners till June 2021. The funds received for the project could not meet all the procurement requirements of HPSN. USD 106,319 was mobilized from WHO funds to meet the gap. WHO will continue to provide technical support to HPSN till end of 2021. In January 2020, The Government of Japan provided a grant of USD 86,961 for “Upgrading of Home for People with Special Needs in Guraidhoo Island, Kaafu Atoll” to refurbish the clinic and making comfortable seating arrangement for counselling sessions and wheelchair accessibility for patients with disabilities. The COVID-19 MPTF project is further complementing by strengthening of HPSN by supporting the establishment of an Intensive Care Unit and necessary training for the health professionals and care workers at the center.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]: The resilience of most at-risk persons affected by the collateral impact of the COVID-19 pandemic in the Maldives is improved as a result of the expanded capacity of service providers to deliver timely and quality mental health and psychosocial support services. | 1.a. 59 MHPSS Volunteers & staff completed the 20 hr comprehensive training on providing psychosocial support in emergencies. 19 of them completed GBV sessions 138 counsellors and teachers trained on PFA for children 1.b. 86.4% for MRC, 100% for Blue hearts |  | 1.a. Partner reports 1.b. Data from helpline
Indicator: 1.a. # of trained MHPSS volunteers and counsellors on PSS including Gender and GBV per 10,000 persons 1.b. % of persons calling in to seek MHPSS services who receive timely and quality assistance from a trained PSS worker or counsellor within 24h
Baseline: 1.a. Trained personnel: to be established 1.b. Baseline to be established
Planned Target: 1.a. Trained personnel: 30-50 new MHPSS counsellors 1.b. 100%
Output 1.1 2.1a.1 At-risk women, elderly persons, children (girls/boys) and young people (girls/boys), migrant community, persons with disabilities and persons at risk access quality community-based mental health and psychosocial support services in a gender and age sensitive manner | 1,546,227 SM users reached on Facebook, Instagram, and twitter 130 + posts (posts, comics, videos, GIFs, illustrations) (unable to gauge Viber dissemination, expected to be 50% of other SM reach | The target was taken by considering the population number, and individuals who were above 14 years. The social media analytics collects data on reach of every post, and is unable to count individual people reached across all posts. The number of posts from all partners also exceeded the initial projected number. | Social media tracking, TV, radio watching/listener data
Indicator 1.1.1: # of people reached by MHPSS related messages, disaggregated for men, women, age groups and nationality
Baseline: 0
Planned Target: 447,487
Indicator 1.1.2: # at-risk women, elderly persons, children and young people, migrants, persons with disabilities and persons at risk provided with community-based mental health and psychosocial support services | 2,649 Individuals callers to MHPSS helpline provided with community-based mental health and psychosocial support services. In addition, 306 accessed counselling services through chat sessions. | The target was an over estimate, based on a maximum. In addition, a number of people had specific information needs which was attended to by the COVID hotline 1612. Also, building preventive mechanisms and promoting resilience and self help will also help lower the number. | Monthly reports collected from service providers; hotline data; IM system
Baseline: estimated 400 persons per month (mainly those in quarantine/ isolation)
Planned Target: 25,000 over six months
Indicator 1.1.3: Inter-agency information management system supporting and tracking the mental health services established, disaggregated by sex, nationality and age groups | Agency based system established. And informal referral system established. | Computer-based system challenged due to pending work of HMIS / DHIS-II system. The inter-agency IMS also requires long term work with Government, and high level engagement. | Regular reports generated for analyzing progress
Baseline: No formal mechanism exists
Planned Target: Information management system on referral and cases updated daily
Outcome 2[1]: Critical care capability increased within HPSN during a potential COVID-19 outbreak, and any potential future health crises, to cater for Vulnerable people in society including geriatric patients | No COVID-19 positive cases were reported from HPSN |  | Data from the health centre
Indicator: Low mortality from COVID-19 at the HPSN
Baseline: 0
Planned Target: <4%
Output 2.1 COVID-19 prevention and management services established in HPSN | Although WHO has already handed over all the medical equipment, the set up of the clinic is still not complete and therefore, the clinic is still not operational. | The equipment is to be installed with support from IGMH. However, due to the pandemic IGMH has not been able to provide this support so far and hence the clinic remains non-operational. It is targeted to complete installation and training and start the services by May 2021. | Project/ monitoring report
Indicator 2.1.1: Number of people in the HPSN visiting the health care clinic in the center
Baseline: 0
Planned Target: 194
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Helping people, promote, protect & care for mental health during the global COVID-19 pandemic The effects of the COVID-19 global pandemic on mental wellbeing have required countries across the world to mobilize more mental health and Psychosocial Support (PSS) resources to reach out to and help those bearing the brunt of the pandemic and its socioeconomic impacts. In Maldives, the Maldivian Red Crescent (MRC) launched a small PSS operation as the country’s capital went into its first lockdown in March 2020. Since then, a young team of dedicated volunteers have been operating the helpline, reaching out to, and extending support to thousands of people living across the country. UNICEF engaged with MRC with the aim of expanding and enhancing the existing Mental Health and Psychosocial Support (MHPSS) services offered by MRC. The UN COVID-19 Multi Partner Trust Fund (MPTF) was instrumental in strengthening resources required to ensure timely expansion of key interventions. Shifa Ahmed, a 37-year-old laboratory technician, had just recently completed her PSS and Psychosocial First Aid (PFA) training when the first cases of COVID-19 were reported in the Maldives. “Since I had completed my PSS & PFA training very recently, I saw the COVID-19 pandemic as a very good opportunity to use what I had learned. The fact that the pandemic hit really hard and affected the mental health of so many people made me realize the importance of such a service and so I wanted to continue the work,” Shifa said. Maldivian Red Crescent volunteers, including Shifa, continue to work on several PSS activities such as the PSS telephone helpline (1425). They also organized a special operation during the first peak of the pandemic, to check up on and address the needs of thousands of people being quarantined in designated facilities upon return to the country. The volunteers have also run PSS interventions to support those in the frontlines of the COVID-19 response to help them deal with the sensitive workload and stress positively. During the peak of the lockdown in June 2020, the helpline received an average 3,198 calls daily. UNICEF, through the COVID-19 MPTF supported this program through from June to December 2020 and are planning to extend the support with additional resources. An unprecedented global pandemic is not an ideal first run for a beginner in PSS work, however, Shifa says that helping others has really helped her cope better with her own mental well-being as well. “The voluntary work was a real challenge to boost my confidence in the field. To be able to use the knowledge I gained practically in real life really helped me build myself in so many ways. Given the life challenges due to the pandemic, help and support for so many people around the country was very important”. Based on pre-existing social norms, lack of acceptance of mental health problems as real issues of concern and limited avenues to seek help on PSS prevents young people from reaching out and acknowledging that they need help. These challenges can only be overcome with systemic as well as social change and the current COVID-19 pandemic has provided a good opportunity to increase awareness around the vitality of addressing mental health issues for a happy and healthy society. One of the main challenges in running PSS operations amid the pandemic for MRC was the lack of trained volunteers, which led to the organization having to work with a small core group of volunteers. “With the very limited number of people in the field, it was really important for everyone in the field to put in an effort to make a difference in society. The UN support for a volunteer program was the best platform for it,” Shifa said.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
The Fund branding guideline came in after the IEC materials were developed. Due to this, Fund logos and other guidelines were not captured in the related social messaging. 1. Social media coverage during the handover ceremony of medical equipments, consumables, medicines & MHPSS to HPSN shelter, & essential care items for PWD’s https://twitter.com/whomaldives/status/1286622347429064704?s=21 https://twitter.com/MoGFSSmv/status/1286330022203023360 2. PSS training for school teachers and counsellors https://twitter.com/maldivianrc/status/1274270514396098560
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board