## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Protection of Women and Girls from Sexual and Gender Based Violence in the times of COVID-19 | Overall Duration (months) | 13 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 16.11.2020
MPTF Office Project Reference Number: | MPTF_00209 | Original End Date (dd.mm.yyyy) | 31.12.2021
Country | India | Current End date(dd.mm.yyyy) | 31.03.2022 (Tbc - per approval of no-cost extension request)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF, UNWOMEN, UNHCR, WHO | National counterparts (government, private, NGOs & others) and other International Organizations | Line Ministries (MoWCD) the Judiciary, the Police, academic institutions (such as The Tata Institute of Social Sciences), professional associations, law enforcement agents such as police personnel and protection officers, NGOs/CSOs (such as SEWA BHARAT, SANWED, Guild for Service) and the One Stop Centers, 181 Helpline and counselling centers, helplines, etc.
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | Despite the devastating 2nd wave of the pandemic, programme interventions by UNICEF, UNHCR, UNWOMEN and WHO continued to strengthen the protection of women and girls in India from sexual and gender-based violence amidst the COVID-19 pandemic. Progress was made to ensure gender responsive and age sensitive SGBV related essential services are available for women and girls and survivors of SGBV during first half of 2021. UNICEF strived to support government and partners at national and state level with multi-sectoral approaches to address impact of COVID-19, including SGBV concerns. A total of 896,451 children and women across programme states (Chhattisgarh, Bihar, Uttar Pradesh, Madhya Pradesh, Rajasthan) were reached by interventions aimed at mitigating, preventing and responding to GBV, as a result of UNICEF-supported training of 62,315 child protection functionaries and partners. 34,752 children and caregivers benefitted from community-based MHPSS through expanded helplines, virtual safe spaces, online counseling sessions and community-based channel through mobilization of youth and community-based volunteers. A total of 7707 functionaries and personnel of the Department of Women and Child Development in Delhi, Madhya Pradesh and Rajasthan received capacity building through UN Women supported interventions, including the 8 "Ask the Expert" training sessions which were the first of a series of trainings to build capacities of functionaries from OSC and other shelter services to help survivors of SGBV. In continued partnership with the law enforcement and justice sector, through a continuous process of advocacy at the highest level, handholding at the mid-level and building capacities at the high-mid- lower levels on issues related to child protection, SGBV and mental health, UNICEF programme contributed to improve the access to justice for women and girls and survivors of SGBV. 831 personnel of the law enforcement and justice sector, 1688 paralegal volunteers and 110 support persons were trained on SGBV/VAC and gender/child friendly procedures, resulting in more than 2000 cases reported under the Protection of children from sexual offences Act. A total of 737,014 women, girls, boys, men were reached and engaged through continued outreach interventions conducted by UN agencies on online and offline platforms, raising awareness on SGBV prevention and response, mental health and COVID-19 related information so that women and girls are aware of the risks of SGBV and harmful practices, and increasingly engaged in decision making processes related to COVID-19 response and recovery. Joint sessions were conducted by UNHCR with UNICEF and UNWOMEN for women, children, adolescents and young people of refugee communities, covering issues of SGBV and PSS in times of COVID-19. The devasting second wave of COVID-19 resulted in loss of jobs, food insecurity for vulnerable women and girls. UN Women and partners supported conditional and unconditional cash transfers programme by linking women to government security and livelihood schemes in the three programme states. In Delhi NRC and Telangana, UNHCR has conducted skill trainings for 203 women and 16 men on enterprise development, tailoring, paper bag and jute bag making with monthly incentive and 51 women were provided with microgrants of $INR 25000/person and started small businesses.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | • 896,451 children and women in Chhattisgarh, Bihar, Uttar Pradesh, Madhya Pradesh reached by interventions aimed at mitigating, preventing, responding to GBV • 70,022 frontline functionaries and personnel of MWCD, One Stop Centers, Childline, and other shelter and safe spaces for women through series in the states of Delhi, Madhya Pradesh, Rajasthan, Bihar, Chhattisgarh, Uttar Pradesh * 34,752 children and caregivers benefitted from community based MHPSS; * 737,014 women, girls, boys and men reached and engaged in community based outreach interventions; * 831 personnel of the law enforcement and justice sector, 1688 paralegal volunteers , 110 support persons trained on SGBV/VAC and COVID-19; 203 refugee women and 16 refugee men trained on enterprise development and other business skills; 51 refugee women received microgrants to start their small business
3.1 | Results: Outcome Level | Please include outcome level results achieved | By December 2021, women and girls in India are protected from sexual and gender based violence and are empowered to use gender responsive and age sensitive essential services and recover from violence amidst the COVID19 pandemic. (in progress)
3.2 | Results: Output Level | Please include output level results achieved | 1. Improved gender responsive and age sensitive protection and SGBV related multi-sectoral essential services are available for women and girls and other groups at risk of and/or survivors of SGBV. Despite challenges caused by the 2nd wave, UNICEF strived to support governments and partners at national and state level to ensure multi-sectoral approaches to address impact of COVID-19, including SGBV concerns. A total of 896,451 children and women across programme states were reached by interventions aimed at mitigating, preventing and responding to GBV, as a result of UNICEF-supported training of 62,315 child protection functionaries and partners (Bihar, Chhattisgarh, UP, Rajasthan and MP). 34,752 children and caregivers benefitted from community-based MHPSS (Bihar, Chhattisgarh, UP, Rajasthan and MP) through expanded helplines, digital platforms, virtual safe spaces, online counseling sessions and community-based channel through mobilization of youth and community-based volunteers. A total of 7707 functionaries and personnel of the Department of Women and Child Development in Delhi, Madhya Pradesh and Rajasthan received consistent capacity building measures through UN Women supported interventions, including the 8 "Ask the Expert" training sessions which were the first of a series of trainings to build capacities of functionaries from OSC and other shelter services to help survivors of SGBV. Subsequent training sessions will include topics such as laws impacting women affected by SGBV, gender awareness and sensitization and cyber security. UN Women also initiated and supported the Government of National Capital Territory of Delhi (GNCTD) in the development of COVID-19-related Standard Operation Protocols/guidelines, which were issued by Women and Child Development Department. The SOP aims to provide assistance and outreach to women in distress, in coordination with Mahila Panchayats (Women headed local governance in rural areas), and all the Protection Officers. The SOP was also circulated among Saheli Samanvay Kendra (Women Coordination Centre), Cluster Coordinators of the Integrated Child Development Scheme , the Department’s District Officers designated as Nodal Officers for all women’s shelter homes, district coordinators of the District Level Centres for Women, all district commissioners, and member secretary of District State Legal Services Authority. 2. Women and girls and victims of SGBV have improved access to gender-sensitive justice systems. During the reporting period, UNICEF continues strengthening the partnership with actors from the law enforcement and justice systems, especially to improve access to justice for women and girls and survivors of SGBV. In particular, UNICEF provides technical support to the National Police Academy as well as Police Departments at state level; the oversight mechanisms like national and state level commission for protection of child rights, juvenile justice boards (JJB), juvenile justice committees (JJC), High/Supreme Courts, etc.; legal aid service providers and para legal volunteers through a continuous process of advocacy at the highest level, handholding at the mid-level and building capacities at the high-mid- lower levels on issues related to child protection, violence and abuse, gender and mental health. As a result, within the first half of the year, 831 personnel of the law enforcement and justice sector, 1688 paralegal volunteers and 110 support persons were trained on SGBV/VAC and gender/child friendly procedures, resulting in more than 2000 cases reported under the Protection of children from sexual offences Act. 3. Women and girls are aware of the risks of SGBV and harmful practices, and increasingly engaged in decision making processes related to COVID-19 response and recovery. During the reporting period, a total of 737,014 women, girls, boys, men have been reached and engaged through online and offline platforms and community-based outreach interventions, raising awareness on SGBV prevention and response, mental health and COVID-19 related information. Through UNHCR’s interventions, 103 awareness raising sessions were conducted for 2,367 (549 Male & 1,818 Females) refugees and asylum seekers and volunteers in the states of Delhi NCR, Telangana, Uttar Pradesh, Haryana, Rajasthan and Jammu. In partnership with UNICEF and UNWOMEN, UNHCR conducted webinar sessions and developed communication materials on PSS, SGBV and violence against women and girls targeting refugee and host communities across Telangana, Uttar Pradesh, Haryana, Rajasthan and Jammu. A total of 203 women and 16 men were trained on GBV SOP and Psychosocial First Aid in Telengana and Delhi through UNHCR’s interventions, and further provided support and raised awareness on the same in their refugee communities. Joint sessions were conducted by UNHCR with UNICEF and UNWOMEN for women, children, adolescents and young people of refugee communities, covering issues of SGBV and PSS. UNWOMEN supported interventions have reached a total of 7333 women, girls, boys, men reached with messages on SGBV prevention and response through community-based outreach, media campaigns, including social media platforms. In particular, in the state of Madhya Pradesh, under the directions from DWCD, UN Women organized an ‘Ask the Expert: Supporting Women & Girls during COVID-19’ virtual session for women frontline functionaries of DWCD in the state, reaching 333 functionaries. Through UNICEF supported interventions, a total of 727,095 adolescents and young people were mobilized for COVID-19 appropriate behaviors and as child protection advocates through various platforms including the Young Warriors movement led by YuWaah, the India’s Generation Unlimited programme. 4. Vulnerable families of women and girls at risk of and/or survivors of SGBV/VAC have reduced their economic vulnerability and increased access to livelihood and income generation programs.The devasting second wave of COVID-19 resulted in loss of jobs, food insecurity for vulnerable women and girls. UN Women is responding to this urgent need, through its implementing partner SEWA, by providing conditional and unconditional cash transfers by linking women to government security and livelihood schemes in the three programme states. While, the unconditional cash transfers have been designed to provide vulnerable women with a safety net to tide over food security and loss of pay. The conditional cash transfers have been designed to enable women entrepreneurs in the informal economy, who are left with no capital to re-start their business and livelihoods, by providing money for raw materials. In Chhattisgarh, Rajasthan and UP, UNICEF continued advocacy and technical support to local schemes and compensation programmes for survivors of GBV and children who are affected by COVID-19. UNICEF in Rajasthan continued its technical support to Department of Social Justice and Empowerment (SJE), to ensure 2258 women victim of violence continue to receive their financial support. In Uttra Pradesh, several applications under Rani Laxmi Bai Samman Kosh were pending and survivors were not receiving their compensation amount. Through UNICEF's advocacy and regular follow up at state level, 721 female survivors of GBV received compensation amount. The total disbursement was INR 26.46 Cr. In Delhi NRC and Telangana, UNHCR has conducted skill trainings for 128 women and 16 men on Enterprise Development, 75 refugee women on tailoring, paper bag and jute bag making with monthly incentive of INR 3,000 in Telangana. 51 women were provided with microgrants of $INR 25000/person and started their small businesses. A livelihood hub with creche facility for children is functional in Telanaga, provides a safe space for children when their mothers are engaged in skill development and livelihood activities. The creche has a refugee caretaker who receives monthly incentive for her volunteer work. In Delhi, 4 refugee volunteers provide interpretation support and mobilize community members for the EDP trainings and facilitations of microgrants and receive monthly incentives.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | COVID-19 pandemic and related restrictions on mobility may affect outreach and on-ground implementation of programme, as well as pace of the project activities. Especially, within the first half of 2021, India experienced the devastating hit from the 2nd wave, with staff from UN agencies and partners being severely infected. UN agencies continued maintaining close partnerships with the government and implementing partners to expand the outreach of project interventions through innovative methods including virtual platforms. Inclusion of mixed methods of delivery of interventions, both in person where feasible, and online, building on the current experiences in mobilizing online platforms have been explored, especially with non-traditional partners such as the technology firms. Some challenges were identified when involving refugees and host communities especially about lack of access to basic financial services for refugees, which were addressed by partnering with local NGOs and local social enterprises. UN agencies continue leveraging existing institutional relationship and forge formal partnerships with the national and relevant state level government counterparts as well as implementing partners (via MoU and/or any forms of collaboration framework/agreement) to ensure the implementation of the program. Dynamic political context, especially priorities shift due to the affects of the second wave, might have impacts on prioritizing and mainstreaming issues of Gender Equality and Women's Empowerment, particularly ending sexual and gender-based violence. To overcome that, UN agencies have been and continue focusing on the institutionalization of partnerships with key government agencies to ensure that programme activities are not affected by leadership change. Strategy of embedding consultants in Ministries by UN agencies has ensured consistent support to the Government on these substantive issues. Strategic alignment and inclusion of GBV as a core activity within the health sector response was helpful. Ensuring that GBV was included in strategic priorities of the organization like the UN Joint Response Plan, the socio-economic response framework and working with stakeholders through the national RG-7 (results group 7 for SDGs) was crucial in ensuring that the agenda was included and addressed. This has also contributed significantly to institutionalizing capacities on gender responsive governance, to mitigate risks accruing from changes in the larger political environment or churn at the individual level. Finally, the initiative will also rely on CSO partnerships to ensure adequate support and engagement with civil society. In order to avoid the backlash from and in line with the Do No Harm principle, the programme has also focused on increasing the engagement with men and boys in communities and other platforms to improve buy in for women and girl's leadership and reduce acceptance of gender based violence as a social norm. Alternatively, the programme will establish links with government departments and women's rights organizations to ensure economic and community focused interventions are complemented with access to referral services like counselling, shelter and child support where possible.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Through the MPTF programme, UN agencies have contributed to increase the SGBV visibility by engaging in public fora, investing in evidence building, strengthening alliances with civil society organizations, and through collaborating with other sectors to ensure multidimensional nature of some SGBV risks. There is a need to build on this opportunity galvanizing attention from different stakeholders towards this critical agenda. The Pandemic also brought into focus the need for better digital communications and digital solutions for delivering programmatic results. Frontline workers could not work to full capacity, physical access and support was rendered difficult and lack of online tools and connectivity, all hampered provision of essential GBV services. In the context of travel restriction and social distancing, technology and online platforms came in as prominent way to deliver capacity building sessions for partners in all fronts. By engaging with technology firms and digital platforms, the programme interventions would be able to reach out to a broader scope of target population despite the limited movement. At the same time, it is important to also address the issue of digital divide while promoting digital based programming, in order to ensure that the most vulnerable groups of women and children are reached. COVID-19 response has brought along opportunities for leveraging resources, partnerships and joining forces to address UN’s priority agenda. UN agencies have been able to turn the opportunity of the MPTF call for COVID-19 response to leverage funding for regular systems strengthening interventions to address SGBV. Moreover, through the MPTF funded programme, the participating UN agencies managed to create the momentum for close collaboration among UN agencies, leaving the way for joining forces on boosting the agenda of SGBV, for example, joint initiative on MHPSS and referral of SGBV services between WHO and UNICEF; joint collaborative framework between UNICEF and UNWOMEN with UNHCR targeting women and girls of refugee communities
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UN agencies continues building on existing partnerships with the line Ministries (MoWCD, MoE, MoHFW), Niti Ayog, the Judiciary, the Police, oversight mechanisms such as NCPCR, S/DCPCRs, CHILDLINE FOUNDATION, NIMHANS, academic institutions (such as Tata University), professional associations, NGOs/CSOs and youth platforms (NYKS, NCC and NSS), the one stop centers and counselling centers, helplines, etc. to ensure interventions reach the most vulnerable children/community, especially in the hard-to-reach areas. In addition, COVID-19 context has created favorable conditions for exploring non-traditional partnerships, especially the private sector to bring in innovative and technology-based solutions to address SGBV in the unprecedented context. For example, exploring technology firms to explore innovative digital solutions for women and girls at risks/survivors of SGBV for enhanced access to Artificial Intelligence (AI) based solutions, virtual safe space and e-referral pathways for survivors of SGBV, chatbots (Facebook, Websites, WhatsApp) for information dissemination, identifying and reporting, as well as referral to specialized services for women and girls experiencing SGBV. UN agencies continue strengthening the inter-agency coordination thanks to the MPTF funded joint programme and leveraging different platforms/networks to move the SGBV related agenda forward in a more systematic and coordinated way, which is critical especially in the times of COVID-19
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Not applicable
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Not applicable
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UNWOMEN: Project Coordinator and Training and Logistics Coordinator joined in 26 April 2021; UNICEF: Advocacy Specialist to support the advocacy agenda on Ending Violence Against Children, including SGBV recruitment process finalised

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 896451 |  | Quarterly internal reporting from each agency
Indicator: a. Number of women and girls and other vulnerable groups at risk and or survivors of SGBV have improved access to effective gender based violence preventive and responsive services
Baseline: 260,000
Planned Target: 930,500
Indicator: b. Number of girls and boys, women that have increased their socio-economic empowerment and agency to be able to prevent and address SGBV
Baseline: 270,600
Planned Target: 1,200,000
Output 1: Improved gender responsive and age sensitive protection and SGBV related multi-sectoral essential services are available for women and girls and other groups at risk of and/or survivors of SGBV |  |  | Quarterly reporting by agency
Indicator 1.1: Number of women and girls at risk and/or survivors of SGBV have access to SGBV case management and MHPSS services (Disaggregated by age, disability, ethnicity)
Baseline: 240,000 | 34752
Planned Target: 800,000
Indicator 1.2: Number of frontline healthcare professionals, staff of OSC, child protection functionaries have enhanced capacity on providing SGBV related services | 70022
Baseline: 124,000
Planned Target: 248,000
Indicator 1.3: Number of women and girls at risks/survivors of SGBV have access to Artificial Intelligence (AI) based solutions (Disaggregated by age, disability, ethnicity)
Baseline: 10,000 | The baseline was updated
Planned Target: 30,000
Output 2: Women and girls and victims of SGBV have improved access to gender-sensitive justice systems. |  |  | Quarterly reporting by agency
Indicator 2.1:Number of women and girls at risk and /or survivors of sexual and gender-based violence received legal aid support (Disaggregated by age, disability, ethnicity) | 2250
Baseline: 0
Planned Target: 8,500
Indicator 2.2: Number of states with referral mechanisms and training schemes in place by the National Police Academy to prevent and respond to SGBV/VAC
Baseline: 1
Planned Target: 8 | 3
Indicator 2.3: Number of officials from the law enforcement, security forces, CP functionnairies trained on cyber safety and security | 50
Baseline: 2000
Planned Target: 132,000
Output 3: Women and girls are aware of the risks of SGBV and harmful practices, and increasingly engaged in decision making processes related to COVID-19 response and recovery |  |  | Quarterly reporting by agency
Indicator 3.1: Number of local authorities, women's and community groups and women elected representatives benefit from participation-based comprehensive interventions to prevent and respond to SGBV
Baseline: 20,000 | The baseline was updated
Planned Target: 100,209
Indicator 3.2: Number of women, girls, boys, men reached with messages on SGBV prevention and response through community based outreach, media campaigns, including social media platforms | 737014
Baseline: 1, 187,400
Planned Target: 2,662,000
Indicator 3.3: Number of girls and boys, male and female youth collectives actively participated in community led outreach interventions and movements on SGBV and VAC | This indicator to delete as it is captured in the indicator 3.2
Baseline: 250,000
Planned Target: 1,000,000
Output 4: Vulnerable families of women and girls at risk of and/or survivors of SGBV/VAC have reduced their economic vulnerability and increased access to livelihood and income generation programs | 2979 |  | Quarterly reporting by agency
Indicator 4.1: Number of women and girls at risk and/or survivors of SGBV benefit from social protection and livelihood programmes (Disaggregated by age, disability, ethnicity)
Baseline: 20,600
Planned Target: 30,850
Indicator 4.2: Number of India's Flagship programmes on livelihoods that are gender sensitive | 2 |  | Quarterly reporting by agency
Baseline: 1
Planned Target: 3
Indicator 4.3: Number of states with Gender Action Plan, including responding to SGBV, developed and implemented | 1 |  | Quarterly reporting
Baseline: 2
Planned Target: 4
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Not available
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Social media post for SGBV and COVID-19. UNW with Govt. of Madhya Pradesh.
UNW twitter post:UN Women & SANWED South Asia Consultation on Widows
ASK THE EXPERT SESSION with GOVT.OF DELHI Frontline Functionaries (4th June 2021)
ASK THE EXPERT SESSION with GOVT. of Rajasthan Frontline Functionaries (18th June 2021)