## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | INTERIM REPORT
DEADLINE:
4 | ALL Call 2 projects must complete an interim report
5 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Interim
Programme Title & Project Number |  | Programme Duration
Programme Title: | Promoting Innovative Service Provision Models to Support the COVID-19 Health System Response | Overall Duration (months) | 14
Programme Number (if applicable) | N/A | Start Date (dd.mm.yyyy) | 12.02.2021
MPTF Office Project Reference Number:[2] | 125919 | Original End Date (dd.mm.yyyy) | 01.12.2021
Country | Turkey | Current End date(dd.mm.yyyy) | 31.03.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA WHO | National counterparts (government, private, NGOs & others) and other International Organizations | -Ministry of Health (DG of Public Health, DG of Health Information Systems, District Health Directorates in Ankara, Konya and Samsun) -Ministry of Family and Social Services -WHO -UNHCR
Report Cleared By
o Name: | Alvaro Rodriguez
o Title: | Resident Coordinator
o Email address: | alvaro.rodriguez@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Interim
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project effectively began as of February 12th, 2021 with the release of funds. Under Result 1; UNFPA Turkey CO immediately started to complete necessary procedures for recruitment of the project team as well as procuring necessary equipment and materials. Such processes consisted of drafting ToRs, vacancy announcements (for programme manager, project associate, field associates, nurses and translators), interviews, pre-service trainings (orientation), preparing ToRs for medical equipment and personal and protective equipment, acquiring no objection letters from Ministry of Health of Turkey and WHO as well as taking necessary steps to ensure that communication and visibility materials were ready before project activities started. Following the recruitment, the project team worked on logistics, distribution and storage of equipment and materials. There were several meetings with the Ministry of Health and District Health Directorates to introduce the project team, plan and coordinate project activities, formulate an action plan on how to adapt Mobile Health Units (MHUs) into existing system and discuss the method for monitoring and evaluation. With the finalization of such processes, six MHUs (three units for each province) started to effectively work in Ankara and Konya as of May 27th, 2021. All units are currently providing uninterrupted access to essential health counseling, services and referrals in the field of COVID-19 pandemic as well as sexual and reproductive health and gender based violence (where needed). Within the framework of Result 2; a meeting was held with the General Directorate of Public Health of MoH regarding the training materials to be prepared for family health workers, physicians and patients, and to identify the most appropriate communication methods. In addition, two consultant service agreements were signed regarding the protection of personal data and legal infrastructure of Telehealth. A virtual meeting was held with Ankara, Samsun and Konya district health directors. During the meeting, high-level contact persons were determined to ensure smooth implementation of the project. Preparation of training materials and service procurement have been completed. Konya District Health Directorate and Family Health Center were visited, and the project was explained in details to the district directors, family physicians and family health workers. Necessary technical material procurement process is underway. After the trainings are completed, materials will be sent to the relevant healthy life centers along with migrant health centers. For Result 3; Standard Operation Procedure (SOP) was developed in an inclusive approach through which all team’s (including field associates and MHU staff) views and opinions were reflected on the document. The document covers several critical issues such as provision of preventive health services that are integrated to filiation; identification of risk groups and improvement of their access to healthcare; and promoting public health literacy. Field associates and MHU staff are scheduled to receive training on the SOPs during August 2021. MHUs are regularly raising awareness on Covid-19 related prevention measures as well as sexual and reproductive health during their service provision through brochures and short informational sessions. Field associates are holding regular meetings with local governmental organizations in Ankara and Konya to ensure efficient provision of MHU services as well as risk communication. They are also in touch with certain NGOs, which are specifically providing services to refugees, to develop specific cooperation modalities to use MHUs in local refugee contexts.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The purpose of the project is to ensure increased access to immediate health and socio-economic support to respond to the health and social impact of the COVID-19 pandemic. To that end; In Result 1, six mobile units in two provinces have been providing mobile Covid-19 screening and tracking services as well as other essential health counselling, services and referrals through provision of primary health care via mobile health staff. Between May 27th and July 29th 3069 individuals have accessed to 5388 services provided by the MHUs (See Annex-1 for the breakdown). For Result 2,beneficiaries will be reached out after the preparation of the training documents and the organization of training. For this reason, the number of beneficiaries will be mentioned in upcoming reports. In Result 3, SOP was prepared with a view to guiding Field Associates (1 female, 1 male) and 6 MHU (9 female, 3 male) staff on how to conduct risk communication in the field. A follow-up training will be conducted on August 2021. Besides, in scope of the risk communication, mobile service units distribute informative brochures regarding COVID-19 protection, hygiene, birth, breastfeeding, prenatal, postnatal and newborn care, nutrition during pregnancy, infant feeding, violence against women, sexually transmitted infections and contraception to the beneficiaries to increase awareness.
3.1 | Results: Outcome Level | Please include outcome level results achieved | With service provision by 6 MHUs in two provinces, there is a significant increase in access to immediate health and socio-economic support to respond to the health and social impact of the COVID-19 pandemic (See Annex-1). With additional MHUs and the operationalization of telemedicine along with enhanced communication efforts, the access is expected to increase further in the second half of the project.
3.2 | Results: Output Level | Please include output level results achieved | Result 1 1- Project team (Programme Manager, Project Associate and 2 Field Associates) was recruited (ToR drafting, vacancy announcement, interviews). 2- MHU staff (6 nurses, 6 translators, 6 drivers) was recruited (vacancy announcement, interviews) and 6 vehicles were procured. 3- Medical Equipment and PPEs were procured (ToR drafting, announcement, no objection letters by Ministry of Health and WHO). 4- Communication, visibility and accountability materials were developed and procured. 5- Preparations regarding logistics, distribution and storage of relevant equipment and materials were completed. 6- Coordination meetings with Ministry of Health and District Health Directorates were held to integrate MHUs into existing system. 7- Orientation and pre-service trainings for MHUs were organized between May 24th and 25th, 2021. 8- MHUs have been operational since May 21th, 2021 for Ankara and May 27th, 2021 for Konya. 9- MHUs provided service to 2954 people as of July 29th, 2021. Result 2 1- Draft legal regulations regarding the usage of telemedicine, and informational documents were prepared. 2- Draft patient consent forms was prepared. 3-Preliminary work has begun for the necessary software and to integration of this software into the information systems of the Ministry of Health 4- The contents and properties of the video and training materials on the usage of telemedicine were identified. (For doctors, nurses/midwives working at the Family Health Centres and Healthy Life Centres and Refugee Health Centres and Beneficiary Population). 5- Two consultants were recruited on legal regulations. 6- Procurement processes for the preparation of training videos to be prepared for patients, doctors and healthcare professionals have been completed. Result 3 1- A consultant were recruited to prepare SOP. 2- SOP was developed. 3- SOP training for MHUs and field associates is scheduled to take place during August 2021. 4- Programme Manager and field associates have been in close communication with district health directorates to ensure operational effectiveness of MHUs. 5- Field Associates held meetings with certain NGOs (working with refugee populations) to discuss possible cooperation opportunities to be seized in local refugee contexts. 6- 1300 awareness raising materials were distributed to 370 people within the framework of mobile service provision.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Under Result 1, several challenges have been faced and addressed accordingly. One of them was about staff turnover. In Konya province, one of the nurses quitted and the one who was hired in his stead also left after a couple of days. Following this experience, the team was extra careful during the recruitment process and took additional measures to ensure that nothing similar was to happen. As a result newly hired nurse has been providing service in the field for a month without any problem. A second challenge was about some minor difficulties experienced by MHU staff in terms of providing health services in addition to the ones that are related to COVID-19 (where needed) in the presence of COVID positive individuals. Nonetheless, as the SOP is now finalized and the relevant training programme is scheduled to be organized in the coming weeks, this problem is expected to be over soon. Last but not least, district health directorates requested additional MHUs to be mobilized under the project due to the emerging need in the field. Therefore, the team initiated necessary procedures to mobilize 4 new MHUs (2 for Ankara and 2 for Konya) under the project. In Result 2, digital literacy might be a challenge. For this particular Result, an electronic system will be developed and used for access to healthcare. Nevertheless, some patients or senior physicians are expected to face difficulties in using the system. In this sense, the team will work to develop a user-friendly software by taking into account the views and suggestions of all stakeholders. For instance, in a meeting with family physicians, they asked that what would happen to the patients who came in front of the doctor's room while they were interviewing the patients remotely. It was agreed,in this respect, with the provincial administrators and the ministry that family physicians will take care of telehealth patients while face-to-face patients who come for medical exam without an appointment will wait until the online appointments are over. For Result 3, there were certain issues on how to execute joint risk communication efforts together with UNHCR. Project teams in UNFPA and UNHCR discussed the issue several times and assessed certain options ranging from developing different messages to using existing COVID-19 related messages developed by UNHCR at the beginning of the pandemic. As a result, UNFPA project team decided to carry out new communication efforts that address the effects of the pandemic on a sexual and reproductive health aspect. The team already shared a news article in UNFPA Turkey Website and will continue to execute the campaign in this sense.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | An important challenge that might be considered as an operational lesson and significant finding was about different modus operandi of MHUs that is embraced by different district health directorates. To ensure convergence among different service provision modalities used by MHUs, the field associates were in close communication with the authorities to ensure uniformity among MHUs service provision models. The modus operandi for all MHUs is currently, to a large extent, the same. In addition, during service provision process, project team as well as MHU staff have come to a conclusion that having a medical doctor in each MHU would be highly beneficial especially in terms of efficiency. The project team, field associates particularly, has been in close contact with district health directorates to this end. In a nutshell, as different districts might have different priorities and requirements, the project team strongly believes that ensuring uniformity among MHU services is critical. To achieve that the team (particularly field associates) has been following-up the situation in the field by maintaining close communication both with MHUs and district directors and proposing corrective actions where necessary.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | Project is being executed in close partnership with Ministry of Health, district health directorates, WHO and UNHCR. It is safe to say that the communication and cooperation capacity with the Ministry of Health, DG of Public Health, DG of Health Information Systems and district directorates is improving. The Ministry and district directorates are particularly pleased with the contribution of MHUs to pandemic related health services (including Covid- 19 prevention, surveillance, detection, filiation and referral) and therefore asked for additional MHUs to be mobilized. In addition, draft legal documents will be prepared for the telehealth infrastructure to be established within the Ministry. These documents are of vital importance for such services, which are planned to be extended to all provinces in the future. With the partnership built under the project, all stakeholders witness the convenience of the services provided to people with chronic diseases and vulnerable groups. For instance, it will help to reach the goals of the 3 billion people targeted by the World Health Organization at the global level. (One billion more people are benefiting from universal health coverage, One billion more people are better protected from health emergencies, one billion more people are enjoying better health and well-being) The project also facilitated cooperation among UNFPA, WHO and UNHCR by providing all sides the opportunity to closely examine and (where available) contribute to the work done by others. Agencies gather in every three weeks to discuss project's progress and coordination related issues along with how to benefit from others' efforts or execute joint activities in an effective manner. One concrete example to that end would be UNHCR's assistance to UNFPA in terms of extending UNFPA's risk communication endeavors (not only about COVID-19 pandemic but also sexual and reproductive health) to refugee population in Turkey by using UNHCR's existing mechanisms and channels.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | N/A
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | N/A
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | N/A

## RBM-Interim
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
RESULT 1
Output 2.1: Mobile health service provision for enhanced outreach to vulnerable populations | 6 | N/A | UNFPA Turkey CO -Vehicle Daily Logsheets for the 6 vehicles -Timesheets of the MHU staff -Regular field visits to Ankara and Konya by UNFPA project staff
Indicator 2.1.1:6 MHUs are operational
Baseline: 0
Planned Target: 6
Indicator 2.1.2: 18 personnel in the MHUs and 2 Field Associates trained | 20 | N/A | UNFPA Turkey CO -Recording of the orientation -Training and attendence sheet
Baseline: 0
Planned Target: 20
Indicator 2.1.3: # of beneficiaries receiving services from 6 MHUs | 3069 | The monthly planned target for this indicator was 786. By reaching out to 1534 individuals monthly, the MHUs have overperformed in terms of outreach (See Annex-1 for the breakdown). This is largely due to several facts such as, inter alia, close communication among partners, swift deployment capabilities of MHUs as well as increasing trend in daily COVID-19 cases in Turkey. | UNFPA Turkey CO Online Database
Baseline: 0
Planned Target: 11000
RESULT 2
Output 2.2: Telemedicine for increased access and coverage of services in primary health care | N/A | Indicators of the project can be formed after the preparation of the training documents and the training. For this reason, it will be mentioned in the future reports of the project.
Indicator 2.2.1: 18 modules of Telemedicine guidelines, algorithms, and patient information materials developed
Baseline: 0
Planned Target: 18
Indicator 2.2.2: Draft Regulation on telemedicine and personal data protection is developed
Baseline: No
Planned Target: Yes
Indicator 2.2.3: 10 HLC and 3RHC equipped with hardware for technology based patient consultation
Baseline: 0
Planned Target: 13
Indicator 2.2.4: 222 FHC center employees trained on telemedicine
Baseline: 0
Planned Target: 222
Indicator 2.2.5: 80 HLC center employees trained on telemedicine
Baseline: 0
Planned Target: 80
Indicator 2.2.6: # of beneficiaries reached through telemedicine
Baseline: 0
Planned Target: 204,175
Indicator 2.2.7: 40 RHC center employees trained on telemedicine
Baseline: 0
Planned Target: 40
Indicator 2.2.8: 3 press conferences to promote telemedicine are conducted
Baseline: 0
Planned Target: 3
RESULT 3
Output 2.3: Risk communication on Covid-19, essential health services and social protection services through multiple channels | 370 | During two months of project implementation, 1300 materials were distributed to 370 people. With additional MHUs and the operationalization of telemedicine along with enhanced communication efforts, the number of beneficiaries reached through risk communication is expected to increase further in the second half of the project.
Indicator 2.3.1: # of beneficiaries reached through risk communication
Baseline: 0
Planned Target: 30000
Indicator 2.3.2: Information Platform on service delivery regularly updated | N/A | The platform will be developed in the second half of the project
Baseline: No
Planned Target: Yes
Please inlcude all three: Baseline, Planned Target and Achieved Targets
_ftnref1

## Communication-Interim
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
During the pandemic, curfews have been imposed in Turkey to protect citizens over the age of 65. For this reason, people over the age of 65 will only be able to go out on weekdays between 10.00 am and 14.00 pm.This restriction has brought more limitations in the health follow-ups of people who are over 65 years old and have chronic diseases.In the meeting held with the physicians in the Family Health Center in Konya, the physicians stated that it would be very good for these patients to reach them via telehealth, especially for their psychology and health. In addition, the project team will conduct a photo/video mission to the field to collect visual materials and human interest/success stories to bring attention to the importance and objectives of the project and also showcase the service provision and outcomes in an impresive way. The visual materials and stories will be provided in the next report.
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
[UNFPA] During the project implementation, we conduct communication/visibility activities through both digital and traditional media. The informative brochures regarding COVID-19 protection and women's health have been uploaded to UNFPA Turkey website. In addition, a web story has been drafted and published to announce the project's objectives and targeted achievements. Web story has been shared through UNFPA Turkey social media platforms (Twitter, Instagram, Facebook) along with project's photos from the field. Social media activities will increase with thee visual meaterials and stories that will be collected through the photo/video mission. All the communication materials can be found in the Comms Annex. In the following months, UNFPA will be conducting 2 different awareness raising campaigns on social media on vaccination process and general information which is provided to beneficiaries through brochures, targeting general public. In addition, a few human interest stories will be drafted to bring attention to the project, its objectives and outcomes and to showcase how our services positively affect people. Also, a project video with the project staff and beneficiaries will be produced to visually document the service provision and its achievements.
Note on A1: @atilganozgenc@unfpa.org @kozdemir@unfpa.org _Assigned to ZEYNEP atilganozgenc_ -Zeynep Buker

## Annex-1 MHU Services Breakdown
MHU Number of Services Provided by Service Type (May-July 2021)
Service Type | # of Service
COVID-19 Vaccination | 569
Other COVID-19 Related Services | 2792
Other Services (incl. SRH and GBV) | 2027
TOTAL | 5388
Number of Beneficiaries Received MHU Services by Age, Gender and Nationality (May-July 2021)
Column1 | Female | Male | Total
Below 15 | 294 | 234 | 528
15 to 49 | 1013 | 749 | 1762
49 to 65 | 329 | 333 | 662
65 and above | 61 | 56 | 117
TOTAL | 1697 | 1372 | 3069
Turkish | 999 | 973 | 1972
Syrian | 607 | 303 | 910
Other | 91 | 96 | 187
TOTAL | 1697 | 1372 | 3069