## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Strengthening of the Educational System to address challenges derived from the Emergency before and after COVID-19 that promote educational care with a gender perspective | Overall Duration (months) | 12 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-05-25
MPTF Office Project Reference Number: | 00121773 | Original End Date (dd.mm.yyyy) | April 30, 2021
Country | Nicaragua | Current End date(dd.mm.yyyy) | 2021-10-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNICEF; WFP | National counterparts (government, private, NGOs & others) and other International Organizations | Nicaragua's MInistry of Education
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project aimed at supporting the Ministry of Education of Nicaragua to ensure educational services to children and adolescents in the context of th COVID-19 pandemic. It addressed 5 important aspects: socioemotional support in time of crisis; curriculum adaptation to respond to the special context imposed by COVID-19; online services for MINED to reach out to all personnel for training and other matters related to its functions; safe preparation and handling of school hot meals; and provision of safe drinking water. In regard to the socioemotional support component, guidelines were produced in 5 different languages (Spanish, Maygana, Miskito, Ulwa and Panamahka) to inform teachers of the best way to provide socioemotional support to children during the crisis. Thttps://www.petit-bateau.dehe guidelines were the basis for a long learning process that involved nearly 60,000 teachers (100% of the teachers in preschool, primary and secondary education). Along with the guidelines, at least 200 schools from the most isolated geographic regions of the country were equipped with ludic kits (745 kits in total) which helped teachers to implement a psychosocial strategy named “I feel good when I express myself”. Part of the strategy was to communicate key messages for which 50,000 educational posters were produced, with messages on how to manage stress, express solidarity, and respect during crisis. Guidelines were also produced to inform teachers on strategies to prioritize and adapt curriculum content to the specific needs of children in the COVID-19 pandemic context. 100% of teachers in the educational system received the guidelines. To contribute to online services by MoE staff at different levels, the MoE was equipped with access to a digital platform to have online meetings for a period of one year. Nearly 1,000 MoE officers that in turn reached out to more than 50,000 teachers benefitted from the online services, being able to improve their technical skills to deliver quality education during the COVID-19 pandemic. Along with the provision of a virtual platform, MoE was equipped with 221 technological kits, each one comprised a laptop, a pair of speakers and a projector (datashow) distributed among MoE municipal offices and certain school centers that serve as teachers training centers in the teachers monthly gatherings for evaluating, planning and being trained on an array of pedagogical themes. Regarding safe cooking and handling of school hot meals and provision of drinking water, with the project support, 625 public schools received recipients for safe food storage at school level (4 70-liter plastic recipients with lid per school; 2500 in total) as well as soap and paper towels for hand washing prior to food cooking; water recipients with faucet (2,500 120- and 70-liters for schools, 3,750 15-liters for classrooms); as well as hygienic kits containing soap, reusable fabric face masks and chlorine solution. These inputs allowed to improve school meal storage and preparation conditions and to prevent the contagion of COVID-19 among 12,400 school teachers. Finally, 25 hand-washing stations with water tanks (for schools with intermittent water supply) were built and installed in 25 schools of the Caribbean Region, each one including a kit for COVID-19 prevention (alcohol and spray bottles, chlorine solution, detergent, liquid soap and soap dispensers, mops and brooms, disposable masks) supporting hand-washing practices for COVID-19 prevention, and also improving water availability in schools located in hurricane affected areas.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | Nearly 1,000 education officials participated in a range of training activities conducted through the digital platform. Some 50,000 teachers and school principals benefitted indirectly from this, as education officials reproduced the trainings at local level. 60,000 teachers received the guidelines on socioemotional support and curriculum adaptation in emergency situations, instead on the 5,500 that were estimated in the project proposal. Indirect beneficiaries are the 1,808,293 children enrolled in preprimary, primary and secondary education. 67,279 students in 625 school centers benefitted from improved safe cooking and handling of school hot meals and provision of recipients for drinking water. 12,400 school teachers benefitted from hygenic COVID-19 prevention kits. 2,125 school children benfited from better water availability and handwashing conditions through 25 handwashing stations. Generally, MoE improved its COVID-19 response and food management through project activities in safe cooking and handling of school hot meals and provision of drinking water. | 2125
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1.1 The educational community, especially in the territories potentially most vulnerable to the impact of the COVID-19 pandemic, is better prepared, guaranteeing safe and protective learning spaces. Achieved. MINED was able to conduct online activities with its staff at national, departmental and municipal level, taking into consideration the current pandemic and related biosafety protocols. Coordination, planning, follow up and training continued in a virtual modality allowing MINED to ensure the necessary flexibility to ensure that the school year could be completed successfully. Moreover, MINED and all of its preschool, primary and secondary teachers (60,000) are now equipped with concrete guidelines on socioemotional support for children to better recover from trauma and stress related to COVID-19, as well as guidelines on how to adapt school curricula to emergency situations. Provisions have been made for teachers from indigenous and afro Caribbean communities to have access to their training materials in their own languages (Creole, Miskito, Mayangna, Panamaka and Tuaka). To enhance the socioemotional support, 50,000 posters were produced and distributed with messages relating to how best deal with stress in school and at home due to the special conditions that children, the school community and the families have to undergo during the Covid-19 pandemic. MoE in particular, and educative communities of 650 schools, including 12,400 teachers, 69,404 students and their families, improved its COVID-19 response and food management through project activities on safe cooking and handling of school hot meals; and provision of drinking water.
3.2 | Results: Output Level | Please include output level results achieved | 1.1.1 Teachers put into practice a school curriculum adapted to the particular / special situation, which prioritizes the basic and fundamental contents that can guarantee the educational continuity of the students. Achieved. Nearly 100% of teachers serving in the public education system (60,000) were trained on strategies to adapt the current curricula to the special situation imposed by COVID-19. The training was based on the guidelines produced (60,000 copies of the guidelines were financed by the project) and, in most cases, an online training was facilitated, using the digital platform that was also supplied by the project.
1.2.1 Girls, boys and adolescents, particularly adolescent girls, have psychosocial support tools that help them better face the challenges that the special situation caused by covid19 poses for them. Achieved. Guidelines on how to provide socio-emotional support to children at school in times of COVID-19 were produced. The document integrates topics such as resilience, recreational spaces, and socio-emotional support to students and the educational community in general. It also contains a component on practical exercises that help work with emotions during crisis or emergency situations. Originally intended for 5,500 teachers, the document will be reproduced to cover the entire teachers' population (60,000 copies) from the three different educational levels (preschool, primary, secondary). The document was translated into indigenous and Afro Caribbean languages (Creole, Miskito, Mayangna, Panamahka and Tuahka) thus reaching out indigenous and Afro Caribbean populations from the Nicaraguan Caribbean Coast. Along with the guidelines, 745 “ludic kits” were acquired and distributed to schools in the Caribbean Coast, for teachers to count with games, toys, didactic material that would help them put into practice socioemotional strategies to help students overcome stress, trauma and other problems they may face due to confinement or other special circumstances they are undergoing as result of the COVID-19 pandemic. 50,000 units of 5 different posters with messages supporting the campaign to reduce stress among the school community due to the covid19 pandemic were also reproduced, reaching out to 50% of the schools (4,500 schools) and nearly 900,000 students.
1.3.1 Municipal and departmental education offices, run mostly by women, are technologically able to carry out on-line administrative and educational processes. Achieved. With access to 180 virtual rooms which allow nearly 1,000 attendees in a video-conference setting, the project created a virtual platform that has strengthened the capacities of MINED in planning and institutional communication at central, departmental, municipal and school level. Along with access to a virtual platform, 221 locations among department and municipal MoE offices, as well as schools that serve as teachers training centers at local level, were equipped with technological kits (laptops, data-shows, speakers), thus, creating a virtual network that has ben functioning during the emergency. Main activities carried out include: orientation sessions on strategies for school principals and administrative personnel to ensure the adequate facilitation of the learning process; training on the use and management of curricular documents; guidelines for school reinforcement and catching up activities; matrix of prioritized indicators; and self-study guides. Also, the platform was used to train teachers on activities leading to promote values for the care of life in all its forms, how to provide socio-emotional support in crisis situation, and recommendations for parents of children in early learning and/or children with disabilities.
1.4.1 The educational community has better access to drinking water service in prioritized schools, which contributes to improving school and personal hygiene actions, thus reducing the risk of contagion of communicable diseases, and in particular, in COVID-19 Achieved. The project contributed to the promotion of hygiene and preventive health before COVID-19. 625 educational centers have enhanced access to drinking water through two main activities: internal water storage improvement, with six 15-liter containers and two 120 + 70 liter containers at each center, placed at waist height, adapted with a tap for hand washing. Also, 25 additional schools were provided with handwashing water stations, each one with a elevated tank for water captation and suplly to faucets. These centers have intermitent water provision, meaning that water is provided to schools when there are students, or only some days a week), so now students and teachers have enough water for handwashing and for other basic needs in schools, like school cleaning and - specially - toilet cleaning. Having water at school reduces the risk of harassment and sexual violence for girls and women (female students, teachers and mothers)
1.5.1 Educational community in prioritized schools puts into practice better gender sensitive habits that contribute to guaranteeing food hygiene, in the context of the provision of school meals. Achieved: The project provided 3,100 hygienic COVID-19 prevention kits for teachers and 625 kits to safely prepare and handle school meals (which includes food storage recipients + hygienic kits), which were acquired in coordination with MoE and transferred to them. The COVID-19 prevention kits support MoE efforts to reduce or avoid COVID-19 prevalence in schools. The kits to safely preparare and handle school meals also support COVID-19 prevention efforts and improve storage conditions and handling and provision of school meals.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The project encountered two main difficulties related to WASH: the provision of clean water for schools due to planning related to well construction and the procurement of technological kits as a result of supply chain problems in the context of COVID-19. Risk Management Matrix Due to poor offer, inputs are not locally available The risk materialized when trying to procure technological kits (laptops, datashows) and international suppliers needed to be involved, leading to delays in delivery. It also materialized when procuring water storage recipients: prices increased and the offers were insuficient. Procuring size-alternatives and providers with import capacity was a solution for the project. Social norms do not favor gender equality This has not been a constraint so far in the process of project implementation Technical and operational demands placed by expanding the MINED’s virtual network are not met due to lack of resources This has not been a constraint so far in the process of project implementation.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | The construction of critical infrastructure for emergency projects in an extremely short time frame should be considered a high risk and costly endeavor. Mitigation measures should be clearly stated in the Risk Management Matrix. Moreover, on national emergencies and national institutional capacity, competing priorities should be considered, which may lead to delays in the implementation. Supporting the MoE to conduct online services in the context of the COVID-19 pandemic was crucial. Online services should become more a norm than the exception in the future. This will require the MoE to make adjustments that are of long-term impact, for instance, instead of depending on external services for a virtual platform, the MoE must equip itself with its own technology. Water provision in schools is critical both for learning in normal conditions and for education continuity and health protection in emergency situations. Solutions provided by the project should be continued, initially focusing in these regions with high risk of natural disasters.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | Main partner in this project is the Ministry of Education (MINED). Both UNICEF and WFP have a long working experience with MINED, easing the two-way communication and understanding mutual needs.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | None yet.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The acquisition of 745 ludic kits to support the implementation of the psychosocial support strategy “I feel good when I express myself”, not foreseen in the original proposal, was possible as there was a good saving in the production of the teachers guidelines. The ludic kits were distributed in schools in the Caribbean Coast of the country, reaching out to at least 300 schools and some 30,000 students. 25 additional schools were provided with hand-washing stations with elevated water tanks, specially designed for schools having intermitent provision of water. These stations were pre-fabricated, which eased the construction process.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Procurement processes have been carefuly managed to ensure that no negative impact on local markets are made, as well considering local procurement capacities. Some items had to be imported, such as technological equipment, which has added some complexity to the procurement process.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1.1: The educational community, especially in the territories potentially most vulnerable to the impact of the COVID-19 pandemic, is better prepared, guaranteeing safe and protective learning spaces |  | School completion rate from MoE not available yet. | 2020 administrative data from MINED
Indicator:1.1.a : % of children who complete their school year with no major challenges due to covid19 crisis
Baseline:
Planned Target:100%
Output 1.1.1 Teachers put into practice a school curriculum adapted to the particular / special situation, which prioritizes the basic and fundamental contents that can guarantee the educational continuity of the students. |  |  | Administrative data
Indicator 1.1.1.a: # of teachers who implement the curriculum adaptation strategy | 60000 | The cost of printing the document was far less than the cost in budget. Also, MINED considered that the material should be accesible to all teachers from the various educational levels.
Baseline:None
Planned Target: 5,500 teachers receive the guidelines for Curriculum adaptation - 63% women n=beneficiaries
Output 1.2.1 : Girls, boys and adolescents, particularly adolescent girls, have psychosocial support tools that help them better face the challenges that the special situation caused by covid19 poses for them.
Indicator 1.2.1.a: # of children who receive sico-social support in the year 2020 | 1800000 | By reaching out to 100% of teachers with the sico-social support material, it is safe to say that 100% of children attended by the education system were reached out with actiivties to help them cope with the crisis. | Administrative data
Baseline:
Planned Target: 5,500 teachers support the psico-social strategy to ensure reintegration of student to school - 63% women beneficiaries
Output 1.3.1: Municipal and departmental education offices, run mostly by women, are technologically able to carry out on-line administrative and educational processes.
Indicator 1.3.1.a: # of municipal education offices connected to the MINED´s national virtual network. | 221 | 221 technological kits were acquired, 96 more than estimated, which represents an exceeding 77% over the target. More MINED municipal offices and schools (221) received the kits, allowing more offices and teachers to be connected to the national virtual network. | - Administrative data - Reports of virtual activity by municipal offices
Baseline: 20 education offices are already connected
Planned Target: 125 municipal offices will be connected additionally - 55% women beneficiaries
Output 1.4.1: The educational community has better access to drinking water service in prioritized schools, which contributes to improving school and personal hygiene actions, thus reducing the risk of contagion of communicable diseases, and in particular, in covid19.
Indicator 1.4.1: # of schools that have access to potable water | 25 (hand-washing stations with elevated water tanks instead of wells) | Hand-washing stations with elevated water tanks were provided instead of wells, as per project adjustmen approved. | -Administrative registries - field Reports on task completion
Baseline: 3,057 schools have acccess
Planned Target: 40 schools will have access to potable water, permanently
Indicator 1.4.2: # of schools that count with safe storage and distribution of potable water | 650 | 25 addtional schools reached with hand-washing stations | Administrative registries
Baseline: 1,386 schools are in need of equipping themselves
Planned Target: 625 schools will have the equipment to storage and distribute potable water in a safe manner – 52% women beneficiaries
Output 1.5.1: Educational community in prioritized schools puts into practice better gender sensitive habits that contribute to guaranteeing food hygiene, in the context of the provision of school meals. |  |  | Administrative registries
Indicator 1.5.1: # of teachers equipped with hygiene kits | 12400 | -
Baseline: 0
Planned Target: 12,400 teachers
Indicator 1.5.1.b: # of kits provided to teaches for their classrooms | 3125 | 25 additional kits brought to the 25 schools were handwasing water stations were installed | Administrative registries
Baseline:
Planned Target: 3,100 kits delivered – 54% women beneficiaries
Indicator 1.5.1.b: # of kits to safely handle provision of school meal | 625 | - | Administrative registries
Baseline: 0
Planned Target: 625 kits delivered – 54% women beneficiaries
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
https://www.unicef.org/nicaragua/historias/unicef-entreg%C3%B3-hoy-al-mined-221-kits-tecnol%C3%B3gicos https://www.unicef.org/nicaragua/comunicados-prensa/unicef-entrega-60000-gu%C3%ADas-al-ministerio-de-educaci%C3%B3n-para-promover-entornos https://www.unicef.org/nicaragua/comunicados-prensa/153-escuelas-recibir%C3%A1n-kits-l%C3%BAdicos-donados-por-unicef-para-contribuir-la
https://medium.com/world-food-programme-insight-espanol/wfp-entrega-kits-de-prevenci%C3%B3n-covid-19-y-materiales-para-higiene-para-625-escuelas-74da475a3d48 https://radionicaragua.com.ni/pma-entrega-al-mined-kits-de-prevencion-al-covid-19/ https://www.mined.gob.ni/pma-entrega-a-mined-kits-de-higiene-para-aplicacion-de-medidas-de-prevencion-para-el-cuido-de-la-vida/ https://www.el19digital.com/articulos/ver/titulo:114999-pma-y-unicef-entregan-donacion-al-mined https://canal6.com.ni/2021/04/14/mined-recibe-kits-para-prevencion-del-covid-19-por-parte-de-unicef-y-pma/
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words) There were organized media-events for official transfer of assets to MoE, both by WFP and UNICEF in close coordination. Links above shows media coverage and how MTPF was mentioned. Also, WFP and UNICEF agreed on a project logo, wich was used in stickers for visibility in items transferred to MoE (reffered in previous annual reports). Pictures are included below as example.
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Fotos de una de las estaciones de lavado de manos en el Caribe nicaragüense. Nótese la calcomanía en el tanque de agua. Nótese los dos tamaños de lavamos, que son activados con los pies y cuentan con un espejo metálico, entre otras elementos. Fotos: PMA - Nicaragua.