## OVERALL REPORTING INSTRUCTIONS (hidden)
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General information - Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Implementation of a gender-sensitive Social Household Registry in Guatemala. | Overall Duration (months) | 12 months
Programme Number (if applicable) | 00124304 | Start Date (dd.mm.yyyy) | 2020-10-31
MPTF Office Project Reference Number: | 00124304 | Original End Date (dd.mm.yyyy) | 2021-12-31
Country | Guatemala | Current End date(dd.mm.yyyy) | 2021-12-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UNFPA, UNICEF and UNHCHR. | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Social Development, National Institute of Statistics, Presidential Secretariat for Women, and Vicepresidency of the Republic.
Report Cleared By
o Name: | Rebeca Arias Flores
o Title: | Resident Coordinator
o Email address: | rebeca.ariasflores@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | In the first half of 2021, efforts have focused on positioning the importance of the Social Registry of Households at the political and strategic level for its contribution to the National Social Protection System. The joint program has been presented at the Cabinet of Social Development and the Cabinet of Ministers, as one of the most important projects for the commemoration of the bicentenary of the Republic of Guatemala. Lobbying for the program at the political level has been important to obtain commitment from MIDES to support the technical implementation of the program, considering that MIDES did not have public funds reserved for this purpose. As of June 2021, community consultations and validation of program´s tools were completed in the pilot municipalities of the Social Registry of Households: San Gaspar Ixil (Huehuetenango), Santa Lucía Reforma and Santa María Chiquimula (Totonicapán), San Bartolomé Jocotenango (Quiché), Santa Cruz la Laguna (Solololá) and Santa Apolonia. (Chimaltenango). During this phase the dimensions and variables included in the elaboration of the socio-economic conditions assessment sheet (FECS), were validated with community leaders, local authorities, women’s organizations and the field offices of the Ministry of Social Development (MIDES), which also contributed to provide updated information on the social register of households and its field work. The information collected on households, at the field level, will be geo-referenced. The implementation of geo-referenced technologies is an important and innovative step for MIDES and for the country, this information and methodologies will support reaching the poorest people in the pilot municipalities, who may not be identified in general surveys. MIDES technical teams have validated the content of the Social and Economic Conditions Assessment Sheet (FECS), a key element for the development of the digital platform and the collection of information in the field. Sixty per cent of this platform is being developed by UNICEF,this agency is responsible for the design, technical support, and the development of control panels to follow-up and monitoring the SRH. The FECS will make possible to identify people living in multidimensional poverty who sould be covered by social programmes, the FECS can be used by the Social Cabinet, as an inter-ministerial tool, to support a coordinated response. The technical teams of MIDES are currently managing all the human and financial resources in the field to ensure 20,000 households are included in this pilot exercise. The program plans to start activities in the first municipality, San Gaspar Ixil, in September 2021
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The Social Registry of Households (SRH) will provide information to characterize population living in poverty, prioritizing women, indigenous women, women with disabilities and women heads of households, in condition of vulnerability, with this purpose, a tool is being developed (FECS) to identifify women in multidimensional poverty. Additionally, consultations with prioritized women's groups to ensure their full participation in the design and implementation of the SRH have began and will continue throught the life of the program. The pilot exercise in 6 municipalities will provide information to design social protection programs that will contribute to the leadership and empowerment of women, in support of the design and implementation of the National Social Protection System. The Program will target 20,000 households in the pilot phase.
3.1 | Results: Outcome Level | Please include outcome level results achieved | No results achieved at this level yet.
3.2 | Results: Output Level | Please include output level results achieved | Community consultations were conducted with community leaders, women, youth and indigenous peoples. The information collected in this consultations was used to feed the FECS, ensuring that this Social Registry of Households key tool captures multidimensional poverty in Guatemalan households. The consultations focused on access to food and water, health, employment, education, migration, climate events, and security. A total of 36 men, 43 women and 28 young people participated in the consultations.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken +B7:B8D3B6:B7 | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | 1. One of the main challenges to design and implement a gender sensitive Social Registry of Households (SRH) is the absence of instruments for the identificat of households living in poverty and extremy poverty in rural Guatemala. The needs of the family should be identified, using a multidimensional and life-cycle approach, and considering the characteristics of target population. Also, the methodology to develop these instruments should be participatory to promote women leadership and empowerment. 2. The UNS is jointly developing with the Ministry of Social Development the field methodology and the instruments for data collection (FECS) taking into account interface between information systems. 3. Institutionalization of one data base for the beneficiaries of social protection programs. 4. the implementation of community consultations that will feed the socioeconomic profile (FECS), following COVID-19 protocols in populated communities. 5. Weak institutional capacity and limited movilization, due to COVID19, to update digital cartography and databases disaggregated by ethnicity, sex and age, also for planning and implementing the field work in prioritized municipalities, which has resulted in delays in the implementation of the pilot program.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Between 5 April and 11 May 2021, OHCHR Guatemala conducted consultations in the municipalities selected for the pilot project: Santa Cruz la Laguna, Santa Apolonia, San Bartolome Jocotenango, San Gaspar Ixil, and Santa Maria Chiquimula, respectively. In each municipality, a group of local authorities was also involved. The consultations focused on issues related to access to food and water, health, employment, education, migration, climate events, and security, according with the instrument for data collection (FECS). A total of 36 men, 43 women and 28 young people participated in the consultations. These consultations made ipossible to validate the dimensions and indicators that make up the FECS, which will be approved by MIDES as a unique tool for focusing social programmes.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | In the planning phase, meetings were held in collaboration with the National Institute of Statistics – INE (for its acronym in Spanish) and MIDES, where the importance of digital cartography was raised. Other relevant actors such as the National Registry of People, RENAP, has been reached to formalize a partnership in the near future.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | No assesments, evaluations or studies undertaken during the reported period.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | No major adjustments have been made during the reported period.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The interagency team has been lobbying for the allocation of public funds for the collection of data at the field level, considering that MIDES and UNDP financing the appointment of al least 100 people for this purpose. Resources are needed to rent vehicles and to provide per diem for field staff. UNFPA has allocated additonal core resources to support quality of the cartography.
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Por favor incluir el dato sobre cuantas households estuvieron representadas por el número de personas que fueron consultadas, ya que parece bajo el número de personas. Indicar también que las consultas se han realizado bajo condiciones dificiles por la Pandemia y que las personas tienen miedo de participar.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] |  | On going
Indicator:Result 1: A Gender-sensitive Social Registry of Households pilot plan implemented in five prioritized municipalities with higher incidences of poverty and extreme poverty and vulnerable populations, including women, indigenous women, women with disabilities, and female heads of household.
Baseline: 0
Planned Target: 1
Output 1.1 Output 1.1. A tool to characterize the socioeconomic conditions of households is implemented with a multidimensional approach that is sensitive to women's rights. | On going | Joint work is under way, through inter-agency meetings, the development of a socio-economic profile.
Indicator 1.1.1: Form designed and institutionalized for regular use in ministry.
Baseline: NO
Planned Target: YES
Indicator 1.1.2: Percentage of population identified in the Household Registry, according to the characterization tool. | On going
Baseline: 0
Planned Target: 20,000
Indicator:Result 1: Proposal of social protection programs designed in a discernable way for the empowerment and leadership of women which contribute to the establishment of a gender-sensitive NSPS, particularly for women, indigenous women, women with disabilities and women heads of household. disabilities, and female heads of household. Baseline:0 Planned target: 1 |  | On going
Output 1.2 Consultation processes are carried out with women, indigenous women, women with disabilities, and women heads of household at all stages of the process to ensure their full involvement in the implementation of the SRH. | 56 women, young women (29%), indigenous women (60%) and women with disabilities (0,5%) were consulted in this phase | On going | workshops and consultations
Indicator 1.2.1: Number of women, indigenous women, women with disabilities and women heads of households consulted, in all stages of Social Household Registry development.
Baseline: 0
Planned Target: TBD
Indicator 1.2.2: Number of consultations with women, indigenous women, women with disabilities, and women heads of households, in all stages of Social Household Registry development. | 5 consultations with women, young women, indigenous women and women with disabilities were conducted in this phase | On going | workshops and consultations
Baseline: 0
Planned Target: 3
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
No results achieved at this level yet. (The program started in november 2020)
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
https://guatemala.un.org/es/99803-registro-social-de-hogares-sensible-al-genero
https://twitter.com/midesgt/status/1325828427056898048
https://www.prensalibre.com/guatemala/comunitario/en-que-consiste-el-registro-social-de-hogares-que-impulsa-el-mides-y-donde-sera-ejecutado/
https://lahora.gt/gobierno-lanza-programa-de-gran-cruzada-por-la-nutricion-en-chiquimula/
https://twitter.com/unfpaguatemala/status/1391899832843898883
https://twitter.com/midesgt/status/1394403966516178944
https://twitter.com/midesgt/status/1410694919551848448
https://twitter.com/midesgt/status/1394331197556264970
https://twitter.com/midesgt/status/1412456959798878208
https://twitter.com/midesgt/status/1413208822861156352
https://twitter.com/midesgt/status/1413562090158178315
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board