## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Supporting marketplaces to respond to dual crises of COVID-19 and Tropical Cyclone Harold in Vanuatu | Overall Duration (months) | 6.5 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-05-13
MPTF Office Project Reference Number: | 00121530 | Original End Date (dd.mm.yyyy) | 2020-12-31
Country | Vanuatu | Current End date(dd.mm.yyyy) | 31/12/2020 (UN Women)
01/03/2021 (UNDP)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN Women and UNDP | National counterparts (government, private, NGOs & others) and other International Organizations | Local Government and municipal councils, UNDP and UN Women, NIMVA and SIMVA.
Report Cleared By
o Name: | Mohammed Mozeem
o Title: | UN Partnerships Specialist, RCO
o Email address: | mohammed.mozeem@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | In Vanuatu, market vendors' incomes were heavily impacted by the twin crises of TC Harold and COVID-19. The SOE disrupted markets, reducing the number of vendors and working hours, particularly in Port Vila and Efate. Social distancing measures heavily impacted vendors, with 60 percent of respondents in Vanuatu stopping their market business at some point when restrictions were implemented. The crisis resulted in a sharp economic shock to the informal sector, with 97.7 percent of vendors surveyed indicating that the COVID-19 pandemic had impacted their income. The Council similarly experienced a revenue reduction due to the decrease in numbers of vendors and table fees. UN Women and UNDP worked together in a close partnership, under the umbrella of the Markets for Change project, to deliver this project. UN Women, via the Markets for Change Project, supported the procurement of WASH and PPE supplies for market vendors to ensure that they continue operating safely. While there have been delays in delivering these materials, the following items have been procured: signage, washable and reusable face masks, stainless-steel sinks, water blusters and trailers for M4C markets. Additional communications materials such as PA systems and screens were procured to support public health announcements. UNDP worked with partners across government, civil society and the private sector. The Department of Agriculture and Rural Development (DARD) was an active partner in this response. The agricultural extension officers assisted greatly in the distribution of seeds and tools in the areas that they were responsible for. They assisted by organising the vendors to meet and wait at a central location to receive the agricultural inputs, advised on how seeds were to be planted and answered any other farming queries from the farmer vendors. These extension officers also helped the Northern Islands Market Vendors Association (NIMVA) members with the running of their satellite nurseries. The main nursery in Luganville, Santo was built in the DARD agriculture station staffed by a nursery officer that is supervised by the DARD department. The seedlings germinated from the nursery were distributed by the agricultural extension officers to their areas. Material support from the fund was central to this partnership by enabling the provision of agricultural supports. NIMVA executives worked in close partnership with the project team and DARD. Consultations before and during the distribution took place with the two stakeholders. The Vendors Association ensured that vendors were aware of the distribution taking place in their areas and ensured that the vendors turned up with their identification cards. The distribution of agricultural inputs provided market vendors with the means to increase their productivity. During the distribution of seeds and tools, capacity building also took place as often there were queries from vendors with regards to farming and other issues that they faced. Vendors sought advice and built on basic knowledge gained during training or through word of mouth by fellow vendors. Vendors who had not attended training were identified and conveyed their interest in specific training to assist in their market vending business.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | There were two purposes of this project: a) Supporting local government to ensure markets are safe and clean and women market vendors protected in Vanuatu by reducing risk of COVID-19 transmission in marketplaces; b) Support increased agricultural production in Vanuatu in the wake of twin crises of COVID-19 and TC Harold in order to boost food supply and protect women market vendor’s incomes. a) WASH supplies: The beneficiaries of this project were the vendors at Marobe, Luganville and Port Vila market. To date, some supplies have been delivered to all three markets. The total number of vendors in these marketplaces that benefitted directly from the delivery of WASH supplies and COVID-19 prevention interventions is 1,000 in Port Vila Market directly benefitting, and indirectly benefitting 40,000 people who live in the market catchment area; 3,000 vendors in Luganville Market directly benefitted and a market catchment population of around 10,000 people were indirect beneficiaries. In Marobe market the direct beneficiaries were around 100 vendors. b) Agricultural inputs: There were over 4,500 direct beneficiaries of this project, with more than 90 percent being women. There are approximately 3,000 vendors sell in Luganville market and were direct beneficiaries of the project. The Luganville market services a population of around 10,000 people, who were indirect beneficiaries of this project. In addition, 692 vendors benefitted directly from the delivery of agricultural inputs (679F, 13M and 28 people with disabilities). Additional gardening tools procured in the 4th quarter will be distributed in the final distribution in February. At the end of the distribution 2,892 vendors will have been assisted through agricultural inputs surpassing the proposed target. C) The agricultural inputs enabled vendors and vendor farmers to make the most of training provided under Markets for Change, which included demonstrating gardening techniques like planting techniques for root crops and preparing soil for growing seeds in nurseries and grafting. This joint project directly supports Pillar 3 “Economic Response and Recovery: Protecting jobs, small and medium sized enterprises, and vulnerable workers in the informal economy” of the UNCT Multi-Sectoral Response Plan.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Supported local government to ensure markets are safer and cleaner and women market vendors were protected in Vanuatu by reducing risk of COVID-19 transmission in marketplaces. Supported increased agricultural production in Vanuatu in the wake of twin crises of COVID-19 and TC Harold to boost food supply and protect women market vendor’s incomes.
3.2 | Results: Output Level | Please include output level results achieved | WASH items were procured to ensure markets are safer and cleaner for vendors in Vanautu. Initial distribution completed to three markets and final distribution to be completed in coming months. Materials procured included: 36 x 20L liquid hand soap, 36 x 20L disinfectants, 378 pieces of public health signage, 90 packets of cleaning cloths, 66 commercial grade floor mops, 21 mop buckets, 30 hoses, 36 industrial toilet cleaners, 7000 face masks, 66 brooms, 44 wheelie bins, 8 water blasters, 1 rubbish bin collection trailer, 12 stainless steel sinks, thermometers, LED screen for public announcements, PA system for public announcements. To date, sinks and signange have been delivered to the markets. Agricultural inputs comprised of the distribution of gardening tools of 60 knives, 100 gardening forks, 100 gardening spades, 313 seed packs distributed, and 138 germinated seedling trays distributed. Nursery materials of 7 wheelbarrows, 2 rolls shade cloth, 2 x 30m coil hose pipes and 300 plastic strainers for seedling trays. Three areas received satellite materials and 1 main nursery set up in Luganville. 2,200 gardening tools yet to be distributed and 5 tillers to be handed over to Department of Agriculture.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Supply chains were extremely disrupted both at a national and international level, leading to lengthy delays, shortage in supplies, and difficulties in obtaining required quantities of materials. Given international supply chain complications caused by COVID-19 it was difficult to get the quantity and quality of products (both WASH and seeds) required for vendors. After TC Harold there was a significant demand for supplies, which made the process difficult. A significant amount of the WASH supplies had to be shipped from other countries, which meant that there were delays in delivery. Likewise, numerous vendors had to be approached to get the necessary numbers of units of WASH supplies, as no single vendor had the required amounts. After TC Harold there was a high demand for seeds from the public as vendors and people unemployed due to COVID 19 had to plant food for consumption or to sell to earn income. Having only one major seed supplier in country meant that there was a shortage and the other outlet that sells seeds were unable to provide the requested quantity. There were direct and indirect challenges that contributed to the delay in the distribution and the completion of the assistance of agricultural inputs on time. TC Yasa was an unforeseen circumstance that indirectly led to a delay in the procurement processes. The cyclone devasted Fiji towards the end of last year, during which time the Suva office had to close due to security reasons, thus the finance team were not able to complete procurement on time thus delay in delivery. Vanuatu had its first border case of COVID-19 in November, resulting in restricted movement to outer islands, thus distribution and follow up monitoring on the agricultural inputs did not occur as planned.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | COVID-19 highlighted the fragility of women working in the informal sector – but also highlighted their resilience as well. Working with women in the informal sector should be a key strategy towards sustainable livelihoods moving forward. The marketplace absorbed many of those that lost employment during the COVID-19 period – and also engendered many to diversify their businesses in response. Market places and MVAs can provide a key platform to access difficult to reach groups of women and men. Providing services through MVAs, in areas such as health and public health messages, will ensure that a broader range of women are able to access services. Supply chains were extremely disrupted both at a national and international level, leading to lengthy delays, shortage in supplies, and difficulties in obtaining required quantities of materials. Factoring in relaxed processes to be able to adapt to these changed circumstances would be helpful, particularly around procurement but also project flexibility. In a small city like Port Vila, there is not a large variety of specialized shops eg seeds shop. Getting quotes for large procurement is impossible as the requested quantity is not in stock.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UN Women and UNDP worked together in a close partnership, under the umbrella of the Markets for Change project, to deliver this project. UN Women worked with the local governments and municipals councils responsible for the markets to undertake an assessment of WASH needs and has worked with Market Vendors Associations (MVA) to support the delivery of materials. The Silae Vanua MVA and Northern Islands MVA executives worked in close partnership with the project team and Department of Agriculture and Rural Development. UNDP worked with partners across government, civil society and the private sector. The Department of Agriculture and Rural Development (DARD) was an active partner in this response. The agricultural extension officers assisted greatly in the distribution of seeds and tools in the areas that they were responsible for. They assisted by organising the vendors to meet and wait at a central location to receive the agricultural inputs, advised on how seeds were to be planted and answered any other farming queries from the farmer vendors. These extension officers also helped the Northern Islands Market Vendors Association (NIMVA) members with the running of their satellite nurseries. The main nursery in Luganville, Santo was built in the DARD agriculture station staffed by a nursery officer that is supervised by the DARD department. The seedlings germinated from the nursery were distributed by the agricultural extension officers to their areas. Material support from the fund was central to this partnership by enabling the provision of agricultural supports. NIMVA executives worked in close partnership with the project team and DARD. Consultations before and during the distribution took place with the two stakeholders. The Vendors Association ensured that vendors were aware of the distribution taking place in their areas and ensured that the vendors turned up with their identification cards. The distribution of agricultural inputs provided market vendors with the means to increase their productivity. During the distribution of seeds and tools, capacity building also took place as often there were queries from vendors with regards to farming and other issues that they faced. Vendors sought advice and built on basic knowledge gained during training or through word of mouth by fellow vendors. Vendors who had not attended training were identified and conveyed their interest in specific training to assist in their market vending business. This ties in closely with the broader Markets for Change project, and in particular capacity building training for women market vendors on Financial Literacy, Sustainable Arigurcultural Productivity, Financial Services Accessibility and Product Value Addition. As part of the broader Markets for Change project, financial service providers such as Vanuatu National Provident Fund for voluntary saving and Vancare for insurance bundles are also provided a space to onboard the market vendors and farmers as well as other vulnerable members of the community.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | A survey and assessment of the socioeconomic impact of COVID-19 on market vendors was undertaken. This was not undertaken with this project funding.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | Timelines had to be slightly adjusted due to difficulty in obtaining materials in-country. Shipping delays and issues around procurement complicated this process, meaning timelines had to be adjusted.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | As noted in previous point, there were very serious delays and issues around procurement in terms of ability to get the quantity and quality of materials required in country.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 3 | Three markets have received some supplies. Supply chain disruptions have meant not all supplies have yet been delivered. | Receipts, routine project reporting
Indicator: Marketplaces and women vendors are able to operate safely in the face of twin crises of COVID 19 and TC Harold, contributing to increased food security in Vanuatu.
Baseline: 0
Planned Target: 3 markets
Output 1.1 | 3 | Three markets have received some supplies. Supply chain disruptions have meant not all supplies have yet to be delivered. | Receipts, routine project reporting
Indicator 1.1: Number of markets that have WASH support and materials
Baseline: 0 markets
Planned Target: 3 markets
Output 1.2 Number of vendors who have increased post TC Harold agricultural inputs, including seeds and seedlings | 692 vendors benefitted directly from the delivery of agricultural inputs (679F, 13M and 28 people with disabilities). | Variance is because final distribution will be done in February 2021. At the end of the distribution 2,892 vendors will have been assisted through Agricultural inputs. | Sign-ups, receipts and routine project monitoring
Indicator 1.2:
Baseline: 0
Planned Target: 2500 vendors have access to increased agricultural inputs
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Responding to COVID-19 and TC Harold: a fork was all she needed
Photo: Anna Rose Andikar posing with her garden fork during distribution in August at Nambauk village (Credit: UNDP/Vasemaca Takau)
“We faced a lot of challenges after the cyclone. Our home was destroyed, and we didn’t have any food. We only used an axe and knife to build a temporary shelter after the cyclone as my chainsaw was bad. We only ate rice. We lost money during the cyclone. I didn’t feel safe,” said Anna Rose Andikar from Nambauk village in Santo.
Rebuilding after Category 5 TC Harold was challenging for many market vendors in Luganville as most were unprepared for it. For the 36-year-old, any support to help her husband and four children restore their home and garden was much needed. Help arrived in August in the form of a garden fork for her market business. The single fork was not much to many, but to Anna Rose, it was everything she needed to start again. The help was made possible by Markets for Change project through funding support from the Secretary General’s UN COVID-19 MPTF.
“After the cyclone, we didn’t even replant our garden. We survived on rice. Our association bought some seeds and shared it among us, but I didn’t plant it. I started to replant my garden as soon as I received the garden fork,” she said.
Anna used the garden fork to replant crops in her garden in August, including the Chinese cabbage seeds she received from the Northern Islands Market Vendors Association. In October, Anna harvested the Chinese cabbage and sold them at Luganville market. With the income earned, she bought roofing flashing and timber and completed the walls and roof of her home. She moved into the house with her family right after finishing the house.
“When they came and asked us to choose something that we wanted, I told my friend I want a garden fork because it can do anything,” she recalled. “I chose this tool because I knew it would help me because it can be used with many things. It would have taken me a long time to rebuild my home if I had not received the garden fork. I use it to plant kumala, yam, taro, ginger and vegetables. I even dug holes for my kava with it. This small tool really helps me. I am grateful for the help that came from you.”
Vendors of Nambauk area after receiving farming tools - Photo credit UNPD/ Pioni Willie