## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | SUPPORTING THE ESWATINI GOVERNMENT’S URGENT NEED IN RESPONDING TO THE COVID-19 HEALTH & FOOD EMERGENCY | Overall Duration (months) | 7
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-05-10
MPTF Office Project Reference Number: | 121729 | Original End Date (dd.mm.yyyy) | 2020-12-31
Country | Eswatini | Current End date(dd.mm.yyyy) | 2021-02-11
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA WHO UNICEF | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health (Government of Eswatini)
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | In light of the COVID-19 pandemic and the rapidly increasing number of confirmed cases in Eswatini, the Government prepared a comprehensive multisectoral National COVID-19 Plan prioritising infection prevention and control, risk communication as well as protection and safety of health care workers and their families. The COVID-19 MPTF funding arrived at an opportune time for the UN with a total of USD135,000 received by UNFPA; $125,000 by WHO; and $120,000 by UNICEF to support capacity building for frontline health care workers at both facility and community on COVID 19 prevention, testing and management. This included much needed personal protective equipment and comprehensive training of most frontline health care works from all health facilities. In addition, the MPTF funding supported the development of urgently needed technical guidelines and Standard Operating Procedures (SOPs) for provision of COVID-19 related services and other essential health care services by frontline health care workers. WHO and UNFPA supported the Ministry of Health in periodic review and adaptation of technical guidelines and tools; including provision of technical support in building frontline health care workers capacity in all pillars which strengthened the quality of care for confirmed COVID-19 cases. Following the declaration of the COVID-19 pandemic as a national public health emergency, social distancing regulations were adopted across the country. These included lockdowns and limitation of public gatherings. Due to the scale of the COVID-19 pandemic, the Ministry of Health had to ensure continuity of essential services while combating the pandemic. WHO undertook a rapid assessment on continuity of essential services and Infection and Prevention Control (IPC) compliance in 177 health facilities in the Manzini region. Findings revealed that continuity of essential services were largely interrupted and only 32% of health facilities complied with IPC standard operating procedures. With the implementation of the recommendations, an improvement in compliance was shown in at least 88% of the health facilities. Supportive supervision (couching is continuously done) was provided and on average 48 health facilities were covered monthly. IPC champions were identified and trained in all health facilities. In addition, there were reports of increasing home births which puts the lives of women and newborns at risk for death due to increased potential for complications. Field officers reported lack of the PPE and information on COVID-19. Some critical services were no longer being provided by health care workers as they felt these were not essential. These included antenatal care, child welfare (immunization), PNC, family planning etc. This had the potential to impact negatively on the SDG indicators and reverse gains achieved so far. Furthermore, the COVID-19 outbreak and measures taken to address exacerbated an existing and underlying national food insecurity challenge. This is due to below-average agricultural production and rising food prices resulting in a 49% deficit in national consumption requirement. The travel restrictions and partial lockdown immediately reduced income for small, micro and medium enterprises while also impacting the informal sector as and self-employment activities. Remittances were also impacted and a year-on-year decline of 39% in remittances received was recorded for the period January to March 2020. As a result, an estimated 301,762 people (27% of the population) were at risk of food insecurity. Technical guidelines on MNH, immunization and vaccine preventable diseases in the context COVID-19 were developed and disseminated to guide health workers in their operations. Government, in particular the Ministry of health has been instrumental in the implementation of the activities. Strengthening of the health system through procurement of PPE, hiring of vehicles and other logistics for RRTs and office support equipment yielded positive results in the fight against COVID-19. The provision of PPE facilitated execution of the activities by various COVID-19 pillars such as laboratory testing, case management and treatment, case investigation and contact tracing. UNICEF used the MPTF funds to support training of 120 health care workers including 60 nurse midwives on COVID-19 infection prevention and control. The participants were drawn from six health facilities that provide maternity services in the Manzini region. The funds were also used to revitalize and strengthen routine integrated outreach services throughout the country following a three months suspension as part of the CID-19 emergency response measures. Each of the four regions of the country was supported with one hired vehicle and fueling of two government outreach vehicles. In collaboration with WHO immunization catch-up activities regions developed micro-plans and executed by rendering all antigens including Vitamin A supplementation and deworming, targeting high risk populations in urban and rural settings. An overall increase of DPT3 coverage was recorded from 76.7% in March 2020 to 84% by December 2020.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | This intervention sought to strengthen capacity building and procurement of additional health supplies and commodities, to support the health system in stemming the growth of local transmission of COVID-19. On 30 January 2020, the WHO Director General declared that the outbreak of coronavirus disease (COVID-19) constitutes a Public Health Emergency of International Concern. The increasing number of positive confirmed for COVID-19 in the Kingdom of Eswatini, which currently stands at 36, with 10 reported recoveries and 1 death poses a huge strain on the health system. The of lack of essential equipment including PPE and limited information on COVID prevention, management and treatment among health care workers is a threat to the COVID-19 and health response as a whole. These have resulted in some frontline health workers abandoning patients as they fear being infected by the dreadful virus. Unfortunately, there are already infected frontline health care workers. The following were the most targetted: 1. Frontline health care workers: they are at risk of being infected. On the other hand, provision of services is being compromised. 2. Newborns: with the increasing number of home births, a number of neonates might be lost. 3. Children: The limited provision of immunizations for instance might lead to resurgence of vaccine controlled health problems like measles, polio myelitis, diphtheria and others. 4. Adolescents & young people: Non provision of some health services might exacerbate the teenage pregnancies, unsafe abortion, HIV infections, SGBV etc 5. Women: Not accessing all health services, in particular SRH services might lead to unplanned pregnancies due to unmet need for FP, increasing maternal morbidity and mortality, increasing unmet need, STI including HIV re-infections. 6. Older persons 7. Persons with underlying health conditions, with disabilities, persons living with HIV, sex workers.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Proportion of COVID-19 suspected cases referred to Health Facilities according to National Guidelines: Baselinie: Results: Review of health facility registers have shown that referral of suspected cases to health facilities has stabilized at 100% and national guidelines and adhered to. Proportion of COVID-19 confirmed cases treated according to National Guidelines Baseline: Results: Hundred percent of the admitting health facilities are using and adhering to the National treatment guidelines.
3.2 | Results: Output Level | Please include output level results achieved | Proportion of health care workers trained on COVID-19 prevention, management & treatment has increased from 36% to 95% according to Ministry of Health COVID-19 Training Reports UNFPA and WHO. A total of more than 6,772 (95%) health care workers have been trained on COVID 19 prevention, testing and management. A National MNH-COVID 19 Technical Guidance has been developed, all aimed at rebuilding the health system and limit the impact of COVID 19. PPE was provided to 88% of the public health facilities. 100% health facilities both public and private have resumed provision of continuity of essential health servicesSome degree of increase in the availability of key and or lifesaving medicines, supplies and commodities are on the rise. All fixed health facilities are rendering MNH, immunization and nutrition catch up activities. As per available reports, outreach services were revived and integrated MNCH services provided in all sites. All regions executed their microplans for immunization catch up activities targeting hard to reach areas and high risk population in urban and rural settings and a DPT 3 coverage of 84% attained.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | Following the declaration of the COVID 19 pandemic as a national public health emergency, a number of regulations were established including lockdowns, reductions of gatherings such as trainings. However, due to the scale and scare of the COVID 19 pandemic, the Ministry of Health, and development had to continue providing services essential for combating the pandemic. Government, in particular the Ministry of Health, was instrumental in implementation of activities. The provision of personal protective equipment (PPE) made things more easily for the activities to be executed. Unanticipated periodic review of all pillars’ technical guidelines and tools resulted in consistent reorientation of health care workers and rapid response teams to improve efficiency for COVID-19 response activities. Restrictions in international flights led to delayed shipments of personal protective equipment, commodities and supplies. Adherence to ordering timelines has reduced delay in deliveries. Due to government COVID-19 lockdown regulations, continuity of essential services was disrupted including outreach services which were suspended for more than three months depriving targeted population of essential health services. In regularizing the situation, all partners supported maternal child health guidelines development in the context of COVID-19 based on WHO generic guidelines and these were disseminated to stakeholders for reference. Outreach sites were revitalized, and outreach activities were ongoing although attendance was low. Intensive social mobilization through community-based health volunteers and media channels was used to sensitize and encourage community members to attend the outreach services. The situation further prompted WHO to conduct rapid assessments on continuity of essential services and compliance to IPC measures in Manzini region informed decision-making to improve the health system.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Sustaining interventions warrants relevant technical guidance, capacity building and transfer of skills for better health outcomes. • Government leadership and support is crucial for the implementation of the activities, in particular during the COVID 19 lockdowns. The Government, especially the Ministry of Health facilitated the implementation activity amidst the COVID-19 emergency. • Direct technical support in a decentralized manner has a positive impact to an outbreak response. • Regular supportive supervision is essential to monitor efficiency of teams on the ground and compliance to COVID – 19 pillars’ standard operating procedures at different levels. • In order to achieve effective and efficient utilization of outreach services, it is important to give adequate time for planning and community engagement for ownership of the services and support including social mobilization prior to execution.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | UN partner’s coordination structures and multisector collaboration have been instrumental in mobilizing financial and human resource required for the implementation of the National COVID – 19 response plan. Jointly partners have guided strategic planning and decision making by the Ministry of Health and other implementing partners regarding the response and actions to be taken. UNICEF jointly with WHO supported the MoH to revitalize and strengthen the integrated outreach services. and guided regional microplans development for routine immunization catch up activities targeting hard to reach areas and populations in readiness for implementation. This intervention also leveraged support such as additional vehicles and nurses from regional based implementing partners such the Eswatini Baphalali Red Cross and Doctors without Borders. Collaboration with PEPFAR, civil society and continuous capacity building is vital for sustained effective performance. This has helped in training a number of health care workers through off-site and onsite trainings, thus reducing the impact of essential health care disruption. All involved partners provided technical officers, who available to train health care workers from low level health facilities.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | In light of the COVID-19 pandemic and the rapidly increasing number of confirmed cases in Eswatini, the Government prepared a comprehensive multisectoral National COVID-19 Plan prioritising infection prevention and control, risk communication as well as protection and safety of health care workers and their families. The COVID-19 MPTF funding arrived at an opportune time for the UN with a total of USD135,000 received by UNFPA; $125,000 by WHO; and $120,000 by UNICEF to support capacity building for frontline health care workers at both facility and community on COVID 19 prevention, testing and management. This included much needed personal protective equipment and comprehensive training of most frontline health care works from all health facilities. In addition, the MPTF funding supported the development urgently needed technical guidelines and Standard Operating Procedures (SOPs) for provision of COVID-19 related services and other essential health care services by frontline health care workers. WHO and UNFPA supported the Ministry of Health in periodic review and adaptation of technical guidelines and tools; including provision of technical support in building frontline health care workers capacity in all pillars which strengthened the quality of care for confirmed COVID-19 cases. Following the declaration of the COVID-19 pandemic as a national public health emergency, social distancing regulations were adopted across the country. These included lockdowns and limitation of public gatherings. Due to the scale of the COVID-19 pandemic, the Ministry of Health had to ensure continuity of essential services while combating the pandemic. WHO undertook a rapid assessment on continuity of essential services and Infection and Prevention Control (IPC) compliance in 177 health facilities in the Manzini region. Findings revealed that continuity of essential services were largely interrupted and only 32% of health facilities complied with IPC standard operating procedures. With the implementation of the recommendations, an improvement in compliance was shown in at least 88% of the health facilities. Supportive supervision (couching is continuously done) was provided and on average 48 health facilities were covered monthly. IPC champions were identified and trained in all health facilities. In addition, there were reports of increasing home births which puts the lives of women and newborns at risk for death due to increased potential for complications. Field officers reported lack of the PPE and information on COVID-19. Some critical services were no longer being provided by health care workers as they felt these were not essential. These included antenatal care, child welfare (immunization), PNC, family planning etc. This had the potential to impact negatively on the SDG indicators and reverse gains achieved so far. Furthermore, the COVID-19 outbreak and measures taken to address exacerbated an existing and underlying national food insecurity challenge. This is due to below-average agricultural production and rising food prices resulting in a 49% deficit in national consumption requirement. The travel restrictions and partial lockdown immediately reduced income for small, micro and medium enterprises while also impacting the informal sector as and self-employment activities. Remittances were also impacted and a year-on-year decline of 39% in remittances received was recorded for the period January to March 2020. As a result, an estimated 301,762 people (27% of the population) were at risk of food insecurity. Technical guidelines on MNH, immunization and vaccine preventable diseases in the context COVID-19 were developed and disseminated to guide health workers in their operations. Government, in particular the Ministry of health has been instrumental in the implementation of the activities. Strengthening of the health system through procurement of PPE, hiring of vehicles and other logistics for RRTs and office support equipment yielded positive results in the fight against COVID-19. The provision of PPE facilitated execution of the activities by various COVID-19 pillars such as laboratory testing, case management and treatment, case investigation and contact tracing. UNICEF used the MPTF funds to support training of 120 health care workers including 60 nurse midwives on COVID-19 infection prevention and control. The participants were drawn from six health facilities that provide maternity services in the Manzini region. The funds were also used to revitalize and strengthen routine integrated outreach services throughout the country following a three months suspension as part of the CID-19 emergency response measures. Each of the four regions of the country was supported with one hired vehicle and fueling of two government outreach vehicles. In collaboration with WHO immunization catch-up activities regions developed micro-plans and executed by rendering all antigens including Vitamin A supplementation and deworming, targeting high risk populations in urban and rural settings. An overall increase of DPT3 coverage was recorded from 76.7% in March 2020 to 84% by December 2020. Following the declaration of the COVID 19 pandemic as a national public health emergency, a number of regulations were established including lockdowns, reductions of gatherings such as trainings. However, due to the scale and scare of the COVID 19 pandemic, the Ministry of Health, and development had to continue providing services essential for combating the pandemic. Government, in particular the Ministry of Health, was instrumental in implementation of activities. The provision of personal protective equipment (PPE) made things more easily for the activities to be executed. Unanticipated periodic review of all pillars’ technical guidelines and tools resulted in consistent reorientation of health care workers and rapid response teams to improve efficiency for COVID-19 response activities. Restrictions in international flights led to delayed shipments of personal protective equipment, commodities and supplies. Adherence to ordering timelines has reduced delay in deliveries. Due to government COVID-19 lockdown regulations, continuity of essential services was disrupted including outreach services which were suspended for more than three months depriving targeted population of essential health services. In regularizing the situation, all partners supported maternal child health guidelines development in the context of COVID-19 based on WHO generic guidelines and these were disseminated to stakeholders for reference. Outreach sites were revitalized, and outreach activities were ongoing although attendance was low. Intensive social mobilization through community-based health volunteers and media channels was used to sensitize and encourage community members to attend the outreach services. The situation further prompted WHO to conduct rapid assessments on continuity of essential services and compliance to IPC measures in Manzini region informed decision-making to improve the health system. Sustaining interventions warrants relevant technical guidance, capacity building and transfer of skills for better health outcomes. • Government leadership and support is crucial for the implementation of the activities, in particular during the COVID-19 lockdowns. The government, especially the Ministry of Health facilitated the implementation activity amidst COVID • Direct technical support in a decentralized manner has a positive impact to an outbreak response. • Regular supportive supervision is essential to monitor efficiency of teams on the ground and compliance to COVID – 19 pillars’ standard operating procedures at different levels. • In order to achieve effective and efficient utilization of outreach services, it is important to give adequate time for planning and community engagement for ownership of the services and support including social mobilization prior to execution. Due to paucity of data on status of Infection Prevention and Control (IPC), WHO, in collaboration with the Ministry, took a decision to carry out an assessment in all health facilities in the country to establish comprehensive baseline data against which to compare future improvements. Funding challenges limited the assessment to the Manzini region. A cross-sectional study design was used. IPC audit tools and observation guides were utilized for data collection. The performance of health facilities was categorized into Inadequate (≤30%), Basic (31-54%), Intermediate (55-74%) and Advanced (75-100%). A total of 117 health facilities participated in the assessment, out of which 5 (4%) were classified as having ‘Advanced level’ of IPC development, 12(10%) were at ‘Intermediate level’, 34 (29%) at ‘Basic level’ while 66 (56%) were classified as ‘Inadequate’. The average (mean) score across all the IPC core components was 32%. The median score was 25.3%%. The IPC core component with the highest score was infrastructure and logistics (58%) while the weakest was workload, staffing and bed occupancy (12%). The contributory factors to the better performance on the infrastructure and logistics core component were wide availability of the following: 24 hours in in the health facilities109 (93%); functioning hand hygiene stations at all points of entry and all points of care in the health facilities (97%); toilet facilities 106 (91%); power supply (91.5%); and ventilation (87%). Performance on environmental cleaning and availability of Protective Personal Equipment (PPE) were above average. However, performance on mechanisms for patient placement, including availability of triage and isolation facilities were inadequate. 86 (73.5%) of the health facilities did not have a written policy/ guideline for placing patient with potentially contagious or communicable infection in isolation. Sixty-three (63%) of the health facilities had no single patient rooms or areas for cohorting patients with similar pathogens if the number of isolation rooms is insufficient (for example, TB, measles, cholera, Ebola, SARS. Overall, health facilities owned by Non-Governmental Organizations (NGOs) performed better (50%). The overall scores for government health facilities was 39%, mission (31%), industrial (20%), private-doctor (26%) and private-nurse owned (17%). The regional average performance on adherence to social hand washing protocol was 48%. Clinics with maternity were scored 100% while the public health unit and specialized hospitals scored 0%. When compared by ownership, health facilities owned by industries got 67% and government-owned health facilities had 56 on adherence to hand washing protocols. The low performing category of health workers on adherence to social hygiene were the housekeeping (27%) and laboratory (27%) staff. Some of the key strategic and policy actions include amongst others: a) Conducting similar assessments in the other regions b) Nominating IPC focal persons for all health facilities and constitution of IPC multidisciplinary teams to provide technical guidance on IPC implementation c) Putting in place performance measurement system to regularly assess their performance. In addition, WHO conducted an assessment on continuity of essential services aiming at ascertaining the status of disruptions in essential health services delivery within the context of COVID-19 to guide the mitigation and improvement strategies to assure continuous service delivery and plan for recovery. The assessment used an exploratory approach that combined qualitative and quantitative method. A tool was developed and used to collect data. A total of 117 health facilities participated in the assessment. The labour strength in the facilities varied with smaller units possessing fewer staff compared to the bigger facilities ranging from 4 to 560 staff. On average there was about 11 staff in each health facility. Overall, the assessment confirmed that there were interruptions in the provision of essential services in almost all the facilities in the Manzini region. There was a low (48.2%) bed occupancy during the period of the assessment in all but one, of the participating health facilities which admit inpatients. An investigation into policy, plans and budgets revealed that the COVID-19 outbreak prompted health facilities to define the essential health service package and prioritize the list of essential services to be provided during the epidemic. Preparedness for COVID-19 response was inadequate at the facility level. It is worth noting that of the participating health facilities only 46% had defined an health care package prior to COVID-19 and 53.8% defined the essential health service package during the pandemic while 46% had identified a prioritized list of essential service to deliver during the pandemic. About 40.1% of the facilities had received any financial support from Ministry of Health for the response. The assessment also confirmed disruption of services during this period. Functionality was interrupted for inpatient, outpatient, emergency and outreach services. The hardest hit services were outreach services with 62% of facilities that provide the service reporting disruption and 11% reporting that they suspended the service. Essential health care services that were interrupted include maternal and child health care services (ANC, FP, Immunizations and nutrition services) and NCDs, to name a few. The identified disruptions were said to be related to: disturbances in the supply chain for medical and lab supplies as well as insufficient PPE, inadequate/inappropriate workspace (considering the policy changes in treatment directives), inadequate information leading to fear of infection, patient flow disruptions/managing queues whilst maintaining safe distance, inadequate staff complements (due to stay at home directives, infected/ exposes staff, redeployed staff). A range of mitigation measures were put in place during the epidemic. These included telemedicine deployment to replace in-person consults; task shifting/role delegation; novel supply chain and/or dispensing approaches for medicines through other channels; triaging to identify priorities; community outreach to inform the public on service disruptions and changes; and strengthening of infection control measures. However, some health facilities reported that there was nothing they were doing to mitigate the impact of COVID-19. The highlighted priority needs or areas were: Identification of a range of human resource; medical equipment and supplies; safety gear and protective clothing; cleaning materials; drugs/medicines supplies; additional vehicles; staff training; collaboration between Government and private sector (procurement of supplies, training and laboratory services); supervision and monitoring support including strengthening of health Management Information Systems; and financial support.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | No budget revision made during implementation. No adjustments made on strategies and targets
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | None

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1 | Review of health facility registers have shown that referral of suspected cases to health facilities has stabilized at 100% and national guidelines adhered are to. | None | MoH COVID 19 reports
Indicator 1.1.1: Proportion of COVID-19 suspected cases referred to Health Facilities according to National Guidelines
Baseline:0%
Planned Target: 100%
Indicator 1.1.2:Proportion of COVID-19 confirmed cases treated according to national guidelines | 100% health facilities both public and private treat COVID – 19 confirmed according to periodically reviewed national guidelines. | None | MoH COVID 19 reports
Baseline: 0%
Planned Target: 100%
Output indicator 1.1.1: Proportion of health facilities provided with COVID-19 equipment, commodities & supplies | 88% of the public health facilities were provided with COVID - 19 equipment. Reports show some degree of improvement in the availability of key and or lifesaving medicines, supplies and commodities. | None | MoH COVID 19 Reports
Baseline: 0%
Planned Target: 25%
Output Indicator 1.2.1: Proportion of health care workers trained on COVID-19 prevention, management & treatment | A total of more than 6,772 (95%) health care workers were trained on COVID 19 prevention, testing and management. A National MNCH-COVID 19 Technical Guidance was developed. All were aimed at rebuilding the health system and limiting the impact of COVID 19. | None | MoH COVID 19 Reports
Baseline: 36%
Planned Target: 95%
Output indicator 1.3.1a: Proportion of health facilities implementing MNH, immunization and nutrition catch up activities including outreaches post COVID | All fixed health facilities both public and private are rendering MNH, immunization and nutrition catch up activities. As per available reports, outreach services were revived and integrated MNCH services provided in all sites. All regions developed Periodic Intensification of Routine Immunization Microplans. Catch up activities targeting high risk populations in urban and rural settings were implemented. An improvement in overall DPT3 coverage was recorded from 76.7% in March 2020 to 84% in December 2020 . | None | MoH HMIS
Baseline:40%
PlannedTarget: 100%
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
https://eswatini.unfpa.org/en/news/unfpa-eswatini-robust-serving-most-vulnerable 1. UNFPA ESWATINI ROBUST IN SERVING THE MOST VULNERABLE Fine wine matures with time, so are good relationships. That also can be said with UNFPA’s commitment to serving society’s susceptible especially pregnant women. This was evident today, as the protective equipment for maternity units was delivered to the Ministry of Health. Margaret Thwala-Tembe, the UNFPA Eswatini Acting Head of Office, described the impact of COVID-19 to disrupt way more than people’s general health. She said, “COVID-19 has severely disrupted access to life-saving SRHR services, and hampered ability to respond to GBV, at a time where women and girls need these services most.” The Acting Head of Office, painting the bigger picture, stated that the PPE goes beyond COVID-19 prevention, but a contribution towards achieving the three zeroes by 2030. In her own words, “UNFPA is working with government and partners to prioritise women and girls, in line with our goals to end unmet need for family planning, preventable maternal deaths and gender-based-violence &harmful practices by 2030.” According to the One Vision Three Zeroes, Annual Report of 2018, in the East and Southern Africa region, the unmet need for family planning is at 22%, maternal death is at 455 per 100000 live births while 28% of women and girls are subjected to gender based violence. Ecstatic. That’s one word to describe Senator Lizzie Nkosi, the Minister of Health, upon receiving the consignment. In her words, Nkosi described the gesture as appropriate and linked to the significance of 2020 in the health sector. “This year is the year of the midwife. The whole world celebrates the midwife and here we are talking about COVID-19 and how exposed midwives are. We have a challenge of safety equipment supplies and are concerned with keeping healthcare workers safe as they keep the nation safe.“ The minister also alluded that COVID-19 prevention, doesn’t end with healthcare workers, but their clients too. Therefore, there is a demand of protective equipment in the health facilities to protect the health workers so that they can protect the women and babies. The ministered also dropped some pebbles with respect to other COVID-19 response initiatives the country has. “We are trying to scale up COVID-19 screening and also actively looking for cases with teams in identified hot spots. Every facility in the country will do proper triage to ensure prevention control.” Lobesutfu Nkambule, a Midwife at Pigg’s Peak Government Hospital also shares the same sentiments on the negative effects of COVID-19 on midwifery, a profession she associates with compassion and love for clients. “Midwives feel the impact of COVID-19. The time you spend with your client cannot be shortened without compromising the quality of your work and there is no way you can ask a woman in labour to go back home when you running short of equipment.” For that reason, personal protective equipment is a high demand in the maternity ward. “Having enough personal protective gear makes our work easy. It also enables us continue deliver quality service to mothers and their babies without fear of getting the virus,” said Nkambule. Impeccable timing. That’s exactly what describes the act of UNFPA in delivering the highly in-demand PPE. The ministry’s Situation Update No. 32 of April 18th, 2020 indicates an escalated need for protective equipment for health care workers as 2 of the 19 confirmed cases are health workers with no history of travel outside the country. https://eswatini.unfpa.org/en/news/unfpa-brings-family-planning-sms-innovation-against-looming-post-covid-19-births-spike UNFPA Brings Family Planning SMS Innovation against a looming Post COVID-19 Births Spike Nolwazi Myeni, by virtue of being a young woman, is one of thousands of other women, who, once a month, receives an SMS through her mobile phone to notify her that family planning services were still available at all clinics amid COVID-19. “I felt very encouraged to be assured that I could visit any clinic amid COVID-19 for my contraceptive needs. This is all I needed to hear as I toyed with the idea of what action to take to ensure that I continued to practice family planning during this era of COVID-19. With the lockdown’s movement restrictions, it’s easy to even forget the return date to the health facility. These SMSes, beyond encouraging us to go for the service, they also act as a reminder.” That is how Nolwazi i responded to the news on young women receiving Family Planning messages in their mobile phones. Aged 24 and mothering a 6 year old, she still has a dream of becoming a teacher. For this reason, access to family planning services in the local health clinics is vital. She believes if she could prevent falling pregnant, she could focus on completing her Primary Teacher’s Diploma training and also remain a role model to the hundreds of adolescent girls she mentors in her community. Continued access to family planning would avert thousands of unplanned pregnancies in the country during this pandemic period. Subsequently, UNFPA, in partnership with the World Food Programme and the Sexual Reproductive Health Unit in the Ministry of Health came up with a Short Message Service (SMS) mobilisation campaign. These messages are sent together with food relief messages to the communities by the World Food Programme. The campaign aims to reach a total of 80,000 young women, who are also receiving assistance through the WFP COVID-19 relief project in Eswatini. The campaign aims at encouraging uptake of family planning services among women of reproductive age including adolescent girls. In part, the messages raise awareness on available innovations for limiting overcrowding in the already overburdened health facilities. Family Planning Coordinator Lindiwe Malaza explains some of the COVID-19 customised dosage dispensing particularly designed for women on the Pill. “We want to encourage the people to continue accessing the family planning services during this COVID-19 period. In addition, we want to emphasize that women can now consult with their nurse or doctor on the possibility of getting a 3-months’ supply of the Pill. Those using the injectable and IUD will continue on the normal procedure as they need regular monitoring,” the Coordinator explained. A recent report by the Social Protection Cluster Partners indicates a 47% drop in family planning services uptake in Eswatini during this period compared to the same time in the previous year. This is a sign of a possible boom in births after the COVID-19 battle has been won. UNFPA Acting Head of Office Margaret Thwala-Tembe, explaining the importance of accessing family planning in times of pandemics, said, “Pandemics like COVID-19 challenge UNFPA to be more robust and innovative towards ending the unmet need for family planning. Ensuring that women continue accessing these services is one way we can mitigate COVID-19’s impact on the health of vulnerable groups like women and girls.” In a recent briefing with the World Health Organisation, UNFPA Executive Director Dr Natalia Kanem had lamented on the dire effects the COVID-19 pandemic has on women’s health considering that, “Sexual reproductive health services are not just necessities’, they are essential to the lives of women,” These indirect effects of COVID-19 tarnish the work of the already overburdened health workers. Also identified as an indirect effect of the pandemic in the country, some health facilities, especially those serving rural communities, report a decline in number of women attending ANC and an increase in home deliveries and deliveries on the way to the health facilities. “Since the start of the lockdown, we have noted an increase in incidents of women delivering babies either at home or on their way to the facility,” lamented Midwife Lobesutfu Nkambule in an earlier interview. According to the recently released 2017 National Housing and Population Census report, a woman of reproductive age has an average of 3.2 children. If access to family planning services continues to drop in this pandemic, these numbers may worsen. WHO 2. Door-to-door COVID-19 for Manzini and Hhohho regions launched Following the upsurge of COVID-19 cases in the Kingdom of Eswatini, the Ministry of Health, with support from the World Health Organization (WHO) has embarked on an intensified case finding exercise to respond to the epidemic. A rapid increase of COVID-19 cases is currently being experienced in the Manzini region, now the epicentre as well as Hhohho region. Manzini had 895 of the 1826 reported cases in the country by 20 July 2020, followed by Hhohho with 650 cases. On the same day Minister of Health Honorable Lizzie Nkosi launched the intensified six-point response plan, which is aimed at controlling the increase of COVID-19 cases for both regions. The launch was held at Caritas Centre in Manzini and was attended by the Manzini Regional Administrator (RA) Chief Gija, the WHO Officer in Charge Dr Brian Chirombo, Ministry of health Principal Secretary Dr Simon Zwane, Director of Health Services Dr Vusi Magagula, Senior officials in the Ministry of Health and officials from the Manzini Health Administration office. The six-point plan entails engagement and education, finding cases, testing, treating of confirmed cases with a focus on those with co-morbidities such HIV, TB, diabetes, hypertension, chronic lung diseases and cancers, who are at increased risk of developing severe disease or dying. Other steps including isolation and tracing of contacts. The purpose of this exercise is to intensify case finding and control the spread of the disease in the two regions. The country has a small population of just over one million people and urgently needs curb the spread of infections which is threatening to spiral out of control. A total of 10 teams comprised of surveillance officers, emergency preparedness and response officers, medical doctors and nurses will move from house to house in the two regions offering screening, testing and education about COVID-19. This exercise follows another WHO and UNICEF supported exercise conducted by Red Cross volunteers, who were moving from door-to-door (gate-to-gate) in selected hot spots around the Manzini region communicating COVID-19 prevention messages. Both activities are aimed at engaging and increasing knowledge among the people and improve compliance with the regulations in order to slow down the spread of the disease. In his welcome remarks, the Manzini Regional Administrator Chief Gija urged the people of Manzini to comply with the prevention measures in order to turn around the epicentre status of the region. The RA said people who do not comply should be brought to him for questioning and urged everyone to take the responsibility of protect themselves. 2. COVID - 19 Door to door Door-to-door COVID-19 plan for Manzini and Hhohho regions launched The WHO Officer in Charge Dr Brian Chirombo noted that while the Kingdom of Eswatini has not been spared from this rapid increase of cases experienced globally, there is still hope to slow down the spread of the disease, taking lessons learnt from other countries during this pandemic. He stated that even though the Manzini and Hhohho regions are the hardest hit in the Kingdom, everyone remains at risk of COVID-19. He thus reminded people of the measures that WHO has put in place to prevent infection from COVID-19 which include handwashing, social distan+A1cing and respiratory hygiene. Further, Dr Chirombo informed the team that WHO is happy to support this initiative and also revealed that WHO, UNICEF and UNDP are already jointly contributing funding and technical input towards this activity. He said WHO is currently reorganizing its team to provide more support not only to the central level of the Ministry of Health, but also to the Regional Health Management Teams to help strengthen their technical capacity and support implementation of the six-point plan towards flattening the curve and reducing morbidity and mortality. In her remarks, Minister of Health Honorable Lizzie Nkosi welcomed the team of newly recruited officers. She said this team joins the ministry at a good time because the fire is already burning hence, they will need to hit the ground running and learn fast. “Unlike those who were already in the system when the fire started, those who tried this and that to put out the fire, you will need to put all your effort. First, you need to protect yourselves otherwise you will be consumed by the fire. Currently we have 91 health workers who have been infected with the virus and we don’t want that to happen because if health workers get sick, the public will have no one to take care of them,” the Minister said and further urged the teams use their skills and learn. Adding the Minister said “We trust you to work hard and dedicate yourselves to the task ahead in order to control the spread of the disease. Together we can beat the disease.” https://www.facebook.com/WHOEswatini/videos/292209555192178
2. Upload here: Communications and Visibility (OPTIONAL)
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | SUPPORTING THE ESWATINI GOVERNMENT’S URGENT NEED IN RESPONDING TO THE COVID-19 HEALTH & FOOD EMERGENCY | Overall Duration (months)
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy)
Country | Eswatini | Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | WHO UNFPA UNICEF | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board