## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Empowering women through safe, resilient, gender responsive food markets and systems in response to covid 19 in Zimbabwe | Overall Duration (months) | 18 Months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy)
Country | Zimbabwe | Current End date(dd.mm.yyyy) | 2021-04-30
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN Women, UNDP and ILO | National counterparts (government, private, NGOs & others) and other International Organizations | Oxfam, NSSA
Report Cleared By
Name: | Maria Manuel Gomes Do Valle Ribeiro
Title: | UN Resident Coordinator
Email address: | ribeiro6@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative Report Jan-June 2021
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The activities that were implemented in the first half of the year were foundational in nature and significantly contributed to how the programme will move along throughout the year. It was critical to identify and engage key stakeholders that the project partnered with such as the Ministry of Local Government, Ministry of Agriculture, Ministry of Women Affairs, Community, Small and Medium Enterprise Development, Harare City Council, financial institutions and other private sector organisations such as Knowledge Transfer Africa to create a strong basis for activity implementation. Engagements with the financial institutions such as the Women's Bank, Empower Bank, Commercial Bank of Zimbabwe and Micro Finance Institutions (VIRL) was initiated to get an appreciation and a better understanding of the financial products and services available that women marketers might benefit from to boost their businesses. Cognisance of the value of institutional capacity strengthening especially for institutions such as local authorities, the programme engaged a partner - Development Governance Institute (DEGI) to undertake a comprehensive review of the council by-laws and other regulatory frameworks to measure the extent of their gender responsiveness and to also come up with Safe Markets Standard Operating Procedures (SOPs) for all targeted locations. The Standard Operating Procedures being developed will guide the stakeholders in market regulation as well as monitoring the implementation of regulations, including COVID-19 preventative measures in the market places. A baseline assessment of the programme conducted in the reporting period provided benchmark information for measuring project achievements, outcomes and intermediate result levels based on the project log frame and verify the project result framework’s adequacy with realities observed on the ground and provide inputs that will assist in updating the actions to be undertaken to the targeted markets. Joint assessments to the satellite markets conducted jointly with the City of Harare authorities were critical as the assessments informed the decisions on which satellite markets to target for refurbishments in the remaining six months, the infrastructural requirements and the needs of the target beneficiaries. As part of developing and coordinating partnerships with the private sector to invest in safe markets, Agritex (and their partner - Knowledge Transfer of Africa) were engaged and have kick-started the development and upscale of online pllatform to help link small holder farmers and female vendors and improve food affordability and accessability, transactions and marken information sharing. The development of the programme communication and visibility strategy was also critical as it will provide guidance on how to capture project stories, highlight programme impact and increase visibility of the programme to the communities. Community engagement and awareness raising through the 3 deployed UN Community Volunteers in Mbare increased the communities' knowledge on COVID-19 prevention measures and this will continue through out the year as well as trainings for informal vendors and market committees on SGBV and sexual harassment prevention and response, value addition, transformative leadership, e- commerce, etc. As part of preparatory work on OSH interventions, OSH materials suitable for informal economy workers that include training manuals and OSH assessment tools were developed. The manuals will guide the trainings whilst the tools will ne used to identify OSH gaps in the markets. In addition, consultations for the developing of OSH strategy workers in the informal sector and OSH management systems have begun. The OSH strategy and management system will protect workers in the informal economy and ensure that the Government has an obligation to support them especially in times of pandemics like COVID-19. Interactions with project stakeholders and institutuional partners, reports the field and current impacts from lockdown on informal traders - all confirm that project interventions that are already underway or being rolled our are very timely and strategic in responding to the emerging needs.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | As most of the activities that were done in the first half of the year were foundational, a total of 120 youth ( 66 females and 54 males) were trained on gender based violence and drug abuse. These and other beneficiaries will be targeted in the trainings that will be done in the remaining half of the year. In terms of beneficiaries in Mbare, in order to fast-start interventions and build on ongoing work, through Oxfam, the project re-engaged earlier identified beneficiaries. 10 food chain players (8 females and 2 males) and 20 (12 females and 8 males) youth volunteers were trained on food safety and hygiene, and these will also be reengaged for further capacity building and training in COVID-19, Health and Hygiene, PSEA and gender. In regards to other beneficiaries in food supply chains, through the programme informal female vendors to be trained in e-transacting. The exact numbers of vendors to be trained will be determined in the coming quarters, once Agritex Extension officers are capacitated with ICT and the market aggregation platform is set up and ready for use. National and local level institutions who form part of secondary beneficiaries have already been idenified and will benefit from the exercise to develop guidelines and regulations to support safe markets and local economic development. The programme shall reach out to vulnerable women marketers and girls who are survivors of sexual gender based violence, women with disabilities and young women who are survivors of harmful practices such as child marriages and sex workers who are or have the potential to participate.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Within the reporting period January to June 2021, much of the interventions/ activities done were foundational in nature and would contribute to the results at outcome level within the next six months of implementation. The ongoing refurbishment of the Mbare mass market, the implementation of standard operating procedures related to market regulation as well as UN Volunteers community engagements and awareness raising on COVID-19 and gender based violence are all contributing to a safe operating environment and improved livelihoods of women marketers. In addition, support from key stakeholders such as the Ministries of Local Government; Agriculture, Women Affairs, Community, Small and Medium Enterprises Development as well as the local authority and the private sector during the reporting period is commendable. In the spirit of partnership, the City of Harare came on board and supported the programme with skilled architects and engineers who designed the market sheds. The market designs/drawings will be adopted during the construction of the market sheds for the satellite markets, contributing to outcome 1 on improved livelihoods of women marketers and vulnerable groups through safe, gender responsive safe market infastructure and systems. The successful engagements of financial institutions such as banks and other private sector players such as Knowledge Transfer Africa and VIRL is a positive development as this will allow women marketers and other vulnerable groups to have access to e- platforms, receive training on transformative leadership, business management, e-commerce and also access credit facilities, insurance and other services from these institutions. Scaling up on online eMkambo platform through Agritex has started with procurement of ICT infrastrcture (such as laptops and tablets for Extension offiices, transport tracking and chatbot tools). National and Harare Province Key Stakeholders Awareness and Engagement Workshop has also been conducted in July. Once the the platform is upscaled and operational, trainings will be cascaded to female users - informal traders. The outcome of the review of policies, laws and regulations from a gender lens and development of SOPS which is being done by a Consultant will strengthen the local authority's capacities and their governance systems. This work will contribute to one of the outcomes of the programme which is an enabling gender responsive policy framework and institutions responsible for administration, regulation and monitoring of food supply systems. In addition, the findings of the baseline assessment enabled the programme team to have a clear understanding of the status of the indicators and will be able to measure and track the project indicators at both output and outcome level. Further to this, the OSH assessment tools have already been used to assess occupational hazards being faced by SMEs on the markets. The outcomes of the assessments will guide the trainings and response services in the third quarter. The response will promote decent work by SMEs and make their work spaces productive and safe.
3.2 | Results: Output Level | Please include output level results achieved | The programme have successfully engaged with key government stakeholders such as the Ministry of Local Government, Ministry of Agriculture and the Ministry of Women Affairs, Community, Small and Medium Enterprise who already are involved in project implementation. The local authority - Harare City Council was successfully engaged and has gone ahead in providing its skilled architects and engineers who have produced designs/plans for the market sheds. The RUNOs provided technical support to the local authority in terms of guidance around the designing of gender responsive markets. The programme also engaged with financial institutions such as the Women's Bank, Empower Bank and Commercial Bank of Zimbabwe to initiate conversations that will facilitate linkages of women beneficiaries to some of the packages offered by the banks such as credit facilities, insurance, and other facilities to protect against economic shocks. Through facilitating linkages with financial institutions and training of women marketers on key financial literacy concepts and use of ICT in marketing and women’s economic security, the joint programme seeks to increase the economic security of women marketers. In addition, engagements with private sector companies such as Knowledge Transfer Africa (working though Government RP - Agritex) and VIRL have been pursued and the companies have expressed interest and commitment in partnering with the project in providing services and goods that will help project beneficiaries in the value chain system and the acquiring of knowledge and skills in running their businesses respectively. Agritex and Knowledge Transfer Africa (with the help of Community UNVs) will provide training to women in the use of E platforms and the value chain systems, while VIRL will be engaged to conduct trainings in business management and transformative leadership. VIRL has already expressed interest in delivering some of the trainings for free as part of their corporate social responsibility, which is a positive and welcome development for continuity and sustainability. The project have already gone a step ahead in seeking information and collecting a data base of the market beneficiaries in satellite markets in preparation for the capacity building initiatives to be rolled out commencing in the third quarter. A Baseline assessment of the markets commenced that would prepare ground work for the capacity building of institutions on gender responsive governance systems, identification of women vendors have also commenced and training materials are already in place. The project has also gone further to engage a Consultant to facilitate the review and development of policies, regulations and legal frameworks with a gender lens as well as facilitate the participatory development of SOPs and Guidelines for safe markets, including broader national-level generic SOPs to guide other ULAs. Once these documents are developed, the agencies will roll out trainings targeting municipal authorities and local level informal market institutions in rolling out safe market guidelines. Consultations for the development of OSH National Strategy and OSH Management System has begun. The consultations will lead to the development of policy documents that would lead to the protection of SMEs in the informal sector. Workers in the informal economy have not been part of the government support and cushioning to promote their work hence vulnerability to hazards and lack of support during times of pandemics like COVID-19. Tools for OSH assessments are a key result that the project is using to identify hazards being faced by SMEs in the informal economy. The response by the project will be informed by the baseline survey and OSH assessments in the third quarter.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | COVID-19 continued to pose serious risks considering its impact on women and vulnerable groups' incomes and livelihoods. The COVID-19 pandemic continue to have an impact on the delivery of the project considering the lockdown conditions that were introduced by the Government during the first quarter of the year. Steps taken to prevent and contain the pandemic such as restricted movement affected the full implementation of the project. Although virtual means of communication were adopted, some interventions required on site visits, for instance the assessment of the satellite markets could not be done in the first quarter of the year. The introduction of the vaccination programme by the Government in early May is likely to ease some of the challenges associated with the implementation of the project as the Government is ear marking those in the informal sector for targetted vaccination. The project frequently assesses the situation and make necessary adjustments in planned interventions to ensure inclusivity, timeliness and effectiveness of measures on the ground. To date the project team has begun to implement flexible approaches which include in person and virtual activities to ensure the project implementation is not halted. The finalisation and the identification of the satellite markets took longer than anticipated and the selection of the implementation partner took longer than anticipated due to protocols and finalisation of engagements with the local authority and the required approvals.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | It is critical to ensure that the selection and registration of beneficiaries is carried out and finalised before the construction or renovation of the markets. A data base with all the project beneficiaries is finalized and updated and the selected beneficiaries are involved from the planning, designing of the market, construction and implementation. The identification and registration of the project beneficiaries in the initial stages helped to limit the politicisation of the project and disagreements on the exact project beneficiaries. A selection criteria was developed and women will be involved and also take leadership positions in the vendor associations or cooperatives. Involvement of key stakeholders is critical at all stages of the project cycle, particularly during the planning stages. Stakeholder participation is important so that they get to understand the project in detail as well as their contributions to the project and their roles and responsibilities. Building upon existing initiatives and partnerships is also critical for learning and exchange of experiences as this was reflected during the implementation of the programme where a partner in other similar projects such as Katswe Sistahood was involved in the project team retreat and shared their experiences in safe markets. The country does not have an Occupational Safety and Health Management System which has led to the vulnerability of informal economy workers. The system is only available for the private sector and its development during the project will be valuable towards promoting decent work in the informal economy. An Informal Sector National OSH Policy is being developed to safeguard informal economy workers especilly in times of pandemics like Covid-19.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The programme aims to build upon existing initiatives and partnerships to ensure timely and adequate response, at the same time new partnerships are being built, with continued mobilisation of resources for a scaled up and thorough inclusive response with nation-wide geographical coverage that would ensure stronger impact. The plan is to work closely with a private sector player Knowledge Transfer Africa (and/or other similar private sector stakeholders operating through online market platforms) to facilitate coordination of farm produce supply chains and support the livelihoods and ICT access of vulnerable women in food supply chain that were disrupted through Covid-induced lockdown measures. Oxfam has been re-engaged and resumed kisk-started activities as one of the key Responsible Parties to support interventions in Mbare, and the programme is finalising the engagement of other CSO partners that will lead the implementation of the programme with the support of the UN agencies. CSOs conduct routine monitoring of the project activities, and liaise with relevant government ministries and departments providing technical expertise and playing the role of coordination and integrating of the various stakeholders for the achievement of key project activities. The programme engaged with partners including financial institutions who expressed commitment to partner with the programme to assist vulnerable groups and building their skills in business management and financial literacy. Due to acute need of similar approach in other locations not currently covered by MPTF funds, the programme leveraged technical expertise of three RUNOs and conducted a workshop to mainstream safe markets guidelines (with focus on gender, OSH, regulatory environment and climate proofing) to other partenr CSOs and Local authorities that are working on safe markets in location other than Harare.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | A baseline assessment was finalised in the reporting period. Key findings revealed that there is high prevalence of sexual gender based violence in market places; no adequate reporting mechanisms and education to prevent and respond to SGBV and sexual harassment; the markets are not sensitive to the needs of women, and lack compliance with occupational health and safety regulations, etc. The project will be addressing the identified gaps during project implementation and spear head interventions that are sensitive to women's needs and complies with occupational health and safety regulations. The OSH assessments will inform the project response and promote safety and productivity by SMEs in the selected markets. The partner will further undertake a risk assessment of the current work place and identify good local practices to reduce vulnerability to hazards and COVID-19.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | There were no adjustments during the reporting period
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The programme aims to build upon existing initiatives and partnerships to ensure timely and adequate response, at the same time new partnerships shall be built, with continued mobilisation of resources for a scaled up and thorough inclusive responses. The programme was able to engage with partners already implementing the similar projects such as Katswe Sistahood and NSSA which was able to share experiences and best practise around safe markets. The programme was able to draw learning and best practise on how Katswe and NSSA has implemented safe markets in other districts.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:Number of resilient food and vegetable markets and systems that are safe, responsive to women's needs and fully functional during the Covid-19 outbreak and beyond
Baseline:0
Planned Target:
Output 1.1 | Yet to be realised since the market are yet to be constructed
Indicator 1.1.1:Number of markets adhering to public and occupational health and safety requirements (including COVID-19) and standards for gender sensitive infrastructure and including green energy solutions
Baseline:1
Planned Target:
Indicator 1.1.2:Number of gender responsive mechanisms established to prevent and address GBV and harassment in public spaces | Yet to be established
Baseline:
Planned Target:
Indicator 1.1.2: Number of women working in established safe makets
Baseline: | Yet to be identified
Planned Target:
Output 1.2 | Yet to be determined
Indicator 1.2.1:Number of women supported to access financial credit facilities
Baseline:
Planned Target:
Indicator 1.2.2:Number of women with increased capacity in business management including e-commerce | Yet to be determined
Baseline:
Planned Target:
Indicator 1.2.3:Percentage increase in growth of women businesses | To be detemined
Baseline:
Planned Target:
Output 1.3 | To be created
Indicator 1.3.1: A platform that ensure regular supply of quality produce to women marketers and facilitate electronic sales to a broad range of consumers established
Baseline:
Planned Target:
Indicator 1.3.2: Number of women trained on utilisation of the E-platform | To be identified
Baseline:
Planned Target:
Indicator 1.2.3: Proportion of women reporting increased market sales through use of multiple marketing avenues
Baseline:
Planned Target:
Outcome 2[1] | This is work in progress
Indicator:Number of gender responsive laws, policies and strategies effectively implemented to facilitate last mile food supply management system in compliance with OSH standards, and address gender differential needs.
Baseline:0
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Empowering women through safe, resilient, gender responsive food markets and systems in response to covid-19 in zimbabwe | Overall Duration (months) | 18 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy)
Country | Zimbabwe | Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN Women, UNDP and ILO | National counterparts (government, private, NGOs & others) and other International Organizations | Oxfam, NSSA
Report Cleared By
Name: | Maria Ribeiro
Title: | UN Resident Coordinator
o Email address: | ribeiro6@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board