MDG ACHIEVEMENT FUND (MDG-F)

“Mobilization of the Dahshour World Heritage Site for Community Development”

ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 29 APRIL 2009 – 31 December 2009

| Submitted by: Mohammed Shaker: Programme Manager (Shaker.hebara@undp.org) Sheriff El tokali -UNDP (Lead Agency) (sherif.el.tokali@undp.org) Fatoumatta Sabally – RC Office (Fatoumatta.Sabally@undp.org |  | Country and Thematic Area Egypt / Culture and Development |
| --- | --- | --- |

| Programme No: 00058644 MDTF Office Atlas No: 00048469 Programme Title: Mobilization of the Dahshour World Heritage Site for Community Development |  | Participating Organization(s): UNDP ILO UNESCO UNWTO UNIDO |
| --- | --- | --- |

| Implementing Partners: Ministry of Tourism (MoT) Supreme Council of Antiquities (SCA) Social Fund for Development (SFD) Industrial Modernization Center (IMC) Egyptian Environmental Affairs Agency (EEAA |  | Programme Budget (from the Fund): |
| --- | --- | --- |
|  |  | UNDP ILO UNESCO UNWTO UNIDO TOTAL | 966,160 450,363 772,005 565,816 340,742 3,095,086 USD |

Programme Duration (in months) : 36 Start Date : 29th April 2009 End Date : 28 April 2012 Budget Revisions/Extensions : N/A

# Purpose

“Mobilization of the Dahshour World Heritage Site for Community Development” Joint Programme is considered a model for cultural development as it combines cultural and natural heritage aspects, and community development components.

It is structured within the United Nations Development Assistance Framework (UNDAF) with the Government of Egypt and seeks to support the reduction of human development disparities, with special reference to addressing the gender gap and achieving environmental sustainability. The project strategy is working in two dimensions; first to reduce poverty of the local communities in Dahshour, and second to enhance the national institutional capacities so as to better protect and manage the archeological and natural resources of the area. Thus, a two dimensional matrix of outputs are designed with a number of activities to realize this strategy. The table below shows the linkage between the JP and the UN Strategic Planning framework.

UNDAF Outcome: By 2011, regional human development disparities are reduced, including reducing the gender gap, and environmental sustainability improved

Outcome 1 : Employment, especially of youth and women in heritage arts, crafts, tourism and creative industries increased, contributing to poverty alleviation and empowerment Outputs 1.1 Socio-economic community profile surveyed and LED forum operational to facilitate full community participation. 1.2 Sensitization to entrepreneurship and capacity building on decent work conditions conducted 1.3 Locally driven tourism sector fostered through training, stocktaking, and technical support to Dahshour tourism M/SMEs 1.4 Creative industries supported, building upon existent local capacities within the Dahshour community 1.5 BDS and micro-finance facilities provided to Dahshour and the surrounding communities

Outcome 2: Enhanced institutional capacity to manage cultural heritage and natural resources Indicators: Action Plan for the Dahshour Site produced and disseminated. Outputs 2.1 The development and implementation of SCA's action plan for the Dahshour component of the UNESCO WHC and its environs is supported. 2.2 Rural tourism and eco-tourism activities are supported through the development of a government corroborated and locally driven Spatial Tourism Development Plan 2.3 Environmental support to the Dahshour Lake provided through assessment and development of a GoE approved sustainable strategy

# Resources

Financial Resources:

The project is in the first year and has not received other funding resources.

The budget of some activities is being revised and fine-tuned based upon the availability of more information during early phase of implementation  and during the preparation of the inception report. However, this budget update will not impact the total allocated budget of the JP, and the budget of each UN agency. UNESCO-SCA and UNDP-EEAA are now revising their activities and thus will fine-tune the budget within their total planned budget for operational and functional reasons. These minor updates will appear in the inception report which is now being developed and will be finalized on April 11th, 2010.

The financial resources  allocated by the MDG-F for each UN agency remains the same. The table below gives a summary of the allocated budget for each agency.

| Budget Breakdown by Agency | Total USD | F&A | Grand Total |
| --- | --- | --- | --- |
| ILO | 420,900 | 29,463 | 450,363 |
| UNDP (+ F&A and support to NSC) | 902,954 | 63,207 | 966,160 |
| UNESCO | 721,500 | 50,505 | 772,005 |
| UNIDO | 318,450 | 22,292 | 340,742 |
| UNWTO | 528,800 | 37,016 | 565,816 |
| GRAND TOTAL USD | 2,892,604 | 202,482 | 3,095,086 |

Human Resources:

In general, the project is using the existing human resources of the implementing agencies for operation. For programmes, and as outlined in the Results & Resource Framework, national and international experts are mobilized to provide expertise required for the project interventions. In addition, the Project Coordination Unit (PCU) is currently headed by a National Programme Coordinator who is now in the process of recruiting national support staff; this will include an admin and finance assistant and an office messenger. The table below lists the existing human resources of the Dahshour Joint Programme.

| S/N | Post | Agency | National/ International | Programme/ Operation | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Environmental Consultant | UNDP-EEAA | National | Programme | 3 months assignment |
| 2 | Coordinator for LED | ILO - SFD | National | Programme | Recruited in February 2010 |
| 3 | Occupational Safety expert | ILO - SFD | National | Programme | Short term |
| 4 | Egyptian handcraft expert | UNIDO- IMC | National | Programme | Part time |
| 5 | Photographer/anthropologist | UNIDO- IMC | National | Programme | Short term |
| 6 | Creative industries consultant | UNIDO- IMC | International | Programme | Short term |
| 7 | Multi Media Consultant | UNIDO- IMC | National | Programme | Short term |
| 8 | Secretary – UNIDO - IMC | UNIDO- IMC | National | operation | Part time |
| 9 | Liaison Officer for Tourism | WTO – MoT | National | Programme/Operation |  |
| 10 | Logistics Officer for Tourism | WTO – MoT | National | Programme/Operation |  |
| 11 | Team Leader for Tourism | WTO – MoT | International | Programme |  |
| 12 | Training Consultant -Tourism | WTO – MoT | International | Programme |  |
| 13 | Infrastructure Expert - Tourism | WTO – MoT | International | Programme |  |
| 14 | Spatial Planning Expert - Tourism | WTO – MoT | International | Programme |  |
| 15 | Programme Coordinator - JPM | UNDP - PCU | National | Programme/Operation |  |

# Implementation and Monitoring Arrangements

Each UN agency works with its national partner based on its established rules and regulations to implement the activities and to ensure accountability and transparency. The institutional arrangements design allowed the programme to capitalize on the strengths of each organization for the interest of the whole programme; as each agency is working on the component it has a comparative advantage in and substantial experience. UN agencies and National Partners are represented in the Project Management Committee (PMC). This mechanism brings necessary coordination to the project and ensures integration while delivering the project activities.

Operational processes such as contracting and procurement have followed the open competitive procedures according to the rules and regulation of the involved UN agency. They have been conducted in a participatory manner, with one agency taking the lead and ensuring all Programme Management Committee (PMC) members are in agreement and endorse the selection process.

Quarterly Progress reports, Monitoring reports, field visits and mission reports provide the basic platform for monitoring. For instance, the Biannual Monitoring report which was developed and submitted to the Secretariat in February 2010 has provided detailed monitoring framework for the JP in the reporting period.

The following statement gives an example from (ILO) reporting on their implementation mechanism and monitoring of the JP:

“ILO is in compliance with the standards and regulations with regards to implementation mechanisms. All the national staff have been chosen and selected through a full and open bidding competition according to their experiences and the quality of their submitted proposals on different activities. Monitoring process has been carried out through field visits to Dahshour, and also through working closely with other local and international partners and continuous and close follow-up of the firms/Experts during their implementation of their assigned activities clearly stated and explained in the TORs.”

The implementation modalities of the UN agencies involved in the Joint Programme are:

- UNDP: According to the CPAP,

(part VI, 6.3) all cash transfers to an implementing Partner are based on the Annual Work Plans agreed between the Implementing Partner and UNDP).

Part VI, 6.4 Cash transfers for activities detailed in the AWPs can be made by UNDP using the following modalities:

1. Cash transferred directly to the Implementing Partner: a) prior to the start of activities (direct cash transfer) or b) after activities have been completed (reimbursement)

- ILO: Direct agency implementation.

- UNWTO: advances.

- UNESCO: direct payment modality.

- UNIDO: direct payments modality

# Results

Summary of Programme Progress in relation to planned outcomes and outputs

Outcome 1: Employment, especially of youth and women in heritage arts, crafts, tourism and creative industries increased, contributing to poverty alleviation and empowerment

The JP is now building momentum and has done necessary preparations in order to create synergy and achieve expected results. The first year of the project was dedicated to baseline studies, surveys and preparation for poverty reduction interventions; the Socio-economic profile for the target area has been completed and most of the implementing partners have done, or are currently conducting the necessary field work and surveys. International and national consultants are now onboard and preparing their reports to guide the implementation process. Capacity building programs are now underway; training needs analysis has been done and training programs and modules have been developed. Business Development Services and micro-finance programs are now at the introductory phase; ToRs have been developed to recruit competent partners for the implementation of this component.

Progress in Output 1.1: Socio-economic profile surveyed and LED forum operational to facilitate full community participation

A National Local Economic Development coordinator has been recruited to be responsible for the Follow-up of the daily activities and to coordinate and liaise with other implementing agencies, and also to provide the operational and administrative support for the ILO component in the project and to create a LED forum and ensure its effective operation.

The first draft of the Socio- Economic Survey was prepared and distributed to implementing partners for comments and feedback.  Preliminary findings of the survey are largely in harmony with the JP’s design and interventions, thus there is likely no need for significant changes in the project strategy.

In February 2010, beyond the date of this report, the final version of the Socio- economic survey was prepared and distributed to implementing partners for refining planned activities. The Programme Manager, in full cooperation with ILO, has organized a workshop on March 1st, to share the findings of the of the socio- economic study with the PMC. The feasible findings and recommendations were incorporated in the inception report which will be submitted in the coming few days to National Steering Committee for endorsement.

Progress in Output 1.2: Sensitization to entrepreneurship and capacity building of decent work conditions conducted

A national firm has been contracted for this component through ILO and the outline for the awareness and sensitization sessions has been developed.  Training materials have also been developed and the training courses are planned to start in March/April 2010. Approximately 1000 individuals from Dahshour are expected to attend the training. A workshop on development of decent work environment is scheduled to take place in the next quarter.

Progress in Output 1.3: Locally driven tourism sector fostered through training, stocktaking, and technical support to Dahshour tourism M/SMEs

Training needs analysis for the Dahshour community is completed. This information was essential to design the training program. Additionally, in August 2009, a detailed audit of existing skills in tourism sector was undertaken. Subsequently, preparation of “Training-of-Trainers (TOT)” started with 14 members of Dahshour trained on 6 modules. Training courses, potential trainers and participants and venues have been identified for the trainees. Training of Trainees is planned to commence in April 2010 in Dahshour and will include about 3000 participants.

Progress in Output 1.4: Creative industries supported, building upon existing local capacities within the Dahshour community

A five-day technical assistance mission to Egypt was conducted in September 2009 to closely work with the Industrial Modernization Centre (IMC), and the PMC. The Expert held presentations on the approach and strategy of the project, which also has been closely linked to the UNWTO component. An analysis on niche markets, tourism markets and the creative industries potential in Dahshour was conducted, including a rapid assessment on creative entrepreneurship within local communities. The report and audiovisual material on Dahshour creative sectors were subsequently finalized by the UNIDO Expert. The material included examples of how to use elements of the classic handicraft traditions and available resource materials in Dahshour for new product design and development.

A national expert with experience in the development and promotion of Egyptian ethnic products was recruited on a part-time basis in November 2009 to, inter alia, work closely with international experts on the organization of training and capacity building workshops in the creative industries and business sectors. A photographer and an assistant researcher/anthropologist with local field experience have been recruited to gather visual material, iconography and technical information available in the project community, museums, galleries and crafts workshops to set up the project’s image & techniques bank.

During this reporting period a field design research was undertaken by the photographer and the anthropologist under the supervision of the National Expert. The research resulted in the production of around 1000 photos/ images and related editing, description and classification into folders of animals, food, people, archeology, nature and objects. In parallel, the anthropologist undertook a research on the historical photos of Dahshour by visiting several museums, libraries and surfing relevant websites. He also took 120 photos reflecting the history and traditions of Dahshour. These photos may serve as a good way of documenting the history and culture of Dahshour.

Progress in Output 1.5: BDS and micro-finance facilities provided to Dahshour and the surrounding communities

This output depends on the results of the socio-economic survey that is why the implementation was put on hold until the findings of the study has been finalized. However the Social Fund for Development (SFD) finalized the Terms of Reference for the Business Development Services (BDS) providers and Micro-Finance Institutions (MFI) in order to invite qualified NGOs to implement this component. The process of contracting a relevant NGO to implement this component is ongoing according to competitive bidding procedures of SFD. The qualified NGO is planned to be on board by mid April.

Outcome 2: Enhanced institutional capacity to manage cultural heritage and natural resources

The three implementing agencies working under this outcome area have started the development of strategic documents such as the Tourism Master Plan, Archaeological Master Plan and ecological assessments of the natural resources of the area. At the end of the current phase, the developed plans will be endorsed and will lead to enhanced institutional capacity to protect and sustainably manage the natural and archaeological resources.

Progress in Output 2.1: The development and implementation of SCA’s action plan for the Dahshour component of the UNESCO World Heritage Site and its environment is supported

Data collection and mapping, including collecting data from archaeological missions working in the Dahshour area are underway.   Several meetings with the Metropolitan Museum mission have been conducted in the process of obtaining a complete work report on the integration of the Master Plan. Furthermore due to the different schedules of the international missions, some had to be scheduled at later dates (for example the German Institute mission and the Waseda University mission). Once the data collection and mapping is finalized the planning process will commence.

Several consultative meetings with the UNWTO consulting teams for the training programs have been conducted. In these meetings a mapping and planning consultant for the Master Plan exchanged data and conducted a planning workshop with the UNWTO consultants. As the environmental assessment component of the work plan requires a high level of coordination with UNESCO/UNDP/ EEAA team, UNESCO has located several environmental consulting firms as candidates for selection to work closely with the consultant working on the master plan as well as coordinating the effort of identifying and assessing of the surrounding area of the archaeological site, in particular the Dahshour Lake and palm groves.

Progress in Output 2.2: Rural tourism and eco-tourism activities are supported through the development of a government corroborated and locally driven Spatial Tourism Development Plan

A comprehensive draft spatial tourism development plan/strategy for Dahshour region including spatial land use plan for the 5 villages and the Berket Dahshour region were prepared in July-August 2009 in line with the national sustainable tourism development strategy, master plan project and the Greater Cairo Strategic Vision 2050. The draft was submitted to UNWTO HQ in mid-August and it was refined and shared with the PMC during a meeting in early November 2009. SWOT analysis has been conducted as part of the draft report and compared in detail with the SCA plan and concepts in order to ensure consistency. A workshop with local stakeholders (Government, community leaders and private sector) is scheduled for April 2010 in the process of consultation and endorsement of the strategy.

Progress in Output 2.3: Environmental support to the Dahshour Lake provided through assessment and development of a nationally approved strategy

Team of environmentalists from EEAA visited the Project Site for primary assessment of the natural resources of Dahshour with focus on the Lake. ToR for a comprehensive ecological assessment of the Dahshour Lake and associated ecosystems has been developed jointly by UNDP and EEAA. The ToR has been advertised on the UNDP site. A national consultant was contracted to conduct the study which will be completed within three months. The availability of comprehensive ecological assessment of the area will lead to the development of the national environmental management strategy for the lake and its ecosystems.

See annex 1: for detailed activities, key partners and budget

Constraints and mitigation measures

- Some of the national implementing partners are overwhelmed with their activities, priorities and bureaucracy and thus have little time and exert limited effort to the implementation process of the project.  The project is addressing this issue with implementing partners based on the circumstances of each partner. In some cases, an internal coordinator was assigned to facilitate the implementation and follow up on interventions and to increase the delivery rate.  In other cases, external support in the form of part time or short term services was also used to mitigate bottlenecks and ensure smooth implementation.

- The Programme Management Unit (PMU) is planned to be located in Cairo and hosted by SCA (National Partner). Currently, SCA Premises in Cairo is overcrowded and has no available space to accommodate the PMU. After a number of meetings and discussions, SCA has alternatively offered a site office in Sakkara, nearby Dahshour area (35Km from Cairo) to be used for the field work and for coordination of the field activities. In the mean time, the JP Manager is exploring the possibilities of the  PMU to have an office in Cairo in one of the offices of other national partners.  In the event that the national partners are not able to allocate an office in Cairo, then arrangements will be made to either share office space with other JPs being funded by the MDG Achievement Fund or to rent a unit to PMU.   Meanwhile, UNDP is temporarily hosting the PMU in their premises and providing logistical support until the final arrangements are in place.

- It took almost 6 months to recruit a Programme Manager and that has had some effect on the implementation of the joint programme and the establishment of the PMU. The Program Manager is now on board and working with the PMC to ensure smooth implementation of the project interventions as planned.

- Project started on 29th April 2009, and implementation was slowed down by the summer holidays and various religious festivals and holidays.

  - Holy Month of Ramadan followed by Islamic Feast “Eid- El Fitr”  (August – September)

  - Great Islamic Feast “Eid-El Adha” (November)

  - Christmas Holidays (December- January)

- For the Creative Industries component, lack of proper handicraft skills, activities, workshops and industries in the area requires more effort to revive and/ or start up handicraft activities through technical and professional training. In addition, lack of available natural resources and raw material aside from the palm trees in the project area limit the scope of creativity. However, consultations with IMC are underway to select and design new lines of productions based on palm trees.

In general, there are no serious bottlenecks or risks that could block the progress or affect the natural rate of implementation. The current progress rate is expected to improve significantly in the coming reporting periods mainly because; the JP’s coordination and management set up are in place, task managers are nominated, some bottlenecks have been resolved and the Program Manager was recruited in November 2009.

Key partnerships and collaborations

JP is building a team of partners and collaborators at different levels. This is a crucial factor to ensure efficient use of local expertise and resources that would ensure sustainability of the JP. The JP has brought together for the first time partners (national and international) from the tourism sector, the cultural and natural heritage sector to work with community members on poverty reduction initiatives to ensure sustainable community development. The partnerships created include members of the following organizations: Local NGOs such as;

  - The Community Development Association of Dahshour

  - Torathiet association

  - Local artists and groups of artisans

- Local administration Units and government offices

- Community leaders

- Educational institutes

- Ayade Masreya/ Fair Trade Umbrella organization

- COSPE, Italian organization working in the Egypt since 1998 and started with handicraft sector 10 years ago

- National consultants, photographers and trainers

- Media

The relationship with these partners will have a strong impact on the achievement of the results by facilitating:

- A smooth access to the target groups of the project at the community level

- Possible access to the database and contacts network of those partners and collaborators

- Proper selection of the beneficiaries of the different training programs

- Ensure complementary and an integrated approach to community development

- Capitalize on existing local resources and available expertise

- Transfer of knowledge and expertise that would be built throughout the project to ensure sustainability

# Future Work Plan

The AWP for the first year is valid until end of April 2010. In consultation with all members of the PMC, minor changes to the AWP have been recommended in order to include the lessons learned during the previous period and incorporate the findings of the baseline study. These changes are meant to increase effectiveness and ensure smooth implementation. The inception report which will be finalized in April 2010, will adopt these minor adjustments, to be endorsed by the National Steering Committee during the workshop.

No major adjustments in strategies, targets or key outcomes and outputs were recommended in the work plan. The detailed annual work plan is shown in Annex 2

# Performance Indicators

The complete performance indicators are now being developed. The inception report will be finalized in the coming few days and will include the fine-tuned version of whole set of the indicators.   The progress against the output indicators (updated version) is shown in the following table:

| Outputs, Responsible UN Organization and Outputs Indicators | Progress |
| --- | --- |
| Output 1.1 Socio-economic community profile surveyed and LED forum operational to facilitate full community participation. Responsible UN : (ILO) Indicators: Detailed socio-economic profile developed and integrated into community intervention Number of active beneficiaries participating in LED Forum | The detailed socio-economic profile has been already developed and integrated into community intervention during a workshop attended by Project Management Committee and PCU. Survey findings and recommendations were discussed in the workshop and final adjustments were drafted to be included in the inception report which will be ready in the coming few days. (indicator 1 is realized) The formulation of the LED Forum is now ongoing. The LED coordinator has been already recruited and is currently guiding the establishment of the Forum. A consultancy firm is contracted for a short term assignment to assist in establishing the LED Forum. The forum is planned to be created in Mid April and will include local leaders and community members. (indicator 2 is partially realized) |
| Output 1.2 Sensitization to entrepreneurship and capacity building on decent work conditions conducted Responsible UN : (ILO) Indicators Number of persons trained on decent working conditions Number of persons trained on entrepreneurship Number of materials produced on decent work environment Number of workshops implemented Total number of locals attending the workshops | This output is planned to start after output 1.1 as it was thought that the socio-economic study will help to figure out the target groups and the real needs of the community. Actual training has not started yet, however preparation for the training is ongoing. A national firm has been contracted for this component through ILO and the outline for the awareness and sensitization sessions has been developed. Training materials have been also developed and the training courses are planned to start in March/April 2010. Approximately 1000 individuals from Dahshour are expected to attend the training. A workshop on development of decent work environment is scheduled to be undertaken in the next quarter. (This set of indicators are expected to be realized in the next reporting period since preparation is ongoing) |
| Output 1.3 Locally driven tourism sector fostered through training, stocktaking, and technical support to Dahshour tourism M/SMEs Responsible UN : (UNWTO) Indicators Availability of Training Needs Analysis Availability of training modules Total Number of locals trained on Tourism Creation of Local Guides Association Number of new tourism oriented M/SMEs established a functional website on tourism Products of Dahshour is created availability of feasibility studies for developing eco-tourism and signposting in Dahshour | Training needs analysis for the Dahshour community is completed (indicator 1 is realized). Training modules are developed (indicator 2 is realized). “Training-of-Trainers (TOT)” has started with 14 members of Dahshour trained on 6 modules. Training courses, potential trainers and participants and venues have been identified for the trainees. Training of Trainees is planned to commence in April 2010 in Dahshour and will include about 3000 participants. Implementation of the activities related to indicators from 4 : 7 are planned for the second and third year of the project. However preparation for these activities is ongoing. |
| Output 1.4 Creative industries supported, building upon existent local capacities within the Dahshour community Responsible UN : (UNIDO) Indicators Number of persons trained on entrepreneurial and/or technical subjects Number of seminars conducted on entrepreneurship and M/SME Creation of entrepreneurial group | These indicators are expected to be realized during the next reporting period. Meanwhile, the following steps have been taken to prepare the ground for implementation of component: An analysis on niche markets, tourism markets and the creative industries potential in Dahshour was conducted, including a rapid assessment on creative entrepreneurship within local communities. The report and audiovisual material on Dahshour creative sectors were subsequently finalized by the UNIDO Expert. The report included examples of how to use elements of the classic handicraft traditions and available resource materials in Dahshour for new product design, training and development. A national expert with experience in the development and promotion of Egyptian ethnic products was recruited on a part-time basis in November 2009. Additionally, a photographer and an assistant researcher/anthropologist with local field experience have been recruited to gather visual material, iconography and technical information available in the project community, museums, galleries and crafts workshops to set up the project’s image & techniques bank. During this reporting period a field design research was undertaken by the photographer and the anthropologist under the supervision of the UNE. The research resulted in the production of around 1000 photos/images and related editing, description and classification into folders of animals, food, people, archeology, nature and objects. In parallel, the anthropologist undertook a research on the historical photos of Dahshour by visiting several museums, libraries and surfing relevant websites. This resulted in the collection of further 120 photos reflecting the history and traditions of Dahshour. |
| Output 1.5 BDS and micro-finance facilities provided to Dahshour and the surrounding communities Responsible UN : (UNDP) Indicators Number of loans dispersed Number of M/SMEs receiving BDS | SFD is now creating the enabling environment and is setting the stage for BDS and Micro- Finance programme. That is why no loans are dispersed. In this regard, the Social Fund for Development (SFD) finalized Terms of Reference for Business Development Services (BDS) providers and Micro-Finance Institutions (MFI) in order to invite qualified NGOs to implement this component. The process of contracting a relevant NGO to implement this component is ongoing a according to competitive bidding procedures of SFD. The qualified NGO is planned to be on board Mid April. Indicators are expected to be realized in the next stage of the project. |
| Output 2.1 The development and implementation of SCA's action plan for the Dahshour component of the UNESCO WHC and its environment is supported Responsible UN : (UNESCO) Indicators SCA master plan/site management plan for Dahshour finalized Number of SCA staff who receive technical training Availability of design for CHDC Number of workshops and training on visitor management of Archeological sites Production of public booklet , visitors guidebook, informative materials and signage on archeological resources of Dahshour Availability of a dossier prepared for WHC to enlarge the WHS based upon assessment studies Availability of GIS-based maps for Dahshour archeological sites | The process of developing a Master Plan has started with Data collection and Mapping, specifically ; The team is currently collecting data from archaeological missions working in the Dahshour area. Several meetings with the Metropolitan Museum mission have been conducted in the process of obtaining a complete work report on the integration of the Master Plan. Once the data collection and mapping stage is finalized the planning process will commence. In addition, several consultative meetings with the UNWTO consulting teams for the training programs have been conducted. UNESCO has, also contacted number of environmental consulting firms as candidates for selection to work closely with the consultant working on the master plan as well as coordinating the effort of identifying and assessing of the surrounding area of the archaeological site. To conclude, indicator 1 and 2 are not fully realized, however preparation is ongoing to implement the activities and thus realize the indicators. Indicators 3: 7 are designed to cover activities which will take place in the second and third year of the project. |
| Output 2.2 Rural tourism and eco-tourism activities are supported through the development of a government corroborated and locally driven Spatial Tourism Development Plan Responsible UN : (UNWTO) Indicators Spatial Tourism Plan for Dahshour finalized Spatial Tourism Plan for Dahshour approved | As planned a comprehensive draft spatial tourism development plan/strategy for Dahshour region including spatial land use plan for the 5 villages and the Berket Dahshour region were prepared in July-August in line with the national sustainable tourism development strategy (indicator 1 is realized). The second indicator is designed to ensure adoption and implementation of the developed Plan. A workshop with local stakeholders (Government, community leaders and private sector) is scheduled for April 2010 in the process of consultation and endorsement of the strategy. (indicator 2 is partially realized) |
| Output 2.3 Environmental support to the Dahshour Lake provided through assessment and development of a nationally approved sustainable strategy Responsible UN : (UNDP) Indicators Environmental Sustainable Strategy for the Lake is developed Dahshour lake and associated ecosystems are ecologically assessed Availability of Public Awareness materials on Natural Resources of Dahshour Lake and associated ecosystems | The planned activity for this reporting period is the ecological assessment study which will provide a baseline to the environmental component. So, the applicable indicator for this period is partially achieved (indicator 2). Specifically the environmental authorities and the contracted environmental consultant have already started the assessment of the ecological resources of the area and several field visits have been undertaken for this purpose. The study is planned to be finalized within three months. The availability of comprehensive ecological assessment of the area will lead to the development of the national environmental management strategy for the lake and its ecosystems. |

# Abbreviations and Acronyms

AA		Administrative Agent

BD		Business Development

BDS		Business Development Services

CCA 		Common Country Assessment

CDS                        Center for Development Services

CHDC		Cultural Heritage Development Centre
CI		Creative Industries

CSO		Civil Society Organization

DNA		Designated National Authority

EEAA		Egyptian Environmental Affairs Agency

ETA		Egyptian Tourism Authority

GoE	  Government of Egypt

ILO		International Labour Organization

IMC		Industrial Modernization Centre

JP		Joint Programme

JPD		Joint Programme Document

JPM                        Joint Programme Manager

KAB		Know About Business

LED		Local Economic Development

M&E		Monitoring and Evaluation

MCIT		Ministry of Communication and Information Technology

MDCD                   “Mobilization of the Dahshour World Heritage Site for Community Development” Project

MDG-F	               Millennium Development Goals Achievement Fund

MDGs		Millennium Development Goals

MDTF		Multi-Donor Trust Fund

MFI		Micro Finance Institution

MSME		Micro, Small and Medium Enterprise

MoC		Ministry of Culture

MoFA		Ministry of Foreign Affairs

MoIC		Ministry of International Cooperation

MoT		Ministry of Tourism

MoTI		Ministry of Trade and Industry

MSEA	Ministry of State for Environmental Affairs

PCU                        Programme Coordination Unit

PMC	Programme Management Committee

PMF	               Programme Monitoring Framework

PMU                      Programme Management Unit

RC	               Resident Coordinator

RRF                        Results and Resource Framework

NSC	               National Steering Committee

SCA	               Supreme Council for Antiquities

SFD	               Social Fund for Development

SMART                  Specific – Measurable – Achievable – Relevant – Timely

SME	Small and Medium Enterprise

STEP	               Sustainable Development- Eliminating Poverty

TNA                       Training Needs Assessment

ToR	               Terms of References

ToT	               Training of Trainers

UNDAF	               United Nations Development Assistance Framework

UNDP	              United Nations Development Programme

UNESCO	               United Nations Educational, Scientific and Cultural Organization

UNIDO	               United Nations Industrial Development Organization

UNWTO	               United Nations World Tourism Organization

UNE                       UNIDO National Expert

UNS	               United Nations System

V & A	Vulnerability and Adaptation

WIND	Work Improvements for Neighborhood Development

WISE	Work Improvements in Small Enterprises

WHC	World Heritage Centre

WHS		World Heritage Sit

Annex 1 : Resource and Results framework with detailed activities and progress

|  | D | JP output: 1.1 Please highlight the rate of delivery for each joint programme’s output: a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 d. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  |  | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| 1.1 Socio-economic community profile surveyed and LED forum operational to facilitate full community participation. | 1.1.1 Conduct field survey for baseline data on Dahshour and surrounding communities | x |  |  | ( ILO) | SFD | MDG-F | consultant | 50,000 | 50,000 | 22,275 | 100 |
|  | 1.1.2 JP Manager will disseminate report to UN agencies and national partners and lead a workshop to refine intervention strategy and create plan of action | x |  |  | (ILO) | SFD | MDG-F | Workshop | 5,000 |  |  |  |
|  | 1.1.3 Recruit National Local Economic Development Coordinator (National Coordinator for ILO subcomponent) | x | x | x | (ILO) | SFD | MDG-F | Consultants | 12,000 |  |  |  |
|  | 1.1.4 Awareness sessions to the local community to promote their understanding of the touristic value of the area, and prepare for the formation of the LED Forum | x | x | x | (ILO) | SFD | MDG-F | Training | 10,000 |  |  |  |
|  | 1.1.5 Creation and facilitation of the LED Forum of local stakeholders, natural leaders, trade unions, employers, local authorities and representatives of disadvantaged groups. | x | x | x | (ILO) | SFD | MDG-F | Meetings, Workshops And consultants | 20,000 |  | 10,620 | 53 |
| Total | 97,000 | 50,000 | 32,895 | 85 |

|  | A | JP output: 1.2 Please highlight the rate of delivery for each joint programme’s output: a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 d. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  |  | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| 1.2 Sensitization to entrepreneurship and capacity building on decent work conditions conducted | 1.2.1 Recruit national trainers/coaches on entrepreneurship and decent working conditions | x | x | x | ( ILO) | SFD | MDG-F | Consultants | 18,000 |  |  |  |
|  | 1.2.2 Conduct sensitization workshops and coaching on entrepreneurship for Dahshour and Memphis and its Necropolis (3000 persons) | x | x | x | (ILO) | SFD | MDG-F | Training | 20,000 |  |  |  |
|  | 1.2.3 Conduct workshops on developing decent working conditions, respect for environment and gender equality and issues of child labour for Dahshour and Memphis and its Necropolis (3000 persons). | x | x | x | (ILO) | SFD | MDG-F | Training | 20,000 |  |  |  |
|  | 1.2.4 Basic Occupational Safety and Health material produced and distributed to Dahshour and surrounding communities. | x | x | x | (ILO) | SFD | MDG-F | Publications | 8,000 |  |  |  |
| Total | 66,000 |  |  |  |

|  | B | JP output: 1.3 Please highlight the rate of delivery for each joint programme’s output: a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 d. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  |  | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| 1.3 Locally driven tourism sector fostered through training, stocktaking, and technical support to Dahshour tourism M/SMEs | 1.3.1 Prepare and Conduct Training Needs Analysis (TNA) | x |  |  | (UNWTO) | MoT | MDG-F | Consultants | 35,000 |  | 30,707 | 88 |
|  | 1.3.2 Conduct ToT for Tourism Training Courses | x |  |  | (UNWTO) | MoT | MDG-F | Training | 30,000 |  | 3,114 | 10 |
|  | 1.3.3 Implement Training Courses using TNA for Dahshur and Memphis and its Necropolis (3000 persons). | x | x | x | (UNWTO) | MoT | MDG-F | Training | 12,000 |  |  |  |
|  | 1.3.5 Hold tourism awareness sessions with each community in Dahshur and the surrounding area | x | x | x | (UNWTO) | MoT | MDG | Consultants and training | 13,000 |  |  |  |
|  | 1.3.9 Audit existing skills in the tourist sector | x |  |  | (UNWTO) | MoT | MDG | consultants | 12,000 |  | 4,553 | 38 |
|  | 1.3.10 Train local community members on M/SME development in tourism sector | x | x | x | (UNWTO) | MoT | MDG | Training | 18,000 |  |  |  |
| Total | 120,000 |  | 38,375 | 32 |

|  | B | JP output: 1.4 Please highlight the rate of delivery for each joint programme’s output: a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 d. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  |  | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| 1.4 Creative industries supported, building upon existent local capacities within the Dahshour community | 1.4.1 Recruit National Consultant for technical training | x | x | x | UNIDO | IMC | MDG-F | Consultants | 12,000 |  |  |  |
|  | 1.4.2 Conduct training and in-house training on technical subjects (production processes, productivity enhancement, packaging, quality) with focus on crafts and agro-industries for Memphis and its Necropolis (1500 persons) | x | x | x | UNIDO | IMC | MDG-F | Training | 30,000 |  | 18,700 | 62 |
|  | 1.4.3 Carry out entrepreneurship development programmes (basic accounting, marketing, enterprise management, business planning) for Memphis and its Necropolis (1500 persons) | x | x | x | UNIDO | IMC | MDG-F | Training | 15,000 |  |  |  |
|  | 1.4.4 Assist in the formation of self-help entrepreneurial groups | x | x |  | UNIDO | IMC | MDG-F | Training and logistic support | 12,500 |  | 2,123 | 17 |
|  | 1.4.5 Conduct awareness seminars to stimulate BDS demand | x | x |  | UNIDO | IMC | MDG-F | seminars | 10,000 |  | 1,896 | 19 |
|  | 1.4.6 Provide enterprise level technical advice in product development, design and quality for Memphis and its Necropolis | x | x | x | UNIDO | IMC | MDG-F | Consultants | 25,000 |  | 21,046 | 84 |
|  | 1.4.7 Organize participation of local MSEs in Trade Fairs | x | x | x | UNIDO | IMC | MDG-F | Consultants | 2,000 |  |  |  |
| Total | 106,500 |  | 43,765 | 41 |

|  | B | JP output: 1.5 Please highlight the rate of delivery for each joint programme’s output: a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 d. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  |  | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| 1.5 BDS and micro-finance facilities provided to Dahshour and the surrounding communities | 1.5.1BDS provider granted fund to provide non-financial services to local community SMEs (UNDP) | x | x | x | UNDP | SFD | MDG-F | Consultants | 35,000 |  | 4,919 | 13 |
|  | 1.5.3 Assess needs of local administrative units (UNDP) | x |  |  | UNDP | All national partners | MDG-F | Consultants | 10,000 |  |  |  |
|  | 1.5.4 National Manager (UNDP) | x | x | x | UNDP | All national partners | MDG-F | Consultant | 30,250 | 30,250 | 7,067 | 100 |
|  | 1.5.5 National Community Development/SME Coordinator (UNDP) | x | x | x | UNDP | All national partners | MDG-F | Consultants | 15,000 |  |  |  |
|  | 1.5.8 Documentary film with before and after footage for awareness, appreciation and documentation purposes (UNDP) | x |  | x | UNDP | All national partners | MDG-F | Audio/Visual Production | 10,000 |  | 5,007 | 50 |
|  | 1.5.9 Project Management equipment and transportation to and from Dahshour (UNDP) | x | x | x | UNDP | All national partners | MDG-F | Equipment and Transportation | 12,000 |  |  |  |
| Total | 112,000 | 30,250 | 16,993 | 42 |

|  | a | JP output: 2.1 Please highlight the rate of delivery for each joint programme’s output: a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 d. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  |  | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| 2.1 The development and implementation of SCA's action plan for the Dahshur component of the UNESCO WHC and its environs is supported. | 2.1.1 Develop master plan/ site management plan, including programming and feasibility studies for the Dahshour archaeological area | x |  |  | UNESCO | SCA | MDG-F | Consultants | 120,000 |  | 24,000 | 20 |
|  | 2.1.2 Studies and designs developed for the CHDC Includes architects fees for design and development of visitors center and technical office + the design for interior spaces and the display for visitors | x | x |  | UNESCO | SCA | MDG-F | Consultants | 80,000 |  |  |  |
|  | 2.1.3 Support the constitution of a visitor center in the CHDC. Equipment and furnish administrative center for the visitors' center including the administrative unit | x | x |  | UNESCO | SCA | MDG-F | Office Machinery | 9,000 |  |  |  |
|  | 2.1.8 Acquisition of topographical maps | x | x |  | UNESCO | SCA | MDG-F | Goods | 750 |  |  |  |
|  | 2.1.12 Assessment of the surrounding area of the archaeological site, in particular the Lake area and the Palm Grove. Assistance in the preparation, by local authorities of a file for a tentative inclusion of these two areas in the WHC and MAB lists | x | x | x | UNESCO | SCA | MDG-F | Consultants | 12,000 |  |  |  |
|  | 2.1.14 Mapping of the Dahshour area using Geographic Information Systems (GIS) and disseminate data to national and UN partners | x | x |  | UNESCO | SCA | MDG-F | Consultants | 16,000 |  | 16,000 | 100 |
| Total | 237,750 |  | 40,000 | 17 |

|  | e | JP output: 2.2 Please highlight the rate of delivery for each joint programme’s output: a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 d. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  |  | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
|  | 2.2.2 Prepare with community pilot draft spatial tourism development strategy in line with the national sustainable tourism development strategy and master plan project (UNWTO) | x |  |  | UNWTO | MoT | MDG-F | Consultants | 50,000 |  | 37,217 | 74 |
|  | 2.2.3 Refine and publish approved spatial tourism development plan/strategy (UNWTO) | x |  |  | UNWTO | MoT | MDG-F | Consultants | 25,000 |  | 12,294 | 49 |
| Total | 75,000 |  | 49,511 | 66 |

|  | a | JP output: 2.3 Please highlight the rate of delivery for each joint programme’s output: a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 d. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  |  | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| 2.3 Environmental support to the Dahshur Lake provided through assessment and development of a GoE approved sustainable strategy | 2.3.1 Assess ecological value of seasonal lake (UNDP) | x |  |  | UNDP | EEAA | MDG-F | Consultants | 10,000 |  |  |  |
|  | 2.3.2 Review legal position of land tenure/ownership (UNDP) | x |  |  | UNDP | EEAA | MDG-F | Consultants | 5,000 |  |  |  |
|  | 2.3.3 Review existing protected area boundaries and identify opportunities for creating new Protected Areas and buffer zones (UNDP) | x | x |  | UNDP | EEAA | MDG-F | Consultants | 5,918 |  |  |  |
| Total | 20,918 |  |  |  |

Annex 2: Annual work plan (first year)

| Outcome 1: Employment, especially of youth and women in heritage arts, crafts, tourism and creative industries increased, contributing to poverty alleviation and empowerment. |
| --- |
| JP Output 1.1 Socio-economic community profile surveyed and LED forum operational to facilitate full community participation. (ILO) |
| Annual targets | Activities | Time frame | UN AGENCY | Responsible party | Planned Budget |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  | Source of Funds | Budget Description | Amount USD |
| Socioeconomic survey completed LED Forum established and operational | 1.1.1 Conduct field survey for baseline data on Dahshour and surrounding communities | x |  |  |  | ILO | SFD | MDG-F | Local Consultants | 50,000 |
|  | 1.1.2 JP Manager will disseminate report to UN agencies and national partners and lead a workshop to refine intervention strategy and create plan of action |  | x |  |  | ILO | SFD | MDG-F | Local Consultants | 5,000 |
|  | 1.1.3 Recruit National Local Economic Development Coordinator (National Coordinator for ILO subcomponent) | x |  |  |  | ILO | SFD | MDG-F | Local Consultants | 12,000 |
|  | 1.1.4 Awareness sessions to the local community to promote their understanding of the touristic value of the area, and prepare for the formation of the LED Forum (ILO) |  | x | x | x | ILO | SFD | MDG-F | Local Consultants | 10,000 |
|  | 1.1.5 Creation and facilitation of the LED Forum of local stakeholders, natural leaders, trade unions, employers, local authorities and representatives of disadvantaged groups. (ILO) |  |  | x | x | ILO | SFD | MDG-F | Local Consultants | 20,000 |
| Annual Output Total |  |  |  |  |  |  |  |  | 97,000 |
| JP Output 1.2 Sensitization to entrepreneurship and capacity building on decent work conditions conducted (ILO) |
| 1000 individuals from Dahshour and the communities surrounding Memphis and its Necropolis coached on entrepreneurship and decent working conditions | 1.2.1 Recruit national trainers/coaches on entrepreneurship and decent working conditions |  | x |  |  | ILO | SFD | MDG-F | Local Consultants | 18,000 |
|  | 1.2.2 Conduct sensitization workshops and coaching on entrepreneurship for Dahshour and Memphis and its Necropolis (3000 persons) |  | x | x | x | ILO | SFD | MDG-F | Trainings | 20,000 |
|  | 1.2.3 Conduct workshops on developing decent working conditions considering environment and gender equality and issues of child labour for Dahshour and Memphis and its Necropolis (3000 persons). |  | x | x | x | ILO | SFD | MDG-F | Trainings | 20,000 |
|  | 1.2.4 Basic Occupational Safety and Health material produced and distributed to Dahshour and surrounding communities |  |  | x | x | ILO | SFD | MDG-F | Printing and Publication | 8,000 |
| Annual Output Total |  |  |  |  |  |  |  |  | 66,000 |
| JP Output 1.3 Locally driven tourism sector fostered through training, stocktaking, and technical support to Dahshour tourism M/SMEs (UNWTO) |
| TNA Conducted | 1.3.1 Prepare and Conduct Training Needs Analysis (TNA) | x | x |  |  | UNWTO | MoT | MDG-F | Local Consultants | 35,000 |
| 500 people from Dahshour and the communities surrounding Memphis and its Necropolis trained on SME tourism development and basic tourism skills | 1.3.2 Conduct ToT for Tourism Training Courses |  |  | x | x | UNWTO | MoT | MDG-F | Trainings | 30,000 |
|  | 1.3.3 Implement Training Courses using TNA for Dahshour and Memphis and its Necropolis (3000 persons). |  |  |  | x | UNWTO | MoT | MDG-F | Trainings | 12,000 |
|  | 1.3.5 Hold tourism awareness sessions with each community in Dahshour and the surrounding area |  | x | x | x | UNWTO | MoT | MDG-F | Local Consultants | 13,000 |
|  | 1.3.9 Audit existing skills in the tourist sector |  |  | x | x | UNWTO | MoT | MDG-F | Local Consultants | 12,000 |
|  | 1.3.10 Train local community members on M/SME development in tourism sector |  |  | x | x | UNWTO | MoT | MDG-F | Trainings | 18,000 |
| Annual Output Total |  |  |  |  |  |  |  |  | 120,000 |
| JP Output 1.4 Creative industries supported, building upon existent local capacities within the Dahshour community (UNIDO) |
| 500 persons trained on entrepreneurship development in Dahshour and the communities surrounding Memphis and its Necropolis Local M/SMEs participate in national trade fairs. Enterprise level technical advice provided to M/SMEs operating in Dahshour and the communities surrounding Memphis and its Necropolis | 1.4.1 Recruit National Consultant for technical training | x | x | x | x | UNIDO | IMC | MDG-F | Local Consultants | 12,000 |
|  | 1.4.2 Conduct training and in-house training on technical subjects (production processes, productivity enhancement, packaging, quality) with focus on crafts and agro-industries for Memphis and its Necropolis (1500 persons) |  | x | x | x | UNIDO | IMC | MDG-F | Trainings | 30,000 |
|  | 1.4.3 Carry out entrepreneurship development programmes (basic accounting, marketing, enterprise management, business planning) for Memphis and its Necropolis (1500 persons) |  | x | x | x | UNIDO | IMC | MDG-F | Local Consultants | 15,000 |
|  | 1.4.4 Assist in the formation of self-help entrepreneurial groups | x | x | x | x | UNIDO | IMC | MDG-F | Local Consultants | 12,500 |
|  | 1.4.5 Conduct awareness seminars to stimulate BDS demand |  | x | x | x | UNIDO | IMC | MDG-F | Local Consultants | 10,000 |
|  | 1.4.6 Provide enterprise level technical advice in product development, design and quality for Memphis and its Necropolis |  |  | x | x | UNIDO | IMC | MDG-F | Local Consultants | 25,000 |
|  | 1.4.7 Organize participation of local MSEs in Trade Fairs |  |  | x | x | UNIDO | IMC | MDG-F | Local Consultants | 2,000 |
| Annual Output Total |  |  |  |  |  |  |  |  | 106,500 |
| JP Output 1.5 BDS and micro-finance facilities provided to Dahshour and the surrounding communities (UNDP) |
| BDS provider and MFI identified BDS provider actively supporting enterprises in Dahshour and the communities surrounding Memphis and its Necropolis | 1.5.1 BDS provider granted fund to provide non-financial services to local community SMEs |  |  | X | X | UNDP | SFD | MDG-F | Local Consultants | 35,000 |
|  | 1.5.3 Consultative meetings and workshops with National/Local administrative units and community members on MDCD strategy and its linkage to national policies and MDGs | x | x | x |  | UNDP | PMU | MDG-F | Local Consultants | 10,000 |
|  | 1.5.4 National Manager | x | x | x | x | UNDP | PMU | MDG-F | Local Consultants | 30,000 |
|  | 1.5.5 National Community Development/SME Coordinator and Supportive Staff | x | x | x | x | UNDP | PMU | MDG-F | Local Consultants | 15,000 |
|  | 1.5.8 develop and implement Project’s communication strategy | x | x | x |  | UNDP | PMU | MDG-F | Audio/Visual Production | 10,000 |
|  | 1.5.9 Project Management equipment and transportation to and from Dahshour | x | x | x | x | UNDP | PMU | MDG-F | Office Machinery/ Transportation | 12,000 |
| Annual Output Total |  |  |  |  |  |  |  |  | 112,000 |
| Outcome 1 Annual Total |  |  |  |  |  |  |  |  |  | 501,500 |
| Outcome 2: Enhanced institutional capacity to manage cultural heritage and natural resources |
| JP Output 2.1 The development and implementation of SCA's action plan for the Dahshour component of the UNESCO WHC and its environs is supported. (UNESCO) |
| Master Plan/Site Management Plan completed and incorporated into Master Plan for Memphis and its Necropolis Capacity Development of 100 SCA inspectors | 2.1.1 Develop master plan/ site management plan, including programming and feasibility studies for the Dahshour archaeological area | x | x | x | x | UNESCO | SCA | MDG-F | Local Consultants | 120,000 |
|  | 2.1.2 Studies and designs developed for the CHDC Includes architects fees for design and development of visitors center and technical office + the design for interior spaces and the display for visitors |  |  |  | x | UNESCO | SCA | MDG-F | Local Consultants | 19,250 |
|  | 2.1.8 Acquisition of topographical, Satellite and survey maps of the natural and archeological resources of the Dahshour WHS | x | x | x | x | UNESCO | SCA | MDG-F | Material and Goods | 25,500 |
|  | 2.1.12 Assessment of the surrounding area of the archeological site, in particular the Lake area and the Palm Grove. Assistance in the preparation, by local authorities of a file for a tentative inclusion of these two areas in the WHC and MAB lists |  |  | x | x | UNESCO | SCA | MDG-F | Local Consultants | 40,000 |
|  | 2.1.14 Mapping of the Dahshour area using Geographic Information Systems (GIS) and disseminate data to national and UN partners | x | x | x | x | UNESCO | SCA | MDG-F | Local Consultants | 33,000 |
| Annual Output Total |  |  |  |  |  |  |  |  | 237,750 |
| JP Output 2.2 Rural tourism and eco-tourism activities are supported through the development of a government corroborated and locally driven Spatial Tourism Development Plan (UNWTO) |
| Spatial Tourism Development Plan/Strategy approved by Dahshour community | 2.2.2 Prepare with community pilot draft spatial tourism development plan/strategy in line with the national sustainable tourism development strategy and master plan project (UNWTO) | x | x |  |  | UNTWO | MoT | MDG-F | Local Consultants | 50,000 |
|  | 2.2.3 Refine and publish approved spatial tourism development plan/strategy |  |  | x | x | UNTWO | MoT | MDG-F | Local Consultants | 25,000 |
| Annual Output Total |  |  |  |  |  |  |  |  | 75,000 |
| JP Output 2.3 Environmental support to the Dahshour Lake provided through assessment and development of a GoE approved sustainable strategy (UNDP) |
| Ecological value of Birket Dahshour assessed, with findings disseminates to local stakeholders, and government counterparts | 2.3.1 Assess ecological value of lake | x | x | x | x | UNDP | EEAA | MDG-F | Local Consultants | 10,000 |
|  | 2.3.2 Review legal position of land tenure/ownership | x | x | x | x | UNDP | EEAA | MDG-F | Local Consultants | 5,000 |
|  | 2.3.3 Review existing protection measures and identify opportunities for creating new Protected Areas and buffer zones in Dahshour |  |  |  | x | UNDP | EEAA | MDG-F | Local Consultants | 5,918 |
| Annual Output Total |  |  |  |  |  |  |  |  | 20,918 |
| Outcome 1 Annual Total |  |  |  |  |  |  |  |  |  | 334,668 |
| Total |  |  |  |  |  |  |  |  |  | 836,168 |
| F&S (7%) |  |  |  |  |  |  |  |  |  | 60155 |
| RC (.5%) |  |  |  |  |  |  |  |  |  | 4183.75 |
| GRAND TOTAL |  |  |  |  |  |  |  |  |  | 919507 |

# Footnotes

Details of the activities and allocated budget are shown in Annex 2:  Annual work plan

See annex 1 for detailed activities and % of completion and achieved outputs

This development took place  in February and March 2010

This is an ongoing process and some of the developments  are as recent as March 2010

See annex 2 for details of the annual work plan

The progress  in this output is reported till March 2010