2008 JOINT PROGRAMME PROGRESS REPORT

| Date of Submission: April 09, 2009 Submitted by: Mona ElAgizy, JP Manager, UNDP ccrmp.egypt@gmail.com |  | Country and Thematic Window Egypt / Environment and Climate Change |
| --- | --- | --- |

| OPAS No. MDGF-1675 MDTF Atlas Award No: 00048176 MDTF Atlas Project No: 00058197 Title: Climate Change Risk Management in Egypt |  | Report Number: 1 Reporting Period: October 15 - Dec. 31 2008 Programme Duration: 36 months |
| --- | --- | --- |

| Participating UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| UNDP, UNESCO, IFAD, FAO, UNEP, UNIDO |  | EEAA, MWRI, MALR, CoM |

| Abbreviations and Acronyms: CDM Clean Development Management. CoM Cabinet of Ministers. EEAA Egyptian Environmental Affairs Agency. MALR Ministry of Agriculture and Land Resources. MDGs Millennium Development Goals. MWRI Ministry of Water Resources and Irrigation. NSC A National Steering Committee. PMC Programme Management Committee. UNDAF United Nation Development Assistance Framework. |  | Programme Budget: UNDP $1,175,262 UNESCO $ 499,500 IFAD $ 500,040 FAO $ 500,040 UNEP $ 824,579 UNIDO $ 500,580 Total $4,000,000 |
| --- | --- | --- |

### I.  PURPOSE

The purpose of the Climate Change Risk Management Programme in Egypt is to strengthen institutional capacity and policies to mitigate Egypt's contribution to greenhouse gases, and to provide tools to policy developers to make strategic decisions for the adaptation to climate change.

The table below summarizes the main outputs and outcomes of the programme.

| Outcome | Output |
| --- | --- |
| Mainstreaming GHG mitigation, CDM into national policy and Expanding access to Finance Frameworks | National Policy Reform for more sustainable energy economy achieved. Expand CDM market. |
| Enhanced Capacity to adapt to Climate Change | Adaptation strategies and practices integrated into Climate Sensitive Development Policies, Plans and Programmes. Pilot measures implemented and scaled up in support of adaptation mainstreaming and policy making. |

UNDAF outcomes one and three constitute the overarching framework for this programme that aims to ensure achievement of the MDGs in the face of climate change in Egypt through sustainable energy development strategies and effective management of climate risks in key affected sectors.

Outcome 1: By 2011, state's performance and accountability in programming, implementing and coordinating actions, especially those that reduce exclusion, vulnerabilities and gender disparities, are improved’

Outcome 3: By 2011, regional human development disparities are reduced, including reducing the gender gap, and environmental sustainability improved’

### 2.  RESOURCES

There are no revisions of the budget at this time. During the Inception Phase in 2009, the detailed work plans and budget will be updated and will be reported in the Inception Report.

3. IMPLEMENTATION ARRANGEMENTS

A national full-time Joint Programme Manager was recruited on December 1, 2008 and the focal points for the six UN agencies and for the four Government agencies were designated. The Joint Programme Manager is responsible for daily programme management and coordination with the ten Focal Points.

All participating UN agencies and their Egyptian partners started to engage in an exercise to prepare an inception report detailing activities, outputs, inputs, indicators and means of verification within the overall log frame of this JP in 2009.

The JP Manager convened the 1st PMC that was held on December 21, 2008. The meeting was chaired by a senior official of EEAA since they are the main government coordinator of the programme. The main purpose of this meeting was to initiate the preparation of the detailed work plans and to start planning the Inception Workshop in 2009. The Inception Workshop’s objective is to communicate the objectives of the programme and to promote cross-sectional dialogue.

### 4.  RESULTS

The following significant achievements were made during the short Inception phase in 2008.

- The Joint Programme (JP) funds were transferred to the HQs of UN Participating Agencies on the 15th of October 2008.

- The post for the JP Manager was advertised and the selection process was concluded with the appointment of the Joint Program Manager on 1st December 2008.

- The Programme Management Unit has been established in the Egyptian Environmental Affairs Agency (EEAA) as the main coordinating agency of the JP from the side of the Government of Egypt

- The first PMC meeting was held shortly after the appointment of the JP Manager on 21st December 2008.  The objective of the first PMC meeting was to discuss the coordination and implementation arrangements, and agree on the necessary steps towards holding the Inception Workshop in 2009

So far, there were no issues impeding implementation. The UN and Government Agencies’ participating in each component have started to work together on the refinement and finalization of the detailed work plans that will be presented in the Inception Workshop.  Before the Inception workshop, the work plans will be reviewed in the second PMC meeting that will be held late in January 2009.  The arrangements of the Inception workshop will also be finalized in the PMC meeting aiming to have the workshop chaired by the relevant Ministers and to include all stakeholders. After the Inception Workshop, the third PMC and first NSC meetings is planned to be held to approve the final work plans in order for the Implementation phase to begin.

5. FUTURE WORK PLAN

In 2009, the future work plan is to complete the Inception phase and to enter the Implementation phase. A second PMC meeting will be held to follow up on the updates of the 3 years Results Frame Work Plan and the 1st year detailed Work Plan in order to prepare for the Inception Workshop.

After the Inception Workshop, a 3rd PMC meeting will be held to analyze the Results Frame Work Plan and the detailed Work Plan. Then, the National Steering Committee meeting will be held to approve the Results Frame Work Plan and Annual Work Plan.

Following the completion of this Inception process, quarterly PMC meetings will be held to monitor progress of the programme. The PMC may meet more often depending on the need to address issues related directly to management and implementation of the programme.

### ANNEX A: The colour-coded work plan.

### ANNEX B: Monitoring framework

Annex A:Work Plan for: Climate Change Risk Management in Egypt			Period:  (Covered by the AWP) October 15, 2008 – October 14, 2009

green (done), yellow (ongoing), and red (not started)

| Annual targets | Key Activities | TIME FRAME | UN AGENCY | Responsible. Party | PLANNED BUDGET |
| --- | --- | --- | --- | --- | --- |
|  |  | Year 1 |  |  |  |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  |  |
|  |  |  |  |  |  |  |  | Source of Funds | Budget Description | TOTAL |
| Detailed work plan and budget for the JP within this JPD | Prepare inception report |  |  |  |  | All UN agencies | Egyptian. partners | MDG-F Fund | Recruit consultants Hold workshops |  |
| Output 1.1 National Policy Reform for a more sustainable energy economy achieved Target: Perform a thorough economic and environmental analysis of the impact of the reduction and progressive phase out of energy subsidies by sector Draft a policy agenda and draft legal text for a national reform on both an energy subsidies reform and promoting of sustainable energy resources (energy efficiency and renewable energy 1. | Recruit an Energy Specialist to support the Technical Secretariat of the SEC Define Capacity Needs for Technical Secretariat |  |  |  |  | UNDP | Cabinet of Ministers | MDG-F Fund | National Consultant Equipment Agency Management Support | 52,000 3,000 4,400 |
|  | Prepare policy paper to support energy policy reform |  |  |  |  | UNDP | Cabinet of Ministers | MDG-F Fund | National Consultant International Consultant Agency Management Support | 18,000 5,000 1,840 |
|  | Initiate preparation of long term national energy strategies/policies |  |  |  |  | UNEP | Cabinet of Ministers | MDG-F Fund | National Consultant International Consultant Agency Management Support | 18,000 5,000 1,840 |
| Output 1.2 Expand CDM Markets Target: Identify new PINs and update CDM portfolio Increase number of registered CDM projects | Survey and identify new carbon finance opportunities and update CDM portfolio to include new projects in key sectors: |  |  |  |  | UNEP | EEAA | MDG-F Fund | National Consultant Agency Management Support | 2,000 160 |
|  | Survey and identify new carbon finance opportunities and update CDM portfolio to include new projects in key sectors: |  |  |  |  | UNIDO | EEAA | MDG-F Fund | National Consultant Agency Management Support | 2,500 200 |
|  | Survey and identify new carbon finance opportunities and update CDM portfolio to include new projects in key sectors |  |  |  |  | UNDP | EEAA | MDG-F Fund | National Consultant Agency Management Support | 2,000 160 |
|  | Support is provided for the development of technical documentation (i.e. PINs and PDDs) for identified projects |  |  |  |  | UNEP | EEAA | MDG-F Fund | National Consultant Agency Management Support | 7,000 560 |
|  | Support is provided for the development of technical documentation (i.e. PINs and PDDs) for identified projects |  |  |  |  | UNIDO | EEAA | MDG-F Fund | National Consultant International Consultant | 3,000 4,000 560 |
|  | Support is provided for the development of technical documentation (i.e. PINs and PDDs) for identified projects |  |  |  |  | UNDP | EEAA | MDG-F Fund | National Consultant Agency Management Support | 7,000 560 |
|  | Strengthen CDM Unit |  |  |  |  | UNEP | EEAA | MDG-F Fund | Training Agency Management Support | 2,000 160 |
|  | Provide hands-on training workshops to implement CDM and energy efficiency projects for policy makers, financial institutions, professional institutions and practitioners |  |  |  |  | UNEP | EEAA | MDG-F Fund | Training Workshops Agency Management Support | 3,000 240 |
|  | Provide hands-on training workshops to implement CDM and energy efficiency projects for policy makers, financial institutions, professional institutions and practitioners |  |  |  |  | UNIDO | EEAA | MDG-F Fund | Training Workshops Agency Management Support | 6,000 480 |
|  | Provide hands-on training workshops to implement CDM and energy efficiency projects for policy makers, financial institutions, professional institutions and practitioners |  |  |  |  | UNDP | EEAA | MDG-F Fund | Training Workshops Agency Management Support | 3,000 240 |
|  | Provide technical assistance to execute some CDM projects that were listed in the investment portfolio and approved by the DNA but in need of technical support |  |  |  |  | UNEP | EEAA | MDG-F Fund | National Consultant Agency Management Support | 3,000 240 |
|  | Provide technical assistance to execute some CDM projects that were listed in the investment portfolio and approved by the DNA but in need of technical support |  |  |  |  | UNDP | EEAA | MDG-F Fund | National Consultant Agency Management Support | 5,000 400 |
|  | Establish a CDM Industry Association |  |  |  |  | UNIDO | EEAA | MDG-F Fund | National Consultants International Consultants Training Workshop Equipment Agency Management Support | 1,200 5,000 3,000 2,000 896 |
|  | Implementation of pilot GHG reduction projects |  |  |  |  | UNEP | EEAA | MDG-F Fund | Sub-Contracts Agency Management Support | 48,300 3,864 |
|  | Implementation of pilot GHG reduction projects |  |  |  |  | UNIDO | EEAA | MDG-F Fund | Sub-Contracts Agency Management Support | 68,800 5,504 |
|  | Implementation of pilot GHG reduction projects |  |  |  |  | UNDP | EEAA | MDG-F Fund | Sub-Contracts Agency Management Support | 48,300 3,864 |
| Output 2.1: Adaptation strategies and practices integrated into climate-sensitive development policies, plans and programmes Target: A National Climate Change Adaptation Plan for the three targets sectors is developed Communication plan for increasing awareness on climate change is prepared Feasibility study and tendering documents for RCM |  |  |  |  |  |  |  |  |  |  |
|  | Adaptation needs and gaps for Integrated Coastal Zone Management assessed and identified |  |  |  |  | UNDP | MWRI | MDG-F Fund | National Consultants International Consultants Agency Management Support | 3,500 3,500 560 |
|  | Adaptation needs and gaps for water resources assessed and identified |  |  |  |  | UNDP | MWRI | MDG-F Fund | National Consultants International Consultants Agency Management Support | 2,000 4,000 480 |
|  | Integrate climate risk management measures into UN development programmes and operations |  |  |  |  | UNDP | EEAA | MDG-F Fund | National Consultants Agency Management Support | 2,000 160 |
|  | Prepare a communication strategy for raising awareness via various media channels |  |  |  |  | UNDP | EEAA | MDG-F Fund | National Consultants Agency Management Support | 7,000 560 |
|  | Adaptation needs and gaps for agriculture assessed and identified |  |  |  |  | FAO | MALR | MDG-F Fund | National Consultants International Consultants Training Transport Travel Equipment Supplies Misc Agency Management Support | 6,000 4,000 12,000 10,000 8,000 10,000 3,000 2,000 4,400 |
| Output 2.2: Pilot measures implemented and scaled up in support of adaptation mainstreaming and policymaking Target: Contract an international modelling center to adapt a RCM to River Nile Identify pilot locations and 3 field crop varieties to be tested and initiate cultivation Prepare a communication strategy for raising awareness on stress tolerant crops Identify pilot locations for testing optimal on farm water use | International tender for adaptation of RCM to River Nile |  |  |  |  | UNEP | MWRI | MDG-F Fund | Sub-Contract Agency Management Support | 100,000 8,000 |
|  | Establish and train a core group of specialist from MWRI and its relevant research institutes to use the models in assessing climate change impacts on water resources of Egypt Organize awareness workshops on climate change impacts and adaptation measures Collect data and information from different sources and establish a database for River Nile |  |  |  |  | UNESCO | MWRI | MDG-F Fund | National Consultants International Consultants Equipment Travel Training Supplies Misc. Agency Management Support | 70,000 30,000 10,000 3,000 17,000 3,000 2,000 10,800 |
|  | Organize joint workshops and seminars with Nilotec countries |  |  |  |  | UNESCO | MWRI | MDG-F Fund | Training Workshops Agency Management Support | 22,000 1,760 |
|  | Identify three pilot locations for developing stress tolerant crops Collect historical data on weather conditions, soil and water resources of the locations of the study Identify varieties of selected crops tolerant to heat, water, salinity stresses Identify crop varieties to be tested Initiate cultivation of selected crops |  |  |  |  | IFAD | MALR | MDG-F Fund | National Consultants International Consultants Transport Travel Equipment Supplies Misc Agency Management Support | 6,000 4,000 5,000 20,000 50,000 28,000 10,000 9,840 |
|  | Identify the stakeholders groups. Establish contacts with targeted stakeholders groups. Prepare targeted oriented information packages to different stakeholders groups Initiate preparation of a communication strategy |  |  |  |  | IFAD | MALR | MDG-F Fund | National Consultants International Consultants Travel Equipment Supplies Misc Agency Management Support | 4,000 2,000 5,000 22,000 5,000 2,000 3,200 |
|  | Study the trend of crop pattern changes through the last 25 years, and identify the key parameters and forces driving the annual changes in crop pattern Identify the current major crop pattern based on historical agricultural statistics. Study the trend of change in cultivated area by using remote sensing techniques Explore cropping pattern alternatives |  |  |  |  | IFAD | MALR | MDG-F Fund | National Consultants International Consultants Transport Travel Equipment Supplies Misc Agency Management Support | 6,000 4,000 1,000 10,000 22,000 3,000 4,000 4,000 |
|  | Collect historical data on weather conditions, soil and water resources of the locations of the study. Identify major field crops that will be studied under this investigation Identify 3 pilot locations for testing optimal use of on-farm water resources |  |  |  |  | FAO | MALR | MDG-F Fund | National Consultants International Consultants Training Transport Travel Equipment Supplies Misc Agency Management Support | 5,000 5,000 4,000 5,000 16,000 27,000 40,000 6,000 8,640 |

Annex B: Programme Monitoring Framework (PMF)

| Expected Results (Outcomes & outputs) | Indicators (with baselines & indicative timeframe) | Means of verification | Collection methods (with indicative time frame & frequency) | Responsibilities | Risks & assumptions |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Mainstreaming GHG Mitigation and CDM into National Policy and Expanding Access to Finance Frameworks Output 1.1: National policy reform for a more sustainable energy economy achieved Output 1.2: Expanded CDM Market | Indicators SEC decrees issued that mainstream GHG mitigation measures through energy efficiency and renewable energy Number of CDM projects registered Energy Intensity Per capita generation of CO2 Baseline: SEC activated with a mandate to reform national energy policies 36 PINs, 7 CDM projects, 2 upcoming CDM projects Per capita emissions of CO2 increased from1.5 ton to 1.8 ton between 1990 and 2003 (IEA 2006) Energy intensity declined from 1,784.2 ton/US$ to 1,663.1 ton/US$ between 1990 and 2002. Indicative time frame: 2008-2010 | Official and external audits to assess amount of GHG reduction and energy savings Expanded list of updated projects r least 3 CDM PDD in 3 sectors are registered through the programme an action plan for capacity building of DNA, with complete scheme for resources Evaluation reports | Official reports Annual, bi-annual and quarterly Progress reports Annual, bi-annual and quarterly, midterm and final M&E reports | UN agencies and Governmental partners | National policy priorities, where energy is one of them Avoid any conflict with other envisaged reforms (social, industrial |
| Outcome 2: Enhanced capacity to adapt to climate change Output 2.1: Adaptation strategies and practices integrated into climate-sensitive development policies, plans and programmes Output 2.2: Pilot measures implemented and scaled up in support of adaptation mainstreaming and policymaking | Indicators: A National Climate Change Adaptation Plan for the three targets sectors endorsed and adopted Successful adaptation and application of a RCM that is incorporated into the NBI Water Resources Management Programs, Projects as well as Decision Support Systems Number of stress tolerant varieties field crops Successful adoption of stress-tolerant crop varieties and proposed cropping patterns in selected locations Crop yield per unit volume of water for selected crops Baseline: A National Climate Change Committee established UNDP-GEF ongoing SNC Project is identifying vulnerabilities and adaptation need for the different Egyptian economic sectors Nile forecasting center of MWRI and its research institutes include hardware systems, hydrological and hydraulic models, data and high caliber professional staff Nile Ministerial Committee has approved the development of a Regional Circulation Model for the River Nile NBI is developing a Water Resources Management Model and a Decision Support System for River Nile A National Committee on climate change and agriculture has been established The Agricultural Research Center, Ministry of Agriculture constitute a research laboratory Indicative time frame: 2008-2010 | Progress reports RCM generated scenarios Supervision missions Evaluation reports | Official reports Annual, bi-annual and quarterly Progress reports Annual, bi-annual and quarterly, midterm and final M&E reports | UN agencies and Governmental partners | Risk associated with this outcome is: availability and reliability of data Limitations on available data to develop and calibrate the models Need to assure government strong commitment to the project activities and to ensure sustainability after the project is completed. |