JOINT PROGRAMME MONITORING REPORT

CULTURE AND DEVELOPMENT THEMATIC WINDOW

This report is due no more than 20 days following the end of the 2nd and 4thquarter. Please submit to the MDF-G Secretariat at: mdgf.secretariat@undp.org

Section 1: Identification and Joint Programme Status

- Joint Programme Identification and basic data

| Date of Submission: 9 February 2010 Submitted by: Name: Carlo Benedetti Title: Programme Management Specialist Organization: UNDP Contact information: carlo.benedetti@undp.org |  | Country and Thematic Window Albania, Culture and Development |
| --- | --- | --- |
| MDTF Atlas Project No: 67185 Title: Culture and Heritage for Social and Economic Development |  | Report Number: 2 Reporting Period: 1 January – 31 December 2009 Programme Duration: 30 months |
| Participating UN Organizations: UNESCO UNDP |  | Implementing partners Ministry of Culture, Tourism, Youth and Sports Ministry of Foreign Affairs Ministry of Education and Science National History Museum Institute of Monuments of Culture National Tourism Agency Municipality of Berat Municipality of Gjirokastra Administrative Office of Archaeological Park of Apollonia Administrative Office of Archaeological Park of Antigonea National Film Archive of Albania Tirana University World Federation of Tour Guide Associations Albanian Forum of Alliance of Civilizations (NGO) Albanian Artisan Association (NGO) |
|  |  | Gjirokastra Conservation and Development Office (NGO) |

| Estimated Budget Summary (USD) |
| --- |
| Total Approved Joint Programme Budget: | UNESCO: 1,393,150 UNDP: 1,866,850 Total: 3,260,000 |
| Total Amount of Transferred to date*: | UNESCO: 694,395 UNDP: 1,236,460 Total: 1,930,855 |
| Estimated Total Budget Committed to date*: | UNESCO: 433,180 UNDP: 841,943 Total: 1,275,123 |
| Estimated Total Budget Disbursed to date: | UNESCO: 193,877 UNDP: 603,962 Total: 797,839 |

* This includes 20,000 USD received as preparatory assistance and spent in 2007 by UNDP

Beneficiaries

Direct Beneficiaries

| Beneficiary type | No. Institutions | No. Women | No. Men | No. Ethnic Groups |
| --- | --- | --- | --- | --- |
| Policy makers | 4 | 9 | 8 | n/a |
| Staff of Culture management Inst/s | 12 | 10 | 20 | n/a |
| NGO/s | 3 | 10 | 15 | n/a |
| Total | 19 | 29 | 43 |  |

Indirect Beneficiaries

| Beneficiary type | No. Institutions | No. Women | No. Men | No. Ethnic Groups |
| --- | --- | --- | --- | --- |
| Private owners | n/a | 50 | 30 | n/a |
| Tourists | No data available | n/a | n/a | n/a |
| Communities nearby cultural sites | 2 | 100 | 90 | n/a |
| NGO/s | n/a | n/a | n/a | n/a |
| Total | 82 | 150 | 120 |  |

- Joint Programme M&E framework

| Expected Results (Outcomes & outputs) | Indicators (with baselines & indicative timeframe) | Means of verification | Collection methods (with indicative time frame & frequency) | Responsibilities | Risks & assumptions | Updated progress towards the achievement of proposed targets and indicators |
| --- | --- | --- | --- | --- | --- | --- |
| Joint Programme Outcome 1: A transparent and accountable government, developing and implementing effective national policies on culture and cultural-related issues |
| 1.1 Government mechanisms and/or instruments for protecting and preserving culture adhere to principles of good governance and offer improved services to citizens | Indicator: # of government mechanisms and/or instruments on culture improved to follow international standards of good governance Baseline: 6 UNESCO normative instruments on culture have been ratified by the Albanian Government Target: 3 government mechanisms and/or instruments on culture are improved to follow international standards of good governance by 2010 | New Minister’s Orders are signed by the Minister of MoTCYS or the respective Ministry or are passed before the appropriate governing board in Government. Consultants will follow up on the final version of the legal instruments to ensure they are at international standards and in the spirit of global partnership | Follow-up with Director of Cultural Heritage and Tourism Development at the MoTCYS via phone calls or short meetings every month after each consultancy mission. | UNDP (Fiscal/financial mechanisms and policy support) UNESCO (Implementation of int’l conventions on culture) | Medium risk - passing new legislation or legal instruments may involve other unforeseen Government bodies and the process may not be as straightforward as anticipated. The replacement of staff following the general elections may affect the implementation process. | 2 The MoCTYS revised their internal structure to create necessary units dealing with UNESCO conventions and the national action plan on UNESCO’s conventions is being revised |
| 1.2 New ideas to conserve and protect cultural monuments are shared with local communities, civil society and the private sector. | Indicator: # of owners of cultural monuments are better informed on the opportunities to restore their properties Baseline: Partial information is available on the MoTCYS website Target: 60 owners of cultural monuments are better informed on the opportunities to restore their properties by 2010 | Civil society NGO that is hired to administer the public meetings will be required to work with MoTCYS to identify owners of cultural monuments and encourage them to attend the seminars | NGO documents how many owners of cultural monuments are in attendance at public meetings | UNESCO (Architectural Competition) UNDP (How-to seminars) | High risk – Insufficient number of applications can be addressed by advertising the competition well; offer a substantial reward to interest architects and students and intensive outreaching activity. Difficult consensus on the final objects | 0 The architectural competition will take place in the first quarter of 2010; owners of cultural monuments will be involved in public information activities thereinafter |
| 1.3 Government strategies and action plans on culture and related sectors benefit from new data gathered and interpreted | Indicator: Quality and quantity of baseline indicators used in government strategies and action plans on culture and related sectors Baseline: Draft Culture strategy makes no reference to baseline indicators; tourism strategy makes strong reference to both internal and external indicators Target: Government strategies and action plans on culture and related sectors are improved with more and better-informed baseline indicators by 2009 | Draft strategy is revised and Baseline information is incorporated into Culture Strategy and information in Tourism Strategy is augmented | Follow up with MoTCYS counterparts to ensure changes have been made to both strategies. | UNDP | Medium risk – The entire draft strategy has to be revised after the unforeseen rejection by the CoM. In the mean time the Government has already committed to incorporating data collected under this programme of activities into its existing and forthcoming strategies and action plans on culture and tourism. | Revision of draft strategy on culture is ongoing; it will be finalized in the second quarter of 2010 and will include baseline indicators The original indicator was based on the assumption that the strategy on culture would have been in place. Unfortunately, this was not the case and the JP supported the Government not only in developing indicators, but also in the –redrafting of the strategy itself |
| Joint Programme Outcome 2: An enabling environment is in place to ensure people’s access to cultural heritage and participation in cultural heritage decision-making at the local, regional and national levels |
| 2.1 National History Museum is transformed into a modern cultural institution at international standards of governance, management, documentation, presentation, conservation and security | Indicator: quality of visitor experience improved through targeted actions undertaken in conformity with the Museum’s approved strategic guidelines Baseline: to be determined from visitor satisfaction survey in museum Target: Substantial improvement of the quality of visitor experience inside museum by 2010 | Undertake a visitor satisfaction survey in summer 2008, before any transformative activities have taken place; repeat survey in summer 2010 | Questionnaires will be completed individually and turned in to a collection box in the Museum; results will be tabulated by Museum staff in collaboration with joint programme interns | UNESCO (Governance structure and operational plans) UNDP (Physical rehabilitation of museum space) | High risk – unexpected presence of asbestos and electric central station in the basement and elsewhere may delay the entire decision making on NHM. Political changes resulting in replacement of the decision makers at the Ministry and NHM level also may delay the process. | Quality of visitor experience unchanged A preliminary baseline was developed through a test visitor survey and revealed that 70% of visitors was neutral/negative about the quality information available in the museum A more comprehensive baseline will be developed after a full survey is conducted in the second quarter of 2010 Two studies on NHM structure and asbestos’ presence have been conducted in 2009 making it possible to plan and implement future physical interventions A new management structure for NHM was developed and agreed upon and will result in improved management practices in the future |
| 2.2 Albania's archaeological park system upgraded to better safeguard Albania's cultural heritage and ensure environmental sustainability | Indicator: # of measures taken to better protect and preserve Albania’s archaeological parks and their surrounding environments Baseline: Few measures in place to protect Apollonia and Antigonea archaeological parks from vandalism and visitor impact Target: 5 measures taken to better protect and preserve Albania’s archaeological parks and their surrounding environments by 2010 | Follow-up with Director of Cultural Heritage and Tourism Development at the MoTCYS, directors of archaeological parks, director of Institute of Cultural Monuments | In-situ meetings every two months after targeted interventions are be identified in cooperation with MoTCYS and implemented | UNESCO | Low to medium risk – project activities are supported by all stakeholders so limited political risk; minor implementation risk due to parks being scattered around the Albanian countryside and may be difficult to reach on a regular basis. | 1 A new road is being constructed leading to the Antigonea archeological park Two plans for physical interventions have been developed to mitigate risks in the two archeological parks and are being endorsed by the National Council of Restoration |
| 2.3 Albanian film archives are digitalized and preserved for future generations | Indicator: # of Albanian films digitized, stored in a publicly-accessible venue. 35 mm films are screened for the public. Baseline: 100 films are digitalized and none are stored in a publicly-accessible venue. Cinema hall of the National Fim Archive is up (with MoCTYS budget) not running due to lack of necessary equipment. Target: 3000 films are digitalized and stored in a publicly-accessible venue by 2010 | Action plan for digitization. Follow-up with the Director of Cinema. | Short meetings (1/month) and periodical reporting on activities executed (every two months) | UNESCO | No risk. | 613 documentary films 224 Chronicles 66 animation movies around 1000 artistic movies No film have been screened yet, but a 35 mm projector was purchased for the NFA |

| Joint Programme Outcome 3: Increased capacities to manage, preserve and present cultural heritage and cultural industries in an efficient, transparent, accountable and equitable manner |
| --- |
| 3.1 Skill level of staff employed at cultural sites is improved in cultural heritage management, conservation, and protection | Indicator: # of staff employed at cultural sites trained in cultural heritage management, conservation, and protection Baseline: New Center for the Restoration of Cultural Monuments opened and courses on restoration begun in December 2007 Target: 80 people trained on cultural heritage management, conservation and protection by 2010 | Staff at cultural sites perform a self-assessment to determine educational and vocational training needs; international experts and trainers also perform pre- and post-assessments as part of their terms of reference | Follow-up with Director of Cultural Heritage and Tourism Development at the MoTCYS, as well as with directors of archaeological parks; final reports of international experts and trainers hired to run courses. | UNESCO | Low to medium risk – availability of staff is to be assured by directors of cultural sites. | 11 Training for NHM management based on a report on training needs |
| 3.2 Formal training and credentials available to cultural professionals | Indicator: # accredited MA-level courses in Arts and Cultural Resource management are in place Baseline: No programs currently available in Albania Target: One accredited MA-level course in Arts and Cultural Resource Management is in place by 2010 | Accreditation papers from Ministry of Education are finalized | Follow-up with Ministry of Education on a semi-annual basis | UNDP (Training of cultural tourist guides) UNESCO (MA-level program) | Medium to high risk - Unforeseen difficulties may arise in getting courses accredited by the Ministry of Education and Science. Possible pressure coming from implementing partners and interested stakeholders. | 1 MA level course on Cultural Resource management is being set up at the University of Tirana Ongoing approval process for a second Degree programme on Tour Guide education and training |

| Joint Programme Outcome 4: An increased role of cultural heritage in social and economic opportunities and in engaging community participation in regional and local development strategies |
| --- |
| 4.1 Quality of visitor experience improved at cultural heritage sites | Indicator: Improved accessibility of visitor information at cultural sites Baseline: Minimal signage and access to visitor information available in cultural sites Target: Improved quantity and accessibility of visitor information at cultural sites by 2010 | Perform pre- and post-assessments of the cultural sites to be improved; combine with information on any visitor surveys performed at these sites | Follow up with the local focal points at each cultural site; examine results from any visitor surveys used | UNDP (Cultural cities) UNESCO (Archaeological parks) | No risk. | Visitor information at cultural sites was improved In Berat a new Tourism information office was set up; Cultural heritage signage was developed and installed in Berat; A visitor information map of Antigonea archeological park (Gjirokaster area) was developed and produced in 2000 copies |
| 4.2 Albanian artists and artisans are accessing new markets | Indicator: # of artists and artisans able to access international or foreign markets Baseline: Access to international or foreign markets is randomly organized and limited to roadside vendors selling to tourists Target: 30 artists or artisans are able to access new markets by 2010 | Take a baseline of how many artists and artisans who know how to access foreign markets | Ask artists and artisans in training seminars how to access international markets and train them where the knowledge gaps are | UNDP | Low risk – information presented in seminars may not be equally applicable to all types of artistic and artisanal products | 3 Representatives of artisans and artisans’ organizations participated in an international fair; Artists’ and artisans’ products selling points are being set up in Shkodra, Berat, Gjirokaster and will enable at least 30 artisans to have increased access to national and international tourists |
| Joint Programme Outcome 5: A contribution to the National Strategy of the Alliance of Civilization and an increased awareness of Albania’s cultural heritage internationally as a means to promote cultural understanding and religious tolerance |
| 5.1 Increased participation of Albania in global dialogue for cross-cultural and religious understanding | Indicator: # of Alliance of Civilization projects and activities that Albania sponsors or participates in Baseline: Albania has participated in the first Alliance of Civilizations forum, January 2008 Target: Implementation of the National Strategy of the AoC underway by 2010 | Tally total number of global, regional, national and local AoC events that Albania sponsors or participates in | Monitored on an annual basis. | UNESCO | Low risk – goal may be too ambitious for national AoC council to coordinate | 4 Implementation of the National AoC strategy is being supported through two activites (rapid media response mechanism established; textbook revisions ongoing) and by supporting the AoC National Coordinator in attending two AoC international conferences Drafting of a National Cultural Marketing strategy, including marketing tools, is underway; |

- Joint Programme Results Framework with financial information

Please note: to harmonize differing financial reporting rules among participating organizations, throughout this report “committed” funds amount include both disbursed and undisbursed funds. Therefore, the delivery rate is calculated as committed amounts over planned amounts.

|  |  | JP output: 1.1: f. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 |  | NATIONAL/LOCAL | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
|  | Preparatory Assistance |  |  | UNDP (2007) |  | MDG-F | International consultancy | 20,000 | 15,109 | 15,109 |  |
| Output 1.1 Culture is treated as an integral part of national Government strategy, rather than an isolated sector strategy | 1.1.1 Develop new fiscal and financial mechanisms to increase private sector investment and civil society involvement in support of culture and cultural heritage protection, investment and presentation, such as concessions, tax incentives, and PPPs, among others | X | X | UNDP | MoCTYS | MDG-F | International consultant Local Consultant Travel Misc FA | 8,000 3,000 4,500 500 1,400 | 0 1,963 0 500 83 | - 1,963 0 500 83 | 14% |
|  | 1.1.2 Support national authorities on the implementation of UNESCO Conventions of 2003 and 2005 | X | X | UNESCO | MoCTYS | MDG-F | Int’l experts /consultants Subcontracts Travel Misc F/A | 11,000 6,000 6,000 830 1,670 | 5,985 6,139 2,500 0 1,024 | 0 6,139 2,500 0 605.73 | 61% |
|  | 1.1.3. Policy support and programme management, including coordination between UN agencies, implementing partners, and other relevant stakeholders | X | X | UNDP | UNDP | MDG-F | Programme Coordinator Support staff Equipment Travel Communication Misc F/A | 150,000 30,000 15,000 5,000 7,000 2,300 14,660 | 163,002 32,864 37,000 5,011 10,495 6,851 8,627 | 163,002 31,664 37,000 5,011 10,495 6,851 8,586 | 118%% |
| Total | 286,860 | 297,152 | 289,508 | 104% |

|  |  | JP output: 1.2: b. between 31%-50% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 |  | NATIONAL/LOCAL | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Private owners of cultural monuments are given increased opportunities to conserve and protect their properties | 1.2.1 Architectural Competition on new uses for historic structures to protect them through investment and higher valued use | X |  | UNESCO | MoCTYS - IoCM | MDG-F | National professional contracts Subcontracts Travel Misc F/A | 18,000 25,000 54,000 2,000 1,000 7,000 | 15,831 24,064 20,604 313 143 4,267 | 15,463 20,064 11,084 313 143 3,295 | 61% |
|  | 1.2.2 Work with civil society to hold public seminars on how to transform historic buildings and other cultural heritage into local enterprises (funding, business models, etc) and publish “accompanying “how-to” document |  | X | UNDP | IoCM | MDG-F | Local Consultant Travel Publications Misc F/A | 12,000 9,000 3,500 500 1,750 |  |  | 0% |
| Total l | 133,750 | 65,222 | 50,362 | 49% |

|  |  | JP output: 1.3: f. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 |  | NATIONAL/LOCAL | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Gov strategies and action plans on culture and related sectors benefiting from new data gathered and interpreted | 1.3.1 Gather and interpret data and statistics necessary to establish baseline indicators for the implementation of the Culture Strategy and related Action Plans | X | X | UNDP | MoCTYS | MDG-F | Graduate Internship Travel Misc F/A | 5,000 4,500 500 700 | 13,750 1,500 250 524 | 2,200 1,461 250 132 | 149% |
| Total | 10,700 | 16,024 | 4,043 | 149% |

|  |  | JP output: 2.1: b. between 31%-50% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 |  | NATIONAL/LOCAL | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 2.1 National History Museum is transformed into a modern cultural institution at international standards of governance, management, documentation, presentation, conservation and security | 2.1.1 Establish a management and governance structure for a “world-class” National History Museum | X |  | UNESCO | MoCTYS - NHM | MDG-F | Subcontracts Travel Misc F/A | 22,000 2,500 500 1,750 | 21,324 2,195 338 1,670 | 15,059 2,195 307 1,229 | 95% |
|  | 2.1.2 Create operational or action plans for National History Museum in Tirana to meet international standards of documentation, conservation, security, and presentation | X |  | UNESCO | MoCTYS - NHM | MDG-F | International experts /consultants National professional contracts Travel Misc F/A | 75,000 19,000 5,000 1,000 7,000 | 63,012 1,000 4,807 0 4,817 | 42,303 0 4,807 0 3,298 | 69% |
|  | 2.1.3 Execution of activities that are in conformity with the Museum’s approved strategic guidelines that will make a substantial improvement to the visitor experience inside the Museum | X | X | UNDP | MoCTYS - NHM | MDG-F | Local Consultant Contractual Services Equipment/Supplies Misc F/A | 30,000 325,000 110,000 2,280 32,720 | 1,100 151,108 0 2,426 5,227 | 1,100 119,781 0 2,426 4168 | 31% |
| Total | 633,750 | 259,024 | 196,673 | 41% |

|  |  | JP output: 2.2: c. between 51%-60% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 |  | NATIONAL/LOCAL | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 2.2 Albania's archaeological park system upgraded to better safeguard Albania's cultural heritage related as an integral part of national Government strategy, rather than an isolated sector strategy | 2.2.1 Assessment of fiscal, management and governance structure of archaeological parks performed and recommendations shared with GoA and stakeholders | X |  | UNESCO | MoCTYS – Arch. Parks | MDG-F | International experts /consultants National professional contracts Travel Misc F/A | 10,000 6,000 3,000 1,000 1,400 | 11,000 6,422 4,100 1,000 1,577 | 7,420 0 242 0 536 | 113% |
|  | 2.2.2 Improve security and mitigate risk at Antigonea and Apollonia archaeological parks through creation and implementation of risk management plans | X |  | UNESCO | MoCTYS – Arch. Parks | MDG-F | International experts /consultants Subcontracts Misc F/A | 12,000 32,000 1,000 3,150 | 5,000 6,000 90 776 | 3,956 5,000 0 627 | 25% |
| Total | 69,550 | 35,695 | 17,781 | 52% |

|  |  | JP output: 2.3:f. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 |  | NATIONAL/LOCAL | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 2.3 Albanian film archives are digitalized and preserved for future generations treated as an integral part of national Government strategy, rather than an isolated sector strategy | 2.3.1 Albania’s film industry documented, digitalized and archived | X |  | UNESCO | National Film Archive (MoCTYS) | MDG-F | Subcontracts Equipment Misc F/A | 13,000 32,000 1,000 3,220 | 8,769 58,726 0 4,725 | 0 5,859 0 410 | 147% |
| Total | 49,220 | 72,220 | 6,269 | 147% |

|  |  | JP output: 3.1: b. between 31%-50% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 |  | NATIONAL/LOCAL | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 3.1 Staff employed at cultural sites are trained in cultural heritage management, conservation, and protection | 3.1.1 Two courses offered to train museum and archaeological park staff on best practices in cultural heritage management | X |  | UNESCO | MoCTYS , NHM & two Arch parks staff; | MDG-F | Support staff Training Travel Misc F/A | 25,000 15,000 1,000 4,000 3,150 | 23,500 1,325 0 3,076 1,953 | 19,487 0 0 3,076 1,579 | 62% |
|  | 3.1.2 Tailored programme to train state employees in conservation practices, security procedures, and risk management; programme will be offered in 2 courses | X |  | UNESCO | MoCTYS , NHM & two Arch parks staff; | MDG-F | Training Travel Misc F/A | 22,000 7,000 1,000 2,100 | 0 2,000 0 140 | 0 1,000 0 70 | 7% |
| Total | 80,250 | 31,994 | 25,212 | 40% |

|  |  | JP output: 3.2: b. between 31%-50% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 |  | NATIONAL/LOCAL | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 3.2 Formal training and credentials available to cultural professionals | 3.2.1 Curriculum developed and approved for tourist guides at cultural sites and monuments | X | X | UNDP | MoCTYS/University of Tirana | MDG-F | Local Consultant Contractual services Misc F/A | 4,000 25,000 1,000 2,100 | - 16,299 842 579 | - 16,299 842 579 | 55% |
|  | 3.2.2 New MA-level program in Arts and Cultural Resource Management designed and accredited | X |  | UNESCO | MoES; Tirana University (public) | MDG-F | Subcontracts Travel Misc F/A | 45,000 4,000 1,000 3,500 | 12,025 0 0 842 | 9,700 0 0 679 | 24% |
| Total | 85,600 | 30,587 | 28,099 | 36% |

|  |  | JP output: 4.1: d. between 61%-70% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 |  | NATIONAL/LOCAL | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 4.1 Quality of visitor experience improved at cultural heritage sites | 4.1.1 Visitor information improved in the cultural heritage cities of Berat and Gjirokastra through the creation and support to tourist information centers and increased visitor signage | X |  | UNDP | MoCTYS; Municipalities of Berat and Gjirokastra | MDG-F | Local Consultant Contractual services Equipment/Supplies Travel Misc F/A | 10,000 25,000 51,000 2,000 2,000 6,300 | 21,000 22,120 13,690 3,467 3,972 2,172 | 19,642 22,120 13,690 3,467 3,972 2,126 | 67% |
|  | 4.1.2 Access to visitor information improved at Antigonea and Apollonia archaeological parks through signage, informational pamphlets and creation of visitor kiosks where appropriate | X | X | UNESCO | MoCTYS; mgmt staff of the two Arch. Parks; IMC Inst. Archaeology. | MDG-F | Subcontracts Equipment Travel Misc F/A | 6,000 15,500 2,500 1,000 1,750 | 2,417 2,950 1,593 1,762 611 | 1,801 1,929 290 0 281 | 35% |
| Total | 123,050 | 75,753 | 69,318 | 62% |

|  |  | JP output: 4.2: f. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 |  | NATIONAL/LOCAL | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 4.2 Albanian artists and artisans are accessing new markets | 4.2.1 Support the creation of artisan centers, fairs and business incubators in Gjirokastra, Shkodra, Korce and Berat | X | X | UNDP | MoCTYS; Municipalities; artisan associations | MDG-F | National project Manager Contractual Services Equipment/Supplies Travel Misc F/A | 30,000 18,000 20,000 10,000 1,020 5,530 | 43,033 42,140 8,188 491 1,718 3,240 | 23,875 16,603 8,188 491 1,718 1,725 | 116% |
|  | 4.2.2 Train artisans in business planning/marketing activities, with special emphasis on gender equality and the empowerment of women |  | X | UNDP | MoCTYS; Municipalities; artisan associations | MDG-F | Contractual Service Travel Misc F/A | 11,000 3,000 1,000 1,050 |  |  | 0% |
| Total | 100,600 | 98,810 | 52,600 | 98% |

|  |  | JP output: 5.1: f. More than 80% |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 |  | NATIONAL/LOCAL | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 5.1 Increased awareness of Albania’s cultural heritage by foreigners reated as an integral part of national Government strategy, rather than an isolated sector strategy | 5.1.1 Support Albania’s strategic process in the Alliance of Civilizations through the development of its National Strategy of the AoC | X | X | UNESCO | MoFA AFALC (NGO) ICT (under MoES) | MDG-F | Subcontracts Travel Misc F/A | 100,000 35,000 4,135 9,740 | 82,016 2,815 0 5,938 | 0 1,056 0 74 | 61% |
|  | 5.1.2 Support to the development and implementation of a cultural marketing strategy to strengthen Albania’s image abroad | × | x | UNDP | NTA | MDG-F | Local Consultant Contractual Services Printing Production Travel Misc F/A | 10,000 75,000 15,000 20,000 2,500 8,575 | 2,078 175,000 5,470 9,926 2,500 6,629 | 2,078 35,000 5,470 9,926 2,500 1,869 | 153% |
|  | 5.1.3 Support to MoFA strategic efforts for cultural diplomacy |  | X | UNDP | MoFA | MDG-F | Contractual Services Misc F/A | 21,500 1,000 1,575 |  |  | 0% |
|  | 5.1.4 Training of MoFA and/or embassy staff to fulfil the function of cultural attaches |  | X | UNDP | MoFA | MDG-F | International Consultant Local Consultant Contractual Services Travel Misc F/A | 20,000 10,000 15,000 4,000 1,000 3,500 |  | - | 0% |
| Total | 357,525 | 292,372 | 57,973 | 82% |
| Grand Total (UNESCO) | 694,395 | 433,180 | 193,877 | 62% |
| Grand Total (UNDP) | 1,236,460 | 841,943 | 603,962 | 68% |
| Grand Total | 1,930,855 | 1,275,123 | 797,839 | 66% |

Section II: Joint Programme Progress

- Narrative on progress, obstacles and contingency measures

Progress in outcomes:

- A transparent and accountable government, developing and implementing effective national policies on culture and culture-related issues.

Albania’s fiscal and financial policies in support of cultural heritage as well as the overall national Culture Strategy have progressed and the Government, with strong support from the JP, is developing them through broad consultations. The work with civil society has been progressing at a slower pace and is expected to accelerate in the next year.

Structures within the Ministry of Tourism, Culture, Youth and Sports have been revised to better address the issues related to cultural heritage and cultural diversity and are regulated by the two UNESCO Conventions. Groups of experts have also been formed on the various topics within the Ministry.

- An enabling environment is in place to ensure people’s access to cultural heritage and participation in cultural heritage decision-making at the local, regional and national levels.

In 2009, progress with regard to this outcome has picked up substantially. National level physical and governance structures are being redesigned to ensure wider participation and easier public access. The National History Museum (NHM) in Tirana, a flagship activity for the JP, is a clear example. Regional and local level governance structures are also being analysed from a participatory perspective and will benefit from recommendations for improvements in the coming months. Physical access to cultural heritage is also being improved through the digitalization of the country’s film heritage, and the forthcoming improvements to the infrastructure of the NHM and Apollonia and Antigonea Archaeological Parks will enable people to better access and participate in the cultural heritage of the country.

- Increased capacities to manage, preserve and present cultural heritage and cultural industries in an efficient, transparent, accountable and equitable manner.

Preparations for the training and capacity development of the next generation of cultural heritage tour guiding professionals have been carried out. The curriculum for an MA level program on cultural resource management has been prepared and will be presented to the Ministry of Education by the University of Tirana for endorsement in January / February. Graduates of this new programme will be equipped with the knowledge and skills necessary for sustainable management of Albania’s cultural resources, thus contributing towards shaping the future managers of the cultural heritage in Albania.

- An increased role of cultural heritage in social and economic opportunities and in engaging community participation in regional and local development strategies.

Necessary conditions for cultural heritage to create economic and social opportunities have been ensured in various cultural cities with the improvement of visitor information facilities. Improvements to the visitor infrastructure (including access to information) in archaeological parks are also currently underway, strengthening the ability of these cultural attractions to attract more visitors, which in turn will create a greater need and variety of economic and social opportunities within the tourism sector.

- A contribution to the National Strategy of the Alliance of Civilization and an increased awareness of Albania’s cultural heritage internationally as a means to promote cultural understanding and religious tolerance.

Structures have been set up in support of the AoC national strategy. A number of mini-project contributing to various aspects of the National Strategy on the AoC have been supported, such as a Rapid Response Media Mechanism, designed to quickly respond to any emerging issues of cultural or religious conflicts in the Media. Activities such as these provide the basis on which the country can be promoted as a positive example of cultural understanding and religious tolerance.

Work has just started on increasing awareness of Albania’s cultural heritage internationally as this aspect of the outcome has progressed slowly.

Progress in outputs:

  - Government mechanisms and/or instruments for protecting and preserving culture adhere to principles of good governance and offer improved services to citizens:

A background study on fiscal mechanisms related to cultural heritage and cultural heritage revenue management has been completed by the JP. An international consultant is being recruited for the final fiscal policy document containing recommendations on how the system should be revised is being recruited.

The MoCTYS set up a new structure to tackle issues related to the two UNESCO Conventions. UNESCO has printed a set of brochures on the 2005 UNESCO Convention on “Protection and Promotion of Diversity of Cultural Expressions” in Albanian as a useful tool for the awareness raising activities carried out by MoCTYS. A concrete action plan for the further implementation of activities in support of the two Conventions has been thoroughly discussed and endorsed by the MoCTYS with the support of the JP/UNESCO consultant.

  - New ideas to conserve and protect cultural monuments are shared with local communities, civil society and the private sector

Preparations for the launch of the Architectural Competition have been delayed due to a lengthy consensus building process between various stakeholders on which cultural/historical objects the JP should address. Once the historical objects were selected, putting together technical dossiers for each one of them also proved to be a complex process due to the limited availability of information and documents accessible in the historical archives.

  - Government strategies and action plans on culture and related sectors benefiting from new data gathered and interpreted

A draft Culture Strategy is being revised and equipped with cultural indicators and overall recommendations for strategy finalization have been approved with technical support from the JP.

2.1 National History Museum is transformed into a modern cultural institution at international standards   of governance, management, documentation, presentation, conservation and security

An International Advisory Board of the National History Museum has been established by the JP and has convened on a quarterly basis to produce, discuss and endorse four basic NHM related documents were produced: (1)Recommendations on the NHM Governance and Structure; (2) The NHM Background study; (3) The NHM Needs Assessment Report and (4) NHM Overall Concept Note. These four documents have been drafted and finalized. Upon the review and approval of the Ministry, the recommendations will form the basis for eventual changes within NHM management, governance structure, operational plans, and physical improvements to the visitor experience which the government intends to carry out in the first half of 2010.

During the review of the existing situation of the NHM, the JP and the government discovered the presence of asbestos in the building. On the recommendation of the Advisory Board the JP was asked to prepare assessment to determine the presence of asbestos presence and an assessment on the structural stability of the NHM building. These were finalized by the JP and international consultants providing recommendations on the way forward.

  - Albania's archaeological park system upgraded to better safeguard Albania's cultural heritage and ensure environmental sustainability

The national and international consultants have conducted two missions and several meetings/site visits in Albania to prepare: (1) a background study on the Archaeological Park System in Albania which has been finalized; and (2) an assessment of the fiscal management and governance of the Archaeological Park system in Albania which is to be finalized in February 2010.

The international and national consultants have also prepared the draft reports on the immediate interventions to mitigate risks in the Apollonia and Antigonea archaeological parks. The draft reports will be shared with local stakeholders for their feedback and further inputs before the final recommendations are presented to the relevant and responsible authorities. Recommendations from these studies will enable the authorities to better protect archaeological heritage and promote sustainable tourism development. A map guide on the park of Antigonea was also produced for distribution by the park. Technical proposals for risk mitigation interventions are currently being drafted for submission and approval by the National Council of Restorations.

  - Albanian film archives are digitalized and preserved for future generations

At the request of the National Film Archive (NFA) and with the approval of the PMC, the JP provided the NFA with a 35 mm film projector and related sound equipment, as well as a film storage server for the films being digitalized. These contributions will enable NFA to fulfill their mission to make Albania’s cinematic heritage more accessible to its citizenry.

3.1 Skill level of staff employed at cultural sites is improved in cultural heritage management, conservation, and protection

The JP carried out preliminary efforts to arrange a comprehensive training for the staff of the archaeological parks on cultural heritage management, conservation and protection. Contact with institutions in Italy have been initiated and will now be revised and finalized in light of the recent recommendations of the international and national consultants working on this and other component to ensure that there is a streamlined approach to training and capacity building. The JP also undertook a preliminary assessment in December to evaluate the specific skills training needs of the staff at the National History Museum in order to ensure that existing staff will be fully prepared to take on potential new roles in the newly envisaged organigram of the institution.

  - Formal training and credentials available to cultural professionals

A tour guide training course has formally been approved by line ministries and Tirana University. The curriculum was revised and finalized with the support of  international expertise provided by the JP.

A background feasibility study on the establishment of the MA program on Cultural Resource Management has been finalized and the Department of History and Philology within the University of Tirana, a state-run institution, has been identified as the host institution for the course. Preliminary negotiations revealed the full support of the local counterpart. The curriculum is being finalized with courses expected to start in the coming academic year.

  - Quality of visitor experience improved at cultural heritage sites

Cultural heritage signage has been successfully installed in the World Heritage City of Berat by the JP and the tourism Information Office in Berat has been renovated and equipped, with the support o fteh JP, in order to offer professional assistance to the city’s visitors. The same interventions are currently under way in the other World heritage city of Gjirokoaster.

Tourist map guides are being produced for the cities of Berat and Gjirokaster. The tourist map guide for Antigonea has been produced through a highly participatory process and 2000 copies were printed and a distribution plan is being finalized.

The comprehensive technical proposal on upgrading the visitor’s access (i.e. the signage system) for Antigonea and Apollonia is being drafted for submission and approval by the National Council of Restorations.

  - Albanian artists and artisans are accessing new markets

A national artisan conference has been organized in order to orient and inform artisan training needs. Artisans from around the country participated and were informed on the state of the art in artisan self-promotion and design.

Restoration work has started on a second category cultural monument in Gjirokastra that will serve as an artisan incubator for the city.

Artisan selling points are being set up in the cities of Shkoder and Berat. In Shkoder, a broad participatory process with artisans from the town was carried out to finalize the design of the selling point. The selling point is located within the Shkoder castle and, therefore, a thorough review was conducted to ensure that the renovations are in line with conservation standards and guidelines. In Berat, the selling point will be located within a public structure managed by the municipality.

  - Increased participation of Albania in global dialogue for cross-cultural and religious understanding

In support of the Alliance of Civilization (AoC) national strategy, a ‘Rapid Media Response mechanism’ has been established by the Albanian Forum for the Alliance of Civilizations (AFALC NGO) with JP support to monitor and respond to public debates on intercultural issues. AFALC will monitor the national media and ensure that coverage of intercultural issues is balanced and correct. It will also build the capacities of journalists and opinion makers on such topics through a series of trainings and national conferences.

A second partnership has been established with the Institute of Curriculum and Training for the revision of the history and geography textbooks in the spirit of the AoC strategy. The Institute, part of the MoCTYS, is mandated to issues guidelines for authors and publishing houses on text books. It is also in charge of the pre-university teacher training policies and instruments. New guidelines will mainstream the issues of intercultural issues and promote diversity.

A background assessment on Albania’s cultural marketing efforts has been completed. The implementation of a one year contract for the development of Albania’s cultural marketing strategy and action plan by an international contractor has started. A draft cultural marketing strategy will be prepared in the coming months and verified through a participatory process supported by the JP.

The MOFA has prepared a concept note in relation to their needs for support on cultural diplomacy. On that basis, the JP has established a partnership with the Spanish MOFA which will support its Albanian counterparts by providing targeted trainings and share experiences on successful cultural diplomacy abroad.

Are there difficulties in the implementation?  Yes No

If so, what are the causes of these difficulties? Please check the most suitable option

UN agency Coordination

Coordination with Government

Coordination within the Government (s)

Administrative (Procurement, etc) /Financial (management of funds, availability, budget revision, etc)

Management: 1. Activity and output management 2. Governance/Decision making (PMC/NSC) 3. Accountability

Joint Programme design

External to the Joint Programme (risks and assumptions, elections, natural disaster, social unrest, etc)

Other:  Refer to paragraph No.5 in the following subsection.

Please, briefly describe the current difficulties the Joint Programme is facing. Refer only to progress in relation to the planned in the Joint Programme Document. Try to describe facts avoiding interpretations or personal opinions.

Please, briefly describe the current external difficulties (not caused by the joint programme) that delay implementation. Try to describe facts avoiding interpretations or personal opinions.

Please, briefly explain (150 words) the actions planned to eliminate or mitigate the difficulties (internal and external) described in the previous text boxes. Try to be specific in your answer.

- Inter-Agency Coordination and Delivering as One

- Is the Joint Programme in line with the UNDAF? Please check the relevant answer

Yes No

- If not, does the Joint Programme fit into the national strategies?

Yes No

If not, please explain:

What types of coordination mechanisms and decisions have been taken to ensure joint delivery?

Are different joint programmes in the country coordinating among themselves? Please reflect on these questions above and add any other relevant comments if you consider it necessary:

Please provide the values for each category of the indicator table described below:

| Indicators | Baseline | Actual Value | Means of Verification | Collection methods |
| --- | --- | --- | --- | --- |
| Number of managerial practices (financial, procurement, etc) implemented jointly by the UN implementing agencies for MDG-F JPs. | No jointly implemented managerial practices | One joint procurement is ongoing | Internal reporting system | Internal meetings |
| Number of joint analytical work (studies, diagnostic) undertaken jointly by UN implementing agencies for MDG-F JPs. | No joint analytical work in place | No joint analytical work in place | Internal reporting system | Internal meetings |
| Number of joint missions undertaken jointly by UN implementing agencies for MDG-F JPs. | No joint mission | 6 | Internal reporting system | Internal meetings |

Please, provide additional information to substantiate the indicators value (150 words). Try to describe qualitative and quantitative facts avoiding interpretations or personal opinions.

- Development Effectiveness: Paris Declaration and Accra Agenda for Action

Are governments and other national implementation partners involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities is the government involved? Please check the relevant answer

Policy/decision making

Management:  budget procurement service provision

other: The Government sits on the PMC where decisions at both a policy and management level are taken on specific  activities. For example, the Government has requested a certain implementation modality in a given activity providing strong leadership for the JP.

Are civil society and/or the private sector involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities are they involved? Please check the relevant answer

Policy/decision making

Management:  budget procurement service provision

other, specify

Are citizens involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities are citizens involved? Please check the relevant answer

Policy/decision making

Management:  budget procurement service provision

other: Citizens are involved as users of cultural heritage

Where is the joint programme management unit seated?

National Government  Local Government UN Agency By itself other, specify

| Indicators | Baseline | Actual Value | Means of Verification | Collection methods |
| --- | --- | --- | --- | --- |
| % Of UN support to Government sector under the Joint Programme reported on the Government budget | 0 | 0 | Internal reporting system | Internal meetings |
| % of funded Technical Assistance /Technical Cooperation that is coordinated with the country’s capacity development objectives and strategies. | 0 | 100 | Internal reporting system | Internal meetings |

As a One UN Pilot country all activities under the One UN Programme, which the CHSED Joint programme is included under, are fully aligned with the priorities of the Government of Albania. While it is currently not possible to get exact figures, the majority support through the JP should be reflected on the government budget.

Briefly describe the current situation of the government, civil society, private sector and citizens on regards of ownership, alignment and mutual accountability of the joint programme. Try to describe facts avoiding interpretations or personal opinions.  Please be specific on the role of different actors (i.e. implementing partners, or third parties being sub-contracted for specific service delivery).

- Communication and Advocacy

Has the JP articulated an advocacy & communication strategy that helps advance its policy objectives and development outcomes?

Yes   No

Please provide a brief explanation of the objectives, key elements and target audience of this strategy (max. 250 words).

What concrete gains are the advocacy and communication efforts outlined in the JP and/or national strategy contributing towards achieving?

Increased awareness on MDG related issues amongst citizens and governments

Increased dialogue among citizens, civil society, local national government in relation to development policy and practice

New/adopted policy and legislation that advance MDGs and related goals

Establishment and/or liaison with social networks to advance MDGs and related goals

Key moments/events of social mobilization that highlight issues

Media outreach and advocacy

Others (use box below)

What is the number and type of partnerships that have been established amongst different sectors of society to promote the achievement of the MDGs and related goals?

Faith-based organizations	Number: 4

Social networks/coalitions	Number

Local citizen groups		Number

Private sector			Number

Academic institutions		Number: 2

Media groups and journalist	Number: 1

Others (use box below)		Number

What outreach activities does the programme implement to ensure that local citizens have adequate access to information on the programme and opportunities to actively participate?

Focus groups discussions

Household surveys

Use of local communication mediums such as radio, theatre groups, newspapers, etc

Open forum meetings

Capacity building/trainings

Others

Section III: Millennium Development Goals

- Millennium Development Goals

The MDG-F main objective is to contribute to progress to the attainment of the Millennium Development Goals worldwide. This subsection aims to capture data and information on the joint programmes contribution to 1 or more Millennium Development Goals and its targets.

For this purpose the Secretariat has developed a matrix where you should link your joint programme outcomes to one or more Millennium Development Goal and Target. You should also select the most suitable indicators from your joint programme M&E framework as a measure of the Millennium targets selected. Please, refer to the example provided below.

| MDG # | Joint Programme Outcome 1 | MDG Target # | MDG Indicators | JP Indicator |
| --- | --- | --- | --- | --- |
| MDG #1 Eradicate Extreme Poverty and Hunger | A transparent and accountable government, developing and implementing effective national policies on culture and cultural-related issues | National MDG #9: Strengthening Good Governance – no MDG targets were developed locally on this national MDG | N/A | Indicator: # of government mechanisms and/or instruments on culture improved to follow international standards of good governance |
| MDG #3 Promote Gender Equality and Empowering Women |  |  |  |  |
| MDG #7 Ensure Environmental Sustainability | Joint Programme Outcome 2 | MDG Target # | MDG Indicator | JP Indicator |
| MDG #8 Developing a Global Partnership for Development | An enabling environment is in place to ensure people’s access to cultural heritage and participation in cultural heritage decision-making at the local, regional and national levels | MDG #7 - Target: Integrate the principles of sustainable development into country policies and programmes and reverse the loss of environmental resources | 7.6 Proportion of terrestrial and marine areas protected | Indicator: # of measures taken to better protect and preserve Albania’s archaeological parks and their surrounding environments |
| National MDG #9: Strengthening Good Governance |  |  |  |  |
|  | Joint Programme Outcome 3 | MDG Target # | MDG Indicator | JP Indicator |
|  | Increased capacities to manage, preserve and present cultural heritage and cultural industries in an efficient, transparent, accountable and equitable manner | MDG #3 – Target: Eliminate gender disparity in primary and secondary education, preferably by 2005, and in all levels of education no later than 2015 | 3.1 Ratios of girls to boys in primary, secondary and tertiary education | Indicator: # of staff employed at cultural sites trained in cultural heritage management, conservation, and protection |
|  | Joint Programme Outcome 4 | MDG Target # | MDG Indicator | JP Indicator |
|  | An increased role of cultural heritage in social and economic opportunities and in engaging community participation in regional and local development strategies | MDG #1 - Target: Achieve full and productive employment and decent work for all, including women and young people | 1.5 Employment-to-population ratio | Indicator: Improved accessibility of visitor information at cultural sites |
|  | Joint Programme Outcome 5 | MDG Target # | MDG Indicator | JP Indicator |
|  | A contribution to the National Strategy of the Alliance of Civilization and an increased awareness of Albania’s cultural heritage internationally as a means to promote cultural understanding and religious tolerance | MDG #8 –Target: In cooperation with the private sector, make available the benefits of new technologies, especially information and communications | 8.16 Internet users per 100 population | Indicator: # of Alliance of Civilization projects and activities that Albania sponsors or participates in |

# Footnotes

This indicator has been adapted from the Paris Declaration

This indicator has been adapted from the Paris Declaration

# Text boxes

- Lack of information on the baseline conditions for certain activities: the presence of dangerous insulation elements like asbestos in the National History Museum and the unforeseen need to conduct a structural assessment of the NHM made it impossible to carry out activities as planned.

- Change in the institutional priorities: between project formulation and disbursement of funds, the National Film Archive was able to locate funding for the repair of its digitalization machine and therefore reprioritized its needs.

- Some time intensive and budget consuming procedures which had not foreseen in the project document led to some delays in programme implementation: e.g. any intervention in the archaeological parks required the drafting of a technical project proposal and the endorsement by the National Council of Restorations which meets only monthly.

- Long procurement processes for local consultants and companies due to low interest and availability resulting from: the very specific nature of the services required and lack of local expertise and small volumes of interventions procured in the case of restoration/renovation efforts.

- Prolonged decision-making processes during the first year of the Joint Programme, mainly regarding the national history museum re-conceptualization, given the need to ensure Ministry of Culture leadership, consultation with stakeholders, including keen interest of donor and Advisory Board recommendations.

- General elections during the first year of JP implementation (June 29, 2009 with the new Government in place only in September 2009) impacted the overall effectiveness of the work and cooperation with state institutions and caused some delays to programme implementation.

- Leadership of Ministry of Culture could have been stronger during the first year. The replacement of employees in partner institutions impacted the quality and timeliness national inputs and responses of JP activities.

- Intensive communication with stakeholders to facilitate understanding of issues at hand throughout all the stages to speed up implementation. (External)

- New leadership at Ministry of Culture has assumed full ownership of the JP.  Building institutional ownership of the activities initiated under the JP through a participatory approach. (External)

- Additional efforts (sometimes at the expense of timeliness) were made to recruit the best possible local expertise available for the very specific requirements of the JP. (Internal)

- The institutionalization of inter-agency communication through an on-going consultation process brought together (UN Resident Coordinator, Programme Coordinator, UNESCO and UNDP management helped ensure a common understanding and intensified cooperation in joint decision-making at various levels of JP implementation. Weekly meetings of the JP staff and monthly consultations among the participating agencies are being held. (Internal)

To ensure that Government, partners, beneficiaries and other stakeholders are adequately informed about the progress on the CHSED Programme activities, but also bearing in mind that a general awareness needs to be raised with regard to culture being part of development, a communications strategy was developed in coordination with the UN Communications Team, aligned with the One UN Communications Plan, “Communicating as One”.

This communications strategy focuses on both internal and external communication for the joint programme. While the internal communications plan works to mobilize increased support of different stakeholders at different moments of the programme’s implementation, such as line ministries, civil society, and other UN agencies, the external communications plan manages public relations for the joint programme.

Objectives include:

- Raise general public  awareness and understanding about the CHSED Programme

- Through the CHSED Programme, raise awareness and understanding about the One UN Programme in Albania

- Raise awareness about the issue of Culture and Heritage and its potential for social and economic development

- Build partnerships/networks in the field of Culture and Heritage

- Keep the UN agencies, MDG-F, the Albanian Government counterparts and other programme partners well informed about progress and programme status.

- The Government now fully owns the JP and steers its implementation according to national priorities. This is also reflected in the alignment of the JP to both the UN/Government One UN Programme and other National Sectoral strategies

- Implementing partners and the JP are mutually accountable in implementing activities through a number of MOUs and agreements and regular meetings are held under the supervision of the PMC to ensure a smooth implementation

- Constant communication with the central and local government counterparts in all activities at all the levels of their implementations has empowered the Government and ensured a smooth implementation

- UNESCO and UNDP experts have worked closely together on technical issues contributing to more sound conclusions and decisions on specific activities (i.e. NHM).

- Participating agencies have been using each other’s expertise/consultants (i.e in drafting TORs for expertise needed for the NHM).

- Representatives of participating agencies have sat in the various evaluations panels set up on several issues (e.g. recruitment of consultants, selection of bidders, etc.).

- UNESCO is using UNDP country level procurement systems to speed up activities and benefit from VAT exemptions.

- UNDP main office facilities and premises have been shared with the JP when required.

- Joint missions within the country are routinely undertaken by programme staff and, when possible, by visiting consultants and agencies.

The CHSED JP is part of the One UN Programme in Albania. Therefore, its activities are part of the planning and reporting cycle foreseen by the One UN Programme along with other JPs in country.

A Programme Coordinator has been appointed since the beginning of the project to coordinate activities of all the participating agencies and to act as manager of the JP as a whole. The activities have been structured in order to complement each other and are closely interlinked making it impossible for various components of the JP to be run in parallel as separate sub-programmes. Moreover, a Joint Programme office hosting all participating agencies was set up facilitating coordination and fostering a sense of belonging among staff and opportunities for cross fertilization and brainstorming. Quarterly PMC meetings are a forum where activities are presented by output rather than agency implementing them.

There are no other JPs in the country working in the Cultural sector. However, the JP coordinator meets every month, at the invitation of the RC, the other coordinators/CTAs of MDG-F JPs working in the country to share lessons learned and experiences.  This JP will share a vehicle together with the MDG-F JP on Economic Governance to save costs.