### PROGRESS REPORT

Adaptation to Climate Change to Sustain Jordan’s MDG Achievements

Second Quarter Progress report 2009

(2009-2011)

### I.  PURPOSE

This Joint Programme will develop Jordan’s key government and civil society counterparts’ capacity to adapt to climate change threats to health, food security, productivity, and human security under the conditions of severe water scarcity that is expected to be compounded by climate change. This joint programme seeks to enhance capacity to adapt to climate change by addressing Jordan’s long-term adaptation needs through the following outcomes and outputs:

Outcome 1: Sustained access to improved water supply sources despite increased water scarcity induced by climate change

- Output 1.1: National drinking water quality management system at central and periphery level is strengthened: The activities will concentrate on upgrading the national drinking water management systems, increasing the capacity of the national partner staff and improving the working environment for water quality monitoring system.

- Output 1.2: Sustainable and reliable supply of minimum water requirements for health protection is provided to all citizens.  The activities under this output will include inventories to identify the minimum water requirements and the development of policy instruments for securing the supply of these requirements.

Outcome 2: Strengthened adaptive capacity for health protection and food security to climate change under water scarcity conditions

- Output 2.1: Rural sector adaptive capacity for climate variability and change is improved: The activities include the risk assessment of climate change and water scarcity and identification of the adaptation measures to reduce climate change impacts on food (land and water) productivity and control of desertification. In addition to a public awareness campaigns for local community to promote these measures on the target areas.

- Output 2.2: National institutional and community capacity in integrated water resources management is improved: The activities will include development of awareness in available economic incentives to farmers and agricultural policy frameworks that support and realize carbon benefits in Good Agricultural Practices. The activities will also concentrate on the capabilities of the local community institutions and the introduction of water resource management concepts into the school and University curriculum.

- Output 2.3: Adaptation measures, by health sector and other sectors, to protect health from climate change are institutionalized: Activities to achieve this output will focus on assessing the direct and indirect risks of climate change on health sector. Adaptation strategies will be developed and early warning system will be established to protect health from the negative effect of climate change.

- Output 2.4: Adaptation capacity of Zarqa River Basin to climate change is piloted and strengthened: The activities will include the assessment of direct and indirect effects of climate change on water availability and quality in Zarqa River Basin; identify opportunities and barriers to adaptation to climate change; review and deliver reform strategies for legal and institutional frameworks and national water policies and action plans; build local and national capacities for adaptation to climate change using participatory approach; and document and share knowledge generated from the Zarqa River Basin and establish linkages to regional and global experiences.

This Joint Programme will focus on the challenges facing Jordan’s MDG achievements due to water scarcity induced by climate change. The National Agenda that sets Jordan’s development vision till 2015, as well as UNDAF document (2008-2012), stress that Jordan's remarkable development achievements are under threat due to the crippling water scarcity, which is expected to be aggravated by climate change.  The Initial National Communication (INC) to the United Nations Framework Convention to Climate Change (UNFCCC) shows that Jordan will witness a rise in temperature, drop in rainfall, reduced ground cover, reduced water availability, heat-waves, and more frequent dust storms over the next three decades. The Second National Communication (SNC) to the UNFCCC identifies water as a priority area.

The UNDAF (2008-2012) addresses four key related challenges to sustain progress towards the achievement of the MDG's, which include: (i) water scarcity; (ii) drinking water supply security and quality; (iii) health, agriculture and food production vulnerability to climate change; and (iv) vulnerability of local biodiversity to climate change. This JP will support the United Nations Country Team’s (UNCT) efforts to achieve the UNDAF outcome of healthy and sustainable environment. This programme also will help Jordan governmental agencies in developing a national strategy to 1) Sustain access to improved water supply sources despite increased water scarcity induced by climate change; and 2) Strengthen adaptive capacity for health protection and food security to climate change under water scarcity conditions. These JP outcomes address the barriers to adaptation and provide support to Jordan’s priorities of sustainable management of its natural resources; reducing poverty; and enhancing health indicators.

This programme is linked to UNDP CPAP outcome 3.1 National institutional and community capacities strengthened for more sustainable management of water resources and the corresponding output 3.1.1. Adaptation capacity of Zarqa River Basin to climate change is piloted and strengthened.

This joint programme will directly contribute to the achievement of the MDGs; linkages to the MDGs are evident with goal number 7 “ensure environmental sustainability”. The programme will contribute to the process of achieving two targets under Goal 7: target 7a: Integrate the principles of sustainable development into country policies and programmes; reverse loss of environmental resources and target 7c: Reduce by half the proportion of people without sustainable access to safe drinking water and basic sanitation.

The programme is also in harmony with Goal 4 of the UNDP strategic Plan: “To strengthen national capacities to achieve sustainable development through environmental management, adaptation to climate change, and expansion of access to environmental and energy services for the poor”. It is also linked directly to Key Result Area 4.3

The issue of scalability is addressed throughout the programme design in a number of ways. Community-level interventions, in particular, have been designed to be replicable both in terms of the design of the activities themselves and in the synergies that will be created between different agency-led activities. It is intended that these activities will provide the basis for best practices in forming innovative links between indigenous knowledge and the use of water resources Zarqa River Basin.  Scalability will be achieved through facilitating vertical information flows in which information on these best practices in the field will be fed into policy-level activities, through reporting and knowledge sharing on implementation and experiences. This will provide valuable information into the policy debate and will allow for systematization and institutionalization.

- The main implementing partners:

| UN Organizations | National Partners |
| --- | --- |
| UNDP | Ministry of Environment |
| WHO/CEHA | Ministry of Health |
| FAO | Ministry of Agriculture |
| UNESCO | Ministry of Education/ Ministry of Water and Irrigation |

### II.  RESOURCES

This joint programme is under the MDG-F Environment and Climate Change thematic window and aligned with the ‘Enhancing Capacity to Adapt to Climate Change’ priority area. The UNDP/Spain MDG Achievement Fund allocated US$ 4,000,000 for the programme activities managed by four UN organizations working in Jordan, namely UNDP, FAO, WHO, and UNESCO.  UNDP has made available an additional amount of US$ 126,667 from its own core resources and the UNDP Water Governance Facility at SIWI bringing the total fund available for this joint programme from all sources to US$ 4,126,667.

### III.  RESULTS

This joint programme has received the MDG F approval end of 2008, and the funds were transfer to the participating UN agencies in January and February 2009. UN participating agencies in cooperation with the government counterparts and implementing partners are taking the necessary actions to launch the joint programme. Hence, the expenditures during the first and second quarters are very minimal.  The joint programme will officially start its implementation when the programme team are on board.  The JP program coordinator has already started his work and it is expected that the two remaining TA (for WHO and FAO components) will soon join the JP team. More specifically, the following actions have been undertaken and achieved:

| UNDP | UNDP is following up on the launching of the joint programme and the UNDP component implementation, the following tasks have been achieved to date: TOR for the joint programme coordinator was drafted, shared with UN participating agencies and finalized UNDP has initiated the recruitment process of the Joint Programme Coordinator. Ministry of Environment has designated the UNDP project component focal point. Ministry of Water and Irrigation has designated the Joint Programme Focal point. Discussion with the Spanish Government representative is ongoing concerning the linkages between this programme and other initiatives supported by the Spanish Government. Discussion is going on with the Zarqa Rehabilitation Unit at the Ministry of Environment to integrate efforts. The set up of the Joint programme unit at the Ministry of Water and Irrigation was discussed and agreed with the Ministry’s officials The JP coordinator has been appointed and started as of July 15th, 2009. Office spaces on both the Ministry of water and irrigation, MWI, (for the JP coordinator and TA’s) and the Ministry of Environment, MoEnv, (for the UNDP component TA and the project assistant) have already been taken. Efforts are underway to furnish and equip both offices spaces with the needed furniture, and IT tools and equipments. The TOR for the project assistant was drafted to start the process of appointing him/her during the month of August. Initial meetings were held between the JP coordinator and the Secretary General of both the MWI and MoEnv to discuss issues related to the collaboration between the JP and both ministries. A Meeting was held with the Spanish funded project team on the rehabilitation of Amman Zarqa basin for possible collaboration and coordination with the UNDP component of the JP. |
| --- | --- |
| UNESCO | MDG Project Inception workshop of the UNESCO’s component held on the 26th of May 2009. Two days working group workshop were the Jordan IHP national committee submit six proposals for approval by UNESCO Amman office. Three research proposals were approved and shall be implemented before the end of January 2010. A planned conference on Climate Change Impact on Water Resources: Risk, Assessment and Management in Arid and Semi- Arid Regions” will be held from the 24- 26 November 2009. A consultant will be work with the curricula directorate at the Ministry of Education for need assessment of the current situation of the water and climate change education in the current curricula. Training workshop on the Transboundary management will be held on October. Discussion with potential collaboration with Columbia research centre for the Middle East. Training of the climate change modelling will be held on January 2010. Setting up the water centre at Al Balqa Applied University is under process. One research study will be conducted for Zaraq basin. |
| FAO | FAO has initiated actions to implement the Joint Environment -Climate Change Programme by: Designating the Lead Technical Unit responsible for its implementation in Jordan. The Ministry of Agriculture has designated a Focal point for the programme. Actions are taken to arrange for the programme Inception workshop soon. |
| WHO | Initiation meeting with the Ministry of Health discussed programme details and modalities for implementation; The Ministry of Health designated the focal points for the implementation of the programme components; The TOR for the Technical Advisor on health and climate change (member of the programme coordinating unit) has been developed and the vacancy announcement is planned shortly. |

The intended beneficiaries of the joint programme are twofold: At the policy level, the primary beneficiaries are the policy makers and planners responsible for delivery of the programme’s services to the selected pilot areas. These include the Ministry of Environment, Ministry of Water and Irrigation, Ministry of Education, Ministry of Health and Ministry of Agriculture and other national authorities as well as civil society organizations and academic sector. The public awareness and capacity development programme will be implemented in the pilot areas to empower local communities, including women and the poor, and strengthening their institutions capacity for climate change adaptation within the Zarqa governorate and other rural/urban pilot areas.

### IV. ANNEXES

- 2009 work plan

| Annual targets | Activities | TIME FRAME | UN AGENCY | RESPON-SIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  | Source of Funds | Budget Description | Amount |
| JP Outcome 1: Strengthened adaptive capacity for health protection and food security to climate change under water scarcity conditions |
| JP Output 1.1: National drinking water quality management system at central and periphery level is strengthened. |
| 5 operational water safety plans. | 1.1: Upgrade the national drinking water quality (DWQ) system for comprehensive national coverage. |  |  |  |  | WHO | MOH | MDG-F | Local Staff | 15000 |
|  |  |  |  |  |  |  |  |  | int. consult | 10000 |
|  |  |  |  |  |  |  |  |  | local contract | 15000 |
|  |  |  |  |  |  |  |  |  | Int. contracts | 0 |
|  |  |  |  |  |  |  |  |  | Training | 8000 |
|  |  |  |  |  |  |  |  |  | Transport | 1000 |
|  |  |  |  |  |  |  |  |  | Equipment | 0 |
|  |  |  |  |  |  |  |  |  | Travel local | 1000 |
|  |  |  |  |  |  |  |  |  | Supplies | 900 |
|  |  |  |  |  |  |  |  |  | -Misc. | 502 |
|  |  |  |  |  |  |  |  |  | M & E | 15577 |
|  |  |  |  |  |  |  |  |  | Support (7%) | 4688 |
|  |  |  |  |  |  |  |  |  | Total | 71667 |
| Output 1.2: Sustainable and reliable supply of minimum water requirements for health protection is provided to all citizens |
| Policy on minimum water requirements for health available No. of training courses conducted. | 1.2: Develop and implement 5 demonstration water safety plans (3 urban & 2 rural). |  |  |  |  | WHO | MOH | MDG-F | Local Staff | 20000 |
|  |  |  |  |  |  |  |  |  | int consult | 15000 |
|  |  |  |  |  |  |  |  |  | local contract | 15000 |
|  |  |  |  |  |  |  |  |  | Int. contracts | 0 |
|  |  |  |  |  |  |  |  |  | Training | 10000 |
|  |  |  |  |  |  |  |  |  | Transport | 2000 |
|  |  |  |  |  |  |  |  |  | Equipment | 0 |
|  |  |  |  |  |  |  |  |  | Travel local | 1000 |
|  |  |  |  |  |  |  |  |  | Supplies | 1500 |
|  |  |  |  |  |  |  |  |  | Misc. | 921 |
|  |  |  |  |  |  |  |  |  | Support (7%) | 4579 |
|  |  |  |  |  |  |  |  |  | Total | 70000 |
|  | 1.3: Design and implement training programme on DWQ management system for all levels. |  |  |  |  | WHO | MOH | MDG-F | Local Staff | 16800 |
|  |  |  |  |  |  |  |  |  | int consult | 0 |
|  |  |  |  |  |  |  |  |  | local contract | 0 |
|  |  |  |  |  |  |  |  |  | Int. contracts | 25000 |
|  |  |  |  |  |  |  |  |  | Training | 8000 |
|  |  |  |  |  |  |  |  |  | Transport | 1500 |
|  |  |  |  |  |  |  |  |  | Equipment | 0 |
|  |  |  |  |  |  |  |  |  | Travel local | 2000 |
|  |  |  |  |  |  |  |  |  | Supplies | 1775 |
|  |  |  |  |  |  |  |  |  | -Misc. | 1000 |
|  |  |  |  |  |  |  |  |  | Support (7%) | 3925 |
|  |  |  |  |  |  |  |  |  | Total | 60000 |
|  | 1.4: Provide critical supplies and equipment for DWQ laboratory networks of the |  |  |  |  | WHO | MOH | MDG-F | Local Staff | 10500 |
|  |  |  |  |  |  |  |  |  | int consult | 6000 |
|  |  |  |  |  |  |  |  |  | local contract | 0 |
|  |  |  |  |  |  |  |  |  | Int. contracts | 0 |
|  |  |  |  |  |  |  |  |  | Training | 5000 |
|  |  |  |  |  |  |  |  |  | Transport | 1700 |
|  |  |  |  |  |  |  |  |  | Equipment | 25000 |
|  |  |  |  |  |  |  |  |  | Travel local | 1000 |
|  |  |  |  |  |  |  |  |  | Supplies | 1200 |
|  |  |  |  |  |  |  |  |  | Misc. | 1002 |
|  |  |  |  |  |  |  |  |  | Support (7%) | 3598 |
|  |  |  |  |  |  |  |  |  | Total | 55000 |
|  | 1.5: Identify minimum household water security requirements for health protection. |  |  |  |  | WHO | MOH | MDG-F | Local Staff | 15000 |
|  |  |  |  |  |  |  |  |  | int consult | 0 |
|  |  |  |  |  |  |  |  |  | local contract | 27000 |
|  |  |  |  |  |  |  |  |  | Int. contracts | 0 |
|  |  |  |  |  |  |  |  |  | Training/scientific consultation | 40000 |
|  |  |  |  |  |  |  |  |  | Transport | 1500 |
|  |  |  |  |  |  |  |  |  | Equipment | 5000 |
|  |  |  |  |  |  |  |  |  | Travel local | 1500 |
|  |  |  |  |  |  |  |  |  | Supplies | 1500 |
|  |  |  |  |  |  |  |  |  | Misc. | 1958 |
|  |  |  |  |  |  |  |  |  | Support (7%) | 6542 |
|  |  |  |  |  |  |  |  |  | Total | 100000 |
|  | 1.6: Develop national policy and issue legislative policy instruments on securing supply of minimum water requirements for health. |  |  |  |  | WHO | MOH | MDG-F | Local Staff Int. staff Int. Staff Misc. supplies support | 0 |
| Outcome 2: Strengthened adaptive capacity for health protection and food security to climate change under water scarcity conditions |
| Output 2.1: Rural sector adaptive capacity for climate variability and change is improved |
| 3 technical options developed for safe use of treated wastewater in agriculture and forestry. | 2.1: Assess the risks from climate change and water scarcity on food productivity |  |  |  |  | FAO | MOA | MDG-F | - Local Staff - Intrnl staff - local contract. - Training - Transportation - Supplies - Equipments - Travel - Misc. - M& E - support - Total | 15600 7200 9000 17850 2000 2600 5000 5000 2100 1500 4750 72600 |
| 2 persons per stakeholder institution and 1 person per farm to be trained | 2.2: Identify and screen adaptation measures to reduce climate change impacts on food productivity. |  |  |  |  | FAO | MOA | MDG-F | - Local Staff - Intrnl staff - local contract. - Training - Transportation - Supplies - Equipments - Travel - Misc. - M&E - support - Total | 8000 3000 5200 10000 1400 1700 3200 2900 2000 1700 2737 41837 |
|  | 2.3: Identify and test adaptation options and improvements of crop /trees/ livestock for increased productivity in irrigating with treated wastewater. |  |  |  |  | FAO | MOA | MDG-F | Local Staff - Intrnl staff - local contract. - Training - Transportation - Supplies - Equipments - Travel - Misc. - M&E - support - Total | 10000 4000 6000 12100 1500 2500 4000 4000 2000 1500 3332 50932 |
|  | 2.4: Design and implement national and community awareness campaign, with focus on women farmers, on climate change adaptation measures as well as incentive mechanisms. |  |  |  |  | FAO | MOA | MDG-F | - Local Staff - Intrnl staff - local contract. - Training - Transportation - Supplies - Equipments - Travel - Misc. - M&E - support - Total | 15600 6200 9400 16500 3500 3500 2000 5000 2800 1500 4620 70620 |
|  | 2.5: Establish model farms using treated wastewater as adaptation to climate change and other agricultural climate mitigation strategies in capacity building efforts. |  |  |  |  | FAO | MOA | MDG-F | - Local Staff - Intrnl staff - local contract. - Training - Transportation - Supplies - Equipments - Travel - Misc. - M&E - support - Total | 16000 7000 9600 16500 2000 2500 5000 4000 2000 1500 4627 70727 |
| Output 2.2: National institutional and community capacity in integrated water resources management is improved |
|  | 2.6: Design and implement a training programme in integrated water resources management for the Ministry of Water and Irrigation, national non-governmental organizations (NGOs), and stakeholders. |  |  |  |  | UNESCO | MWI | MDG-F | Local Staff Training Int. Consult Int. Travel equipment Misc. Support 7% M&E Programme Coordinator Total | 13000 81000 18000 7000 5000 10 10990 19000 3000 157000 |
|  | 2.7: Design and implement research projects and improve database in integrated water resources management in arid and semi arid areas |  |  |  |  | UNESCO | MWI | MDG-F | local contract Training Transport Misc. Support 7% M&E Total | 17000 6000 2000 3060 2940 11000 42000 |
|  | 2.8: Develop water education and awareness programme focusing on curriculum, resource manuals, training of trainers and teacher-in-service training for the Ministry of Education with the close partnership of the Ministry of Water and Irrigation |  |  |  |  | UNESCO | MOE, MWI | MDG-F | Local Staff local contract Training Supplies Misc. Support 7% M&E Total | 5000 9000 7000 1830 1000 2170 5000 31000 |
|  | 2.9: Design and establish one environmental and water resource centre for advocacy education and capacity building. |  |  |  |  | UNESCO | MMWI | MDG-F | local contract Training Equipment Supplies Support7% M&E Total | 5000 5000 30000 1385 3115 0 44500 |
| Output 2.3: Adaptation measures, by health sector and other sectors, to protect health from climate change are institutionalized |
| 4 institutional adaptation interventions to protect health available | 2.10: Develop a cooperative framework on the criteria for sustainable management of shared water resources including trans-boundary water resources. |  |  |  |  | UNESCO | MWI | MDG-F | local contract. Misc. Support7% M&E Total | 7000 2300 700 0 10000 |
| National strategy on protecting health from climate change available. | 2.11: Conduct an assessment of direct and indirect risks to health from climate change |  |  |  |  | WHO | MOE | MDG-F | Local Staff | 22000 |
|  |  |  |  |  |  |  |  |  | int consult | 11000 |
|  |  |  |  |  |  |  |  |  | local contract | 28000 |
|  |  |  |  |  |  |  |  |  | Int. contracts | 0 |
|  |  |  |  |  |  |  |  |  | Training/scientific consultation | 8000 |
|  |  |  |  |  |  |  |  |  | Transport | 2000 |
|  |  |  |  |  |  |  |  |  | Equipment | 0 |
|  |  |  |  |  |  |  |  |  | Travel local | 1500 |
|  |  |  |  |  |  |  |  |  | Supplies | 1466 |
|  |  |  |  |  |  |  |  |  | Misc. | 800 |
|  |  |  |  |  |  |  |  |  | Support (7%) | 5234 |
|  |  |  |  |  |  |  |  |  | Total | 80000 |
| National early warning system on health and climate change available. | 2.12: Screen and prioritize adaptation strategies, by the health sector and others to protect health from climate change |  |  |  |  | WHO | MOH | MDG-F | Local Staff | 7000 |
|  |  |  |  |  |  |  |  |  | int consult | 5000 |
|  |  |  |  |  |  |  |  |  | local contract | 6365 |
|  |  |  |  |  |  |  |  |  | Int. contracts | 0 |
|  |  |  |  |  |  |  |  |  | Training/scientific consultation | 0 |
|  |  |  |  |  |  |  |  |  | Transport | 2000 |
|  |  |  |  |  |  |  |  |  | Equipment | 0 |
|  |  |  |  |  |  |  |  |  | Travel local | 1500 |
|  |  |  |  |  |  |  |  |  | Supplies | 1000 |
|  |  |  |  |  |  |  |  |  | Misc. | 500 |
|  |  |  |  |  |  |  |  |  | Support (7%) | 1635 |
|  |  |  |  |  |  |  |  |  | Total | 25000 |
|  | 2.13: Develop and implement adaptation strategies to protect health from the negative effects of heat waves |  |  |  |  | WHO | MOH | MDG-F | Local Staff | 4000 |
|  |  |  |  |  |  |  |  |  | int consult | 0 |
|  |  |  |  |  |  |  |  |  | local contract | 8300 |
|  |  |  |  |  |  |  |  |  | Int. contracts | 0 |
|  |  |  |  |  |  |  |  |  | Training/scientific consultation | 0 |
|  |  |  |  |  |  |  |  |  | Transport | 500 |
|  |  |  |  |  |  |  |  |  | Equipment | 0 |
|  |  |  |  |  |  |  |  |  | Travel local | 500 |
|  |  |  |  |  |  |  |  |  | Supplies | 500 |
|  |  |  |  |  |  |  |  |  | -Misc. | 220 |
|  |  |  |  |  |  |  |  |  | Support (7%) | 980 |
|  |  |  |  |  |  |  |  |  | Total | 15000 |
|  | 2.14: Design adaptation projects to protect health from identified high risk environmental conditions induced by climate change |  |  |  |  | WHO | MOH | MDG-F | Local Staff | 2800 |
|  |  |  |  |  |  |  |  |  | int consult | 0 |
|  |  |  |  |  |  |  |  |  | local contract | 5200 |
|  |  |  |  |  |  |  |  |  | Int. contracts | 0 |
|  |  |  |  |  |  |  |  |  | Training/scientific consultation | 0 |
|  |  |  |  |  |  |  |  |  | Transport | 500 |
|  |  |  |  |  |  |  |  |  | Equipment | 0 |
|  |  |  |  |  |  |  |  |  | Travel local | 0 |
|  |  |  |  |  |  |  |  |  | Supplies | 500 |
|  |  |  |  |  |  |  |  |  | Misc. | 346 |
|  |  |  |  |  |  |  |  |  | Support (7%) | 654 |
|  |  |  |  |  |  |  |  |  | Total | 10000 |
|  | 2.15: Establish a national early warning system to monitor and assess health impacts of climate change |  |  |  |  | WHO | MOH | MDG-F | Local Staff | 4200 |
|  |  |  |  |  |  |  |  |  | int consult | 5000 |
|  |  |  |  |  |  |  |  |  | local contract | 3000 |
|  |  |  |  |  |  |  |  |  | Int. contracts | 0 |
|  |  |  |  |  |  |  |  |  | Training/scientific consultation | 0 |
|  |  |  |  |  |  |  |  |  | Transport | 700 |
|  |  |  |  |  |  |  |  |  | Equipment | 0 |
|  |  |  |  |  |  |  |  |  | Travel local | 500 |
|  |  |  |  |  |  |  |  |  | Supplies | 300 |
|  |  |  |  |  |  |  |  |  | Misc. | 320 |
|  |  |  |  |  |  |  |  |  | Support (7%) | 980 |
|  |  |  |  |  |  |  |  |  | Total | 15000 |
| Output 2.4: Adaptation capacity of Zarqa River Basin to climate change is piloted and strengthened. |
| Integrated water resource management plan for Zarqa River Basin that includes adaptation to climate change is available. plans for water sector includes adaptation to climate change. | 2.16: Assess direct and indirect climate change risks to water availability and quality in Zarqa River Basin. |  |  |  |  | UNDP | MOEnv | MDG-F | Local contract | 8220.27 |
|  |  |  |  |  |  |  |  |  | M&E | 8417 |
|  |  |  |  |  |  |  |  |  | 7 % GMS | 618.73 |
|  |  |  |  |  |  |  |  |  | Total | 17256 |
|  | 2.17: Assess opportunities and barriers to adaptation to climate change risks |  |  |  |  | UNDP | MOEnv | MDG-F | Local Staff | 6000 |
|  |  |  |  |  |  |  |  |  | Local contract | 17000 |
|  |  |  |  |  |  |  |  |  | Travel local | 1000 |
|  |  |  |  |  |  |  |  |  | Supplies | 3900 |
|  |  |  |  |  |  |  |  |  | 7 % GMS | 2100 |
|  |  |  |  |  |  |  |  |  | Total | 30000 |
|  | 2.18: Review and devise a reform strategy for legal and institutional framework approaches and tools for adaptation to climate change and IWRM in the Zarqa River basin. |  |  |  |  | UNDP | MOEnv | MDG-F | Local Staff | 7000 |
|  |  |  |  |  |  |  |  |  | local contract | 10000 |
|  |  |  |  |  |  |  |  |  | Training | 3000 |
|  |  |  |  |  |  |  |  |  | Transport | 500 |
|  |  |  |  |  |  |  |  |  | Travel local | 500 |
|  |  |  |  |  |  |  |  |  | Misc. | 3500 |
|  |  |  |  |  |  |  |  |  | 7% GMS | 1750 |
|  |  |  |  |  |  |  |  |  | Total | 25000 |
|  | 2.19: Review national water policies and action plans for adaptation to climate change. |  |  |  |  | UNDP | MOEnv | MDG-F | Local Staff | 23250 |
|  |  |  |  |  |  |  |  |  | 7 % GMS | 1750 |
|  |  |  |  |  |  |  |  |  | Total | 25000 |
|  | 2.20: Develop local and national capacities for adaptation to climate change and IWRM using effective participatory approaches and tools |  |  |  |  | UNDP | MOEnv | MDG-F | Local Staff | 15000 |
|  |  |  |  |  |  |  |  |  | Intrnl staff | 10000 |
|  |  |  |  |  |  |  |  |  | Local contract | 30000 |
|  |  |  |  |  |  |  |  |  | Training | 19702 |
|  |  |  |  |  |  |  |  |  | Transport | 5000 |
|  |  |  |  |  |  |  |  |  | Travel Intrnl | 10000 |
|  |  |  |  |  |  |  |  |  | Supplies | 1000 |
|  |  |  |  |  |  |  |  |  | Equipment | 5000 |
|  |  |  |  |  |  |  |  |  | Misc. | 6000 |
|  |  |  |  |  |  |  |  |  | 7 % GMS | 7118 |
|  |  |  |  |  |  |  |  |  | Total | 108820 |
|  | 2.21: Develop, document, and share knowledge generated from Zarqa River basin on the local and national levels, and establish linkages to regional and global experiences. |  |  |  |  | UNDP | MOEnv | MDG-F and UNDP | Local Staff | 20000 |
|  |  |  |  |  |  |  |  |  | Intl. Staff | 22500 |
|  |  |  |  |  |  |  |  |  | local contract | 35000 |
|  |  |  |  |  |  |  |  |  | Training | 15000 |
|  |  |  |  |  |  |  |  |  | Transport | 2000 |
|  |  |  |  |  |  |  |  |  | Travel local | 1919 |
|  |  |  |  |  |  |  |  |  | Travel Intrnl | 7600 |
|  |  |  |  |  |  |  |  |  | Supplies | 2000 |
|  |  |  |  |  |  |  |  |  | 7 % GMS | 7071 |
|  |  |  |  |  |  |  |  |  | Total | 108,090 |
| TOTAL |  | 1,407,049 |

- Monitoring Framework (PMF)

| Expected Results (Outcomes & outputs) | Indicators (with baselines & indicative timeframe) | Means of verification | Collection methods (with indicative time frame & frequency) | Responsibilities | Risks & assumptions |
| --- | --- | --- | --- | --- | --- |
|  | Indicator | Baseline | Target |  |  |  |  |
| Outcome 1: Sustained access to improved water supply sources despite increased water scarcity induced by climate change |
| Outcome level | % of urban households with reliable access to minimum water requirements for health under water scarcity conditions induced by climate change | in 2004 the percent of urban households with reliable access to minimum water requirements for health was 50%. | Increase % of urban households with reliable access to minimum water requirements for health to 75% in the pilot sites | Government Policy documents and National Agenda Recommendations of NSC | Collecting for Mid-term and final project reviews Collected for the Independent evaluation | WHO/MOH/MWI WAJ | Commitment of governmental agencies Suggested policies, laws and procedures are not adopted |
|  | Percentage of water supply systems meeting requirements of the national drinking water quality standards | 95% (Report on Rapid Assessment of Drinking Water quality, 2006) | Maintain the current status in the face of additional water stress | Report on survey of rapid assessment of drinking water quality 2009-2011 | Conduct survey & rapid Assessment of Drinking Water Quality (WHO protocol) | WHO/MOH/MWI | Commitment of national authorities to establish national framework for water safety Risks: Legislative and institutional setup and national resources are not committed by government. |
| Output 1.1 Strengthened national drinking water quality management system at central and periphery level | No. of operational water safety plans resilient to climate change | there are no operational water safety plans | 5 operational water safety plans for different sources developed | Plans documents adopted by government agencies | Assessment of Plans documents Collected for Mid-term review | WHO/ MOH WAJ | Commitment of governmental agencies Availability of experts in water quality management |
|  | No. of drinking water quality (DWQ) systems upgraded. | the current DWQ system is not responsive to expected climate change impacts | Operational DWQ system upgraded MOH network of DWQ laboratories are upgraded | DWQ system documents Equipment and supplies are in place | Review of national Standards on Water Quality by PTC Quality monitoring procedures at government laboratories. Frequent visits to existing labs Conduct survey | WHO/MOH | Availability of financial resources to upgrade systems beyond the project |
|  | No. of training courses conducted | Limited and weak capacity currently exists in MOH network | three local institutions staff per target area trained (6 areas) | Training materials Feed back report on training courses | Collected for Annual Reports on Capacity Development component. Analysis of feedback on training courses. | WHO/MOH | Cooperation between training institutions and MOH. Adoption of DWQ proposed procedures. |
| Output 1.2 Sustainable and reliable supply of minimum water requirements for health protection | Legislative instruments for the national policy on minimum water requirements for health, taking into account climate change and variability | no policy on minimum water requirements for health | Policy on minimum water requirements for health adopted | Policy document that determines the minimum water requirement | Collected for Mid-term and Final review of project. | WHO/MWI/MOH/ WAJ | Willingness of government to develop legislation and policy Conflict between water users (Domestic vs. agriculture) |
|  | No. of inventories conducted to determine minimum water requirement | No evidence -based guidance available on minimum water requirement for health | 3 comprehensive inventories conducted | Inventories reports | Collected for Mid-term and Final review of project. | WHO/MOH | Suggested policies, laws and procedures are not adopted |
| Outcome 2: Strengthened adaptive capacity for health protection and food security to climate change under water scarcity conditions |
| Outcome level | Policies and adaptive capacities developed to manage environmental health and food security issues from the threat posed by climate change under water scarcity conditions Health vulnerability assessment, national adaptation strategy and plan of action for health protection from climate change | No policy on adaptation to climate change exists in Jordan none existent | Policy options including options for health, for environment, and for food security are developed and submitted along with capacity development needs to government Health vulnerability assessment completed & national strategy and plan of action for health protection from climate change completed | Policy options document Policy document and reports published | Review through Project Evaluation Minutes of NSC submission of policy options to concerned authorities Hold a national meeting to launch and announce the national strategy by the second year. Policy documents widely disseminated | UNDP UNESCO and FAO WHO | WHO regional committee issues resolution on action to protect health from climate change and national government undertakes to implement the resolution National government have capacity to implement the WHO Regional Committee resolution |
| Output 2.1 Improved rural sector adaptive capacity for climate variability and change | No. of risk assessment studies to identify the impact of CC and water scarcity on food production. | No information available on risk of climate change on food production in Jordan | 3 risk studies on climate change and water scarcity on food productivity conducted | Risk assessment reports Modelling Report | Review Survey reports Collected for progress reports Collected for Mid-term and Final review of project. | FAO/UNDP/MOA | Willingness of the stakeholders and local community in Zarqa River to participate effectively. |
|  | No. of adaptive mechanisms to reduce the impact of CC adopted | Adaptive mechanisms to reduce impact of CC not existed | 3 adaptation plans developed on identified constraints | Adaptation plans documents Field reports | Adaptation field tests Collected for Mid-term and Final review of project. Field visits | FAO/MOA/Local Communities | Acceptance of the stakeholder institutions to adopt the mechanisms. |
|  | No. of on-farm technical approaches developed for safe use of treated wastewater in agriculture | On-farm technical approaches are not existing | 3 technical options developed for safe use of treated wastewater in agriculture | Document including the adaptive mechanisms Assessment report Progress reports | Visits to the target area. Conduct Inventory | FAO/MOA/Local communities and farmers | Acceptance of the stakeholder institutions to adopt the mechanisms. |
|  | No. of policy options suggested to support the adaptation mechanisms | Policy framework is not available | Policy framework in place | List of policy options suggested | Collected for Mid-term and Final review of project. . | FAO/MOA | Suggested policies not adopted |
|  | No. of stakeholders trained on the operational approaches | Limited number of trained personnell on the operational approaches | 2 persons per stakeholder institution and 1 person per pilot farm to be trained | Feed back report on training programs Training material manuals | Assessment of training conducted. Progress reports | FAO/MOA/Local communities | Willingness and commitment of the stakeholder institutions to participate |
| Output 2.2 Improved national institutional and community capacity in integrated water resources management (IWRM) | No. of training courses conducted | Jordan does not have a well developed IWRM national plan, but has major elements such as a water strategy and policies | 7- 10 stakeholder institution are trained 1000 persons from the stakeholder are trained | Training materials List of institutions trained on IWMR No. of brochures printed database website developed assessment report | Assessment of training course feedback report Progress reports approval by PMC Survey stakeholder satisfaction | UNESCO/MWI Training institutions UNDP | Willingness and commitment of the stakeholder institutions to participate |
|  | No. of institutions participated | limited participation of stakeholder institutions in IWRM | 7- 10 stakeholder institutions are trained 1000 person from the stakeholder are trained | List of the participating institutions | Analysis of training reports Prepared for progress reports | UNESCO/MWI | Commitment of governmental agencies Adoption of training material by training institutions and MWI |
|  | No. of concepts of IWRM introduced in the curricula | Weak integration of the concepts of IWRM in curricula No Guidelines and manual on IWRM | Integration of the concepts of IWRM in Curricula One guideline and one manual on IWRM | Curricula that include IWRM concepts Guidelines and Manual of IWMR Syllabus of university courses | Reporting by the education institutions on progress and adoption of curricula | UNESCO/MWI/MOE | Adoption of training material by training institutions and MWI |
|  | Establish environment and water resources center for advocacy education and capacity building. | Center for advocacy, education and capacity building does not exist | Centre established and operating | Document on center mandate Advocacy and awareness strategy document for the center | Collected for Mid-term and final evaluation. | UNESCO/MWI | Financial sustainability of the center. Adoption by MWI as an awareness advocacy arm |
| Output 2.3 Adaptation measures, by health sector and other sectors, to protect health from climate change are institutionalized | No. of adaptation measures adopted by each sector. | no institutionalized adaptation interventions at present | Sectoral Adaptation plans to protect human health from climate change are in place One adaptation strategy to protect health from negative effects of heat waves developed | List of adopted mechanisms List of measures adopted and sectors participated. | Review of adaptation plans for progress reporting to NSC | WHO/MOH | Adoption of plans by government institutions High cost of adaptation plans |
|  | No. of sectors adopted the adaptation measures | There is no national strategy on protecting health from climate change. | national strategy on protecting health from climate change is made available | National strategy and policy document | Minutes of the NSC submitting proposed strategy for adoption | WHO/MOH | Adoption of strategy by government institutions |
|  | No. of projects used the adaptation measures. | adaptation projects do not exist | At least 3 adaptation projects designed and submitted to donors for funding | National strategy document Project proposals Progress reports | Minutes of the NSC submitting proposed projects for funding Minutes of UNCT working group on climate change | WHO/MOH | Lack of interest from the donor community. Capacity to develop technically sound and convincing proposals |
|  | Early warning system to monitor and assess health impacts of climate change established and operated | There is no national early warning system on health and climate change | At least one National early warning system on health and climate change established | Database Forecast indicators Prediction models | Conduct a test on scenarios and potential responses by the third year | WHO/MOH | Availability of data as input to the system. Commitment of government agencies to release existing data |
| Output 2.4 Adaptation capacity of Zarqa River Basin to climate change is piloted and strengthened | No. of climate change impact studies on water availability and quality on Zarqa River basin conducted | Limited number of cc impact studies on water resources availability and quality in Zarqa River basin | At least four climate change risks to water resources availability and quality in Zarqa River basin are identified | Reports of CC change impact studies Documents including the adaptive mechanisms | Collected for progress reports | UNDP/MOEnv | Commitment of governmental agencies Availability of experts in climate change adaptations |
|  | No. of opportunities and barriers to adaptation to climate change identified | studies on adaptation to climate change are not sufficient | At least 3 opportunities and 5 barriers to adaptation to climate change risks assessed | Document on opportunities and barriers to adaptation to climate change | Collected for progress reports Minutes of RSC | UNDP/MOEnv | Availability of financial resources |
|  | No. of policy options for adaptation to CC adopted by policy makers | No policy options for adaptation to CC | At least one strategy for legal and institutional frameworks approaches and tools for IWRM in the Zarqa River basin reviewed Adaptation to climate change mainstreamed into national action plans and policies | Legal framework proposal document. National Development Plans | Collected for progress reports | UNDP/MOEnv | Willingness of government to develop legislation and policy Policy options to adaptation to CC adopted by policy makers |
|  | No. of training courses and workshops conducted | Limited no. of training courses and workshops | At least 3 local institutions and 100 individuals participating in the capacity building programme | Training courses manuals Workshops feed back reports | Review training feedback reports Prepared for progress reports | UNDP/MOEnv/MOE and local communities | Capacity of training institutions. Willingness of local stakeholders |
|  | No. of Community member participated | Little awareness on CC issues within the community | At least 3 local institutions and 100 individuals participating in the capacity building programme | List of participants Reports of field visits Mid-term evaluation Progress reports | Collected for progress reporting Conduct field visits | UNDP/MOEnv | Weak cooperation or willingness to participate by key stakeholders Conflict of interest among implementing agencies |
|  | No. of farms implementing the adaptation measures | None of the farms in Jordan implementing any adaptation measures to CC | 5 farms implementing the adaptation measures | Documentation on farms adaptation Field visits reports Progress reports | Conduct field visits | UNDP/MOEnv | Willingness of farmers to adopt measures |
|  | No. of successful cases documented and upscaled | Information on national successful cases is not available | At least 3 successful cases are documented and upscaled or out-scaled | Case studies documentation | Collect case studies and dessiminate among stakeholders | UNDP/MOEnv | Willingness of local communities to share knowledge and success stories. Lack of incentives. |
|  | No. of linkages to regional and global experiences established IWRM plan for Zarqa River basin including adaptation measures. | Knowledge from Zarqa River Basin is not developed. Linkages to regional and global experiences are of non existence | At least 2 linkages to regional and global experiences established Knowledge from Zarqa River Basin developed, documented and shared on local and national levels. Linkages to regional and global experiences exist | Documents on knowledge generated and shared. Reports and feedback from regional and global entities | Conduct and inventory of knowledge shared Collected for progress reporting | UNDP/UNESCO/MOEnv MWI | Availability of experts in IWRM Conflict between participating agencies |