UNESCO-UNDP Joint Programme Culture and Heritage for Social and Economic Development

Annual Work Plan for 2009 (updated after Quarter 2)

| ANNUAL TARGETS | ACTIVITIES (*) | Q2 | Q3 | Q4 | Q5 |
| --- | --- | --- | --- | --- | --- |
|  |  | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII |
| Output 1.1 Culture is treated as an integral part of national Government strategy, rather than an isolated sector strategy |
| Three fiscal and/or financial mechanisms are identified | 1.1.1 Develop new fiscal and financial mechanisms to increase private sector investment and civil society involvement in support of culture and cultural heritage |
|  | Actions: a. Develop two consultancies, on fiscal and financial mechanisms respectively, starting with the fiscal component | X |  |  |  |
|  | b. Prepare TORs for a local consultant to prepare an overview document on the current situation | X |  |  |  |
|  | c. Prepare TORs for an international consultant to develop the fiscal mechanisms and suggest follow-up procedure |  | X |  |  |
|  | d. Organize open bid for intl. consultant with both law and finance expertise |  | X |  |  |
|  | e. Hire consultants and have study completed |  |  | X |  |
|  | f. Present study to lawmakers |  |  | X |  |
| Implementation is underway on two UNESCO normative instruments on culture | 1.1.2 Support national authorities on the implementation of UNESCO Conventions of 2003 and 2005 |
|  | Actions: a. Contact relevant stakeholders to find out the state of affairs regarding the UNESCO conventions 2003 and 2005 and Governmental actions taken | X |  |  |  |
|  | Convention 2005 (Cultural Diversity) b. Meetings with key government stakeholders to agree on procedure | X |  |  |  |
|  | c. Hold inception meeting and agree on activity plan | X |  |  |  |
|  | d. Assist in establishment of an inter-ministerial committee for the convention (Postponed due to elections) | X |  |  |  |
|  | e. Hold workshop on the convention with line ministry officials |  |  |  | X |
|  | f. Translate two UNESCO booklets about the convention, and print | X | X |  |  |
|  | g. Establish the core group for Cultural Diversity, and initiate national consultation process | X | X |  |  |
|  | h. Support delegate of the National Coalition to COP in Paris (June) |  | X |  |  |
|  | Convention 2003 (Intangible Heritage) i. Hold inception workshop with MTCYS, Nat. Com. for Intangible Heritage and Gjirokastra Folk Festival Committee | X |  |  |  |
|  | j. Collect project ideas and agree on priority action plan | X |  |  |  |
|  | k. Identify project partners and develop project proposals |  | X |  |  |
|  | l. Implement activities |  | X | X | X |
| Successful and effective implementation of year one annual work plan | 1.1.3 Policy support and programme management, including coordination between UN agencies, implementing partners, and other relevant stakeholders |
|  | Actions: a. Project Management Unit completed | X |  |  |  |
|  | b. Office Premises secured | X |  |  |  |
|  | c. Adopt Communication Strategy | X |  |  |  |
|  | d. Hold Launch Event and Inception Meeting | X |  |  |  |
|  | e. Draft fact sheet and draft quarterly newsletter published | X | X | X | X |
|  | f. Draft Annual Work Plan for 2009 completed | X |  |  |  |
|  | g. Draft Procurement Plan for 2009 completed | X |  |  |  |
|  | h. Annual Work Plan adopted by PMC | X |  |  |  |
|  | i. Quarterly Reports adopted by PMC | X | X | X | X |
| Output 1.2 Private owners of cultural monuments are given increased opportunities to conserve and protect their properties |
| Architectural competition (w/ website) completed and criteria for demonstration project award announced | 1.2.1 Architectural Competition on new uses for historic structures to protect them through investment and higher-value use |
|  | Actions: a. Hire a local architect consultant | X | X |  |  |
|  | b. Hire a website company | X |  |  |  |
|  | c. Prepare the background information for the historical sites to be referred to by interested applicants | X | X |  |  |
|  | d. Decide on how to use the prize money | X | X |  |  |
|  | e. Clarify copyright issues | X | X |  |  |
|  | f. Design the CHSED main website and the architectural competition link | X |  |  |  |
|  | g. Website fully operational | X | X |  |  |
|  | g. Identify the members of the panel of judges | X | X |  |  |
|  | h. Announce the start of the competition |  | X |  |  |
|  | i. Maintain communication (on–line) with interested applicants |  | X |  |  |
|  | j. Panel of judges convenes for the evaluation of the proposals |  |  | X |  |
|  | k. Announcement of the winners |  |  | X |  |
| 40 owners of cultural monuments are better informed on the opportunities to restore their properties | 1.2.2 Work with civil society to hold public seminars on how to transform historic buildings and publish accompanying “how-to”- document |
|  | Actions: a. Draft TORs and hire a local NGO/consultant | X |  |  |  |
|  | b. Local NGO/consultant to undertake research on how to access funds, pertinent regulations, and to identify participants |  | X |  |  |
|  | c. “How-to” document published |  |  | X |  |
|  | d. Hold seminars |  |  | X | X |
| Output 1.3 Government strategies and action plans on culture and related sectors benefiting from new data gathered and interpreted |
| Baseline indicators identified and incorporated into Culture Strategy and Action Plans | 1.3.1 Gather and interpret data and statistics necessary to establish baseline indicators for the implementation of the Cultural Strategy and related Action Plans |
|  | Actions: a. Prepare TORs for international consultant to determine culture indicators | X |  |  |  |
|  | b. Hire international consultant | X |  |  |  |
|  | c. Cultural indicators study drafted in cooperation with MoTCYS statistician |  | X |  |  |
|  | d. Culture indicators’ study adopted by MTCYS |  |  | X | X |
| ANNUAL TARGETS | ACTIVITIES | Q2 | Q3 | Q4 | Q5 |
|  |  | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII |
| Output 2.1 National History Museum is transformed into a modern cultural institution at international standards of governance, management, documentation, presentation, conservation and security |
| New public-private governance structure for National History Museum identified and approved by Government | 2.1.1 Establish a management and governance structure for a “world-class” National History Museum (NHM) |
|  | Actions: a. Have inception workshop with key stakeholders and agree on procedure | X |  |  |  |
|  | b. Finalize and announce TORs for NHM local consultant | X |  |  |  |
|  | c. Hire local consultant | X |  |  |  |
|  | d. Develop and announce TORs for NHM international consultant | X |  |  |  |
|  | e. Hire international consultant | X | X |  |  |
|  | f. Establish the Advisory Board for the NHM | X | X |  |  |
|  | g. Advisory Board meets in Tirana |  | X | X |  |
|  | h. Draft Concept Paper/Strategic Guidelines for NHM management elaborated and approved by Advisory Board and PMC |  |  | X |  |
| 3 action plans created in conformity with the Museum’s strategic guidelines | 2.1.2 Create operational or action plans for National History Museum to meet international standards of documentation, conservation, security, and presentation |
|  | Actions: a. Develop and announce TORs for 3 international consultants |  |  | X |  |
|  | b. Hire three international consultants to develop three action plans |  |  | X |  |
|  | c. Three action plans adopted, including guidelines for activity 2.1.3.d |  |  | X |  |
| Substantial improvement of the quality of visitor experience inside museum | 2.1.3 Execution of activities that are in conformity with the Museum’s approved strategic guidelines that will make a substantial improvement to the visitor experience inside the Museum |
|  | Actions: a.TORs for architectural consultant drafted and consultant hired |  | X | X |  |
|  | b. Architectural competition started |  |  | X |  |
|  | c. Winner of architectural competition determined |  |  |  | X |
|  | d. First reconstruction activities started which can be done independently from new museum concept and architectural competition |  | X | X |  |
| Output 2.2 Albania's archaeological park system upgraded to better safeguard Albania's cultural heritage |
| Assessment completed and recommendations shared | 2.2.1 Assessment of fiscal, management and governance structure of archaeological parks performed and recommendations shared |
|  | Actions: a. Hire a local consultant on archaeological parks management | X |  |  |  |
|  | b. Draft and announce the TORs for the international consultant |  | X |  |  |
|  | c. Hire international consultant for archaeological parks management |  | X |  |  |
|  | b. Mission of the Int’l consultant to Albania |  |  | X |  |
|  | c. Submission of the study (with an emphasis on Apollonia and Antigonea) |  |  | X |  |
|  | d. Recommendations discussed with decision-makers |  |  | X |  |
| Security measures enacted to mitigate risk at one archaeological park | 2.2.2 Improve security and mitigate risk at Antigonea and Apollonia through creation and implementation of risk management plans |
|  | Actions: a. Draft and announce the TORs for the international consultant |  | X |  |  |
|  | b. Hire the international consultant |  | X |  |  |
|  | c. Mission of the international consultant to the two sites |  |  | X |  |
|  | d. Submission of the risk management plans for the two sites |  |  | X |  |
|  | e. Prepare technical specifications in line with the relevant recommendations (cooperate with communes) |  |  | X |  |
|  | f. Bidding processes carried out |  |  | X |  |
|  | g. Implementation of works |  |  | X | X |
| Output 2.3 Albanian film archives are digitalized and preserved for future generations |
| 600 films of Albanian film are digitalized | 2.3.1 Albania’s film industry documented, digitalized and archived |
|  | Actions: a. NFA submits a proposal on the NFA activities | X | X |  |  |
|  | b. Elaborate and implement action plan |  | X | X |  |
| ANNUAL TARGETS | ACTIVITIES | Q2 | Q3 | Q4 | Q5 |
|  |  | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII |
| Output 3.1 Staff employed at cultural sites are trained in cultural heritage management, conservation, and protection |
| 10 cultural heritage management professionals trained on best practices | 3.1.1 Two courses to train museum and archaeological park staff on best practices in cultural heritage management |
|  | Actions: a. Conduct inception workshop to identify needs of management staff of the museums, archeological parks and MCTYS; the persons to attend the training |  |  | X |  |
|  | b. Organize study tour including training for the management professionals |  |  | X |  |
| 30 employees trained on conservation practices, security and/ or risk management | 3.1.2 Tailored programme to train state employees in conservation practices, security procedures, and risk management; to be offered in 2 courses |
|  | Actions: a. Identify training participants (staff of museums and archeological parks) |  |  | X |  |
|  | b. Identify national expert(s) to draft and conduct training programme (based on action plans produced in the framework of the project) |  |  | X |  |
|  | c. National expert conducts trainings |  |  | X |  |
| Output 3.2 Formal training and credentials available to cultural professionals |
| 25 tourist guides at cultural sites and monument complete tourist guide training course | 3.2.1 Curriculum developed and approved for tourist guides at cultural sites and monuments |
|  | Actions: a. Have inception workshop with MoTCYS and Nat’l Association of Tour Guides of Albania (NATGA) on procedure for the curriculum proposal | X |  |  |  |
|  | b. Follow up on curriculum content, improve or adopt the existing one | X |  |  |  |
|  | c. Identify trainers and participants |  | X |  |  |
|  | d. Implement trainings |  |  | X |  |
| MA Curriculum on Cultural Management developed and approved | 3.2.2 New MA-level program in Arts and Cultural Resource Management designed and accredited |
|  | Actions: a. Develop TORs and hire national consultant | X |  |  |  |
|  | b. Prepare background study to assess the human and institutional capacities, and decide on activities | X |  |  |  |
|  | c. Decide on the institutional arrangement |  | X |  |  |
|  | d. Curriculum developed and accreditation process started |  | X | X |  |
| ANNUAL TARGETS | ACTIVITIES | Q2 | Q3 | Q4 | Q5 |
|  |  | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII |
| Output 4.1 Quality of visitor experience improved at cultural heritage sites |
| Visitor information improved in Berat and Gjirokastra | 4.1.1 Visitor information improved in Berat and Gjirokastra through the creation and support to tourist information centers and increased visitor signage |
|  | Actions: a. Follow-up and finalize bid documents with the Municipality of Berat | X |  |  |  |
|  | b. Implement Berati Tourism Information Center reconstruction and signage improvement | X | X |  |  |
|  | c. Draft and advertise ToRs for local consultant in Gjirokastra | X |  |  |  |
|  | d. Implement improvement activities in Gjirokastra |  | X | X |  |
|  | e. Agree with stakeholders on information materials to be published |  | X |  |  |
|  | f. Prepare TORs and hire designer for information materials |  | X |  |  |
|  | g. Visitor information materials in both cities are published |  |  | X |  |
| Cultural signage improved at one archaeological park | 4.1.2 Access to visitor information improved at Antigonea and Apollonia through signage, informational pamphlets and/or creation of visitor kiosks |
|  | Actions: a. Have inception workshop with stakeholders to agree on activities | X |  |  |  |
|  | Antigonea (bearing the closeness of this archeological site, this activity may start simultaneously with Gjirokastra - 4.1.1) |  |  |  |  |
|  | b. Prepare the technical specifications |  | X |  |  |
|  | c. Implement tender for design and printing of materials (both sites) |  | X |  |  |
|  | d. Prepare map(s), photos and texts of the site | X | X |  |  |
|  | e. Produce information materials |  |  | X |  |
| Output 4.2 Albanian artists and artisans are accessing new markets |
| One business incubator for artists and artisans created and operational | 4.2.1 Support the creation of artisan centers, fairs and business incubators in Gjirokastra, Shkodra, Korce and Berat |
|  | Actions: a. Hold inception meeting with artisan associations | X |  |  |  |
|  | b. Prepare a donor mapping document as to who does what with regard to artisan activities (possibly by the UNV intern) | X |  |  |  |
|  | c. Organize National Conference of Artisans as inception workshop | X |  |  |  |
|  | d. Develop plan of activities and identify partners and project cities in coordination with other donors | X | X |  |  |
|  | e. Implement activities |  | X | X | X |
| 10 artisans trained on business planning or marketing; at least 8 of whom women | 4.2.2 Train artisans in business planning / marketing activities, with special emphasis on gender equality and the empowerment of women |
|  | Actions: a. Prepare TORs for trainer and implement selection process |  | X |  |  |
|  | b. Hire trainer and have training materials and schedules prepared |  | X |  |  |
|  | c. Deliver trainings (emphasis depending on priorities defined on National Conference / inception workshop) |  | X | X | X |
| ANNUAL TARGETS | ACTIVITIES | Q2 | Q3 | Q4 | Q5 |
|  |  | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII |
| Output 5.1 Increased awareness of Albania’s cultural heritage by foreigners |
| National Strategy on Alliance of Civilizations is finalized and approved by GoA | 5.1.1 Support Albania’s strategic process in the Alliance of Civilizations through the implementation of its National Strategy |
|  | Actions: a. Hold inception workshop(s) with key stakeholders and agree on priority activities | X | X |  |  |
|  | b. Collect, develop and approve project proposals | X | X |  |  |
|  | c. Identify implementing partners |  | X |  |  |
|  | d. Implement priority project proposals |  |  | X | X |
| Improved stand at trade fairs designed and new cultural brochures available | 5.1.2 Support to the development and implementation of a cultural marketing strategy to strengthen Albania’s image abroad |
|  | Actions: a. Hold inception workshop with key stakeholders in order to agree on procedure and activities | X |  |  |  |
|  | b. Draft TORs and advertise for a national consultant to work in cooperation with the National Tourism Agency (NTA) on an overview of the situation | X |  |  |  |
|  | c. Local consultant to prepare the hiring of an international firm to draft the Marketing Strategy and Action Plan (including branding exercise) | X | X |  |  |
|  | d. International firm prepares the strategy |  |  | X | X |
| Two Albanian embassy cultural centers supported to deliver cultural activities | 5.1.3 Support to MoFA strategic efforts for cultural diplomacy |
|  | Actions: a. Hold inception workshop to agree on general concept and line of activities | X |  |  |  |
|  | b. Prepare TORs for international consultant of firm | X |  |  |  |
|  | c. Spanish mission to develop the cultural diplomacy concept |  | X |  |  |
|  | d. Cultural diplomacy concept prepared |  | X | X |  |
|  | e. Supporting materials produced |  | X | X |  |
| Train trainers program established for cultural diplomacy | 5.1.4 Training of MoFA and/or embassy staff to fulfill cultural attaché function |
|  | Actions: a. Hold inception meeting with MoFA Official | X |  |  |  |
|  | b. Identify potential trainer | X |  |  |  |
|  | b. Training programme and manual developed | X | X |  |  |
|  | c. Decide on how and where the trainings are going to be conducted |  | X | X |  |
|  | d. Trainings implemented |  |  | X |  |

(*) Legend:

UNESCO implemented activities are in black letters

UNDP implemented activities are in blue letters

Color Codes:

Green stands for completed activity

Yellow stands for on-going activity

Red stands for not-yet-started activity