# United Nations Development Group Iraq Trust Fund

# Project #:A5-12

# Date and Quarter Updated: October 2008 (3rd Quarter)

# Part One: Summary

| Participating UN Organisation: UNESCO | Sector: Agriculture and Food Security |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Education – Baghdad, Iraq |

# Programme/Project Number: A5-12

| Title | Capacity Building in Water Institutions of Iraq |
| --- | --- |
| Location | Nationwide |
| Project Cost | US $ 3,275,550 |
| Duration | 26 Months |
| Approval Date (SC) | 22/08/2004 | Approval Date (SC) | 22/08/2004 | Approval Date (SC) | 22/08/2004 |
| Project Description | To respond an urgent request from Ministry of Water Resources, the programme aims at building up human resources, technical and institutional capacity of water planning sector through training courses and workshops. The programme also supports to initiate a regional dialogue over the Tigris and Euphrates Rivers among riparian countries. |

# Development Goal and Immediate Objectives

Development goals of this programme are two-fold; 1) ensuring the water security of Iraq through integrated water resources management and 2) establishing the regional framework on equitable water sharing on the Tigris and Euphrates Rivers. In order to achieve the overall goals, the programme has five components to produce the following outcomes; 1) technical capacity of IWRM enhanced, 2) institutional capacity of water planning developed, 3) the training and research centre inside Iraq rehabilitated and developed, 4) pilot studies and researches as a preliminary water resources assessment launched and 5) the dialogue of the regional cooperation on transboundary water issues on the Tigris and Euphrates Rivers initiated.

# Outputs, Key activities and Procurement

| Outputs | Technical and institutional capacity of water experts/engineers/policy makers of Integrated Water Resources Management strengthened. Regional dialogue on the Tigris and Euphrates Rivers among Turkey, Syria, Iran and Iraq initiated Networking Iraqi water communities with the regional and international water community strengthened. |
| --- | --- |
| Activities | Organize training courses for Iraqi water experts/engineers on several aspects of Integrated Water Resources Management Organize Organize regional meetings and workshops with a attendance of experts from riparian countries in order to facilitate the dialogue on the Tigris and Euphrates Rivers Supply equipments to conduct the study and to implement training courses in the new training center |
| Procurement (major items) | Water sampling and analysis equipments for the laboratory IT equipments for the training and research centre Technical reference books and back issues of academic journals |

# Part Two: Situation as of October 2008

| Funds Committed | $3,188,193 | % of approved | 97.33% |
| --- | --- | --- | --- |
| Funds Disbursed | $3,171,666 | % of approved | 96.83% |
| Forecast final date |  | Delay (months) |  |

# Quantitative achievements against objectives and results

| Build technical capacity to conduct water resources assessment | 250 participants trained on technical aspects of Integrated Water Resources management | % of planned | 100 |
| --- | --- | --- | --- |
| Build institutional capacity of Iraqi policy makers to formulate the national water strategy | 50 participants trained in the institutional aspects of IWRM. Primary discussion among water-related ministries was facilitated by organizing joint trainings. | % of planned | 100 |
| Develop the training centre in Iraq to disseminate the concept of IWRM at all levels | The training and research centre of the MoWR was equipped with necessary equipments. One training course was organized to train the staff member of the centre | % of planned | 80 |
| Assess available water resources through pilot studies and researches | 5 papers of pilot studies were presented by Iraqi water experts in the international and regional conferences. Other pilot studies are ongoing. | % of planned | 80 |
| Enhance regional cooperation of water sharing of Tigris and Euphrates Rivers | 3 trilateral meeting and 2 joint trainings were organized to discuss on the Tigris and Euphrates rivers with the participation from Turkey, Syria, Iraq and Iran. | % of planned | 100 |

# Qualitative achievements against objectives and results

For technical and institutional capacity building, 18 training courses and 6 workshops were organized on a variety of subjects of IWRM resulting in that 300 water experts participated in capacity building activities, involving nine different water-related Ministries. One country preliminary country assessment paper was produced for UNESCO International Hydrological Programme, 4 research papers were presented in the international and regional conferences. 350 titles technical books and 10 titles of academic journals’ back numbers were provided for the restoration of the Ministry library. The one training centre for water experts was equipped with necessary instruments for research and training. A progress on the transboundary water issues on the Tigris and Euphrates rivers was satisfactory. In the reporting period, 3 trilateral meetings attended by government officials from Turkey, Syria and Iraq were organized to discuss on regional cooperation on the shared water issues on the Tigris and Euphrates. As a result of meetings, some joint capacity building activities were implemented: one joint workshop on the international water resources modelling in cooperation with US Department of Energy and a joint training on Dam safety, both were attended by Turkish, Syrian, Iranian and Iraqi experts. Outputs of these activities could bring positive inputs to the official track of on-going diplomatic negotiation among the countries. Challenges however remain. Sharing water is one of the politically sensitive subjects among neighbouring countries, as they have never reached a comprehensive agreement for a long time. Progress made was satisfactory during the period to initiate some joint activities, but intermediary efforts to facilitate continuous dialogues must be sustained with help of the international community.