# United Nations Development Group Iraq Trust Fund

# Project #:A5 -15

# Date and Quarter Updated: October –December, 2009 (Quarter 4)

| Participating UN Organisation: Food and Agriculture Organization of UN (FAO) Sector: Agriculture and Food Security Government of Iraq - Responsible Line Ministry: Ministry of Agriculture (MoA) |  |
| --- | --- |

| Title | Restoration and modernization of fish production in Iraq |
| --- | --- |
| Geographic Location | Iraq - Center/South Provinces ,Missan, Babylon, Wasit ,Baghdad Governornets |
| Project Cost | US$ 7 312,177 |
| Duration | 2 Years |
| Approval Date (SC) | 14/07/2006 | Starting Date | 01/07/2006 | Completion Date | Original: 1/07/2008 Extension until: 31/03/2010 |
| Project Description | Given the large water bodies around the project area, the high market demand for carps, the dynamic private sector, the availability of wide areas of alluvial saline soils and the feasibility of increasing production by reactivating presently non-operational farms, the project aims to support the fish sub sector in Iraq and to increase significantly the production from existing farms through improved and proven management and production technology. |

Development Goal and Immediate Objectives

The development goal is to improve food security through the support of fish production in Iraq by stimulating the resumption of fish farming in large and small scale enterprises through practical demonstrations of applicable fish farming techniques, supply at cost of fingerlings, and on-going support of an active, applied and adaptive research programme. The immediate objectives of this project are to: Build or restore the productive capacity to supply fish fingerlings to the commercial fish farming industry. Build and restore a series of fish farming enterprises in the most needed areas in Iraq. Demonstrate new lake-based fish farming methods, and initiate stocking of native carps in selected lakes. Improve local capacity to manage and develop the fishery/aquaculture sector.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | Ecological and socio-economic baseline study conducted at Huweza marsh in favour of fisheries and aquaculture development. Central fish hatchery and laboratory upgraded, New hatchery for native carp breeding plus two pilot cage fish culture facilities established Complete closed recirculation system for exotic carp fish breeding and fingerling production established. Capacity built among Iraqi scientists and technicians of GBFRD in aquaculture development and current fish farming practices. Relevant extension material prepared. |
| Activities | Complete final report of Huweza marsh survey prepared by Basrah University and send to H.Q in order to print and publication Construction of one Research Center at Huweza and two administrative buildings at Hindia and Kut dams Installation of closed recirculation system at Seweraa and installation of pilot cages at Hindia and Kut Construction of the Chinese hatchery with overhead tank. Preparation of extension materials. Capacity built among Iraqi scientists |

| Funds Committed | USD$ 154,632 | % of approved | 2% |
| --- | --- | --- | --- |
| Funds Disbursed | USD$ 6,697,522 | % of approved | 92% |
| Forecast final date | 31/3/2010 | Delay (months) | N/A |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men* | 9,000 | 70% |
| Women |  |  |
| Children |  |  |
| IDPs |  |  |
| Others |  |  |
| Indirect beneficiaries | 1,250 | 30% |
| Employment generation (men/women) | 60 | 10 % |

*In Iraq fisheries activities are done predominately by men. This programme targets the fishermen but indirectly benefits women and children, etc.

| Quantitative achievements against objectives and results |
| --- |
| Training and capacity building | Completed | % of planned | 100 |
| Installation of closed recirculation system | Completed | % of planned | 100 |
| Construction of building structures and ponds for hatchery facilities at Huweza marsh | Completed. | % of planned | 100 |
| Construction of two administration building of Kut &Hindia sites | Completed | % of planned | 100 |
| Construction of Chinese style hatchery tanks and water tower | Completed. | % of planned | 100 |
| Procurement and installation of laboratory equipments of hatchery at Huweze Marsh | Procurement of the equipments completed and the installation of equipment in progress | % of planned | 95 |
| Preparation and publication of extension materials. | The extension manuals were translated into the English language for HQ review and sent to GBFRD for translation back to Arabic language for MOA. Publication will occur following approval. | % of planned | 90 |  | The extension manual under translation into English language for technical clearance |
| Procuremen truck for fish transfer | Retendering locally in process. See section on Main Implementation constraints and challenges. | % of planned | 25 |  |  |
| Installation of fish pilot cage culture at Kut and Hind dams | Installation in progress and there are some equipments still with the supplier that are yet to be delivered. Contract, yet to be prepared, with supplier for installation the cages at Hindia site | % of planned | 25 |

Qualitative achievements against objectives and results

Positive steps have been taken towards the modernization of the fisheries sector in Iraq starting with the installation of pilot cages and the close recirculation system, and the complete the construction of Chinese type fish hatchery. In addition, hydrological, biological and socio-economic data have been generated to enable the development of a fisheries and aquaculture development plan at Huweza marsh. Furthermore, the operational capacity of fish fry/fingerling production has been enhanced to restore the aquaculture sector. Preparation of extension material in progress. The publication of the materials will disseminate knowledge among aquaculture farmers on fish farming methods. Training programmes, for among Iraqi scientists and technicians of GBFRD, in aquaculture development and current fish farming practices, have been completed.

Main implementation constrains & challenges (2-3 sentences)

The installation of the pilot fish cages systems has been delayed due to relevant damages occurred to the equipment during the installation process. When the first unit of the cage was installed, the cages broke, due to lack of quality. FAO is collaborating with the MOA and the supplier to overcome the technical problems and complete the installation as soon as possible.