# United Nations Development Group Iraq Trust Fund

# Project Summary Sheet

# Project #: A5 - 16

# Date and Quarter Updated: 05 January 2009

# (October-December 2008)

| Participating UN Organisation: FAO | Sector: Agriculture and Food Security |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Agriculture (MoA) |

# Programme/Project Number: A5-16 (OSRO/IRQ/502/UDG)

| Title | Rehabilitation and Development of the National Seed Industry in Iraq |
| --- | --- |
| Geographic Location | Nationwide coverage for the strategy and technical assistance. Seed policy and legislation. Physical rehabilitation in North, Centre and South. Training overseas and in the country |
| Project Cost | USD 5 383 460 |
| Duration | 34 months |
| Approval Date (SC) | 20/4/2006 | Starting Date | 18/05/2006 | Completion Date | 31/03/2009 |
| Project Description | Formulation of a national seed policy; revision and updating of existing seed legislation; improvement of coordination and oversight arrangements; rehabilitation of damaged seed production infrastructure in government research centres and the State Board for Seed Testing and Certification; training of selected personnel in key seed industry disciplines. |

# Development Goal and Immediate Objectives

The development goal of the project is to improve food security and nutrition in Iraq. This will be achieved through the immediate objectives of rehabilitation and improvement of the national seed programme, which will promote the availability and use of high quality seeds of adapted varieties to farmers and provide the foundation of a sustainable seed industry.

# Outputs, Key activities and Procurement

| Outputs | A national seed policy formulated, existing seed legislation reviewed and recommendations provided for its further improvement; A functional seed programme coordination and oversight body, the National Seed Council put in place; existing database for seed quality control operations improved and strengthened; transportation and communication system in SBSTC for field inspection, seed processing plants and other seed quality control operations improved with procurement of essential equipment; Essential buildings for seed testing laboratories constructed. Adapted varieties characterized and breeder seeds produced in the research stations; variety maintenance techniques and procedures for the targeted crops developed; foundation seed production undertaken for wheat, barley, maize and rice using breeder seeds from the research stations; Exposure of 2 senior Iraqi staff and 30 scientists to the latest international technologies and development in improving national seed industry. In-service training of 115 Iraqi technical staff in different areas of seed technology |
| --- | --- |
| Activities | Organize a national seed workshop followed by a national seed policy forum and draft a national seed policy; prepare full TOR, structure and mandate of a National Seed Council; undertake review of existing seed legislation; Undertake laboratory building construction works; as well as install equipment and machines in seed laboratories and research stations; Seeds production and quality control: assist research stations in the production of breeder seeds; assist in production of foundation seed production in the centres; develop required techniques and procedures for variety maintenance; Capacity building: arrange study tour overseas for 2 senior staff; organize fellowships abroad on seed technology of targeted crops for 30 participants; conduct in-service training on variety maintenance, variety development and evaluation, seed production and marketing system, and seed quality control; organize in-service training for 115 technical personnel in area of seed technology including use and management of improved database. |
| Procurement (major items) | Agricultural equipment, green houses, seed processing plant, and seed testing equipment. |

# Situation as of end December 2008

| Funds Committed | USD 833 749 | % of approved | 15 % |
| --- | --- | --- | --- |
| Funds Disbursed | USD 3 240 668 | % of approved | 60 % |
| Forecast final date | 31/03/2009 | Delay (months) |  |

# Quantitative achievements against objectives and results

| Formulation of National Seed Policy document | National Seed Policy document formulated after organizing a national seed policy forum, was adopted by the Government of Iraq | % of planned | 100% |
| --- | --- | --- | --- |
| Seed Legislative Review Meeting | Seed legislative review meeting participated by seed industry stakeholders was organized which resulted in the drafting of Iraq Seed Law | % of planned | 100% |
| Seed technology in-service training | In-service training course on seed quality control organized for 30 technical personnel belonging to SBSTC, SBAR, Mesopotamia State Seed Company and Department of Agriculture | % of planned | 100% |
| Mobile seed processing plants installation | Eight units of mobile seed processing plants to be used for processing foundation class seeds were installed and fully operated | % of planned | 100% |
| Procurement of farm machinery, seed testing equipment and laboratory commodities | Purchase order issued for the procurement of platform balance (3 units). The purchase order for germination paper and certification tags would be implemented soon . | % of planned | 95% |
| Greenhouse construction | Four units of greenhouses were delivered | % of planned | 100% |
| Seed quality control labs construction | The tender has been opened on 5th Nov. and the offers will be sent to TCES for consideration and evaluation | % of planned | 60% |

# Qualitative achievements against objectives and results

Iraq National Seed Policy document formulated following organization of Seed Policy Forum participated by seed industry stakeholders was adopted by the Government of Iraq as blueprint for the growth of the national seed industry. The policy document clearly outlines the regulatory functions of the government and its role in support to the private sector for greater involvement in the seed industry. In line with the Policy, a draft of the Iraq Seed Law has been prepared as result of the seed legislative review meeting through a consultative process participated by legal experts and Iraqi seed industry stakeholders. To present to the Government as the fundamental seed law of the country, further fine-tuning of the draft will be undertaken through seminars/meeting with stakeholders in Iraq.. Through participation in the in-service training course on seed production and marketing (25) trainees and seed quality control, ,thirty technical personnel of the State Board for Agricultural Research (SBAR), State Board of Seed Testing and Certification (SBSTC), Mesopotamia State Seed Company and Department of Agriculture which included women staff, the trainees acquired new skills which were transferred to them by the resource persons trained in overseas training programme (training of trainers programme). The enhanced capacity building of the local staff will contribute positively in the sustainability of the seed programme. . Installation of the mobile seed processing plants in the research centres of the SBAR will strengthen the crop improvement capacity of the Ministry of Agriculture. The processing plants are being utilized in the production of breeders and foundations classes of seed. The procurement of farm equipment like low profile thresher will be useful in Iraqi scientists’ efforts to breeders seed production. Laboratory equipment and supplied commodities are used in seed testing procedures to determine the quality attributes. The aim of supplying these equipments is to avail the farmers of high quality seeds to result improved crops production and productivity. Technical assistance also was provided for the production of foundation seed in the research farms. Construction of greenhouses and seed testing laboratory buildings will further strengthen MoA’s capacity for crop improvement and seed quality control.