# United Nations Development Group Iraq Trust Fund

# Project #: A5 - 16

# Date and Quarter Updated: 10 January 2010 (October-December 2009, 4th Quarter)

| Participating UN Organisation: FAO | Sector: Agriculture and Food Security |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Agriculture (MoA) |

| Title | Rehabilitation and Development of the National Seed Industry in Iraq |
| --- | --- |
| Geographic Location | Nationwide coverage for the strategy and technical assistance. Seed policy and legislation. Physical rehabilitation in North, Centre and South. |
| Project Cost | USD 5 383 460 |
| Duration | 12 months |
| Approval Date (SC) | 20/4/2006 | Starting Date | 18/05/2006 | Completion Date | Original: 18/05/2008 Extension: 31/03/2010 |
| Project Description | This project aims to increase domestic food production thus improving food security and nutrition for the Iraqi people. This will be done through the formulation of a national seed policy; revision and updating of existing seed legislation; improvement of coordination and oversight arrangements; rehabilitation of damaged seed production infrastructure in government research centres and the State Board for Seed Testing and Certification; training of selected personnel in key seed industry disciplines. |

Development Goal and Immediate Objectives

The development goal of the project is to improve food security and nutrition in Iraq through the rehabilitation and improvement of the national seed programme. This will promote the availability and use of high quality seeds of adapted varieties to farmers and provide the foundation of a sustainable seed industry. The immediate objectives are to: Enhance the performance of the national seed industry through formulation of a national seed policy, review and up-grade of the seed legislation in place and improvement of coordination and oversight of arrangement. Increase the capacity of the national seed industry through rehabilitation of the damaged infrastructure for variety development and evaluation, variety maintenance, initial seed multiplication and seed quality control. Improve the quality of key human resources in the national seed industry through training.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | A national seed policy formulated, existing seed legislation reviewed and recommendations provided for further improvement A functional seed programme coordination and oversight body, the National Seed Council, put in place Existing database for seed quality control operations improved and strengthened Transportation and communication system in SBSTC for field inspection Seed processing plants and other seed quality control operations improved with procurement of essential equipment Essential buildings for seed testing laboratories constructed Adapted varieties characterized and breeder seeds produced in the research stations Variety maintenance techniques and procedures for the targeted crops developed Foundation seed production undertaken for wheat, barley, maize and rice using breeder seeds from the research stations Exposure of 2 senior Iraqi staff and 32 scientists to the latest international technologies and development in improving national seed industry In-service training of 115 Iraqi technical staff in different areas of seed technology |
| Activities | Organize a national seed workshop followed by a national seed policy forum and draft a national seed policy Prepare full TOR, structure and mandate of a National Seed Council Undertake review of existing seed legislation Undertake laboratory building construction works as well as install equipment and machines in seed laboratories and research stations Seeds production and quality control: assist research stations in the production of breeder seeds; assist in production of foundation seed production in the centres Develop required techniques and procedures for variety maintenance; Capacity building: arrange study tour overseas for 2 senior staff; organize fellowships abroad on seed technology of targeted crops for 32 participants; conduct in-service training on variety maintenance, variety development and evaluation, seed production and marketing system, and seed quality control; organize in-service training for 115 technical personnel in area of seed technology including use and management of improved database. |
| Procurement (major items) | Agricultural equipment, green houses, seed processing plant, and seed testing equipment. |

| Funds Committed | USD 513 208 | % of approved | 10% |
| --- | --- | --- | --- |
| Funds Disbursed | USD 3 981 972 | % of approved | 74% |
| Forecast final date | 31/03/2010 | Delay (months) | N/A |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 138 | 99% |
| Women | 15 | 99% |
| Children | n.a. |  |
| IDPs | n.a. |  |
| Others | n.a. |  |
| Indirect beneficiaries |  |  |
| Employment generation (men/women) |  |  |

| Quantitative achievements against objectives and results |
| --- |
| Formulation of National Seed Policy document | National Seed Policy document formulated following the national seed policy forum. The document has been adopted by the Government of Iraq | % of planned | 100% |
| Preparation of Seed Law draft | Final draft of the Seed Law prepared by seed industry stakeholders during the final seed legislative review. | % of planned | 100% |
| Installation of mobile seed processing plants. | 8 units installed including the vertical bucket elevators are now fully operational | % of planned | 100% |
| Procurement of additional office automation equipment | Additional unit of laptop, printer and scanner needed for the use of project coordinator at the MoA was undertaken. | % of planned | 100% |
| Procurement of farm machinery, seed testing equipment and laboratory commodities | The procurement of the small remaining four wheel drive tractor was done. | % of planned | 100% |
| Procurement of laboratory commodities | Upon bid evaluation and technical clearance for procurement of 1 million seed certification tags, the purchase order was issued to the supplier. | % of planned | 100% |
| Construction of greenhouses | Four units of greenhouses with climate control facilities were delivered and installed. | % of planned | 100% |
| Construction of Seed quality control labs | The construction of seed testing laboratories being undertaken. | % of planned | 95% |
| Procurement of rice seed lab | Inadequate responses were received in response to the tenders. Technical specifications revised and sent to MoA for endorsement. | % of planned | 50% |
| International Training of Trainers (ToT) programme | Training programme o n corn dryer installation, maintenance and operation to occur. | % of planned | 100% |
| Seed technology in-service training | In-service training course on variety verification and database management completed for 30 technical personnel belonging to SBSTC, SBAR of the MoA | % of planned | 100% |

Qualitative achievements against objectives and results

An Iraq National Seed Policy document has been formulated and adopted by the Government of Iraq as a blueprint for the growth of the national seed industry. The policy document clearly outlines the regulatory functions of the government and its role in supporting an enhanced private sector involvement in the seed industry. In line with the Policy, a draft of the Iraq Seed Law prepared through a consultative process participated by legal experts and Iraqi seed industry stakeholders has been submitted to Ministry of Agriculture in English and Arabic versions. The MoA will advance the law through the parliamentary process for adaptation and enactment. Through participation in the in-service training course on variety maintenance and database management by thirty technical personnel of the State Board for Agricultural Research (SBAR), State Board of Seed Testing and Certification (SBSTC), of the Ministry of Agriculture included women staff, the trainees acquired new skills which were transferred to them by the resource persons trained in overseas training programme (training of trainers programme). The enhanced capacity building of the local staff will contribute positively in the sustainability of the seed programme. The procurement of farm equipment will be useful in Iraqi scientists’ efforts to breeders’ seed production. Laboratory equipment and supplied commodities are used in seed testing procedures to determine the quality attributes. The aim of supplying these equipments is to avail the farmers of high quality seeds to result improved crops production and productivity. The utilization of the climate-controlled greenhouses will facilitate the Iraqi scientists for varietal evaluation and screening all the year round. The rice seed testing equipments are to be used by SBAR. The construction of laboratory buildings which is almost complete will further strengthen MoA’s capacity for crop improvement and seed quality control.

Main implementation constrains & challenges (2-3 sentences)

General implementation and monitoring aspects are affected due to the prevailing situation in Iraq. The general peace, law and order problem in Iraq creates problem for any expatriate staff to visit. Even local staffs have problems visiting concerned offices, research centres and farms. Consequently information flow from the field to Amman has been slow This definitely affects the implementation of this remote-controlled project implementation. As expected, progress may be slow and output not as set in the work plan. However, it should catch up once peace and stability returns to Iraq. Other than this there are no other problems.