# United Nations Development Group Iraq Trust Fund

# Project #: A5-17

# Date and Quarter Updated: 15 October 2008 (Quarter 3)

| Participating UN Organisation: UNIDO | Sector: Agriculture and Food Security |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: | KRG Ministry of Industry KRG Ministry of Agriculture |

| Title: | Community Livelihoods and Micro Industry Support Project in Rural and Urban Areas in Northern Iraq |
| --- | --- |
| Geographic Location | Erbil and Sulaymaniyah |
| Project Cost | $5,800,116 |
| Duration | 32 months |
| Approval Date (SC) | 20 Apr 2006 | Starting Date | 29 June 06 | Completion Date | 28 Feb 2009 |
| Project Description | The purpose of this UNIDO/FAO micro industry support project is to increase the capability of rural and urban communities in northern Iraq to engage in viable non-farming agro-enterprises addressing not only their priorities but also facilitating their on-going participation in their development process. |

Development Goal and Immediate Objectives

Development Goal

To help the peace process and economic recovery of the country. This will be achieved through increased capability of marginalized and poor communities to engage in viable non-farming agro-enterprises, thus reducing their dependency on relief aid and helping them to move towards sustainable livelihood. The project is consistent with the Government of Iraq’s objective to rehabilitate and sustain livelihoods that have been affected by conflict and instability.

Key Immediate Objectives

- Support local communities in the establishment of a variety of viable auxiliary income-generating activities in the food processing sector and other cottage agro-industries, thereby strengthening their household economy so they can contribute to their well-being on their own.

- Raise technology and production levels in targeted villages by providing the poor and marginalized communities the means to process their agricultural products.

- Improve the technical and business management skills of people in the project area especially the women, youth, and the IDPs, through appropriate training in the food processing, construction, manufacturing or agro-supply chain sub-sector.

# Outputs, Key activities and Procurement

# Outputs

# 1.1 A more capable local community addressing not only their priorities but also facilitating their on-gong participation in their development process.

# 1.2 15 model Production Groups in food processing and other micro agro-enterprises established and linked with markets.

# 2.1 Increased small-scale farmers’, IDP’s and returnees’ income through expanded basic agro-industrial production/productivity.

# 2.2 A minimum of 2,000 households benefiting directly from the improved technologies for post-harvest activities.

# 3.1 A minimum of 600 young people provided with marketable skills to enable them to obtain jobs and/or start-up an economic activity to sustain livelihoods for themselves and their families.

# 3.2 A number of small-scale food processing enterprises and other cottage industries established and organized in relevant production networks.

# Key Activities

- Assessing the needs of project beneficiaries (using selected participatory appraisal tools), identifying viable productive income generation activities and appropriate technologies.

- Selecting project sites with the collaboration of all stakeholders, based on the distribution of vulnerable groups in both urban and rural areas and the availability of raw materials and markets.

- Finalising selection and identification of beneficiaries based on the criteria agreed upon by all stakeholders: local governments, women’s associations, directorates of counterpart ministries, village elders and Project Steering Committee members.

- Rehabilitation of vocational training centres.

- Training of trainers in the selected technologies and entrepreneurship.

- Procurement of pilot plants and workshop equipment for the training centre, project beneficiaries, model cottage and micro-industries; and installation of these equipments.

- Training of beneficiaries in entrepreneurial skills and technology to start their own business  or to increase employment opportunities.

# Mentoring the beneficiaries through their businesses.

Procurement

Non-Food: The project has purchased training equipment for industrial schools and vocational training providers in mechanics, metal working, welding, carpentry, leatherworking, and sewing/tailoring. In addition, project procured equipment has also been allocated for the establishment of a number of Production Groups in agro and auto repair, welding and fabrication, machine workshops, carpet weaving, tailoring, and carpentry/joinery. The project has also procured beneficiary toolkits for its various vocational training course participants.

Food: To support food related post-harvest processing activities the project has procured training equipment to upgrade the knowledge and skills that project targeted beneficiaries have in food related technologies. Like in the non-food component of the course, the project is transferring, installing, and commissioning this equipment in a number of training providers throughout the two governorates. In addition, the project is resourcing a number of Production Groups in food technologies. These include, dairy, fruit and vegetable, beekeeping, Burghul, and olive processing. Finally, project targeted beneficiaries will receive toolkits to enable them to start up their own small enterprises or raise household level productivity.

Project funds allocated towards the procurement of equipment and toolkits is budgeted at approximately 2,475,000 USD. Project procured capacity-building equipment transfers accounts for approximately 43% of the total project budget.

| Funds Committed | 3,404,014 | % of approved | 58.69 |
| --- | --- | --- | --- |
| Funds Disbursed | 2,920,075 | % of approved | 51.21 |
| Forecast final date | February 2009 | Delay (months) | 12 Months |

# Quantitative achievements against objectives and results

| Support local communities in the establishment of a variety of viable auxiliary income-generating activities in the food processing sector and other cottage agro-industries, thereby strengthening their household economy so they can contribute to their well-being on their own. | % of planned | 85 |
| --- | --- | --- |
| Raise technology and production levels in targeted villages by providing the poor and marginalized communities the means to process their agricultural products. | % of planned | 80 |
| Improve the technical and business management skills of people in the project area especially the women, youth, and the IDPs, through appropriate training in the food processing, construction, manufacturing or agro-supply chain sub-sector. | % of planned | 65 |

# Qualitative achievements against objectives and results

The design, development, and implementation of project sensitization workshops, with core project stakeholder groups, has been completed. The project has confirmed the needs of project beneficiary groupings through the preparation of a comprehensive needs assessment report.

The selection of project sites and the ‘mapping’ of beneficiary groups, project extension services, project supported training sites, and other agro-infrastructure has been completed. Technical assessments of vocational and technical training institutes and centres and decisions relating to the resourcing of these facilities has been made in conjunction with the PMU, Ministerial Representatives, and other Project Steering Committee members. In addition, the identification and promotion of locally relevant and appropriate agro-economic technologies has been completed. These appraisals were anchored by a market based assessment of raw materials, support services, distribution nodes, and market access points. These identification and mapping initiatives help to ensure that project resources are well targeted adn effectively utilized.

The preparation of the technical specification for project procured equipment has been completed. Procurement activities have been completed and most recently the project has finalized the archiving and tracking of project procured equipment and toolkits. Training equipment has been officially transferred to various project-participating training centres and beneficiary groupings (based on a formal agreement between the PMU, GoI Line Ministries, and end-users). Currently the Project Management Unit is in the process of transferring productivity enhancing equipment to various food and non-food Production Groups established under the terms of the project.

# All Training of Trainers (ToT) training sessions have been completed for skills upgrading of ministerial counterpart staff that will be attached to the project’s food and non-food vocational training and skills upgrading centre. The project has trained 62 Trainers in a variety of technical, enterprise development, and management thematic areas. Project trainers have come from the Ministry of Agriculture, Ministry of Industry, and the private sector. The completion of training sessions associated with the ToT component of the project not only assists in meeting the institutional capacity building component of the project but will also help to ensure that the activities engaged in and results obtained are sustained over time.

To date over 950 project beneficiaries have been involved in a number of food and non-food training sessions. These training sessions have dramatically improved the employment and income generating opportunities for vulnerable and marginalized groups. Recent beneficiary surveys indicate that over 80% of project trained beneficiaries have been able to either gain employment or start up an economic activity. Over 900 individual ‘toolkits’ have been provided to project beneficiaries. These toolkits have provided important start-up ‘capital’ for many of beneficiaries.

The project has made linking Producer Groups (PG) with various agro-related financial facilities an important project activity. Sixteen PGs  are currently being established in a number of food and non-food activities and the transfer of productivity enhancing equipment to these Groups is being finalized. PGs are expected to enhance job creation and income generating aspects of the project and will also help to increase community-level commercial exchange and expand beneficiary coverage by improving access and reach of PG produced products and services. The PMU has also begun the process of tracking changes in the operations, employment levels, and revenue streams of project targeted PGs.