# United Nations Development Group Iraq Trust Fund

# Project #: A6-02

December 2007/4th Quarter 2007

# Project Summary Sheet

| Participating UN Organisation: WFP | Cluster: A – Agriculture, Food Security, Environment and Natural Resources Management |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Health (MoH) and Ministry of Education (MoE) |

| Title | Development of Safety Nets and Food Security through Food Assistance |
| --- | --- |
| Location | Nationwide |
| Project Cost | US $ 9,194,839 |
| Duration | 1 year (project extension until 31 December 2007) |
| Approval Date (SC) | 11 Nov 2004 | Starting Date | February 2005 | Completion Date | 31 Dec 2007 |
| Project Description | Support for access to education and reduction of gender disparity; support to capacity building for development of targeted socio- economic safety nets and identification of cost effective options to the Public Distribution System; establishing an inter- ministerial delivery network for targeting assistance. |

# Development Goal and Immediate Objectives

Development Goal Development of Iraqi Government capacity for the implementation of social safety nets, developing and managing safety net and food security programmes; Support to improved nutrition and health status of vulnerable groups; Improve access to primary education in particular for girls Immediate objectives Assist MOPDC/CSOIT and Food Security Unit in improving Iraq institutional capacity in monitoring and analysing poverty/food security; Support in establishing nationwide school feeding programme; Support MOE in increasing enrolment and regular attendance of children, in particular girls, in primary schools; Assist MOH in improving knowledge of mothers and caretakers of young children on appropriate feeding practices and improving the nutritional status of malnourished children and pregnant and lactating mothers; Assist MOH in increasing attendance of the vulnerable at local health care facilities.

# Outputs, Key activities and Procurement

| Outputs and Key activities | Assist in the establishment of food security unit within MOPDC/CSOIT and strengthen capacity of the Government for continued monitoring and analysis of food security and in developing cost effective and targeted safety net strategies; Support MOE/MOH in establishing inter ministerial project implementation capacity, training of trainers and advocacy/awareness raising on food security and need for education; Train staff and implementing partners in the implementation of targeted assistance programmes; Enhance learning capacity and attendance of children particularly girls in WFP assisted primary schools. |
| --- | --- |
| Procurement | Transport of High Energy Biscuits to 14 Governorates inside Iraq. |

# Situation as of 31/12/2007

| Funds Committed | US $ 8,848,243 | % of approved | 96 % |
| --- | --- | --- | --- |
| Funds Disbursed | US $ 8,785,503 | % of approved | 96 % |
| Forecast final date | 31 December 2007 – The project is operationally closed. Final payments will be complete by the end of Feb 2008. | Delay (months) |  |

# Quantitative achievements against objectives and results

| Over 3,000 primary schools covered by the assistance. | The US $ 2.2 million EC donation was used for the transportation and distribution of 1,242 mt of High Energy Biscuits to Iraq and related direct support costs to support staffing. | % of planned | 100 % |
| --- | --- | --- | --- |
| 1,242 mt of High Energy Biscuits distributed to school children | A total of 450,438 primary school children benefited from the assistance | % of planned | 100 % |

# Qualitative achievements against objectives and results

1.WFP through the implementing partners distributed 1, 242 High Energy Biscuits as a mid-day snack to Primary School Children through 3000 primary schools benefiting 450,438 primary school children. 2. Data collected by project implementation staff revealed that attendance rates increased by 10 % and female student enrolment rate by 12 % in the districts where WFP is providing assistance. 3. In some primary schools, children who completed their Six Grade recorded 95 % success.