Seventh Six-month progress report for project

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| World Food Programme |  | A – Agriculture, Food Security, Environment and Natural Resource Management |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| A6-02 (WFP project EMOP 10360.0) Development of Safety Nets and Food Security through Food Assistance. |  | A6-02 |

| Reporting Period: |  | Project Budget [and revision if applicable]: |
| --- | --- | --- |
| 1 July – 31 December 2007 |  | US$ 9,194,839 |

| List Implementing Partners: |  | Geographic Coverage/Scope: |
| --- | --- | --- |
| Ministry of Health (MoH) Ministry of Education (MoE) Ministry of Planning and Development Cooperation (MoPDC) |  | 14 governorates of Iraq – Anbar, Babel, Basra, Diyala, Thiqar, Wassit, Missan, Qadissiya, Muthanna, Salah Al Din, Baghdad, Kerbala, Kirkuk, and Sulaimaniyah |

| Abbreviations and acronyms: |  | Project Status: Duration/Closed Project/Timeline Extension: |
| --- | --- | --- |
| Ministry of Health (MoH) Ministry of Education (MoE) Ministry of Planning and Development Cooperation (MoPDC) Central Organisation for Statistics and Information Technology (COSIT) World Food Programme (WFP) National Development Strategy (NDS) Millennium Development Goal (MDG) Project Management Committee (PMC) Project Management Unit (PMU) Parent-Teacher Association (PTA) |  | This project was operationally closed at the end of the reporting period on 31 Dec 2007. It will be financially closed, as per WFP internal regulations, on 30 June 2008. Project duration: Mar 2005 – Dec 2007 |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

Development Goal

Development of Iraqi Government capacity for the implementation of social safety nets, developing and managing safety net and food security programmes; Support to improved nutrition and health status of vulnerable groups; Improve access to primary education in particular for girls

Immediate objectives

- Assist MOPDC/COSIT and Food Security Unit in improving Iraq institutional capacity in monitoring and analyzing poverty/food security;

- Support in establishing nationwide school feeding programme;

- Support MOE in increasing enrolment and regular attendance of children, in particular girls, in primary schools;

- Assist MOH in improving knowledge of mothers and caretakers of young children on appropriate feeding practices and improving the nutritional status of malnourished children and pregnant and lactating mothers;

- Assist MOH in increasing attendance of the vulnerable at local health care facilities.

Outputs and Outcomes:

- Assist in the establishment of food security unit within MOPDC/COSIT and strengthen the capacity of the Government for continued monitoring and analysis of food security and in developing cost effective and targeted safety net strategies;

- Support MOE/MOH in establishing inter ministerial project implementation capacity, training of trainers and advocacy/awareness raising on food security and need for education;

- Train staff and implementing partners in the implementation of targeted assistance programmes;

- Enhance learning capacity and attendance of children particularly girls in WFP assisted primary schools.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

The National Development Strategy (NDS) is established on 4 major pillars, the third of which is "Improving the quality of life". This requires actions "to reduce drop-out rates at the primary (school) level" and the enactment of "a social safety net program for the poor and vulnerable".

This WFP assistance to Iraq specifically addresses these requirements of the NDS through the provision of targeted food aid to those identified in WFP's 2004 Baseline Food Security Analysis as being extremely food insecure and to school children to encourage attendance and reduce drop-out rates.

Through the provision of food assistance and by undertaking capacity building activities, mainly based on a training programme, the Operation is addressing the following Millennium Development Goals:

- MDG 1: “Eradicate extreme poverty and hunger” by distributing food to vulnerable groups and school children.

- MDG 2: “Achieve universal primary education” by working towards increasing enrolment and improving the attendance rates of Iraqi primary school level children.

- MDG 3: “Promote gender equality and empower women” by contributing to the elimination of gender disparity in primary education, through provision of incentives to female school children.

- MDG 4 “Reduce child mortality” and 5 “improve maternal health” are addressed through provision of food aid to pregnant women and nursing mothers and malnourished children, and through education aiming to improve knowledge of appropriate feeding practices.

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

WFP’s partners are the Ministries of Health (MOH), Education (MOE) and Planning and Development Cooperation (MoPDC) who manage and implement the EMOP activities through the central Project Management Committee (PMC). Each of the Ministries (MOH & MOE) is represented by two senior staff at policy and decision making levels who are delegated responsibility for the overall implementation of the project with WFP playing an advisory role. The PMC coordinates monitors and reports on the implementation progress.

At the governorate level, a Project Management Unit (PMU) composed of representatives from the Ministries of Health and Education as well as WFP (in an advisory capacity) carries out the day-to-day implementation and oversight activities.

These activities comprise responsibility for receiving and storing of food commodities arriving from neighbouring countries, secondary transport of commodities, distribution, monitoring and reporting. Parent-Teacher Associations (PTAs) are responsible for supervision of food storage and stocks and the organization and supervision of the food distribution process to the beneficiaries.

- Human Resources

  - National Staff & Consultants: Provide details on the number and type (operation/programme)

74 national staff including 57 based inside Iraq (programme and logistics staff).  The 17 staff in Jordan and Syria are also comprised of programme and logistics staff as well as ICT, administration, finance, HR, security and drivers.

  - International Staff: Provide details on the number and type (operation/programme)

9 international staff – 2 management, 1 finance/admin, 1 security, 3 logistics, 2 programme

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

As mentioned above, the key partners in the implementation of the project are the Ministry of Health and the Ministry of Education, together with the Ministry of Planning, Development and Cooperation through COSIT. There is strong inter-agency collaboration with WHO and UNICEF. The input of the line ministries is fundamental to project delivery, as described above.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

All food for this project is either in-kind donations or procured by the Procurement Unit in Headquarters following WFP’s strict procurement protocols.  There have been no variances from the standard procedures.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

Monitoring is carried out by PMU members and WFP staff working together. Information is fed into an M&E database which provides up-to-date information on project progress to date.

  - Report on any assessments, evaluations or studies undertaken.

WFP has been working closely with the Ministry of Planning’s Central Organization for Statistics and Information Technology (COSIT) since 2003 in building their capacity in food security monitoring and analysis.  WFP has helped set up a Food Security Unit within COSIT dealing specifically with this issue.  Two comprehensive food security and vulnerability surveys have been completed with this unit, one published in 2004 and the second in 2006.

The latest survey found that just over 4 million people – or, 15.4% of the surveyed population – were food insecure and in need of humanitarian assistance, including food.  It found that a further 8.3 million people (31.8% of the population) would be rendered food insecure if not provided a food ration through the Public Distribution System (PDS).  The full report can be accessed on COSIT’s website at the following link: http://www.iraqcosit.org/english/activities_reports.shtm. Iraq’s PDS experienced significant shortfalls during 2006 and 2007.  This, coupled with the mass movement of people since the previous survey, would have a major impact on the food security situation of the population.  Thus, it was decided to conduct a follow-up survey to assess current levels of food security and malnutrition.  For the first time, this survey involves the Kurdistan Regional Government and covers all 18 governorates of Iraq.  Data collection went ahead in November and was complete by December.  The results are expected to be published in April 2008.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

- Increase enrollment and regular attendance of children, in particular girls, in primary schools; - not achieved due to the lack of activities during the reporting period. Activities have been suspended since October 2006, as a result of a request from the Ministry of Education to provide a food ration with non-standard WFP commodities.

- Increase attendance of malnourished children and pregnant and lactating women at local healthcare facilities; - achieved during food distributions.

- Improve the nutritional status of malnourished children and pregnant and lactating women; achieved, recovery rate of malnourished children receiving WFP food is over 90%

- Secure regular attendance of tuberculosis patients enrolled in the National Programme at local healthcare facilities; - achieved.  TB patients receiving WFP food.

- Improve the knowledge and daily practices of mothers and caretakers of young children on appropriate feeding practices; - achieved. Mothers receiving WFP food also receive information on good feeding practices.

- Improve Iraqi institutional capacity in monitoring and analyzing food security. – achieved.  Food Security Unit established within Ministry of Planning and Development cooperation.  They have conducted two comprehensive food security and vulnerability surveys with WFP since 2004 and performed the data collection of a third survey in Nov/Dec 2007 which should be published by late May 2008.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

Food purchased under this contribution was dispatched to Iraq under previous reporting periods.  Thus, most outcomes were achieved during previous reporting periods.  This reporting period saw the wrap-up of the project.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

100% of planned results were achieved and previously reported, as detailed below:

- The US $ 2.2 million from the EC donation was used for the transportation and distribution of 1,242 mt of High Energy Biscuits to Iraq and related direct support costs to support staffing.

- Over 3,000 primary schools covered by the assistance.

- A total of 450,438 primary school children benefited from the assistance

- Data collected by project implementation staff revealed that attendance rates increased by 10 % and female student enrolment rate by 12 % in the districts where WFP is providing assistance

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

Distributions were limited in the second half of 2007 primarily by internal funds transfer constraints.  Funds for local transport, storage and handling were not reaching the governorate levels in spite of being received in Baghdad.  Without adequate funds, local officials were not able to accept significant quantities of commodities, nor get them to the health centers for distribution.  The food that did reach the beneficiaries did so because committed PMU staff paid the up front costs out-of-pocket to ensure that food reached those in need.  As such, the MoH requested that WFP stop dispatching food to Iraq after July 2007.  Food already in-country was distributed as planned.

WFP has been in dialogue with the MoH to see if a possible solution can be found to this problem, including the MoH's agreement of direct payment to local authorities at the Governorate level. Should this be resolved, and the MoH puts forward a request, WFP will be able to consider the continuation of the programme.

School feeding remained suspended during the reporting period as a result of the Ministry of Education’s refusal of WFP’s food basket.  In spite of numerous consultations, this impasse was not resolved ahead of the 31 December 2007 closure of the project.

Although outputs under this project were 100% achieved, any extension of this project is pending further discussions with the Ministry of Health and/or Education in order to overcome the constraints listed above.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

WFP worked closely with UNICEF in supporting nutrition and health education training to 153 staff in the PHCs and CCCUs in Basrah province. This coordination between WFP and UNICEF ensured that the same staff who handle WFP food could impart good advice to beneficiaries on feeding practices, health and hygiene.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

Management of WFP's programme in Iraq was handled through the Ministry of Health's PMUs in each province, as well as the overall PMC in Baghdad. More than 60 percent of WFP's beneficiaries in 2007 were women.

- Future Work Plan

  - Summarize the projected activities up to the end of June 2008 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

This project was operationally closed on 31 December 2007.  Financial closure is scheduled for 30 June 2008.

# Footnotes

2006, WFP/COSIT, Food Security and Vulnerability Analysis in Iraq

# Text boxes

Report Formatting Instructions: We kindly ask that you review the instructions below and follow them in the preparation of your report:

- Number all sections and paragraphs as indicated below

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.

- Highlight any new challenges/constraints, mitigation strategies and lessons learned during the reporting period as well as monitoring processes and assessments, evaluations and studies undertaken/published in the period. Attach documents.

- Attach any available photos relevant to the project.