# United Nations Development Group Iraq Trust Fund

# Project #:A6-03

# Date and Quarter Updated: 4th Quarter 2008 – October - December

# Part One: Summary

| Participating UN Organisation: WFP | Cluster: A – Agriculture, Food Security, Environment and Natural Resource Management |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Planning and Development Cooperation |

# Programme/Project Number: A6-03

| Title | Enhancing the Iraqi Institutions’ capacity in monitoring and targeting the most food insecure and vulnerable segments of Iraqi population. |
| --- | --- |
| Location | Country wide |
| Project Cost | USD$ 1,022,457 |
| Duration | December 2007 – June 2009 |
| Approval Date (SC) | 5 December 2007 | Starting Date | 12 December 2007 | Completion Date | Operationally closed on December 12, 2008, and will be financially closed on June 12, 2009. |
| Project Description | In 2003, WFP helped establish a Food Security Unit within the Central Organization for Statistics and Information Technology (COSIT) and the Kurdistan Regional Statistics Office (KRSO) of the Ministry of Planning and Development Cooperation (MoPDC). The following needs were identified to strengthen this food security unit (i) policy advice on food security and safety net options, (ii) necessary technical and conceptual tools, and (iii) provisions for monitoring food security indicators. This project focussed on building capacity for WFP partners by enhancing Monitoring & Evaluation and Reporting systems within the Food Security Unit using a Results-Based-Management approach. This aims not only benefit the implementation of WFP activities, but also help to strengthen COSIT's and KRSO’s own M&E interventions in other social sectors like health, education and employment. |

# Development Goal and Immediate Objectives

The overall development goal is to strengthen the capacity of Iraqi institutions, namely the Central Organisation for Statistics (COSIT) and the Kurdistan Regional Statistics Office (KRSO) in the Ministry of Planning and Development Cooperation, to carry out food security and vulnerability analysis and develop a monitoring tool which will, in turn, contribute to better targeted interventions concerning reconstruction, implementing social safety nets and development activities in Iraq, as well as to the reduction of food insecurity. The key immediate objective is to assist MoPDC/COSIT/KRSO in improving their capacity in monitoring and targeting the food insecure and most vulnerable segments of the population including the unemployed.

# Outputs, Key activities and Procurement

| Outputs | A food security monitoring tool established and functioning which generates analyses and reports on a regular basis Enhanced capacity of the government in food security and nutrition monitoring and analysis and, subsequently, development of safety net strategies strengthened through the provision of training and equipment. Staff trained, capable and equipped to carry out Food Security and nutrition programming. Participation of all stakeholders regarding Food Security interventions maximised. Iraqi partners' ability to perform spatial and geographic analysis enhanced. Geographic dimensions of food insecurity, poverty and malnutrition better understood and analysed. |
| --- | --- |
| Activities | Develop Food Security and Vulnerability Monitoring, and Reporting System (M&E) for the key indicators for to help effective programming and response. Without such an effective M&E System there is a considerable risk/likelihood that resource allocation will be poorly targeted, with all the obvious negative implications regarding poor reporting mechanisms, wrong areas, communities, and individuals either receiving or not receiving assistance. The monitoring and reporting system will also include improving the mechanisms for monitoring and reporting employment status, food security and on nutritional status among the vulnerable groups in Iraq. Put in place a mechanism for monitoring and evaluation of food security and vulnerability indicators to target hunger and tackle unemployment especially among vulnerable groups. Conduct two training sessions (training of trainers) for implementing partners on the Monitoring and Evaluation System including methods of data collection, monitoring, evaluation and reporting systems and performance reviews. 3.1 Conduct Food Security analysis and monitoring and nutrition trainings 4.1 Consult and dialogue with stakeholders (Internal and External) for consensus on targeting. |
| Procurement (major items) | N/A |

# Part Two: Situation as of December 31, 2008

| Funds Committed | USD$ 1,022,140.00 | % of approved | 100% |
| --- | --- | --- | --- |
| Funds Disbursed | USD$ 1,022,140.00 | % of approved | 100% |
| Forecast final date | December 2008 | Delay (months) | 0 |

# Quantitative achievements against objectives and results

| 1.1 M&E system development | Post-Food Distribution Monitoring System developed. Associated databases designed | % of planned | 100% |
| --- | --- | --- | --- |
| 1.2 Mechanism established | M&E reports now received from all 18 governorates | % of planned | 100% |
| 2.1 Training of Trainers | 18 people from COSIT and KRSO, 20 WFP national staff, and 9 cooperating partner staff trained in the PFDM system | % of planned | 100% |
| 3.1 Training | Training of food security analysis and nutrition have been completed | % of planned | 100% |
| 4.1 Dialogue with stakeholders | Internal and external stakeholders consulted on targeting | % of planned | 100% |

# Qualitative achievements against objectives and results

The Post-Food Distribution Monitoring System has been designed and established. It is being implemented in all 18 governorates through roll-out training by those specialists who were trained in Amman. The mechanism for regular data collection has been established and reports received from all 18 governorates.