# United Nations Development Group Iraq Trust Fund

# Project #: A7-05

# Date and Quarter Updated: 1st quarter – 1 January 2009 - 31 March 2009

| Participating UN Organisation: UNDP | Sector: Protection |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Environment |

| Title | Support for Rural Development and Safer Environment through Mine Action |
| --- | --- |
| Geographic Location | Basra, Az Zubair |
| Project Cost | US$ 4,992,892 (US$ 3,231,751 UNDG ITF + Australian and UK bilateral US$ 1,761,141) |
| Duration | 18 months |
| Approval Date (SC) | 4/10/2007 | Starting Date | 19/10/2007 | Completion Date | 31/12/2009 |
| Project Description | This project aims at creating an enabling environment for rural development through prioritized mine action. This will be done through the support for a newly established Iraqi humanitarian mine action national NGO in Basra. This complements the need in southern Iraq where considerable mine clearance and mine risk education capacity is needed to address the Explosive Remnants of War (ERW) contamination problem. |

Development Goal and Immediate Objectives

Support sustainable rural development by removing the threats to human security and livelihood through the increased capacity of the National Mine Action Authority (NMAA) and the organizations and NGOs falling under its mandate, including the Regional Mine Action Centre (RMAC) based in Basra Governorate. This will be done by supporting a national humanitarian mine action NGO that serves and works with the local community, promoting rural development in Basra, and the provision of support to RMAC to carry out technical quality Assurance. Immediate Objectives: Community awareness, agricultural development and income generation activities enhanced (36 square kilometres of agricultural land cleared from mine and UXO) Management and operational capacity of an Iraqi humanitarian Mine Action NGO (whereby the national NGO is strengthened.) 3. Coordination between RMAC, DMA and the national NGO increased

| Outputs, Key activities and Procurement |
| --- |
| Outputs | 1.1. 36 square kilometres of agricultural land cleared of landmines and ERW. 1.2. Changing dangerous behaviour of the rural community through mine risk education 1.3. Increased cash crops from the cleared land. 1.4. Indirect employment increased. 2.1. The Iraq NGO management continues to conduct capacity building activities independently 2.2. General professional skills and technical skills further developed 2.3. Operational coordination capacity is strengthened 3.1. Coordination capacity of RMAC and DMA increased 3.2. RMAC's tasking capacity (to clearance organizations) increased 3.3. Effective information sharing and cooperation between RMAC and the national NGO strengthened |
| Activities | 1.1 Clearance teams deployed and agricultural land cleared. 1.2 Mine risk education activities and community reach-out conducted by the national NGO in cooperation with the UNICEF Project. 2.1 Individual training planning and modules prepared by the national NGO with the assistance from an international monitoring partner 2.2 Participate in external Mine Action specialized courses facilitated by UNDP 2.3 Quality Assurance (QA) processes analyzed in order to strengthen efficient work Flow. 3.1 Coordination between DMA/RMAC supported by National Liaison Officer (Baghdad) and National Mine Action Advisor (Basra) 3.2 QA Advisor provides technical advisory support to RMAC on tasking and technical coordination. 3.3 The Iraqi NGO meets with RMAC and Advisory Committee composed of representatives from Basra Governorate, including the Department of Agriculture, to get their suggestions on priorities relevant to local development. |
| Procurement (major items) | NA |

| Funds Committed | ITF : $2,121,216.19 Australian and UK funding: $1,760,183.19 | % of approved % of approved | 65.6% 99.9% |
| --- | --- | --- | --- |
| Funds Disbursed | ITF: $1,756,987.87 Australian and UK funding: $1,613,917.5 | % of approved % of approved | 54.3% 91.6% |
| Forecast final date | 31 December 2009 | Delay (months) | 8 months |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | No target was set |  |
| Women | No target was set |  |
| Children | No target was set | 2,400 Students |
| IDPs | No target was set |  |
| Others | No target was set |  |
| Indirect beneficiaries | Target set is: 500 farming families Current status is: 1,500 | 300% |
| Employment generation (men/women) | Target set is: 150 deminers Current status is: 68/8 | 50.6% |

| Quantitative achievements against objectives and results |
| --- |
| Community awareness, agricultural development, and income generation activities enhanced | Target: 36 km² of agricultural land cleared from mine and UXO Achievement: 18,136,776m² of agricultural land cleared (from October 07 to end of December 08) | % of planned | 50.4% |

Qualitative achievements against objectives and results

Output 2.2 General professional skills and technical skills further developed - Since the project started in Oct 07, UNDP treats RDO (the national NGO) as an independent organization; it has provided larger responsibility to Iraqi staff members in terms of management including financial and organizational management as well as reporting and donor relations. Financial and operational reports have significantly improved in the past months. RDO also continues to undertake capacity building activities such as refresher training in January 2009, a Manual Mine Clearance (MMC) course, and an EOD course. RDO is also in the process of preparing a funding proposal for 2010. Output 3.3 Effective information sharing and cooperation between RMAC and the national NGO (RDO) Due to uncertainties regarding the institutional setup for Mine Action within the government structure, and the expected corresponding staff changes which affected DMA and RMAC during the reporting period, not much progress has been made for this output. However, since March 2008 when the final decision was made, slow progress continues to take place and more effective information sharing and cooperation between RMAC and RDO is on-going.

Main implementation constrains & challenges (2-3 sentences)

The main challenge facing the project is the order issued by the Ministry of Defence in last week of December 2008 ordering the halt of civil humanitarian demining operations including RDO. Up till the date of this report the operations of RDO have not resumed yet.

# Footnotes

Total is different from that on the signed project document due to the difference in amount actually received bilaterally from the Government of Australia and the Government of U.K.

In December 2008, the national Mine Action authority underwent a name change to become the Directorate of Mine Action (DMA).     The new name and abbreviation will be used in this and any subsequent reports.