# United Nations Development Group Iraq Trust Fund

# Project #:A7-05

# Date and Quarter Updated: 4th  quarter – 31 December 2008

| Participating UN Organization: UNDP | Sector: Protection – Mine Action |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Environment |

| Title | Support for Rural Development and Safer Environment through Mine Action |
| --- | --- |
| Geographic Location | Basra, Az Zubair |
| Project Cost | US$ 4,992,892 (US$ 3,231,751 UNDG ITF + Australian and UK bilateral US$ 1,761,141) |
| Duration | 18 months |
| Approval Date (SC) | 4/10/2007 | Starting Date | 19/10/2007 | Completion Date | 19/04/2009 |
| Project Description | This project aims at creating an enabling environment for rural development through prioritized mine action. This will be done through the support for a newly established Iraqi humanitarian mine action national NGO in Basra. This complements the need in southern Iraq where considerable mine clearance and mine risk education capacity is needed to address the Explosive Remnants of War (ERW) contamination problem. |

# Development Goal and Immediate Objectives

| Support sustainable rural development by removing the threats to human security and livelihood through the increased capacity of the National Mine Action Authority (NMAA) and the organizations and NGOs falling under its mandate, including the Regional Mine Action Centre (RMAC) based in Basra Governorate. It will be done by supporting a national humanitarian mine action NGO that serves and works with the local community, promoting rural development in Basra, and the provision of support to RMAC to carry out technical quality Assurance. Immediate Objectives: Community awareness, agricultural development and income generation activities enhanced (36 square kilometres of agricultural land cleared from mine and UXO) Management and operational capacity of an Iraqi humanitarian Mine Action NGO (hereinafter the national NGO) strengthened Coordination between RMAC, NMAA and the national NGO increased |  |
| --- | --- |

# Outputs, Key Activities and Procurement

| Outputs | 1.1. 36 square kilometres of agricultural land cleared of landmines and ERW. 1.2. Changing dangerous behaviour of the rural community through mine risk education 1.3. Increased cash crops from the cleared land. 1.4. Indirect employment increased. |
| --- | --- |
|  | 2.1. The Iraq NGO management continues to conduct capacity building activities independently 2.2. General professional skills and technical skills further developed 2.3. Operational coordination capacity is strengthened |
|  | 3.1. Coordination capacity of RMAC and NMAA increased 3.2. RMAC's tasking capacity (to clearance organizations) increased 3.3. Effective information sharing and cooperation between RMAC and the national NGO strengthened |
| Key Activities | 1.1 Clearance teams deployed and agricultural land cleared. 1.2 Mine risk education activities and community reach-out conducted by the national NGO in cooperation with the UNICEF Project. |
|  | 2.1 Individual training planning and modules prepared by the national NGO with the assistance from an international monitoring partner 2.2 Participate in external Mine Action specialized courses facilitated by UNDP 2.3 Quality Assurance (QA) processes analyzed in order to strengthen efficient work flow |
|  | 3.1 Coordination between NMAA/RMAC supported by National Liaison Officer (Baghdad) and National Mine Action Advisor (Basra) 3.2 QA Advisor provides technical advisory support to RMAC on tasking and technical coordination. 3.3 The Iraqi NGO meets with RMAC and Advisory Committee composed of representatives from Basra Governorate, including the Department of Agriculture, to get their suggestions on priorities relevant to local development. |
| Procurement (major items) | NA |

| Funds Committed | ITF : $1,427,816.70 Australian and UK funding: $1,752,024.29 | % of approved | 63.7% |
| --- | --- | --- | --- |
| Funds Disbursed | ITF: $1,097,247.95 Australian and UK funding: $1,612994.90 | % of approved | 54 % |
| Forecast final date | 31 October 2009 | Delay (months) | 6 months |

# Quantitative achievements against objectives and results

| Community awareness, agricultural development, and income generation activities enhanced | Target: 36 km² of agricultural land cleared from mine and UXO Achievement: 18.18 km² of agricultural land cleared (from October 07 to end of December 08) | % of planned | 50.4% |
| --- | --- | --- | --- |

# Qualitative achievements against objectives and results

Output 2.2 General professional skills and technical skills further developed - Since the project started in Oct 07, UNDP treats RDO (the national NGO) as an independent organization; it has provided larger responsibility to Iraqi staff members in terms of management including financial and organizational management as well as reporting and donor relations. Financial and operational reports have improved in the past 3 months with close follow up by UNDP. RDO continues to conduct basic capacity building activities such as computer trainings and English language courses, and have arranged for RDO national staff to attend a strategic planning course in Basra. Moreover RDO have conducted 2 Mine Action Exchange Programmes (MAX) to Erbil and to Sulimanieh. Output 3.3 Effective information sharing and cooperation between RMAC and the national NGO (RDO) – During the reporting period, uncertainties regarding the institutional setup for Mine Action within the government structure still abound, with accompanying corresponding staff changes expected to affected NMAA and RMAC. Not much progress has been made for this output and negotiations between the different ministries and governmental departments are on-going. However, since March 2008 when the decision was made to move responsibility for mine action to the Ministry of Environment, modest progress has taken place and more effective information sharing and cooperation between RMAC and RDO has started.

# Footnotes

Total is different from that on the signed project document due to the difference in amount actually received bilaterally from the Government of Australia and the Government of U.K.

Project extension request will be submitted to ITF Support Office once the expected final date becomes certain.

22.7% of total project cost (ITF + AusAID and DFID).  Australian funding was approved and deposited prior to ITF approval; thus it was decided to first utilize Australian funding. ITF started utilizing from July 2008.

Project extension request will be submitted to ITF Support Office once the expected final date becomes certain.

Quantitative and Qualitative Achievements were achieved by utilizing Australian funds.