EIGHTH Six-month progress report for project

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| Participating UN Organization: (if joint programme, indicate the lead agency) |  | Old Cluster: A - Agriculture, Environment and Natural Resources Management |
| --- | --- | --- |
| UNDP |  | New Sector: Protection Outcome Team |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| A7-05 Support for Rural Development and Safer Environment through Mine Action |  | Vol. 2 |

| Reporting Period: |  | Project Budget [and revision if applicable]: |
| --- | --- | --- |
| 1 January – 30 June 2008 (the project commenced its activities with AusAID fund from 1 October 2007) |  | US$3,231,751 from ITF and US$1,652,892.56 from AusAID, and $108,248 from DFID |

| List Implementing Partners: |  | Geographic Coverage/Scope: |
| --- | --- | --- |
| Danish Demining Group Rafidain Demining Organization NMAA / RMAC |  | Southern Iraq, operating from Basra |

| Abbreviations and Acronyms: |  | Project Status: Duration/ Timeline Extension/Closed Project: |
| --- | --- | --- |
| DDG - Danish Demining Group NMAA – National Mine Action Authority RMAC - Regional Mine Action Centre EOD – Explosive Ordnance Disposal IMSMA – Information Management System for Mine Action ERW – Explosives Remnants of War MRE – Mine Risk Education UXO – Unexploded Ordnance RDO – Rafidain Demining Organization |  | The project started on the 19 October 2007 for the period of 18 month. The project is still on-going. |

# NARRATIVE REPORT FORMAT

I. Purpose

a.	Provide the main objectives, outcomes, outputs of the programme/project

Support sustainable rural development by removing the threats to human security and livelihood through the increased capacity of the National Mine Action Authority (NMAA) and the organizations and NGO’s falling under its mandate, including the Regional Mine Action Centre (RMAC) based in Basra governorate through supporting a national humanitarian mine action NGO that serves and works with the local community, promoting rural development in Basra, and the provision of support to RMAC to carry out technical quality assurance.

Objectives:

- Community awareness, agricultural development, and income generation activities enhanced (36 square kilometers of agricultural land cleared from mine and UXO)

- Management and operational capacity of an Iraqi humanitarian Mine Action NGO strengthened

- Coordination between RMAC, NMAA and the national NGO increased

Key Output:

36 square kilometres of agricultural land cleared of landmines and ERW; increased cash crop potential from the cleared land; General professional skills and technical skills further developed; RMAC’s tasking capacity (to clearance organizations) increased

b.	Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq, MDGs, Iraq NDS and ICI

The project contributes to one of the output under the Protection Sector in the UN Assistance Strategy for Iraq (2008-2010), i.e. 1.8 “Mine Action policy, strategy, and regulatory mechanism developed, Iraqi Mine Action operational capacity strengthened and awareness raised.”

The project directly and indirectly contributes to the achievements of the following MDGs: Goal 1 on poverty reduction by mine / UXO clearance of arable land that supports sustainable income generation activities; Goal 7 on ensuring environmental sustainability; and Goal 8 on global partnership for development.

Demining which is one of the main issues of Mine Action is one of the main goals of the second pillar of the Iraqi National Development Strategy 2005-2007 “Improving the quality of Life”. Moreover under the annual review of the International Compact with Iraq – A New Beginning, in May 2007-April 2008, specific reference to capacity building of mine action institutions was reported under Environment.

II.  Human Resources

a.	National Staff and Consultants: Provide the number and role (operation/programme)

National Staff and Consultants: One National Technical Advisor is recruited as a consultant for coordination with RMAC and is based in Basra.  At UNDP, one National Programme Officer and one National Programme Assistant are backstopping on administrative and financial issues to this project along with all other UNDP Mine Action Team projects (their costs are being charged to the other ITF project till 30 June 2008 but to be charged to this project from 1 July 2008.)

Under a Project Cooperation Agreement between UNDP and a national NGO (RDO), currently 71 national staff starting from Director, Administration Manager, Finance Officer, Logistics, and Drivers to Field Operations Manager and 27 Operators are employed.

b.	International Staff: Provide the number and role (operation/programme)

International Staff: At UNDP, one international staff (Programme Specialist) based in Amman is providing overall supervision of this project along with all other UNDP Mine Action projects.  In addition, Senior Mine Action Advisor and Senior Mine Action Consultant have been providing technical inputs, while their costs are charged to other projects. E-Governance Advisor, Mine Action who is seconded by the Swedish Government also contributes to the capacity development of the Government and NGOs in the area of information management.

Under a Project Cooperation Agreement between UNDP and Danish Demining Group (DDG, Monitoring Partner), cost of 2 international staff, Programme Manager and Technical Advisor who are based in Basra are covered by the project budget.

III.  Methods of Operating

a.	Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

RDO is the main implementing partner of this project while DDG acts as an advisory / monitoring partner.  UNDP provides monthly advances to RDO (in order to avoid having large amounts of funds remaining at their end) and quarterly advance to DDG.

b.	Provide details on the procurement procedures utilized and explain variances in standard procedures.

DDG was selected through competitive bidding process.

c.	Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

Both NGOs provide monthly progress reports as well as monthly financial report (in case of RDO) and quarterly financial report (in case of DDG) to UNDP.  Due to security situation in Basra, while physical monitoring visit to Basra by UNDP staff members have been difficult, the following alternative arrangements are put in place: (a) a consultant (national technical advisor) acts independently and report directly to UNDP on the issues of RDO, and (b) meetings among DDG, RDO and UNDP are being arranged in either Amman or Kuwait.

d.	Report on any assessments, evaluations or studies undertaken relating to the project and how they were used in support of the project(s).

An evaluation of the prior project (A7-04) has been conducted in June 2008, and lessons learned from the evaluation have been taken into account as a basis for improvements to this project.

IV. Results

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

Output 1.1 – to meet the target of 36km² of agricultural land cleared from ERW under this project, from 1 October to 31 December 2007, 2,631,165 m² of land was cleared, and from 1 January to 30 June 2008, 6,775,000 m² was cleared making the total cleared under this project 9,406,165 m² which is 26.1% of the target.

Output 2.1 – General professional skills and technical skills further developed - Since the project started in Oct 07, UNDP treats RDO (the national NGO) as an independent organization; it has provided larger responsibilities to its Iraqi staff members in terms of management, including financial and organizational management as well as reporting and donor relations. Financial and operational reports have also improved in the past 9 months. RDO conducted capacity building activities such as computer trainings and Basic English training mainly for national field staff.  Moreover, with continued capacity building activities started from the prior projects under DDG initiatives, those who previously could not read and write their own languages are now able to submit their reports in English.

Output 3.1 – Unfortunately, due to uncertainties regarding the institutional setup for Mine Action within the government structure, and the expected corresponding staff changes which affected NMAA and RMAC during the reporting period not much progress has been made for this output.  However, since March 2008 when the final decision was made, modest progress has taken place and more effective information sharing and cooperation between RMAC and the national NGO started to take place.

In addition to the Australian bilateral funding received and accounted for in the budget of this project, UNDP received additional bilateral funding from DFID ($108,248) which was utilized for funding RDO for the month of March 2008.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period and explain any variance in achieved versus planned outputs and outcomes during the six month reporting period.

The long-term development goal of this project is “support sustainable rural development by removing the threats to human security and livelihood through the increased capacity of the National Mine Action Authority (NMAA) and the organizations and the Regional Mine Action Centre (RMAC) based in Basra governorate.”  The short-term outputs described above directly contribute to this long-term goal.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints and actions taken to mitigate future delays and lessons learned in the process.

It was observed that the financial reporting by RDO needs improvement.  As an international Admin and Finance of DDG has left in late 2007, and the national Administrative Manager did not fully understand the change of the modality (from reimbursement modality to advance payment modality, therefore a face-to-face meeting in the first quarter of 2008 took place to explain how the reporting should be done.

Another fact worth mentioning is that this project is also partially funded bilaterally from AusAID, and since the Australian funding was approved and deposited before gaining UNDG-ITF approval it was decided to utilize Australian funding first and the utilization of  ITF funds will start from July 2008.  Thus in the matter of financial reporting on ITF budget, expenditure will appear as zero. The total cost of the project is US$ 4,884,644 (US$ 3,231,751 UNDG ITF + Australian bilateral US$ 1,652,893).

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

From this project, a national NGO (Rafidain Demining Organization; RDO) became an implementing partner of UNDP, while an international NGO (Danish Deming Group; DDG) acts as an international advisory and monitoring partner.  Both organizations directly report to UNDP monthly.  National Mine Action Authority and its regional arm Regional Mine Action Centre (RMAC) – South continue to be government counterparts on mine action, but they are currently under restructuring as a result of  a transfer of Mine Action jurisdiction from the Ministry of Planning and Development Cooperation to the Ministry of Environment.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

The annual agricultural yield of the cleared land is estimated to be of a value of approximately $5,700,000. Moreover, this land provides grazing pastures for more than 50,000 livestock at different seasons which improve their general health. Furthermore the project placed thousands of dollars into the local community through direct employment of local staff, contracting of local service providers as well stimulated the local market through purchasing of goods and supplies for the NGO.

V.  Future Work Plan

- Summarize the projected activities up to the end of December 2008 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

During the next 6 months, RDO is expected to continue clearance of agricultural land to reach the required target, also management and operational capacity development will continue and it is expected that RDO will draft and submit a proposal for additional funding to UNDP.

With the placement of the Mine Action with the ministry of Environment taking place in March this year, it is expected that some restructuring will happen leading to positive changes within NMAA and RAMC, eventually leading to improved coordination and tasking of RDO.

With the additional funding received from DFID during this reporting period and which covered RDO’s cost for March 2008, it is expected that the duration of the project might eventually be extended due to the savings made. A budget revision will be considered at the appropriate time.

# Text boxes

Report Formatting Instructions:

- Number all sections and paragraphs as indicated below.

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.

- Highlight any new challenges/constraints, mitigation strategies and lessons learned during the reporting period and monitoring processes and assessments, evaluations and studies undertaken/published in the period. Attach documents.

- Attach any available photos relevant to the project.