## Sheet1
Annex II A
Annex II A: Joint Programme Annual Work Plan
*For precise text of the activity please refer to the Results Framework (Annex I)
Annual targets (first year) | Activities* | TIME FRAME |  |  |  | UN AGENCY | RESPON-SIBLE PARTY ** | PLANNED BUDGET
|  | Q1 | Q2 | Q3 | Q4 |  |  | Source of Funds | Budget Descrip-tion *** | Total Amount
1.1 Environment priorities and indicators reflected in planning frameworks and budgets at district and community level | [9 empty] | 47500
Four Climate Change (CC) adaptation policy briefs developed and discussed; CC issues included in one provincial and one district plans and/or strategies; | 1.1.1.1 Provide technical support for policy briefs and advocacy |  |  |  | Q4 | UNDP | UNDP | MDG-F | P; S&C, E, Trav; Misc | 34500
| 1.1.1.3 Mainstream CC in contingency plans |  |  | Q3 | Q4 | WFP | WFP | MDG-F | P, S&C, E, Misc | 11500
| 1.1.1.4 Identify financing mechanisms to fund environment protection |  |  |  | Q4 | UNDP | UNDP | MDG-F | P; Misc; | 1500
1.2 GIS-based data and maps on climate change vulnerability for risk areas | [9 empty] | 92000
Five (5) thematic district maps produced; CC data collected and recorded; | 1.2.1.1 Mapping of areas at risk |  |  |  | Q4 | WFP | WFP | MDG-F |  | 31500
| 1.2.1.2 Collection of Environmental and CC data |  | Q2 | Q3 | Q4 | WFP | WFP | MDG-F |  | 10500
| 1.2.1.3 Assess water-related CC impact and develop strategies for IWRM |  | Q2 | Q3 | Q4 | UNEP | UNEP | MDG-F |  | 50000
1.3 Training programmes on disaster and climate change prediction, including interpretation of maps and application of monitoring data for early warning purposes | [9 empty] | 58500
Develop and apply diagnostic tools on the application and use of CC information; Adapt training materials for trainers and use of maps | 1.3.1.1 Provide technical support in the use and aplication of CC information | Q1 | Q2 |  |  | UNDP | UNDP | MDG-F | P; Trav | 15000
| 1.3.1.2 Select three relevant topics to adapt, print and distribute |  | Q2 | Q3 | Q4 | UN-HABITAT | UN-HABITAT | MDG-F | P; Misc; | 12000
| 1.3.1.3 Adapat River game material to local climate risk context |  |  | Q3 |  | UN-HABITAT | UN-HABITAT | MDG-F | P, C, Miscel | 13250
| 1.3.1.4 Develop training and technical guidelines on hazard resistant housing |  |  |  | Q4 | UN-HABITAT | UN-HABITAT | MDG-F | P, C, travel, equipment, Miscel | 2000
| 1.3.1.6 Set criteria for selecction of candidates for training of trainers |  | Q2 |  |  | UN-HABITAT | UN-HABITAT | MDG-F |  | 1000
| 1.3.1.7 Training on interpretation of CC risk maps and monitoring data |  |  | Q3 |  | WFP | WFP | MDG-F |  | 15250
1.4 Knowledge and experience sharing within the different groups (UN implementing agencies and beneficiaries) | [9 empty] | 5000
3 field days targetting a total of 8 communities | 1.4.1.1 Field days for exchange of best practices experiences |  |  |  | Q4 | FAO | FAO | MDG-F | P, Trans, S&C, E, Trav, Misc | 4000
| 1.4.1.2 Conduct on site technical sessions to share lessons learned |  |  | Q3 |  | FAO | FAO | MDG-F | P, Trans, Trav, Misc | 1000
2.1 National Disaster Preparedness plan and other relevant plans revised/updated to include climate change and environment aspects | [9 empty] | 110600
National disaster preparedness and risk assessment plans, including hazard risk maps, prepared and updated; 1 training sessions on environmental issues and participatory planning; | 2.1.1.1 Provide technical assistance to INGC to incorporarrte results of risk assessment in plans |  | Q2 | Q3 | Q4 | WFP | WFP | MDG-F | P | 12850
| 2.1.1.2 Training programmes on environmental issues and partcipatory planning |  | Q2 | Q3 | Q4 | UNEP | UNEP | MDG-F | P, Train, Trans, S&C, E, Trav, Misc | 68300
| 2.1.1.3 Prepare Hazard risk maps |  |  |  | Q4 | UNEP | UNEP | MDG-F |  | 3150
| 2.1.1.4 Inventory map and roles of all stakeholders |  | Q2 | Q3 | Q4 | UN-HABITAT | UN-HABITAT | MDG-F | P; Trans; S&C, E, Trav; Misc | 26300
2.2 Early warning and communication system enhanced in the Gaza province | [9 empty] | 79565
Increase percentage of areas covered by communications network; Accomplish timely warning of disasters | 2.2.1.1 Analyse availability and needs for radio communication |  |  | Q3 | Q4 | UNDP | UNDP | MDG-F | P, Trav | 13000
| 2.2.1.2 Select and implement radio communication systems | Q1 | Q2 |  |  | UNDP | UNDP | MDG-F | Misc | 5000
| 2.2.1.3 Identify appropriate technologies and equipment requirements, including renewable energy for radio communication |  |  | Q3 | Q4 | UNIDO | UNIDO | MDG-F | P; C; Train; S&C; E; Trav; Misc | 61565
2.3 Authorities, civil society and other relevant actors trained to incorporate and report on environmental and climate change risk events | [9 empty] | 233300
At least one training session on the aplication and use of current and forecasted climate information; Conduct a gender sensitive study on the socio-economic impact of CC on natural resources utilization and management; | 2.3.1.1 Training media and other actors in conveying reliable and factual information on CC | Q1 |  |  | Q4 | UNDP | UNDP | MDG-F | P, C, Train, Trans, S&C, e, Trav, Misc | 48300
| 2.3.1.2 Training civil society on incorpoating environmental CC information into public dialogue |  | Q2 | Q3 | Q4 | UNEP | UNEP | MDG-F | P; C; Train; Trans, S&C; E, Trav; Misc | 60000
| 2.3.1.3 Study on socio economic impact of CC on natural resources utilization and management |  | Q2 | Q3 | Q4 | UNEP | UNEP | MDG-F | P, C, Trav, S&C, Misc | 65000
| 2.3.1.4 Prepare, and publish climate change advocacy materials |  | Q2 | Q3 | Q4 | UN-HABITAT | UN-HABITAT | MDGF | P; C; S&C; Misc | 60000
3.1 Tools for climate proofing of risk zones in the Limpopo River Basin developed | [9 empty] | 40000
| 3.1.1.1 Identify activities/initiatives for climate proofing in Limppopo Basin | Q1 | Q2 | Q3 | Q4 | UNEP | UNEP | MDG-F | P, C | 40000
3.2 Assessment of climate proofing approaches carried out | [9 empty] | 40000
| 3.2.1.1 Support the integration of climate proofing/CC issues in government plans |  | Q2 | Q3 | Q4 | UNEP | UNEP | MDG-F | P, C | 40000
3.3 Stakeholders trained on climate proofing | [9 empty] | 28000
| 3.3.1.1 Develop, and conduct a training programme on climate proofing |  | Q2 | Q3 |  | UNEP | UNEP | MDG-F | P, C, E | 28000
4.1 Inventory of strategies and coping mechanisms currently in use by communities and in the Limpopo River Basin | [9 empty] | 175001
Completion of baseline study, including strategy for assessing and implementing CC coping mechanisms; CC coping mechanisms reinforced and implemented in at least one community | 4.1.1.1 Map CC coping mechanisms of communities | Q1 | Q2 | Q3 |  | UNEP | UNEP | MDG-F | P, C, S&C, E, Misc | 74300
| 4.1.1.2 Design a strategy to implement CC coping mechanisms | Q1 | Q2 | Q3 | Q4 | UNEP | UNEP | MDG-F | P, C, S&C, E, Misc | 5000
| 4.1.1.3 Select 3 communities to implement coping mechanism |  | Q2 | Q3 | Q4 | FAO | FAO | MDG-F | P; C, Train,S&C, E, Trav, Misc | 85701
| 4.1.1.4 Develop and conduct a trainning programme for the implementation of climate adaptation technologies |  | Q2 | Q3 | Q4 | UNDP | UNDP | MDG-F | P; C; Train; S&C; Trav; Misc | 10000
4.2 Community based natural forest resource management system established | [9 empty] | 158800
Certification of community committees/associations and at least one community forest area demarcated; Inventory of forest resources and management plan completed and beginning of implementation | 4.2.1.1 Demarcation of community forest areas in Mapai |  | Q2 | Q3 | Q4 | FAO | FAO | MDG-F | P, C, Trans, S&C, E, Trav, Misc | 40300
| 4.2.1.2 Establish and train community organizations |  | Q2 | Q3 | Q4 | FAO | FAO | MDG-F | P, C, Train, Trans, S&C, E, Trav, Misc | 18500
| 4.2.1.3 Carry out a participatory inventory and develop management plans |  |  | Q3 | Q4 | FAO | FAO | MDG-F | P, C, Train, Trans, S&C, E, Trav, Misc | 80000
| 4.2.1.4 Technical support/training on sustainable forest activities |  |  | Q3 | Q4 | FAO | FAO | MDG-F | P, C, Train, Trans, S&C, E, Trav, Misc | 10000
| 4.2.1.6 Train communities on bush fire control and management |  |  | Q3 | Q4 | FAO | FAO | MDG-F | P, C, Train, S&C, E, Trav, Misc | 10000
4.3 Territorial planning mechanisms at community level introduced | [9 empty] | 72500
Territorial planning including CC and disaster risk reduction completed; One training session on planning and cadastre carried out | 4.3.1.1 Undertake aplicable territorial planning strategies to cope with CC | Q1 | Q2 | Q3 | Q4 | UN-HABITAT | UN-HABITAT | MDG-F | P C, E, Trav | 21000
| 4.3.1.2 Capacity building on participatory planning & cadastre |  |  |  | Q4 | UN-HABITAT | UN-HABITAT | MDG-F | P C, Train, Trav | 8500
| 4.3.1.3 Design and implement shelter structure and roofs |  | Q2 | Q3 | Q4 | UN-HABITAT | UN-HABITAT | MDG-F | P, C, Train, E, Trav, Misc | 26000
| 4.3.1.4 Build demonstrative reinforced shelter |  |  | Q3 | Q4 | UN-HABITAT | UN-HABITAT | MDG-F | P, C, Train, E, Trav | 17000
4.4 Agroforestry practices introduced and applied at the community level | [9 empty] | 121000
Vegetation survey carried out; establishment of one tree nursery; one seed collection training carried out | 4.4.1.1 Identify potential Agroforestry (AF) tree species |  |  | Q3 | Q4 | FAO | FAO | MDG-F | P, C, Trans, S&C, E, Trav, Misc | 50300
| 4.4.1.2 Introduce/develop AF practices |  | Q2 | Q3 | Q4 | FAO | FAO | MDG-F | P, C, Trans, S&C, E, Trav, Misc | 10000
| 4.4.1.3 Establish tree nurseries and trials |  |  | Q3 | Q4 | FAO | FAO | MDG-F | P, C, Train, S&C, E, Trav, Misc | 30000
| 4.4.1.4 Train communities on tree seed collection and processing | Q1 |  | Q3 |  | FAO | FAO | MDG-F | P, C, Train, Trans, S&C, E, Trav, Misc | 30700
4.5 Multi purpose integrated water resource management systems created | [9 empty] | 343145
Baseline document on existing water reserves completed; Reinforcement of rain water harvesting; Increase number for water points | 4.5.1.1 Evaluate potential for boreholes, dams and irrigation systems and rehabilitaion |  |  | Q3 | Q4 | UN-HABITAT | UN-HABITAT | MDG-F | P; C; Trav | 44145
| 4.5.1.2 Identify, design and implement rain water harvesting |  | Q2 | Q3 | Q4 | UN-HABITAT | UN-HABITAT | MDG-F | P, C, S&C, Trav, Misc | 63000
| 4.5.1.3 Support establishment of additional water facilities |  | Q2 | Q3 | Q4 | UN-HABITAT | UN-HABITAT | MDG-F | P, C,Train, S&C, E, Trav, Misc | 93000
| 4.5.1.4 Protect water pumps and install additional water points |  |  | Q3 |  | UN-HABITAT | UN-HABITAT | MDG-F | P, C,Train, S&C, E, Trav, Misc | 7000
| 4.5.1.5 Train local technical staff and communities on water resource management |  |  |  | Q4 | UN-HABITAT | UN-HABITAT | MDG-F | P, C,Train, S&C, E, Trav, Misc | 18000
| 4.5.1.6 Develop water resources management plan |  | Q2 | Q3 | Q4 | UNEP | UNEP | MDG-F | P, C, Train, Trans, S&C, E, Trav, Misc | 118000
4.6 Sustainable conservation agriculture practices introduced and efficiency in small scale irrigation systems improved | [9 empty] | 274284
Soil survey and land use maps for potential agriculture areas completed; At least two fields for sustainable conservation agriculture practices adopted; extension of irrigation systems to improve efficient use of water resources | 4.6.1.1 Soil survey and map out existing farming areas | Q1 | Q2 |  |  | FAO | FAO | MDG-F | P, C, Trans, S&C, E, Trav, Misc | 35300
| 4.6.1.2 Assess soil potential for agriculture activities |  | Q2 | Q3 |  | FAO | FAO | MDG-F | P, C, Trans, S&C, E, Trav, Misc | 55300
| 4.6.1.3 Review community knowledge and introduce drough resistent crops |  | Q2 | Q3 | Q4 | FAO | FAO | MDG-F | P, C, Trans, S&C, E, Trav, Misc | 30000
| 4.6.1.4 Identify, develop and extend irrigation system and improve efficiency of water use |  | Q2 | Q3 | Q4 | FAO | FAO | MDG-F | P; C; Trans, S&C, E; Trav, Misc | 90290
| 4.6.1.5 Establish seed production and nurseries for crop multiplication |  |  |  | Q4 | FAO | FAO | MDG-F | P, C, Trans, S&C, E, Trav, Misc | 15000
| 4.6.1.6 Train commuunity in water and small scale irrigation management |  |  |  | Q4 | FAO | FAO | MDG-F | P, Train, Trans, S&C, E, Trav, Misc | 15000
| 4.6.1.7 Establish demonstration fields of conservation agriculture |  |  |  | Q4 | FAO | FAO | MDG-F | P, C, Train, Trans, S&C, E, Trav, Misc | 28900
| 4.6.1.8 Field days for dissemination of improved techniques |  |  | Q3 |  | FAO | FAO | MDG-F | P, C, Trans, S&C, E, Trav, Misc | 4494
4.7 Prospects of biogas generation and composting using waste manure as coping mechanisms to climate variability determined | [9 empty] | 114044
Inventory of solid waste management sites and mapping carried out; | 4.7.1.1 Carry out an Inventory of solid waste management sites and practices |  |  | Q3 | Q4 | UNIDO | UNIDO | MDG-F | P, C, Trans, S&C, E, Trav; Misc | 55079
| 4.7.1.2 Demonstration sites on waste management and composting incorporated to CC |  | Q2 |  | Q4 | UNIDO | UNIDO | MDG-F | P, C, Trans, S&C, E, Trav, Misc | 41195
| 4.7.1.3 Train on waste management, manure composting and bio-digestion |  |  | Q3 | Q4 | UNIDO | UNIDO | MDG-F | P, Train, Trans, S&C, E, Trav, Misc | 17770
5.1 Options for livelihood diversification identified | [9 empty] | 119600
Feasibility of livestock diversification completed | 5.1.1.1 Undertake feasibility study on livelihood diversification options | Q1 | Q2 | Q3 |  | UNEP | UNEP | MDG-F | P, C, Trans, S&C, E, Misc | 89300
| 5.1.1.2 Undertake in-depth feasibility studies for selected activities |  |  | Q3 | Q4 | FAO | FAO | MDG-F | P, C, Trans, S&C, E, Misc | 30300
5.2 Inventory and feasibility assessment of potential renewable energy sources carried out | [9 empty] | 206364
Existing and feasible energy renewable sources document; | 5.2.1.1 Identify potential renewable energy sources with feasibility studies |  |  | Q3 | Q4 | UNIDO | UNIDO | MDG-F | P; E; Trav; Misc | 20865
| 5.2.1.2 Install five renewable energy pilot demonstration units (one for irrigation) |  |  | Q3 | Q4 | UNIDO | UNIDO | MDG-F | P, C, Trans, S&C, E, Trav; Misc | 114665
| 5.2.1.3 Introduction of improved stoves and assess potential to manufacture |  |  |  | Q4 | UNIDO | UNIDO | MDG-F | P; E; Trav; Misc | 21935
| 5.2.1.5 Identify productive uses that can use renewable energy for income generation |  |  | Q3 | Q4 | UNIDO | UNIDO | MDG-F | P, Train, Trav, | 48899
5.3 Animal husbandry grazing and veterinary service coverage improved | [9 empty] | 159445
| 5.3.1.1 Construction of infrastructure for cattle |  |  |  | Q4 | FAO | FAO | MDG-F | P, C, Trans, S&C, E, Misc | 30000
| 5.3.1.2 Determine/evaluate seasonal amount of biomass available |  |  |  | Q4 | FAO | FAO | MDG-F | P, C, Trans, S&C, E, Trav, Misc, Trav | 11700
| 5.3.1.3 Provide technical advise on livestoch management |  | Q2 | Q3 | Q4 | FAO | FAO | MDG-F | P, Trav, S&C, E, Trav, Misc | 20000
| 5.3.1.4 Strenghtening the production of small stock |  | Q2 | Q3 | Q4 | FAO | FAO | MDG-F | P, Trans, S&C, E, Trav, Misc | 23300
| 5.3.1.5 Train communities on livestock management |  |  | Q3 |  | FAO | FAO | MDG-F | P, Train, Trans, S&C, E, Trav, Misc | 39445
| 5.3.1.6 Support veterinary services for disease prevention and control | Q1 | Q2 | Q3 | Q4 | FAO | FAO | MDG-F | P, c, Trans, S&C, E, Trav, Misc | 35000
5.4 Agro-processing and marketing activities developed | [9 empty] | 46300
| 5.4.1.1 Develop marketing activities for agriculture and animals and its by-products |  |  | Q3 |  | FAO | FAO | MDG-F | P, Train, Trans, S&C, E, Trav, Misc | 16300
| 5.4.1.2 Upgrade existing catlle slaughter and butchery facilities |  |  |  | Q4 | UNIDO | UNIDO | MDG-F | P, C, Trans, S&C, E, Trav, Misc | 30000
5.5 Use of animal traction promoted to encourage land preparation and transport | [9 empty] | 24254
At least 200 farmers introduced in the use animal traction | 5.5.1.1 Train farmers in the use of animal traction |  |  |  | Q4 | FAO | FAO | MDG-F | P, C, Train, Trans, S&C, E, Trav, Misc | 24254
Total Planned Budget for JP | [9 empty] | 2549202
** Responsible Party: |  |  | *** List of categories:
Please note that while a UN Agency has been indicated as the Responsible Party, a number of these activities will be implemented through and/or outsourced to National Partners/NGOs/CSOs. This information will be updated once the programme will be actually implemented and the work plan reviewed. |  |  | P (personnel & management; C (contracts); Train (training); Trans (transport); S&C (supplies and commodities); E (equipment); Trav (travel); Misc (miscellaneous)